## Sheet1
2018/2019 SERVICE DELIVERY BUDGET AND IMPLEMENTATION PLAN: INFRASTRUCTURE AND WATER SERVICES
MEASURABLE OBJECTIVE | INPUT | OUTPUT | OUTCOME | PROJECT | BASELINE 2017/2018 | INDICATORS | ANNUAL TARGET 2018/2019 | Q1 | Q2 | Q3 | Q4 | Portfolio of Evidence | BUDGET 2018-2019
RBIG
To construct pipeline from Burgersfort to Dresden pump station by June 2019 | Financial and Human Resource | Bulk supply line | Improved water supply | Construction of Mooihoek Bulk Water Supply Phase 4E | Mooihoek bulk water supply phase 4D completed | Number of Kilometers of bulk pipeline constructed | 3 Kilometers of bulk pipeline constructed | Site establishment and 0.2km pipeline constructed | 1km of bulk pipeline constructed | 0,8 Km of bulk pipeline constructed | 1 Km of bulk pipeline constructed | Progress Report | 165255056
To construct reservoir at Burgersfort by June 2019 | Financial and Human Resource | Bulk supply line | Improved water supply | Mooihoek bulk water supply phase 4BB | 1 X 5 Ml reservoir completed Phase 4A | Percentage reservoir constructed | 70%, 2 X 5 Ml concrete reservoir constructed | 15%, 2 X 5 Ml concrete reservoir constructed | 20%, 2 X 5 Ml concrete reservoir constructed | 20%, 2 X 5 Ml concrete reservoir constructed | 15%, 2 X 5 Ml concrete reservoir constructed | Progress Report
To construct bulk pipeline from Praktiseer to Motodi by June 2019 | Financial and Human Resource | Bulk supply line | Improved water supply | Mooihoek bulk water supply phase 4F | Mooihoek bulk water supply phase 2 completed | Number of Kilometers bulk pipeline constructed | 4 Kilometers of bulk water pipeline constructed | Site establishment and 0.5km pipeline constructed | 1 km of bulk pipeline constructed | 1,5 Km of bulk pipeline constructed | 1 Km of bulk pipeline constructed | Progress Report
To construct bulk pipeline at Mooihoek by June 2019 | Financial and Human Resource | Bulk supply line | Improved water supply | Mooihoek bulk water supply phase 4H | Mooihoek Bulk water supply Phase 2 completed | Number of Kilometers of bulk pipeline constructed | 4 Kilometers of bulk water pipeline constructed | No activity | Site establishment and 0.5km pipeline constructed | 1,5 km of bulk pipeline constructed | 2 Km of bulk pipeline constructed | Progress Report
To construct bulk pipeline from Praktiseer to Alverton by June 2019 | Financial and Human Resource | Bulk supply line | Improved water supply | Mooihoek bulk water supply phase 4G1 & G2 | Mooihoek Bulk water supply Phase 2 completed | Number of Kilometers of bulk pipeline constructed | 4 Kilometers of bulk water pipeline constructed | Site establishment and 0.5km pipeline constructed | 1 km of bulk pipeline constructed | 1,5 Km of bulk pipeline constructed | 1 Km of bulk pipeline constructed | Progress Report
To construct 400m long, 750mm diameter pipeline and 900m long, 450mm dimeter steel pipe line by June 2019. | Financial and Human Resource | Bulk supply line | Improved water supply | Mooihoek bulk water supply phase C1.2 | 80% completion of 400m long, 750mm diameter pipe line and 900m long, 450mm dimeter steel pipe | Percentage completion of 400m long, 750mm diameter pipe line and 900m long, 450mm dimeter steel pipe | 100% completion of 400m long, 750mm diameter pipe line and 900m long, 450mm dimeter steel pipe | 85% completion of 400m long, 750mm diameter pipe line and 900m long, 450mm dimeter steel pipe | 5% completion of 400m long, 750mm diameter pipe line and 900m long, 450mm dimeter steel pipe | 5% completion of 400m long, 750mm diameter pipe line and 900m long, 450mm dimeter steel pipe | 5% completion of 400m long, 750mm diameter pipe line and 900m long, 450mm dimeter steel pipe | Completion certicicates
To Construct Mooihoek Tubatse 4C2:2700m, 500mm DIA and 2600m,400mm DIA Steel Water Pipeline by June 2018. | Financial and Human Resource | Bulk supply line | Improved water supply | Mooihoek bulk water supply phase 4C2 | 90% Construction of Mooihoek Tubatse 4C2:2700, 500mm DIA and 2600, 400mm DIA Steel Water Pipeline, Installation of chambers fittings | Percentage Construction of 2700m, 500mm DIA and 2600, 400mm DIA Steel Water Pipeline. | 100% Construction of Mooihoek Tubatse 4C2:2700, 500mm DIA and 2600, 400mm DIA Steel Water Pipeline, Installation of chambers fittings | 95% Construction of Mooihoek Tubatse 4C2:2700, 500mm DIA and 2600, 400mm DIA Steel Water Pipeline, Installation of chambers fittings | 5% Construction of Mooihoek Tubatse 4C2:2700, 500mm DIA and 2600, 400mm DIA Steel Water Pipeline, Installation of chambers fittings | No activity | No activity | Completion certicicates
To construct pumping pipeline from T-off of Makgeru to the new 10ML reservoir at Schoonoord, construction of gravity pipeline by June 2019 | Financial and Human Resource | Bulk supply line | Improved water supply | Nebo BWS (RL19) Makgeru to Schoonoord | 55% Reservoir completed, Pipeline is completed | Percentage Bulk Pipeline constructed and Reservoir Completed | 100% Bulk Pipeline constructed and Reservoir completed | 60% Bulk Pipeline constructed and Reservoir completed | 15% Bulk Pipeline constructed and Reservoir completed | 15% Bulk Pipeline constructed and Reservoir completed | 10% Bulk Pipeline constructed and Reservoir completed | Progress Report | 45500000
To commission the 112 reinforced concrete valve chambers, 2 high lift pump stations, 30km 450dia c/m/l steel pipe from the wtw at ga-malekana to the 25ml command reservoir in jane furse by June 2019 | Financial and Human Resource | Bulk supply line | Improved water supply | Nebo BWS Ga Malekana to Jane Furse Phase 1A | 85% Nebo Phase1A pipeline completed . | Percentage of pipeline tested and commissioned | 100% Nebo Phase1A pipeline completed . | 90% Nebo Phase1A pipeline completed . | 10% Nebo Phase1A pipeline completed . | No activity | No activity | Progress Report
To construct bulk pipeline from 25 ML reservoir in Jane Furse to Lobethal and 5 take-offs by June 2019 | Financial and Human Resource | Bulk supply line | Improved water supply | Jane Furse to Lobethal BWS | 70% constructed pipeline from the existing 25ml Reservoir | Percentage of bulk water pipeline constructed connected to existing reservior | 100% Bulk Pipeline constructed and connected to the existing reservior | No activity | 75% Bulk Pipeline constructed and connected to the existing reservior | 10% Bulk Pipeline constructed and connected to the existing reservior | 15% Bulk Pipeline constructed and connected to the existing reservior | Progress Report
To construct Bulk Pipeline and Valve Chambers by June 2019 | Financial and Human Resource | Bulk supply line | Improved water supply | Moutse BWS Phase 1-6 | Bulk Pipeline and Valve constructed up 54% | Percentage Bulk Pipeline constructed | 100% Bulk Pipeline constructed | 55% Bulk Pipeline and Valve constructed | 10% Bulk Pipeline and Valve constructed | 15% Bulk Pipeline and Valve constructed | 20% Bulk Pipeline and Valve constructed | Progress Report | 34244944
To connect mechanical and Electrical (M & E) for the extensions to the Groblersdal Water Treatment Works by June 2019 | Financial and Human Resource | Bulk supply line | Improved water supply | Moutse BWS Project 13 & 14 (RL14) | The upgrading of WTW is completed | Percentage of M&E components installed | 100% M&E Components Installed | 10% M&E Components Installed | 30% M&E Components Installed | 30% M&E Components Installed | 30% M&E Components Installed | Progress Report
To construct Bulk Pipeline and Valve Chambers by June 2019 | Financial and Human Resource | Bulk supply line | Improved water supply | Moutse BWS Project 7 - 12 | Bulk Pipeline and Valve constructed up 54% | Percentage Bulk Pipeline constructed | 100% Bulk Pipeline constructed | 55% Bulk Pipeline and Valve constructed | 10% Bulk Pipeline and Valve constructed | 15% Bulk Pipeline and Valve constructed | 20% Bulk Pipeline and Valve constructed | Progress Report
WATER QUALITY
To generate Water Quality Reports by June 2019 | WSDP and Water Master Plan | Regulatory Compliance | Improved service delivery | Generation of Water Quality Reports | 10 reports generated | Number of Water Quality Reports generated | 12 Water Quality Reports generated | 3 Water Quality Reports generated | 3 Water Quality Reports generated | 3 Water Quality Reports generated | 3 Water Quality Reports generated | Progress Report | 5650000
To conduct Full SANS 241 Analysis by June 2019 | WSDP and Water Master Plan | Regulatory Compliance | Improved service delivery | Full SANS 241 Water Quality Analysis | Signed CSIR SLA in 2015/16 financial year | Number of Full SANS 241 Analysis conducted | 1 Full SANS 241 Analysis (120 samples) conducted | 1 Full SANS 241 Analysis (30 samples) conducted | 1 Full SANS 241 Analysis (30 samples) conducted | Full SANS 241 Analysis (30 samples) conducted | Full SANS 241 Analysis (30 samples) conducted | Progress Report
To purchase Laboratories chemical by June 2019 | WSDP and Water Master Plan | Regulatory Compliance | Improved service delivery | Purchase of LAB Chemicals | WTW & WWTW in place | Percentage of LAB chemical purchased | 100% of LAB chemical purchased | 100% of LAB chemical purchased | 100% of LAB chemical purchased | 100% of LAB chemical purchased | 100% of LAB chemical purchased | Progress Report
To participate in Blue and Green Drops Certification Programme by June 2018 | WSDP and Water Master Plan | Regulatory Compliance | Improved service delivery | Plants participation in Blue and Green Drops Certification Programme | 15 Water Treatment Works participating in Blue Drop Certification programme in place | Number of Plants participating in Blue and Greed Drops Certification Programme | 15 WTW participating in Blue Drop and 16 WWTW Participating in Green Drop Certification Programme | 15 WTW participating in Blue Drop and 16 WWTW Participating in Green Drop Certification Programme | 15 WTW participating in Blue Drop and 16 WWTW Participating in Green Drop Certification Programme | 15 WTW participating in Blue Drop and 16 WWTW Participating in Green Drop Certification Programme | 15 WTW participating in Blue Drop and 16 WWTW Participating in Green Drop Certification Programme | Progress Report
O & M EXPENDITURE
To resolve registered sanitation incidents within 14 days. | Financial and Human Resource | Reduced sewer spillage and environmental pollution | Improved green drop status | Sanitation incidents | 700 registered sanitation incidents resolved within 14 days | Number of registered sanitation incidents resolved within 14 days | 700 registered sanitation incidents resolved within 14 days | 175 registered sanitation incidents resolved within 14 days | 175 registered sanitation incidents resolved within 14 days | 175 registered sanitation incidents resolved within 14 days | 175 registered sanitation incidents resolved within 14 days | Progress Report | 35107845.47
To resolve registered water incidents within 14 days. | Financial and Human Resource | Reduced non-revenue water losses | Improved no drop status. | Water incidents | 7000 registered water incidents resolved within 14 days | Number registered water incidents resolved within 14 days | 7000 registered water incidents resolved within 14 days | 1 750 registered water incidents resolved within 14 days | 1 750 registered water incidents resolved within 14 days | 1 750 registered water incidents resolved within 14 days | 1 750 registered water incidents resolved within 14 days | Progress Report
To render tankering services by June 2019 | Financial and Human Resource | Consistent supply of water | Improved water supply | Delivery of portable water | 9.6 Ml delivery of Potable Water in Jane Furse Hospital and Buffelshoek | Number tankering services rendered | 9.6 Ml delivery of Potable Water in Jane Furse Hospital and Buffelshoek | 2.4 Ml delivery of Potable Water in Jane Furse Hospital and Buffelshoek | 2.4 Ml delivery of Potable Water in Jane Furse Hospital and Buffelshoek | 2.4 Ml delivery of Potable Water in Jane Furse Hospital and Buffelshoek | 2.4 Ml delivery of Potable Water in Jane Furse Hospital and Buffelshoek | Progress Report | 14742000
To provide diesel consistently to diesel driven machines by June 2019 | Financial and Human Resource | Consistant water supply. | Reliable water supply. | Supply of diesel | 40 000ℓ of diesel supplied annually. | Number of Litres of diesel supplied annually | 40 000ℓ of diesel supplied annually. | 10 000ℓ of diesel supplied annually. | 10 000ℓ of diesel supplied annually. | 10 000ℓ of diesel supplied annually. | 10 000ℓ of diesel supplied annually. | Progress Report | 1193000
To provide petrol consistently to petrol driven machines by June 2019 | Financial and Human Resource | Consistant water supply. | Reliable water supply. | Supply of petrol | 400ℓ of petrol supplied annually. | Number of Litres petrol supplied annually. | 400ℓ of petrol supplied annually. | 100ℓ of petrol supplied annually. | 100ℓ of petrol supplied annually. | 100ℓ of petrol supplied annually. | 100ℓ of petrol supplied annually. | Progress Report
To provide oil consistently to diesel and petrol driven machines by June 2019 | Financial and Human Resource | Consistant water supply. | Reliable water supply. | Supply of oil | 300ℓ of oil supplied annually. | Number of Litres of oil supplied annually. | 300ℓ of oil supplied annually. | 75ℓ of oil supplied annually. | 75ℓ of oil supplied annually. | 75ℓ of oil supplied annually. | 75ℓ of oil supplied annually. | Progress Report
To resolve registered M & E incidents within 14 days. | Financial and Human Resource | Consistent supply of water | Improved water supply | Mechanical & Electrical Services | 450 of registered M & E incidents within 14 days | Number of registered M & E incidents resolved within 14 days | 450 of registered M & E incidents within 14 days | 112.5 of registered M & E incidents within 14 days | 112.5 of registered M & E incidents within 14 days | 112.5 of registered M & E incidents within 14 days | 112.5 of registered M & E incidents within 14 days | Progress Report | 3570000
To install Bulk Water Meters by June 2019 | Financial and Human Resource | Consistent supply of water | Improved water supply | Installation of Bulk Water Meters | 8 bulk water meters installed | Number of bulk water meters installed by June 2018 | 8 bulk water meters installed | 2 bulk water meters installed | 2 bulk water meters installed | 2 bulk water meters installed | 2 bulk water meters installed | Progress Report | 500000
To purchase Mℓ Bulk water by June 2019 | Financial and Human Resource | Consistent supply of water | Improved water supply | ML Bulk Water Purchases | 10 062Mℓ of water purchased | Number Mℓ of water purchased | 10 062Mℓ of water purchased | 2 515.5Mℓ of water purchased | 2 515.5Mℓ of water purchased | 2 515.5Mℓ of water purchased | 2 515.5Mℓ of water purchased | Progress Report | 110142000
PLANNING
To develop Water Conservation /Water Demand Management Strategy for SDM by June 2019 | WSDP and Water Master Plan | Document on Water Conservation and Demand Management | Strategy on Water Conservation and Demand Management | Water Conservation and Water Demand Management Plan | Water Services Master Plan and WSDP developed in 2014/15 and 2015/16 FY respectively | Number of WC/WDM Strategy developed | One WC/WDM Strategy developed | Appointment of service provider for WC/WDM Strategy | Collection of information/Assessment of status quo and Inception report of WC/WDM | Draft WC/WDM developed | One WC/WDM strategy developed | Draft WC/WDM strategy | 500000
To develop and review Water & Sanitation Master Plan by June 2019 | Exisitng Water Master Plan | Effective Water & Sanitation Infrastructure Plans | Reviewed Water Master Developed, Sanitation & WSDP | One Water & Sanitation Master Plan (WSMP) & WSDP | Professional Service Provider appointed in Nov 2016 scoping report and methodology developed. | Number of Water & Sanitation Master Plan developed | Drat Water & Sanitation Master Plan developed | Develop Terms of Reference and Appointment of PSP for Water & Sanitation Master Plan & WSDP | Collection of information/Assessment of status quo and Inception report of WSMP & WSDP | Inception report for WSMP & WSDP | Draft of One WSMP & WSDP | Draft WSMP/WSDP | 1300000
To upgrade Groblersdal sewer pump- station by June 2019 | Bulk sewer intervention plan | Upgraded Sewer infrastructure | Enhanced sewer system | Groblersdal sewer network | Assessment report and upgrade portion of the outfall sewer system took place in 2015/16 financial year | km sewer pipe line inspected using the CCTV camera and report analysis. | To conduct 5km sewer pipeline CCTV survey in Groblersdal. | The PSP to submit inception report together with cost estimate for the CCTV survey. | 2km sewer pipeline inspected | 3km Sewer pipeline to be inspected | PSP to submit assessment report and analysis of CCTV survey (Cost estimate for sewer repairs). | Progress Report | 500000
To conduct Condition Assessment and develop O & M Plans by June 2019 | Asset register & O& M plan | Effective Maintenance & Operation of Existing Infratsrucutre | Operation & Manitenance Paln | Conduct Condition Assessment and develop O & M Plans | 40% Development of O&M plan and Condition assesment of IWS infrastructure conducted | Percentage conduct of condition assessment and O & M Plan developed | 60% conduct of Condition Assessment and O & M Plan developed | 45% conduct of Condition Assessment and O & M Plan developed | 5% conduct of Condition Assessment and O & M Plan developed | 5% conduct of Condition Assessment and O & M Plan developed | 5% conduct of Condition Assessment and O & M Plan developed | Progress Report | 800000
To facilitate District Water & Sanitation Summit by June 2019 | Asset register & O& M plan | Effective Maintenance & Operation of Existing Infratsrucutre | Operation & Manitenance Paln | District Water & Sanitation Summit | 2015 Water & Sanitation Resolution | Number of Water & Sanitation Summit facilitated | One District Water & Sanitation Summit facilitated | One District Water & Sanitation Summit facilitated | Adoption of Water & Sanitation summit resolution | Implementartion of Water & Sanitation summit resolutions | Implementartion of Water & Sanitation summit resolutions | Progress Report | 300000
To Conduct Feasibility Studies and develop Technical Report by June 2019 | Assignment of PSP to do the Technical Reports | Technical Reports | MIG registered Projectss | Conduct Feasibility Studies and develop Technical Report | WSDP, IDP and BWS Master completed in plan 2014 | Number of Feasibility Studies conducted and technical report developed | 15 Feasibility Studies conducted and technical Reports developed | 5 Feasibility Studies conducted and technical Reports developed | 4 Feasibility Studies conducted and technical Reports developed | 3 Feasibility Studies conducted and technical Reports development | 3 Feasibility Studies conducted and technical Reports development | Progress Report | 5000000
WSIG PROJECTS
To complete Tukakgomo water reticulation by June 2019 | Financial and human resource | Reticulated water supply | Improved access to safe, reliable drinking water. | Tukakgomo water intervention and refurbishment. | 1 borehole drilled and equipped. Refurbished pumpstation Refurbished Rising main | Percentage completion of Tukakgomo water reticulation | 100% completion of Tukakgomo water reticulation | *Reticulation network at 100% | *Testing and commissioning. | No activity | No activity | Completion certicicates | 3961618
To construct bulk pipeline; reticulation and standpipes by June 2019 | Financial and human resource | Reticulated water supply | Improved access to safe, reliable drinking water. | Mahlwakwena to Mapodile pipeline(Tukakgomo Extension) | 1,8 rising main from the highlift pumpstation to the Elevated Steel tank costructed | Number of Kilometers of bulk pipeline, reticulation and standpipes constructed | 1.8km bulk pipeline, 6.3Km of reticulation network and 29 standpipes completed | *Excavations for internal reticulation(3km). *15 standpipes constructed | *Construction of 3.3km internal reticulation completed. *Installation of 14 standpipes. | Testing & commissioning of 1.8km bulk pipeline, 6.3Km of reticulation network and 29 standpipes completed | No activity | Completion certicicates | 5185203
To complete Phiring water reticulation & storage by June 2019 | Financial and human resource | Reticulated water supply | Improved access to safe, reliable drinking water. | Phiring Water Intervention(Leboeng) | 50% Borehole equipped & Footing for storage constructed. | Percentage of Kilometres of reticulation & storage constructed, borehole drilling & equipping | 100% of 3.5km of reticulation & storage constructed,Drilling and Equipping of boreholes | 40% of 3.5km of reticulation & 50% storage constructed,60% Drilling and Equipping of boreholes | 60% of 3.5km of reticulation & 50% storage constructed,40% Drilling and Equipping of boreholes | Testing and Commissioning | No activity | Completion certicicates | 2353179
To complete Internal Bulk -Distribution mains and Pressure Management System by June 2019 | Financial and human resource | WC/WD Management Provisioning | Improved access to safe, reliable drinking water. | Nebo Phase 1A testing and commissioning | 1.8km pipeline from 25ML reservoir to Mashishing Reservoir constructed | Percentage of Internal Bulk -Distribution mains and Pressure Management System | 100% completion of Internal Bulk -Distribution mains and Pressure Management System | 25% completion of Internal Bulk -Distribution mains and Pressure Management System | 25% completion of Internal Bulk -Distribution mains and Pressure Management System | 50% completion of Internal Bulk -Distribution mains and Pressure Management System | No activity | Progress Report | 6500000
To construct water reticulation at Apel Cross by June 2019 | Financial and human resource | Reticulated water supply | Improved access to safe, reliable drinking water. | Apel Cross RDP Reticulation network | 80% Construction of pipeline , relocation of elevated tanks and communal stand pipes | Percentage of Apel Cross water reticulation | 100% Construction of pipeline , relocation of elevated tanks and communal stand pipes. | 85% Construction of pipeline , relocation of elevated tanks and communal stand pipes. | 5% Construction of pipeline , relocation of elevated tanks and communal stand pipes. | 10% Construction of pipeline , relocation of elevated tanks and communal stand pipes. | No activity | Progress Report | 3000000
To complete reticulation and installations of water meters by June 2019 | Financial and human resource | WC/WD Management Provisioning | Improved access to safe, reliable drinking water. | Flag Boshielo WC/WD Management( Letebejane pilot project) | 10km Reticulation network completed. | Percentage of Letebejane Water Project reticulation and installations of water meters. | 100% completion of Letebejane Water Project reticulation and installations of water meters. | 80% completion of Letebejane Water Project reticulation and installations of water meters. | 10% completion of Letebejane Water Project reticulation and installations of water meters. | 10% completion of Letebejane Water Project reticulation and installations of water meters. | No activity | Progress Report | 8000000
To complete Package Plant , risnig main and storage in Jane Furse RDP by June 2019. | Financial and human resource | Packaged plant | Improved access to safe, reliable drinking water. | Jane Furse RDP Package plant | 68% Borehole drilling & tesing, equipping & securing it with concrete pump house, Rising main complete. | Percentage of Package Plant , risnig main and storage in Jane Furse RDP completed. | 100% completion of Package Plant , risnig main and storage in Jane Furse RDP. | 70% completion of Package Plant , risnig main and storage in Jane Furse RDP | 10% completion of Package Plant , risnig main and storage in Jane Furse RDP | 10% completion of Package Plant , risnig main and storage in Jane Furse RDP | 10% completion of Package Plant , risnig main and storage in Jane Furse RDP | Progress Report | 4000000
To develop water source and installations of rising main at Maebe by June 2019 | Financial and human resource | Developed source | Improved access to safe, reliable drinking water. | Maebe/Mohlaletsi interventions | Three (3) Boreholes drilled, tested and equipped. Securing of boreholes with concrete structures. | Percentage of water source and installations of rising main at Maebe. | 100% development of water source and installations of rising main at Maebe. | 40% development of water source and installations of rising main at Maebe. | 30% development of water source and installations of rising main at Maebe. | 30% development of water source and installations of rising main at Maebe. | No activity | Progress Report | 4000000
To construct VIDP Sanitation units by June 2019. | Financial and human resource | Onsite sanitation, health hygiene & user education | Improved access to safe, reliable sanitation service | Construction of Moretsele VDIP | 632 VDIP sanitations units completed | Number of VDIP sanitation units constructed | 370 VDIP Sanitation units constructed | No activity | 70 VDIP Sanitation units constructed | 100 VDIP Sanitation units constructed | 200 VDIP Sanitation units constructed | Progress Report | 5000000
To refurbish and rehabilitate the existing reservior in Madibong village by June 2019. | Financial and human resource | Developed source | Improved access to safe, reliable drinking water. | Madibong Water Supply | Geohydrological studies 100% complete and the drilled boreholes are dry, then project is halted. | Percentage refurbish and rehabilitate the existing reservior in Madibong village. | 100% refurbishment and rehabilitation of the existing reservior in Madibong village. | No activity | 40% refurbishment and rehabilitation of the existing reservior in Madibong village. | 50% refurbishment and rehabilitation of the existing reservior in Madibong village. | No activity | Progress Report | 3000000
To constuct the water storage in Uitvlught by June 2019 | Financial and human resource | Developed source | Improved access to safe, reliable drinking water. | Uitvlught Water Supply | 69% construction of Pipeline, eskom, boreholes drilling & tesitng, equipping and securing with concrete pump house . | Percentage of water storage constructed in Uitvlught village | 100% of water storage constructed in Uitvlught village | 75% of water storage constructed in Uitvlught village | 10% of water storage constructed in Uitvlught village | 10% of water storage constructed in Uitvlught village | 5% of water storage constructed in Uitvlught village | Progress Report | 3000000
To develop water source by June 2019 | Financial and human resource | Developed source | Improved access to safe, reliable drinking water. | Mapulaneng drilling and equipping of borehole | New Infrastructure | Percentage of water source developed | 100% of water source developed. | 10% of water source developed. | 30% of water source developed. | 40% of water source developed. | 20% of water source developed. | Progress Report | 3000000
To construct water supply pipeline, package plant and steel storage tank June 2019 | Financial and human resource | Bulk Provisioning | Improved access to safe, reliable drinking water. | Maseven Bulk Water supply project. | New Infrastructure | Percentage of water supply pipeline, package plant and steel storage tank completed | 100% completion of water supply pipeline, package plant and steel storage tank | 15% completion of water supply pipeline, package plant and steel storage tank | 45% completion of water supply pipeline, package plant and steel storage tank | 20% completion of water supply pipeline, package plant and steel storage tank | 20% completion of water supply pipeline, package plant and steel storage tank | Progress Report | 14000000
MUNICIPAL INFRASTRUCTURE GRANT (MIG)
To construct VIP Sanitation units by June 2019 within Ephraim Mogale Municipality | Financial and Human Resource | 1 020 VIP Sanitation toilets completed | Improved health and hygiene | VIP Sanitation Programme Phase 2.2 | 15 180 VIP Units constructed | Number of VIP sanitation units constructed | 1020 of VIP sanitation units constructed | No activity | 200 VIP Sanitation toilets constructed | 350 VIP Sanitation toilets constructed | 470 VIP Sanitation toilets constructed | Progress Report | 20424125.3
To construct VIP Sanitation units by June 2019 within Elias Motsoaledi Municipality | Financial and Human Resource | 1 630 VIP Sanitation toilets completed | Improved health and hygiene | VIP Sanitation Programme Phase 2.2 | 15 180 VIP Units constructed | Number of VIP sanitation units constructed | 1630 of VIP sanitation units constructed | No activity | 400 VIP Sanitation toilets constructed | 540 VIP Sanitation toilets constructed | 690 VIP Sanitation toilets constructed | Progress Report | 21476511.6
To complete Zaaiplaas bulk pipeline, command reservior and pump station by June 2019 | Financial and Human Resource | Completed BWS | Improved water supply to Zaaiplaas | Zaaiplaas Village Reticulation Phase 2 | 80% construction of Dindela Reservoir. Commissioning of bulk pipeline and pump station completed | Percentage of Zaaiplaas bulk pipeline, command reservior and pump station constructed | 100% of Zaaiplaas bulk pipeline, command reservior and pump station constructed | 85% of Zaaiplaas bulk pipeline, command reservior and pump station constructed | 10% of Zaaiplaas bulk pipeline, command reservior and pump station constructed | 5% of Zaaiplaas bulk pipeline, command reservior and pump station constructed | No activity | Completion certicicates | 424668.45
To upgrade and extend Roosenekal Waste Water Treatment Works (WWTW) by June 2019 | Improved water supply | WWTW upgrade | Improved Living standards. | Roosenekal WWTW | 70% of Roosenekal WWTW done | Percentage Upgrading and Extension of Roosenekal WWTW constructed | 100% Upgrading and Extension of Roosenekal WWTW constructed | 75% Upgrading and Extension of Roosenekal WWTW constructed | 15% Upgrading and Extension of Roosenekal WWTW constructed | 10% Upgrading and Extension of Roosenekal WWTW constructed | No activity | Completion certicicates | 424668.45
To construct VIP Sanitation units by June 2019 within Makhuduthamaga Municipality | Financial and Human Resource | 1 835 VIP Sanitation toilets completed | Improved health and hygiene | VIP Sanitation programme phase 2.2 | 15 180 VIP Units constructed | Number of VIP sanitation units constructed | 1835 VIP Sanitation units constructed | No activity | 600 VIP Sanitation toilets constructed | 600 VIP Sanitation toilets constructed | 635 VIP Sanitation toilets constructed | Progress Report | 26325000
To construct reticulation network in Ga- Mashabela by June 2019 | Completed Ga-Mashabela water reticulation network | Improved water supply to Ga-Mashabela | Ga-Mashabela water reticulation supply | Ga- Mashabela water reticulation supply | 60% of water reticulation constructed | Percentage of water reticulation supply construction | 100% construction of water reticulation constructed | 85% construction of water reticulation constructed | 10% construction of water reticulation constructed | 5% construction of water reticulation constructed | No activity | Completion certicicates | 23896521.22
To construct reticulation network in Ga- Marishane by June 2019 | Financial and Human Resource | Completed Ga-Marishane water reticulation network | Improved water supply to Ga-Marishane | Ga- Marishane water reticulation supply | 30% water reticulation constructed | Percentage of water reticulation supply constructed | 100% water reticulation supply constructed | 45% construction of water reticulation constructed | 25% construction of water reticulation constructed | 30% construction of water reticulation constructed | No activity | Completion certicicates | 9590358.5
To construct reticulation network in Lobethal by June 2019 | Financial and Human Resource | Completed Lobethal water supply | Improved water supply to Lobethal | Lobethal water supply | 40% construction constructed | Percentage of water reticulation supply constructed | 100% water reticulation supply constructed | 60% construction of water supply constructed | 20% construction of water supply constructed | 20% construction of water supply constructed | No activity | Completion certicicates | 424668.45
To construct reticulation network in Ga- Phaahla by June 2019 | Financial and Human Resource | Completed Ga-Phaahla water supply | Improved water supply to Ga-Phaahla water supply | Ga- Phaahla water supply | 40% construction constructed | Percentage of water supply constructed | 100% water reticulation supply constructed | 60% construction of water supply constructed | 20% construction of water supply constructed | 20% construction of water supply constructed | No activity | Completion certicicates | 6721314.72
To construct Fetakgomo Tubatse LM VIP Sanitation units by June 2019 | Financial and Human Resource | 715 VIP Sanitation toilets completed | Improved health and hygiene | VIP Sanitation programme phase 2.2 | 15 180 VIP Units constructed | Number of VIP sanitation units constructed | 715 VIP Sanitation units constructed | No activity | 300 VIP Sanitation toilets constructed | 300 VIP Sanitation toilets constructed | 115 VIP Sanitation toilets constructed | Progress Report | 9805283.89
To construct completion of bulk water reticulation in Mooiplaas and Strydkraal Supplement by June 2019 | Financial and Human Resources | Refurbished and new developed Water Boreholes | Improved Water Supply | Contract 21,22& 24 : (Bulk, Res, PS & WDM Chamber in various villages | 85% Water supply below RDP level | Percentage of bulk water reticulation in Mooiplaas and Strydkraal Supplement constructed | 100% completion of bulk water reticulation in Mooiplaas and Strydkraal Supplement constructed | 90% completion of bulk water reticulation in Mooiplaas and Strydkraal Supplement constructed | 10% completion of bulk water reticulation in Mooiplaas and Strydkraal Supplement constructed | No activity | No activity | Completion certicicates | 9000000
To complete Concrete reservoirs; Bulk Water Supply;and Reticulation at Nkadimeng: Phase 9 to 11 by June 2019 | Financial and Human Resources | Nkadimeng: Phase 9 to 11 (Makhuduthamaga) - | Improved Living standards. | Nkadimeng RWS Extension 2( Phase 9 to 11) (Fetakgom o) Ga- Mmela to Mashilavele , Ga- Pahla, Molapong, Ga- Magolego, Mankontu and Masehleng | 40% Nkadimeng WTW, Command Reservoir, reticulation and bulk line below RDP level constructed | Percentage Completion of Concrete reservoirs; Bulk Water Supply; Reticulation. | 100% Completion of Concrete reservoirs; Bulk Water Supply; Reticulation at Nkadimeng: Phase 9 to 11 | 60% Completion of Concrete reservoirs; Bulk Water Supply; Reticulation at Nkadimeng: Phase 9 to 11 | 20% Completion of Concrete reservoirs; Bulk Water Supply; Reticulation at Nkadimeng: Phase 9 to 11 | 20% Completion of Concrete reservoirs; Bulk Water Supply; Reticulation at Nkadimeng: Phase 9 to 11 | No activity | Completion certicicates | 15937980.32
To construct VIP Sanitation units by June 2019 (Fetakgomo Greater Tubatse LM) | Financial and Human Resource | 1630 VIP Sanitation toilets completed | Improved health and hygiene | VIP Sanitation programme phase 2.2 | 15 180 VIP Units constructed | Number of VIP sanitation units constructed | 1 630 VIP Sanitation units constructed | No Activity | 400 VIP Sanitation toilets constructed | 540 VIP Sanitation toilets constructed | 690 VIP Sanitation toilets constructed | Progress Report | 25311841.99
To construct command reservoir, pump station and pipelines at GaMaphopha by June 2019 | Improved water supply | Ga - Maphopha Command Reservoir | Improved Living standards. | Ga - Maphopha Command Reservoir | 20% completion of Maphopha Command Reservoir constructed | Percentage completion of command reservoir, pump station and pipelines at Ga-Maphopha constructed | 100% completion of command reservoir, pump station and pipelines at Ga-Maphopha constructed | 40% completion of command reservoir, pump station and pipelines at Ga-Maphopha constructed | 30% completion of command reservoir, pump station and pipelines at Ga-Maphopha constructed | 30% completion of command reservoir, pump station and pipelines at Ga-Maphopha constructed | No activity | Completion certicicates | 9000000
To construct connector pipe network in Lebalelo South by June 2019 | Improved water supply | Lebalelo South connector pipes completed | Improved Living standards. | Lebalelo South connector pipes | 30% connector pipes constructed | Percentage of connector pipe network constructed | 100% of connector pipe network constructed | 40% of connector pipe network constructed | 30% of connector pipe network constructed | 30% of connector pipe network constructed | No activity | Progress Report | 70558516.71
To construct reticulation network and reservoirs in Lebalelo South phase 2 by June 2020 | Improved water supply | Lebalelo South connector pipes completed | Improved Living standards. | Lebalelo South reticulation pipe & water storages | Project advertised and waiting procurement of Contractors | Percentage completion of reticulation network & reservoirs in Lebalelo South phase 2 | 50% of reticulation network and reservoirs in Lebalelo South phase 2 constructed | No Activity | 15% construction of reticulation network & reservoirs constructed | 20% construction of reticulation network & reservoirs constructed | 15% construction of reticulation network & reservoirs constructed | Progress Report | 195614540.39 | ,