## PED
PLANNING AND ECONOMIC DEVELOPMENT
2019-2020 SERVICE DELIVERY BUDGET AND IMPLEMENTATION PLAN
MEASURABLE OBJECTIVE | INPUT | OUTPUT | OUTCOME | PROJECT | BASELINE 2018/2019 | INDICATORS | ANNUAL TARGET 2019/2020 | Q1 | Q2 | Q3 | Q4 | EVIDENCE | BUDGET 2019-2020
SPATIAL RATIONALE
To ensure sustainable spatial and land use development within the District by 2020 |  |  |  | Facilitate Joint District Municipal Planning Tribunal | 4 JDMPT sittings facilitated | Number of JDMPT facilitated | 4 Joint District Municipal Planning Tribunals facilitated | [5 empty] | 400000
|  |  |  | Facilitate Land Acquisition for District Municipal Offices | Land owned by different entities is available for development | Number of hectares of land acquired for development of District Municipal Offices | 10ha of land land for District Municipal Offices facilitated | [5 empty] | R50 000
|  |  |  | Process Land Development applications in line with the reviewed SDF | Processed 100% Land Development applications in line with the reviewed SDF | Percentage Land Development applications processed in line with reviewed SDF | 100% Land Development applications processed in line with reviewed SDF | [5 empty] | 0
|  |  |  | Formalisation of Informal Settlements | None | Number of Informal Settlements within the District formalised | 1 informal Settlement within the District formalised | [5 empty] | 0
|  |  |  | Develop Precinct Plans in Nodal points/Growth points with required economic resources | Reviewed Spatial Development Framework | Number of Precinct Plans in Nodal points/Growth points with required economic resources developed | 1 Precinct Plans in Nodal points/Growth points with required economic resources developed | [5 empty] | 200000
|  |  |  | Integrate Municipal Geographic Information System (GIS), Finance, Asset Management System and WSMP | GIS strategy in place | Percentage integration of Municipal Geographic Information System (GIS), Finance, Asset Management and WSMP | 100% integration of Municipal Geographic Information System (GIS) Finance, Asset Management and WSMP | [5 empty] | R1 000 000
LOCAL ECONOMIC DEVELOPMENT
To promote Job Creation Opportunities through EPWP by June 2022 |  |  |  | Implementation of EPWP | 912 | Number of jobs created through EPWP | 6 1 80 jobs created through EPWP | [5 empty] | R2 665 000
To empower 60 SMMEs by 2020 |  |  |  | Facilitate Enterprise and Supplier Development Programme | 3 Service Providers appointed | Number of SMMEs capacitated | 60 SMMEs capacitated | [5 empty] | 150000
|  |  |  | Trainings for SMMEs and cooperatives | 20 SMMEs trained during 2018/19 | Number of SMMEs trained | 30 SMMEs trained | [5 empty] | 100000
|  |  |  | Support to SMMEs and Co-operatives | 1 SMME and 1 Co-operative supported during 2019 | Number of SMMEs/Co-operative support provided | 2 SMMEs/Co-operatives supported | [5 empty] | 250000
|  |  |  | Feasibility Study on the development of a formal District Flea Market within the District | No formal Flea market within the District | Number of feasibility studies conducted on the development of a Flea Market within the District | 1 feasibility study conducted on the development of a Flea Market within the District | [5 empty] | 300000
To enhance growth of farmers production by June 2020 |  |  |  | Facilitate development of Farmer Support Production Unit (Agri-Park) | Agri Park Business Plan in place | Number of Farmer Support Production Unit (Agri-Park) developed | 1 Farmer Support Production Unit (Agri-Park) developed | [5 empty] | 1 000 000
|  |  |  | Facilitate Rehabilitation of Irrigation Schemes | None | Number of Irrigation Schemes rehabilitated | 1 irrigation scheme rehabilitated | [5 empty] | 0
| Develop Feasibility Study on Marula Processing Plant(Women, Youth and People with disability to be prioritised) |  |  | Develop Feasibility Study on Marula Processing Plant(Women, Youth and People with disability to be prioritised) | Marula Processing Plant business plan in place | Number of feasibility studies conducted | 1 Feasibility Study on Marula Processing Plant conducted | [5 empty] | 0
| Develop Industrial Development Master Plan for the Special Economic Zone (SEZ) |  |  | Develop Industrial Development Master Plan for the Special Economic Zone (SEZ) | SEZ Business Plan in place | Number of Regional Industrial Development Master Plan developed | 1 Regional Industrial Development Master Plan developed | [5 empty] | 500000
| Monitoring of the implementation of Mining Social and Labour Plans (for water & sanitation) |  |  | Monitoring of the implementation of Mining Social and Labour Plans (for water & sanitation) | 4 Mining Social and Labour Plans monitored | Number of Mining Social and Labour Plans monitored | 4 Mining Social and Labour Plans monitored | [5 empty] | 0
| Facilitate Economic Development Forums (Mining, Tourism & Agric) |  |  | Facilitate Economic Development Forums (Mining, Tourism & Agric) | Economic Development Forums (Mining, Tourism & Agric) | Number of Economic Development Forums (Mining, Tourism & Agric) facilitated | 3 Economic Development Forums (Mining, Tourism & Agric) facilitated | [5 empty] | 100000
Enhance the Tourism attraction within the District by 2020 |  |  |  | Develop Business Plan for Tjate Heritage Site | Dilapidated Tjate Heritage Site | Number of Business Plans for Tjate Heritage Site developed | 1 Business Plans for Tjate Heritage Site developed | [5 empty] | 150000
|  |  |  | Tourism Signage for Tourism Establishments (Manche Masemola, King Nyabela and Tjate) by 2020 | 3 existing District Tourism Signage for Tourism Establishments (Manche Masemola, King Nyabela and Tjate) | Number of District Tourism Signage for Tourism Establishments (Manche Masemola, King Nyabela and Tjate) installed | 3 District Tourism Signage for Tourism Establishments (Manche Masemola, King Nyabela and Tjate) installed | [5 empty] | R 500 000
INTEGRATED DEVELOPMENT PLAN
To ensure integrated development planning by June 2020 |  |  |  | Develop 2020/2021 IDP Framework/Process Plan | 2019/2020 IDP Framework/Process Plan in place | Number of IDP Frameworks/Process Plans developed | 1 IDP Framework/Process Plan developed | [5 empty] | 0
|  |  |  | Review of legally compliant Integrated Development Planning(IDP) | 1 legally compliant Integrated Development Planning(IDP) reviewed | Number of legally compliant Integrated Development Planning(IDP) reviewed | 1 legally compliant Integrated Development Planning(IDP) reviewed | [5 empty] | 320000
|  |  |  | Facilitate the IDP Rep Forums | Facilitated 2 IDP Rep Forums | Number of IDP Rep Forums facilitated | 2 IDP Rep Forums facilitated | [5 empty] | 50000

## MMs OFF
GOOD GOVERNANCE AND PUBLIC PARTICIPATION
2019-2020 SERVICE DELIVERY BUDGET AND IMPLEMENTATION PLAN
INTERNAL AUDIT
MEASURABLE OBJECTIVE | PROJECT | BASELINE 2018/2019 | INDICATORS | ANNUAL TARGET 2019/2020 |  | Q3 | Q4 | ACTION(Retained/Removed/Adjust | REASON FOR ADJUSTMENT | POE | BUDGET 2019/2020
To ensure improved internal controls and clean governance in the municipality by June 2020 | Development of the Three(3) Years rolling Plan | 2 approved 3 years rolling plan. | Number of development of 3 years rolling plan | 2 (SDM &SDA) 3 years rolling plan developed | No activity | No activity | No activity | Retain | None | Approved 3 Year rolling Plan for SDM and SDA | 900000
| Conduct Regularity audits | 38 Regularity audits conducetd | Number of regularity audits conducted | 20 Regularity Audit conducted | 5 regularity audit conducted | 6 regularity audit conducted | 5 regularity audit conducted | Retain | None | Signed Regularity Audit Reports
| Conduct Ad hoc Audits | 10 Ad hoc reports conducted | Percentage of Management / investigation conducted | 100% Management requests/ investigations conducted as and when required | 100% Management requests/ investigations conducted as and when required | 100% Management requests/ investigations conducted as and when required | 100% Management requests/ investigations conducted as and when required | Retain | None | Signed Management /Investigation reports
| Conduct ICT Audits | 4 ICT Audit conducted | Number of ICT Audit conducted | 4 ICT Audit conducted | 1 ICT Audit conducted | 1 ICT Audit conducted | 1 ICT Audit conducted | Retain | None | Signed ICT Audit Reports
| Conduct Perfomance Audits | 8 (4 SDM &4 SDA)PMS Audit and 8(4 SDM & SDA) Audit of Perfomance of Information conducted | Number of Performance Audit conducted | 8 PMS Audit (4 SDM & 4 SDA) 8 (4 SDM &SDA) AOPI conducted | 2 PMS and 2 AOPI conducted | 2 PMs and 2 AOPI conducted | 2 PMS Conducted 2 AOPI Audit conducted | Retain | None | Signed PMS and AOPI Audit Report
| Monitoring of implementation of auditor general activities | 100% monitoring of implementation of AG activities for 2018/2019 financial year | Percentage monitoring of implementation of AG activities for 2019/20 financial year | 100% monitoring of implementation of AG activities | 100% monitoring of implementation of AG activities | 100% monitoring of implementation of AG activities | 100% monitoring of implementation of AG activities | Retain | None | Audit Action plan,Agenda,Signed Minutes,proof of payments | R5 691 150.00
| Coordination of Audit Committee and Perfomance Audit Committee | 4 meetings of audit and performance committees coordinated | Number of meetings of audit and performance committees coordinated | 4 meetings of audit and performance committees coordinated | 1 meetings of audit and performance committees coordinated | 1 meetings of audit and performance committees coordinated | 1 meetings of audit and performance committees coordinated | Retain | None | Signed Minutes/Agenda/Signed AC Reports | R550 000.00
RISK MANAGEMENT
To assess, identify, manage risks and uncertainty in order to safeguard assets, enhance performance and ensure sustainability of operations by June 2020. | Conduct and review Strategic Risk Assessment | Strategic Risk Register in place | Number of Strategic Risk Assessment conducted and Strategic Risk Registers reviewed | *1 Strategic Risk Assessment conducted * 4 Strategic Risk Registers reviewed | 1 x Strategic Risk Register reviewed | 1 x Strategic Risk Register reviewed | 1 x Strategic Risk Register reviewed | Retain | None | Signed Strategic Risk Register | R0,00
| Conduct Operational Risk Assessment | Operational Risk Registers in place | Number of Operational Risk Assessment Conducted and Operational Risk Registers reviewed | *1 Operational Risk Assessment Conducted *4 Operational Risk Registers reviewed | 1 x Operational Risk Register reviewed | 1x Operational Risk Register reviewed | 1 x Operational Risk Register reviewed | Retain | None | Signed Operational Risk Register | R0,00
| Conduct Infrastructure and Water Services Projects Risk Assessment | 8 Projects Risk assessment conducted | Number of IWS Projects risk assessments conducted | 10 IWS Projects risk assessments conducted | 3 Projects risk assessments conducted | 3 Projects risk assessments conducted | 2 Projects risk assessments conducted | Retain | None | Signed Projects risk assessments report | R0,00
| Conduct Processes Risk Assessments | 2 Process risk assessment conducted | Number of Processes risk assessments conducted | 7 x Processes risk assessments conducted | 2 x Processes risk assessments conducted | 2 x Processes risk assessments conducted | 1 x Processes risk assessments conducted | Retain | None | Signed Processes Risk Register | R0,00
| Facilitate insurance coverage for municipal assets | Assets Insurance Policy contract facilitaed | Number of insurance coverage for municipal assets facilitated | All insurance coverage for municipal assets facilitated | All insurance coverage for municipal assets facilitated | All insurance coverage for municipal assets facilitated | All insurance coverage for municipal assets facilitated | Adjust | As per Provincial Treasury directive to ensure a funded budget. | Signed Assets Insurance Policy contract and endorsements | R4 603 344.00
| Facilitate Assets Insurance Claims and payments | Insurance claims report facilitated | Percentage processing and facilitation of insurance claims and payments | 100% insurance claims processing and payments facilitated | 100% insurance claims processing and payments facilitated | 100% insurance claims processing and payments facilitated | 100% insurance claims processing and payments facilitated | Retain | None | Signed Insurance Claims report and Claim register | 222183
| Manage Security operations and SLA | 8 Security operations and SLAs managed | Number of incidents occurred reported | All incidents occurred reported | All incidents occurred reported | All incidents occurred reported | All incidents occurred reported | Adjust | As per Provincial Treasury directive to ensure a funded budget. | Signed Security Management report | R 36 000 000
| Conduct Security Operational sites Assessments | Operational Sites Assessment report conducted | Number of Security Operational sites assessments conducted | Forty (40) Security Operational sites assessments conducted | 10 x Security Operational sites assessments conducted | 10 x Security Operational sites assessments conducted | 10 x Security Operational sites assessments conducted | Retain | None | Signed Security Operational sites assessment reports | R0,00
| Facilitate Anti-Fraud & Corruption hotline | 1 Fraud cases investigation | Number of fraud and corruption allegation cases reported for referral and investigations facilitated | All fraud and corruption allegation cases reported for referral and investigations facilitated | All fraud and corruption allegation cases reported for referral and investigations facilitated | All fraud and corruption allegation cases reported for referral and investigations facilitated | All fraud and corruption allegation cases reported for referral and investigations facilitated | Retain | None | Signed Fraud and Corruption report Signed Disclosure Hotline report | R0,00
| Facilitate Risk Management Committee activities | Risk Management training report facilitated | Number of Risk Management Committee(RMC) meetings facilitated | 4 x Risk Management Committee(RMC) meetings facilitated | 1 x Risk Management Committee(RMC)meeting facilitated | 1 x Risk Management Committee(RMC)meeting facilitated | 1 x Risk Management Committee(RMC) meeting facilitated | Retain | None | Signed Risk Management report | Fees paid from Line item - 33052270320EQMRCZZHO - C&PS: B&A AUDIT COMMITTEE
COMMUNICATIONS; ADVOCACY; SOCIAL FACILITATION; SPECIAL PROGRAMMES AND ARTS & CULTURE
To provide communications, stakeholders relations and strategic partnerships by June 2020 | Mayoral Outreaches and Sectoral Engagements | 12 Programmes facilitated | Number of community & sectoral engagements facilitated | 6 stakeholder & sectoral engagements facilitated |  | 2 stakeholder engagement/mayoral outreach facilitated | 2 stakeholder engagement/mayoral outreach facilitated | Adjusted | None | Signed Exit Report and Attendance Register | 1400000
| Executive Support to Mayoral Committee | 12 Mayoral Committee meetings supported | Number of Mayoral Committee meetings supported | 9 Mayoral Committee meetings supported |  | 3 Mayoral Committee meetings supported. | 3 Mayoral Committee meetings supported. | Adjusted | None | Signed Minutes and attendance registers | 0
| Media Relations and Marketing | 12 Media Relations & marketing done. | Number of media Relations | 9 Media Relations |  | 3 media relations facilitated | 3 media relations facilitated | New project | None | Copies of newsletters and puplications | 0
| Newsletter& Publications produced | 16 Programmes produced | Number of news letters and Publications produced | 4 newsletters and publications produced. |  | 1 special, 1 extenal, diaries and calenders produced | 1 special and 1 ertenal newsletter produced | Adjusted | Financial constraints | copies of newsletters and puplications | 400000
| Media Relations and Marketing | 12 Media Relations & marketing done. | Number of sinage and building paranating facilitated | 4 sinage and building paranating facilitated |  | 1 sinage and building paranating facilitated | 1 sinage and building paranating facilitated | Removed | Financial constraints | pictures and signed reports | 385000
| Website Management | 20 Website Updates undertaken | Number of Website Updates undertaken | 11 Websites Updates undertaken |  | 6 Websites Updates undertaken ( Mid-year reports,Budget and SDBIP adjustment,Quarter 2 SDBIP report, Annual report,Draft IDP and Budget, Finance reports) | 3 Websites Updates undertaken (Qarter 3 SDBIP report, Finance report, approved IDP and Budget, | Adjusted | Financial constraints | Screen short reports | 85212
| Traditional Leadership Affairs | 2 SPLUMA meeting supported | Number of Traditional Leaders hip meetings coordinated | 3 Traditional Leadership meeting coordinated |  | 1 Traditional Leadership meeting coordinated | 1 Traditional Leadership meeting coordinated | Adjusted | Financial constraints | Signed minutes and Attendance Register | 30000
| Special Mayoral strategic Events | 5 strategic events Facilitated | Number of Strategic Events facilitated | 7 Strategic Events facilitated |  | 1 x Strategic Events ( Kgoshi Mampuru) | 1x2 Strategic Events ( Bapedi Kings and Bakgaga Bakopa) facilitated | Retained | None | Attendance register and pictures | 400000
| Moral Regeneration Movement Committee | MRM committee established | Number of programmes for MRM committee facilitated | 2 Moral Regeneration Movement Committee facilitated |  | 1 Moral Regeneration Movement Committee facilitated | 1 Moral Regeneration Movement Committee facilitated | Adjusted | Financial constraints | Signed Exit Report and Attendance Register | 33156
To generate customer care reports by June 2020 | Customer Care Services | 24 reports generated | Number of reports generated | 24 queries/ complains reports on customer care generated |  | 6 Reports generates (3 SDM, 3 Premier and Presidential) generated | 6 Reports generates (3 SDM, 3 Premier and Presidential) generated | Retained | None | Signed reports | 0
To generate automated customer care system by June 2020 | Automated customer care system | Maunual System in place | Number of automated customer care system | 1 automated customer care system |  | 1 automated customer care system | No activity | Removed | Financial constraints | Signed reports | 0
To revamp and Maintain call centre by June 2020 | Call Centre Revamping &Maintenance | 24 hour outdated call centre system | Number of call centre revamped and Maintained | 1 call centre revamped and Maintained |  | No activity | No activity | Removed | Financial constraints | Signed Exit Report | R30 000
To inculcate the culture of people first by June 2020 | Batho Pele | 6 Programmes conducted | Number of Batho Pele Programmes conducted | 5 Batho Pele Programmes conducted |  | 1 Bathopele Programme conducted | 2 Bathopele Programme conducted | Retained | None | Signed Exit Report and Attendance Register | 60000
To encalcate culture of good performance by June 2020 | Executive Mayors Performance Excellent Awards | Performance Management Framework/Policy | Number of Performance Awards ceremony coordinated | 1 Performance Awards ceremony coordinated |  | No activity | No activity | Removed | Financial constraints | Signed Exit Report and picture | 0
To coordinate State of the District Address by June 2020 | SODA | 2018/2019 SODA held | Number of SODA coordinated | 1 SODA coordinated |  | 1 SODA coordinated | No activity | Retained | None | Signed exit report and attendance reister | 240000
To facilitate elderly programmess by June 2020 | Aged care | 2 aged programmes facilitated | Number of Aged Care programmes facilitated | 1 Aged Care programme facilitated |  | No activity | No activity | Adjusted | None | Signed exit reports and attendance registers | 90000
To facilitate children's campaigns by June 2020 | Children’s Care | 2 children’s activities facilitated | Number of children's activities facilitated | 1 children's activities facilitated |  | No activity | No activity | Adjusted | Financial constraints | Signed exit reports and attendance registers | R20 520
To facilitate woman development initiatives by June 2020 | Woman Development Initiative | 4 Women Programme initiatives facilitated | Number of woman development initiatives facilitated | 1 woman development initiatives facilitated |  | No activity | No activity | Adjusted | Financial constraints | Signed exit reports and attendance registers | 20000
To facilitate awareness campaigns for people with disability by June 2020 | People with disability | 3 awareness campaigns facilitated | Number of awareness campaigns for people with disability facilitated | 2 awareness campaigns for people with disability facilitated |  | 1 Human rights day for people with disability facilitated | No activity | Adjusted | Financial constraints | Signed exit reports and attendance registers | 20000
To facilitate promotions of indigenous languages and workshop by June 2020 | Cultural Heritage Celebrations and Language Promotions | 3 Programmes facilitated | Number of promotions of art and culture programmes facilitated | 1 promotions of art and culture programmes facilitated |  | No activity | No activity | Adjusted | Financial constraints | Signed exit reports and attendance registers | 220000
To coordinate health calendar days activities by June 2020 | Health calendar days activities | 3 health calendar days activities conducted | Number of health calendar days activities coordinated | 3 Health calendar days activities coordinated |  | 1 STI condom week, 1 TB day coordinated | 1 Canlde light coordinated | Adjusted | None | Signed exit reports and attendance registers | 20000
To coordinate District Health Council Programmes by June 2020 | District Health Council Programmes | Number of Support visits to health care facilities coordinated | 3 Support Visits to health care facilities coordinated | 4 Support Visits to health care facilities coordinated |  | 1 Support Visits to health care facilities coordinated | 1 Support Visits to health care facilities coordinated | Removed | Financial constraints | Signed Exit Report and Attendance Register | 20000
To facilitate Youth development programmes by June 2020 | Youth Opportunities Expo | 3 Programmes facilitated | Number of Youth development programmes facilitated | 2 Youth development programmes facilitated |  | No activity | 1 launching of Youth Council | Adjusted | Financial constraints | Signed exit reports and attendance registers | 100000
To facilitate Mayoral sport activities by June 2020 | Mayoral Sports activities | 3 Programmes facilitated | Number of Mayoral Sport activities facilitated | 1 Mayoral Sport activities facilitated |  | No activity | 1 Executive Mayor's Cup Facilitated | Adjusted | Financial constraints | Signed exit reports and attendance registers | 180000
PUBLIC PARTICIPATION, MPAC SUPPORT SECRETARIAT AND SUPPORT
To provide secretarial support to 10 Council structures to ensure accountability by June 2020 | FORA | 08 FORA facilitated | Number of fora facilitated | 16 Fora facilitated |  | 1 Speakers' Forum, 1 Chief Whips' Forum, 1 Public participation Forum facilatated. | 1 Speakers' Forum, 1 Chief Whips' Forum, 1 Public participation Forum, 1 MPAC forum 1 Secretariat Forum facilatated. | Retained | None | Attendance Register and Signed Notices. | 15000
| Public participation sessions. | 16 public participation sessions facilitated | Number of public consultation meetings facilitated | 15 public consultation meetings facilitated |  | 7 public consultation meetings on 2018/2019 draft annual report facilitated. . | 7 public consultation meetings on the IDP/Budget, 1 District Ward Committee Conference facilitated. | Retained | None | Attendance Register and Signed Notices. | 350000
| SODA & Budget day. | 1 SODA 1 Budget day facilitated. | Number of SODA and Budget days facilitated | 1 SODA and 1 Budget day facilitated |  | 1 Extra Special Council Meeting (SODA) Facilitated. | 1 Extra Special Council Meeting (Budget Speech) Facilitated. | Retained | None | Attendance Register and Signed Notices. | 200000
| Council and portfolio committee meetings. | 22 Council and portfolio committee meetings facilitated. | Number of schedule of council activities facilitated | 4 Ordinary Council Meetings and 20 Portfolio Committee Meetings facilitated |  | 1 Ordinary Council Meetings and 5 Portfolio Committee Meetings facilitated | 1 Ordinary Council Meetings and 5 Portfolio Committee Meetings facilitated | Retained | None | Attendance Register and Signed Notices. | 425 000. 00
| Study group. | New | Number of study groups facilitated | 4 study groups facilitated |  | 1 Study Group Facilitated. | 1 Study Group Facilitated. | Retained | None | Attendance Register and Signed Notices.
| Council whippery meetings | 4 council whippery meetings facilitated | Number of council whippery meetings facilitated | 4 council whippery meetings facilitated |  | 1 Council Whippery meeting Facilitated. | 1 Council Whippery meeting Facilitated. | Retained | None | Attendance Register and Signed Notices.
| Strategic planning sessions for Section 79 Portfolio Committees & MPAC | 2 strategic planning sessions facilitated | Number of strategic planning session facilitated | 2 strategic planning sessions facilitated |  | No Activity | 1 Section 79 Portfolio Committees Strategic planning Session facilitated. | Removed | budgeted constrains | Signed Exit Report. | 0
| Capacity building workshops | 3 capacity building workshops held | Number of capacity building workshops facilitated | 2 workshops facilitated |  | No Activity | 1 capacity building Workshop on Income tax facilitated. | Retained | None | Signed Exit Report. | 0
| Training and development programmes for Cllrs. | 2 X training and development programmes facilitated | Number of Cllrs identified for training programmes facilitated | 2 Cllrs identified for training programmes facilitated |  | No Activity | No Activity | Retained | None | Signed Exit Report. | 90000
| Oversight visits | 4 oversight visits facilitated | Number of oversight visits facilitated | 4 oversight visits facilitated |  | 1 Oversight visit facilitated. | 1 Oversight visit facilitated. | Retained | None | Signed Oversights Report. | 0
| Council Resolution registers | 4 Resolution registers developed and implemented | Number of Council Resolution registers compiled and coordinated | 4 Council Resolution registers compiled and coordinated |  | 1 council resolution register compiled and cordinated. | 1 council resolution register compiled and cordinated. | Retained | None | Council Resolution Register. | 0
| Public participation policy. | 1 public participation policy reviewed | Number of review of public participation policy facilitated | 1 review of public participation policy facilitated |  | Consolidate inputs for public participation policy. | submit draft review policy to council for approval. | Retained | None | Council Resolution Certificate. | 0
| MPAC Working sessions for Cllrs. | 8 MPAC working sessions facilitated | Number of MPAC working sessions for Cllrs held | 8 MPAC working sessions for Cllrs held |  | 2 MPAC working sessions facilitated. | 2 MPAC working sessions facilitated. | Retained | None | Attendance Register and Signed Notices. | 180000
| MPAC Public hearings | 2 MPAC public hearing facilitated | Number of MPAC public hearing facilitated | 2 MPAC public hearing facilitated |  | No Activity | 1 MPAC Public Hearing Facilitated. | Retained | None | Attendance Register and Signed Notices.