## Sheet1
LOCAL ECONOMIC DEVELOPMENT (LED)
2017/2018 SERVICE DELIVERY BUDGET AND IMPLEMENTATION PLAN: LED
MEASURABLE OBJECTIVE | INPUT | OUTPUT | OUTCOME | PROJECT | BASELINE 2016/2017 | INDICATORS | ANNUAL TARGET 2017/2018 | Q1 | Q2 | Q3 | Q4 | ACTION (Retained/Remove/ Adjust) | REASON FOR ACTION | BUDGET ADJUSTED | EVIDENCE(POE) | BUDGET | IMPACT | Amended
To facilitate business seminars by June 2018 | human and financial resources | seminars held | informed SMME's | Facilitate the Business Seminars | 2016/2017 financial year 2 Business seminars facilitated (Tourism and Business Compliance) | Number of Business Seminars Facilitated | 2 Business Seminars Facilitated | N/A | 1 business seminar facilitated | N/A | 2 business seminar facilitated | Retain | None | 50000 | *Seminar Report *Attendance Registers | 100000 | Improved business Information | 150000
To generate reports on municipal job creation by June 2018 | human resources | Job creation report | improved accountability | Municipal Job creation | 4 Reports generated for 2016/2017 | Number of reports generated on Municipal job creation | 4 reports generated on Municipal job creation | 1 report generated on Municipal job creation | 2 report generated on Municipal job creation | 3 report generated on Municipal job creation | 4 report generated on Municipal job creation | Retain | None | None | Quarterly reports | 0 | poverty alleviation
To generate reports on EPWP implementation by June 2018 | human resources | EPWP Reports | Improved EPWP coordination | Implementation of EPWP | 4 Quarterly reports generated | Number of reports on EPWP implementation | 4 reports on EPWP implementation generated | 1 reports on EPWP implementation generated | 2 reports on EPWP implementation generated | 3 reports on EPWP implementation generated | 4 reports on EPWP implementation generated | Retain | None | None | Quarterly reports | 0 | poverty alleviation
To conduct feasibility study for De Hoop dam and Flag Boshielo dam on fish farming by June 2018 | human and financial resources | Feasibility study report | Empowered SMME | Feasibility study on Fish farming | None | Number of Feasibility study conducted | 1 Feasibility study conducted | Conducting feasibility study | Conducting feasibility study | Conducting feasibility study | Finalised 1 feasibility study | Retain | None | 200000 | Feasibility study Report | 300000 | Enterprise development | 500000
To facilitate District Economic Development summit by June 2018 | human and financial resources | Economic Development Summit | Economic Development Summit | Facilitation of District Economic Development summit | None | Number of District Economic Development Summit held | 1 District Economic Development Summit held | N/A | N/A | 1 District Economic Development Summit held | N/A |  |  |  | Report | 500000 | Improved economic developemnt
To facilitate Trainings for SMME’s and Cooperatives by June 2018 | human and financial resources | Increased productivity | Empowered SMME | Trainings for SMMEs and cooperatives. | 2 Trainings provided during 2016/2017 financial year | Number of Trainings provided to SMME’s and Cooperatives | 4 Trainings provided to SMME’s and Cooperatives | No activity | 1 Trainings provided to SMME’s and Cooperatives | 2 Trainings provided to SMME’s and Cooperatives | 4 Trainings provided to SMME’s and Cooperatives | Retain | None | None | *Reports *Attendance registers | 0 | Improved productivy
To facilitate District Youth Opportunities Expo | human and financial resources | Opportunities Expo held | informed Youth SMME's | Facilitation of District Youth Opportunities Expo | 1 Youth Opportunities Expo held in 2016/2017 | Number of District Youth Opportunities Expo held | 1 District Youth Opportunities Expo held | No activity | No activity | No activity | 1 District Youth Opportunities Expo held |  |  |  | Report | 300000 | Improved business Information
To monitor the implementation of Social Labour Plans by June 2018 |  |  |  | Monitoring of Social Labour Plans | SLPs for 22 mines in LIM-476 in place | Number of quartely reports on SLPs implementation | 4 quartely reports on SLPs implementation | 1 quartely reports on SLPs implementation | 2 quartely reports on SLPs implementation | 3 quartely reports on SLPs implementation | 4 quartely reports on SLPs implementation | Retain | None | None | Reports | 0
To review the LED strategy by June 2018 | human and financial resources | Reviewed SDF | Improved spatial planning | Review of Local Economic Development (LED) Strategy | 2007/2008 LED Strategy in place | Number of LED Strategy reviewed | 1 | N/A | N/A | N/A | 1 |  |  |  | Reviewed strategy | 400000 | 0
To facilitate Enterprise and Supplier Development (ESD) by June 2018 |  |  |  | Facilitate Enterprise and Supplier Development (ESD) | None | Number of service providers appointed to implement ESD | 2 service providersappointed to implement ESD |  |  | Advertisement of call for proposals | Appointment of service providers | New project | None | None | *Appointment letters *Signed MOU | 0
To facilitate Regional Industrial Development by June 2018 |  |  |  | Regional Industrial Development (RID) | None | Number of RID Task Teams established | 1 RID Task Teams established |  |  | *Develop Terms of Referrence *Establish Task Team | Develop Terms of Referrence for RID Master Plan | New project | None | None | *Task Team TOR *RID Master Plan TOR | 0
To facilitate establishment of District Mining Forum by June 2018 |  |  |  | Establish Distric Mining Forum | None | Number of District Mining Forum established | 1 District Mining Forum established |  |  | Develop Terms of Referrence | Establish and launch District Mining Forum | New project | None | 150000 | *Terms of Referrence * Attendance register