## Sheet1
PMS
MEASURABLE OBJECTIVE | INPUT | OUTPUT | OUTCOME | PROJECT | BASELINE 2017/2018 | INDICATORS | ANNUAL TARGET 2017/2018 | Q1 | Q2 | Q3 | Q4 | ACTION (Retained/Remove/ Adjust) | REASON FOR ACTION | BUDGET ADJUSTED | EVIDENCE (POE) | BUDGET 2018-2019 | IMPACT
To facilitate Performance Lekgotla sessions by June 2018 | Human and financial Resouces | Lekgotla | Improved performance | Facilitation of Performance Lekgotla Sessions | 4 Performance Lekgotla Sessions held | Number of Performance Lekgotla held | 4 Performance Lekgotla Sessions facilitated | 1 Performance Lekgotla Sessions facilitated | 2 Performance Lekgotla Sessions facilitated | 3 Performance Lekgotla Sessions facilitated | 4 Performance Lekgotla Sessions facilitated | Retain | None | None | *Performance Lekgotla Sessions resolutions *attendence registers | R200 000 | Improved accontability
To develop 2018/2019 Institutional SDBIP by June 2018 | Human and financial Resouces | SDBIP | Improved management of service delivery | Development of 2018/2019 Institutional SDBIP | 2017/2018 Institutional SDBIP in place | Number of 2018/2019 Institutional SDBIP developed | 1 2018/2019 Institutional SDBIP developed | N/A | N/A | Draft 2018/2019 Institutional SDBIP in place | Final 2018/2019 Institutional SDBIP in place | Retain | None | None | Signed 2018/2019 Institutional SDBIP by Executive Mayor | 0 | Improved accontability
To develop 2016/2017 Annual Report by January 2018 | Human Resources | Annual Report | Improved accountability | Development of 2016/2017 Annual Report | 2015/2016 Annual Report in place | Number of 2016/2017 Annual Report developed | 1 2016/2017 Annual Report developed | N/A | N/A | *Draft 2016/2017 Annual Report in place *Public Participation *Final 2016/2017 Annual Report | N/A | Retain | None | None | *2016/2017 Annual Report *Attendance Registers | 0 | Improved compliance
To develop the 2017/2018 Performance Agreements for Senior Managers by 31 July 2017 | Human Resources | Signed performance agreements | Improved commitments | Development of 2017/2018 Performance Agreements for Senior Managers | Performance Agreements 2016/2017 in place | Number of 2017/2018 Performance Agreements for Senior managers developed | 7 2017/2018 Performance Agreements for Senior managers developed | 7 2017/2018 Performance Agreements for Senior managers developed | N/A | N/A | N/A | Retain | None | 0 | Signed Performance Agreements | 0 | Improved accontability
To review 100% PMS policy by June 2018 | Human Resources | Reviewed Policy and framework | Improved governance | PMS Policy and framework reviewal | 2016/2017 PMS policy and framework in place | % Review of PMS policy and framework | 100% Review of PMS policy and framework | 40% Circulation of the policy to stakeholders for inputs | 50% Submision of policy to management and council suport structures | Circulation of policy to management and council structures | 10% adoption of PMS policy and framework by council | Adjust | Target not achievable | 0 | Council resolution | 0 | Improved compliance
To coordinate Back to basics reports by June 2018 | Human Resources | Back to basics reports | Improved service delivery | Coordination of Back to Basics reports | 2016/2017 Back to Basics reports | Number of Back to Basics reports corodinated | 4 Back to Basics quarterly 12 monthly reports coordinated | 4 back to basics reports coordinated(1 quarterly and 3 monthly reports | 4 back to basics reports coordinated(1 quarterly and 3 monthly reports | 3 quarterly back to basics reports coordinated(1 quarterly report) | 4 quarterly back to basics reports coordinated(1 quarterly report) | Adjust | Target not achievable | 0 | Reports | 0 | Improved service delivery