## Sheet1
2018/2019 SERVICE DELIVERY BUDGET AND IMPLEMENTATION PLAN: INFRASTRUCTURE AND WATER SERVICES
MEASURABLE OBJECTIVE | PROJECT | BASELINE 2017/2018 | INDICATORS | ANNUAL TARGET 2018/2019 | Q1 | ACHIEVED/NOT ACHIEVED | ACTUAL PROGRESS | CHALLENGES | REMEDIAL ACTION | Portfolio of Evidence | BUDGET 2018-2019
RBIG
To construct pipeline from Burgersfort to Dresden pump station by June 2019 | Construction of Mooihoek Bulk Water Supply Phase 4E | Mooihoek bulk water supply phase 4D completed | Number of Kilometers of bulk pipeline constructed | 3 Kilometers of bulk pipeline constructed | Site establishment and 0.2km pipeline constructed | not achieved | site establishments. Clearing on the bulk pipeline route and Concrete reservoir position. | fund limitations | budget adjustments on the current financial year allocations to accommodate the project till April 2019 | Progress Report | 165255056
To construct reservoir at Burgersfort by June 2019 | Mooihoek bulk water supply phase 4BB | 1 X 5 Ml reservoir completed Phase 4A | Percentage reservoir constructed | 70%, 2 X 5 Ml concrete reservoir constructed | 15%, 2 X 5 Ml concrete reservoir constructed | achieved | 65% construction of 2x 5ML Concrete reservoir constructed | none | none | Progress Report
To construct bulk pipeline from Praktiseer to Motodi by June 2019 | Mooihoek bulk water supply phase 4F | Mooihoek bulk water supply phase 2 completed | Number of Kilometers bulk pipeline constructed | 4 Kilometers of bulk water pipeline constructed | Site establishment and 0.5km pipeline constructed | achieved | 42% construction of 4F2.5% construction of Phase 4F1 | fund limitations | budget adjustments on the current financial year allocations to accommodate the projects till April 2019 | Progress Report
To construct bulk pipeline at Mooihoek by June 2019 | Mooihoek bulk water supply phase 4H | Mooihoek Bulk water supply Phase 2 completed | Number of Kilometers of bulk pipeline constructed | 4 Kilometers of bulk water pipeline constructed | No activity | no activity | None | None | projects earmarked for implementation in the next financial year. | Progress Report
To construct bulk pipeline from Praktiseer to Alverton by June 2019 | Mooihoek bulk water supply phase 4G1 & G2 | Mooihoek Bulk water supply Phase 2 completed | Number of Kilometers of bulk pipeline constructed | 4 Kilometers of bulk water pipeline constructed | Site establishment and 0.5km pipeline constructed | not achieved | contractors appointed | fund limitations | projects earmarked for implementation in the next financial year. | Progress Report
To construct 400m long, 750mm diameter pipeline and 900m long, 450mm dimeter steel pipe line by June 2019. | Mooihoek bulk water supply phase C1.2 | 80% completion of 400m long, 750mm diameter pipe line and 900m long, 450mm dimeter steel pipe | Percentage completion of 400m long, 750mm diameter pipe line and 900m long, 450mm dimeter steel pipe | 100% completion of 400m long, 750mm diameter pipe line and 900m long, 450mm dimeter steel pipe | 85% completion of 400m long, 750mm diameter pipe line and 900m long, 450mm dimeter steel pipe | achieved | Pressure testing | limitted available water for testing. Lepelle prioritize filling up reservoirs for consumption | filling up pipes slowly whenever Lepelle allows | Completion certicicates
To Construct Mooihoek Tubatse 4C2:2700m, 500mm DIA and 2600m,400mm DIA Steel Water Pipeline by June 2018. | Mooihoek bulk water supply phase 4C2 | 90% Construction of Mooihoek Tubatse 4C2:2700, 500mm DIA and 2600, 400mm DIA Steel Water Pipeline, Installation of chambers fittings | Percentage Construction of 2700m, 500mm DIA and 2600, 400mm DIA Steel Water Pipeline. | 100% Construction of Mooihoek Tubatse 4C2:2700, 500mm DIA and 2600, 400mm DIA Steel Water Pipeline, Installation of chambers fittings | 95% Construction of Mooihoek Tubatse 4C2:2700, 500mm DIA and 2600, 400mm DIA Steel Water Pipeline, Installation of chambers fittings | achieved | Pressure testing | limitted available water for testing. Lepelle prioritize filling up reservoirs for consumption | filling up pipes slowly whenever Lepelle allows | Completion certicicates
To construct pumping pipeline from T-off of Makgeru to the new 10ML reservoir at Schoonoord, construction of gravity pipeline by June 2019 | Nebo BWS (RL19) Makgeru to Schoonoord | 55% Reservoir completed, Pipeline is completed | Percentage Bulk Pipeline constructed and Reservoir Completed | 100% Bulk Pipeline constructed and Reservoir completed | 60% Bulk Pipeline constructed and Reservoir completed | Achieved | Pipework is at 75%, Reservoir is at 90% Overall progress of project is 82% | 1. Delay in the procurement of material by DWS construction west due to budget constraints. 2. Closing of site office by Security company employees due to non-payment of wages as of 2nd October 2018 | 1. The municipality has taken a decision to procure the materials(Pipes) on behalf of DWS construction west. The tender for the pipes closed on the 13th of September 2018 and currently at bid evaluation/adjudication stages 2. Matter being currently addressed by DWS, Unions also involved to resolve the matter. | Progress Report | 45500000
To commission the 112 reinforced concrete valve chambers, 2 high lift pump stations, 30km 450dia c/m/l steel pipe from the wtw at ga-malekana to the 25ml command reservoir in jane furse by June 2019 | Nebo BWS Ga Malekana to Jane Furse Phase 1A | 85% Nebo Phase1A pipeline completed . | Percentage of pipeline tested and commissioned | 100% Nebo Phase1A pipeline completed . | 90% Nebo Phase1A pipeline completed . | Not achieved | Inspection and verifying of pipelines and installations = 80% Mechanical repairs on pipeline 2 = 30%. Overall progress on the commissioning of the project is 62%. | Damaged fittings | Refurbish fittings | Progress Report
To construct bulk pipeline from 25 ML reservoir in Jane Furse to Lobethal and 5 take-offs by June 2019 | Jane Furse to Lobethal BWS | 70% constructed pipeline from the existing 25ml Reservoir | Percentage of bulk water pipeline constructed connected to existing reservior | 100% Bulk Pipeline constructed and connected to the existing reservior | No activity | Not achieved | Draft termination | Water demand management | Align the project to feasibilty. Replace PSP with more capable PSP | Progress Report
To construct Bulk Pipeline and Valve Chambers by June 2019 | Moutse BWS Phase 1-6 | Bulk Pipeline and Valve constructed up 54% | Percentage Bulk Pipeline constructed | 100% Bulk Pipeline constructed | 55% Bulk Pipeline and Valve constructed | Not achieved | Legal handling the contractual matter. Pipes Draft procurement tender ready for advert | Unresolved contract disputes | Resolve contractual disputes | Progress Report | 34244944
To connect mechanical and Electrical (M & E) for the extensions to the Groblersdal Water Treatment Works by June 2019 | Moutse BWS Project 13 & 14 (RL14) | The upgrading of WTW is completed | Percentage of M&E components installed | 100% M&E Components Installed | 10% M&E Components Installed | Not achieved | Legal handling the contractual matter. Pipes Draft procurement tender ready for advert | Unresolved contract disputes | Resolve contractual disputes | Progress Report
To construct Bulk Pipeline and Valve Chambers by June 2019 | Moutse BWS Project 7 - 12 | Bulk Pipeline and Valve constructed up 54% | Percentage Bulk Pipeline constructed | 100% Bulk Pipeline constructed | 55% Bulk Pipeline and Valve constructed | Not achieved | Legal handling the contractual matter. Pipes Draft procurement tender ready for advert | Unresolved contract disputes | Resolve contractual disputes | Progress Report
WATER QUALITY
To generate Water Quality Reports by June 2019 | Generation of Water Quality Reports | 10 reports generated | Number of Water Quality Reports generated | 12 Water Quality Reports generated | 3 Water Quality Reports generated | Achieved | 12 Water Quality Reports generated | None | None | Progress Report | 5650000
To conduct Full SANS 241 Analysis by June 2019 | Full SANS 241 Water Quality Analysis | Signed CSIR SLA in 2015/16 financial year | Number of Full SANS 241 Analysis conducted | 1 Full SANS 241 Analysis (120 samples) conducted | 1 Full SANS 241 Analysis (30 samples) conducted | Achieved | 10 Samples conducted | None | None | Progress Report
To purchase Laboratories chemical by June 2019 | Purchase of LAB Chemicals | WTW & WWTW in place | Percentage of LAB chemical purchased | 100% of LAB chemical purchased | 100% of LAB chemical purchased | Achieved | 30%of the chemicals purchased | None | None | Progress Report
To participate in Blue and Green Drops Certification Programme by June 2018 | Plants participation in Blue and Green Drops Certification Programme | 15 Water Treatment Works participating in Blue Drop Certification programme in place | Number of Plants participating in Blue and Greed Drops Certification Programme | 15 WTW participating in Blue Drop and 16 WWTW Participating in Green Drop Certification Programme | 15 WTW participating in Blue Drop and 16 WWTW Participating in Green Drop Certification Programme | Not achieved | By-Laws, Risk Abatement and Wastewater safety plans uploaded on Green Drop System | Not collecting samples for waste water. Water Quality results not uploaded on Iris System. | None | Progress Report
O & M EXPENDITURE
To resolve registered sanitation incidents within 14 days. | Sanitation incidents | 700 registered sanitation incidents resolved within 14 days | Number of registered sanitation incidents resolved within 14 days | 700 registered sanitation incidents resolved within 14 days | 175 registered sanitation incidents resolved within 14 days | Achieved | 308 registered sanitation incidents resolved within 14 days | NONE | NONE | Progress Report | 35107845.47
To resolve registered water incidents within 14 days. | Water incidents | 7000 registered water incidents resolved within 14 days | Number registered water incidents resolved within 14 days | 7000 registered water incidents resolved within 14 days | 1 750 registered water incidents resolved within 14 days | Not Achieved | 1617 registered water incidents resolved within 14 days | SCM PROCESSES | TURN AROUND TIME | Progress Report
To render tankering services by June 2019 | Delivery of portable water | 9.6 Ml delivery of Potable Water in Jane Furse Hospital and Buffelshoek | Number tankering services rendered | 9.6 Ml delivery of Potable Water in Jane Furse Hospital and Buffelshoek | 2.4 Ml delivery of Potable Water in Jane Furse Hospital and Buffelshoek | Achieved | 8.37Ml delivery of Potable Water in Jane Furse Hospital and Buffelshoek | NONE | NONE | Progress Report | 14742000
To provide diesel consistently to diesel driven machines by June 2019 | Supply of diesel | 40 000ℓ of diesel supplied annually. | Number of Litres of diesel supplied annually | 40 000ℓ of diesel supplied annually. | 10 000ℓ of diesel supplied annually. | Achieved | 15 474.5ℓ of diesel supplied annually. | NONE | NONE | Progress Report | 1193000
To provide petrol consistently to petrol driven machines by June 2019 | Supply of petrol | 400ℓ of petrol supplied annually. | Number of Litres petrol supplied annually. | 400ℓ of petrol supplied annually. | 100ℓ of petrol supplied annually. | Achieved | 329ℓ of petrol supplied annually. | NONE | NONE | Progress Report
To provide oil consistently to diesel and petrol driven machines by June 2019 | Supply of oil | 300ℓ of oil supplied annually. | Number of Litres of oil supplied annually. | 300ℓ of oil supplied annually. | 75ℓ of oil supplied annually. | Achieved | 291ℓ of oil supplied annually. | NONE | NONE | Progress Report
To resolve registered M & E incidents within 14 days. | Mechanical & Electrical Services | 450 of registered M & E incidents within 14 days | Number of registered M & E incidents resolved within 14 days | 450 of registered M & E incidents within 14 days | 112.5 of registered M & E incidents within 14 days | Achieved | 121 of registered M & E incidents within 14 days | NONE | NONE | Progress Report | 3570000
To install Bulk Water Meters by June 2019 | Installation of Bulk Water Meters | 8 bulk water meters installed | Number of bulk water meters installed by June 2018 | 8 bulk water meters installed | 2 bulk water meters installed | Not Achieved | Bid adjudication committee recommended appointment of contractors for installation of bulk water metres | Appointment of Mechanical & Electrical Panel of Contractors | Finalization of Appointment | Progress Report | 500000
To purchase Mℓ Bulk water by June 2019 | ML Bulk Water Purchases | 10 062Mℓ of water purchased | Number Mℓ of water purchased | 10 062Mℓ of water purchased | 2 515.5Mℓ of water purchased | Achieved | 3 966.002Mℓ of water purchased | NONE | NONE | Progress Report | 110142000
PLANNING
To develop Water Conservation /Water Demand Management Strategy for SDM by June 2019 | Water Conservation and Water Demand Management Plan | Water Services Master Plan and WSDP developed in 2014/15 and 2015/16 FY respectively | Number of WC/WDM Strategy developed | One WC/WDM Strategy developed | Appointment of service provider for WC/WDM Strategy | Not achieved | Bid has long closed and evaluation conducted | Late appointment of the PSP | Fast track the appointment of the PSP | Draft WC/WDM strategy | 500000
To develop and review Water & Sanitation Master Plan by June 2019 | One Water & Sanitation Master Plan (WSMP) & WSDP | Professional Service Provider appointed in Nov 2016 scoping report and methodology developed. | Number of Water & Sanitation Master Plan developed | Drat Water & Sanitation Master Plan developed | Develop Terms of Reference and Appointment of PSP for Water & Sanitation Master Plan & WSDP | Not achieved | Terms of referance developed | Finilisation of 5 year reliability plan | Make inputs on draft 5 year reliability plan Present terms of referance to bid committee | Draft WSMP/WSDP | 1300000
To upgrade Groblersdal sewer pump- station by June 2019 | Groblersdal sewer network | Assessment report and upgrade portion of the outfall sewer system took place in 2015/16 financial year | km sewer pipe line inspected using the CCTV camera and report analysis. | To conduct 5km sewer pipeline CCTV survey in Groblersdal. | The PSP to submit inception report together with cost estimate for the CCTV survey. | Not achieved | Flow meters were installed at pump station | Inception report not yet submitted | Instruct the PSP to submit the inception report for review | Progress Report | 500000
To conduct Condition Assessment and develop O & M Plans by June 2019 | Conduct Condition Assessment and develop O & M Plans | 40% Development of O&M plan and Condition assesment of IWS infrastructure conducted | Percentage conduct of condition assessment and O & M Plan developed | 60% conduct of Condition Assessment and O & M Plan developed | 45% conduct of Condition Assessment and O & M Plan developed | Not achieved | Report for data collection Scheduling of workshop | Lack of Integrated review of the work excecuted by PSP | Ensure that the work executed by the PSP is reviewd by both Planning & O&M | Progress Report | 800000
To facilitate District Water & Sanitation Summit by June 2019 | District Water & Sanitation Summit | 2015 Water & Sanitation Resolution | Number of Water & Sanitation Summit facilitated | One District Water & Sanitation Summit facilitated | One District Water & Sanitation Summit facilitated | Achieved | District Water Summit conducted | None | None | Progress Report | 300000
To Conduct Feasibility Studies and develop Technical Report by June 2019 | Conduct Feasibility Studies and develop Technical Report | WSDP, IDP and BWS Master completed in plan 2014 | Number of Feasibility Studies conducted and technical report developed | 15 Feasibility Studies conducted and technical Reports developed | 5 Feasibility Studies conducted and technical Reports developed | Achieved | 5 Technical reports submitted to DWS | None | None | Progress Report | 5000000
WSIG PROJECTS
To complete Tukakgomo water reticulation by June 2019 | Tukakgomo water intervention and refurbishment. | 1 borehole drilled and equipped. Refurbished pumpstation Refurbished Rising main | Percentage completion of Tukakgomo water reticulation | 100% completion of Tukakgomo water reticulation | *Reticulation network at 100% | Not Achieved | SDM and PSP reviewing the scope to prepare for the appointment of the contractor. | Budgetary challenges has caused delays in the finalization of scope. | Adjustment budget item submitted. | Completion certicicates | 3961618
To construct bulk pipeline; reticulation and standpipes by June 2019 | Mahlwakwena to Mapodile pipeline(Tukakgomo Extension) | 1,8 rising main from the highlift pumpstation to the Elevated Steel tank costructed | Number of Kilometers of bulk pipeline, reticulation and standpipes constructed | 1.8km bulk pipeline, 6.3Km of reticulation network and 29 standpipes completed | *Excavations for internal reticulation(3km). *15 standpipes constructed | Achieved | Contractor and Consultant appointed and work on site to resume. | Budgetary challenges has caused delays in the finalization of scope. | Adjustment budget item submitted. | Completion certicicates | 5185203
To complete Phiring water reticulation & storage by June 2019 | Phiring Water Intervention(Leboeng) | 50% Borehole equipped & Footing for storage constructed. | Percentage of Kilometres of reticulation & storage constructed, borehole drilling & equipping | 100% of 3.5km of reticulation & storage constructed,Drilling and Equipping of boreholes | 40% of 3.5km of reticulation & 50% storage constructed,60% Drilling and Equipping of boreholes | Not Achieved | SDM and PSP reviewing the scope to prepare for the appointment of the contractor. | None | None | Completion certicicates | 2353179
To complete Internal Bulk -Distribution mains and Pressure Management System by June 2019 | Nebo Phase 1A testing and commissioning | 1.8km pipeline from 25ML reservoir to Mashishing Reservoir constructed | Percentage of Internal Bulk -Distribution mains and Pressure Management System | 100% completion of Internal Bulk -Distribution mains and Pressure Management System | 25% completion of Internal Bulk -Distribution mains and Pressure Management System | Not Achieved | Project Halted | The project is on the IDP but will be delayed due to the delayed completion of Nebo Phase 1A commissioning and insufficient budget. | The project will be implemented in the next financial year. | Progress Report | 6500000
To construct water reticulation at Apel Cross by June 2019 | Apel Cross RDP Reticulation network | 80% Construction of pipeline , relocation of elevated tanks and communal stand pipes | Percentage of Apel Cross water reticulation | 100% Construction of pipeline , relocation of elevated tanks and communal stand pipes. | 85% Construction of pipeline , relocation of elevated tanks and communal stand pipes. | Not Achieved | Project cancelled. Village benefitted in 2017/2018 | None | None | Progress Report | 3000000
To complete reticulation and installations of water meters by June 2019 | Flag Boshielo WC/WD Management( Letebejane pilot project) | 10km Reticulation network completed. | Percentage of Letebejane Water Project reticulation and installations of water meters. | 100% completion of Letebejane Water Project reticulation and installations of water meters. | 80% completion of Letebejane Water Project reticulation and installations of water meters. | Achieved | Contractor and Consultant appointed and work on site to resume. | There are challenges with subcontracting. The contractor has stopped working. | Local subcontractors to submit quotations to the main contractor. | Progress Report | 8000000
To complete Package Plant , risnig main and storage in Jane Furse RDP by June 2019. | Jane Furse RDP Package plant | 68% Borehole drilling & tesing, equipping & securing it with concrete pump house, Rising main complete. | Percentage of Package Plant , risnig main and storage in Jane Furse RDP completed. | 100% completion of Package Plant , risnig main and storage in Jane Furse RDP. | 70% completion of Package Plant , risnig main and storage in Jane Furse RDP | Not Achieved | A process to appoint a Service Provider for the package plant is ongoing. | None | None | Progress Report | 4000000
To develop water source and installations of rising main at Maebe by June 2019 | Maebe/Mohlaletsi interventions | Three (3) Boreholes drilled, tested and equipped. Securing of boreholes with concrete structures. | Percentage of water source and installations of rising main at Maebe. | 100% development of water source and installations of rising main at Maebe. | 40% development of water source and installations of rising main at Maebe. | Not Achieved | Design approved. PSP busy with Draft tender document completed and to be presented on Bid specification. | None | None | Progress Report | 4000000
To construct VIDP Sanitation units by June 2019. | Construction of Moretsele VDIP | 632 VDIP sanitations units completed | Number of VDIP sanitation units constructed | 370 VDIP Sanitation units constructed | No activity | No activity | Bid closed on the 11th of September 2018.Awaiting appointment of contractor. | None | None | Progress Report | 5000000
To refurbish and rehabilitate the existing reservior in Madibong village by June 2019. | Madibong Water Supply | Geohydrological studies 100% complete and the drilled boreholes are dry, then project is halted. | Percentage refurbish and rehabilitate the existing reservior in Madibong village. | 100% refurbishment and rehabilitation of the existing reservior in Madibong village. | No activity | no activity | Project halted | Area is dry | Commissioning of the 25ML reservoir will make the project functional. | Progress Report | 3000000
To constuct the water storage in Uitvlught by June 2019 | Uitvlught Water Supply | 69% construction of Pipeline, eskom, boreholes drilling & tesitng, equipping and securing with concrete pump house . | Percentage of water storage constructed in Uitvlught village | 100% of water storage constructed in Uitvlught village | 75% of water storage constructed in Uitvlught village | Not Achieved | Project cancelled. Village benefitted in 2017/2018 | None | None | Progress Report | 3000000
To develop water source by June 2019 | Mapulaneng drilling and equipping of borehole | New Infrastructure | Percentage of water source developed | 100% of water source developed. | 10% of water source developed. | Not Achieved | Project Halted | Insufficient funding | Funding to be solicited for feasibility. | Progress Report | 3000000
To construct water supply pipeline, package plant and steel storage tank June 2019 | Maseven Bulk Water supply project. | New Infrastructure | Percentage of water supply pipeline, package plant and steel storage tank completed | 100% completion of water supply pipeline, package plant and steel storage tank | 15% completion of water supply pipeline, package plant and steel storage tank | Not Achieved | Awaiting the appointment of Service provider through regulation 32. All supply chain documents received and verified | Delays in finalising the appoitment letter | Fast track the appointment letter to commence with the project | Progress Report | 14000000
MUNICIPAL INFRASTRUCTURE GRANT (MIG)
To construct VIP Sanitation units by June 2019 within Ephraim Mogale Municipality | VIP Sanitation Programme Phase 2.2 | 15 180 VIP Units constructed | Number of VIP sanitation units constructed | 1020 of VIP sanitation units constructed | No activity | Not Achieved | 1. Evaluation for Emerging contractors development concluded about R10m allocated for the program. 2. Bid closed on the 2 October 2018 | Appointment of Emerging contractors not yet finalised | Finalise Appointmenti of Emerging contractors and establish PSC | Progress Report | 20424125.3
To construct VIP Sanitation units by June 2019 within Elias Motsoaledi Municipality | VIP Sanitation Programme Phase 2.2 | 15 180 VIP Units constructed | Number of VIP sanitation units constructed | 1630 of VIP sanitation units constructed | No activity | No activity | 1. Evaluation for Emerging contractors development concluded about R10m allocated for the program. 2. Bid closed on the 2 October 2018 and the other is closing on the16 October 2018. | Appointment of Emerging contractors not yet finalised | Finalise Appointmenti of Emerging contractors and establish PSC | Progress Report | 21476511.6
To complete Zaaiplaas bulk pipeline, command reservior and pump station by June 2019 | Zaaiplaas Village Reticulation Phase 2 | 80% construction of Dindela Reservoir. Commissioning of bulk pipeline and pump station completed | Percentage of Zaaiplaas bulk pipeline, command reservior and pump station constructed | 100% of Zaaiplaas bulk pipeline, command reservior and pump station constructed | 85% of Zaaiplaas bulk pipeline, command reservior and pump station constructed | Not Achieved | 45% of Zaaiplaas bulk pipeline, command reservior and pump station constructed | Due to poor project performance, an intention to terminate both contractor and consultant have been issued. | The only respond received was from the contractor, a scheduled close-out meeting is scheduled for the 9th October 2018. | Completion certicicates | 424668.45
To upgrade and extend Roosenekal Waste Water Treatment Works (WWTW) by June 2019 | Roosenekal WWTW | 70% of Roosenekal WWTW done | Percentage Upgrading and Extension of Roosenekal WWTW constructed | 100% Upgrading and Extension of Roosenekal WWTW constructed | 75% Upgrading and Extension of Roosenekal WWTW constructed | Achieved | 84% Upgrading and Extension of Roosenekal WWTW constructed | None | None | Completion certicicates | 424668.45
To construct VIP Sanitation units by June 2019 within Makhuduthamaga Municipality | VIP Sanitation programme phase 2.2 | 15 180 VIP Units constructed | Number of VIP sanitation units constructed | 1835 VIP Sanitation units constructed | No activity | No activity | 11. Evaluation for Emerging contractors development concluded about R10m allocated for the program. 2. Bid is closing on the 16 October 2018. | Appointment of Emerging contractors not yet finalised | Finalise Appointmenti of Emerging contractors and establish PSC | Progress Report | 26325000
To construct reticulation network in Ga- Mashabela by June 2019 | Ga- Mashabela water reticulation supply | 60% of water reticulation constructed | Percentage of water reticulation supply construction | 100% construction of water reticulation constructed | 85% construction of water reticulation constructed | Not achieved | Overall 80% progress Mohwelere is at 70% Talane is at 95% Masetlwe is at 85% Mashabela is at 10% | 1. None 2. Masetlwe -Community unrest & ESKOM connection delayed the project 3. None 4.Mashabela:Delays due to disputes on the source, letter for the go ahead received on 04 Oct 2018,signed by the tribal council | 1.None 2. Masetlwe – application for extension of time and engage ESKOM to complete the project 3. None 4. Mashabela- Consultants to be given an instruction to proceed with the works Awaiting the final decision from the community regarding the borehole site | Completion certicicates | 23896521.22
To construct reticulation network in Ga- Marishane by June 2019 | Ga- Marishane water reticulation supply | 30% water reticulation constructed | Percentage of water reticulation supply constructed | 100% water reticulation supply constructed | 45% construction of water reticulation constructed | Not achieved | Overall progress is still at 27%.Time lapsed is 75%. Material (pipes and steel) has been delivered. | Slow progress by the contractor due to poor financial management | Contract has been recommended for termination. | Completion certicicates | 9590358.5
To construct reticulation network in Lobethal by June 2019 | Lobethal water supply | 40% construction constructed | Percentage of water reticulation supply constructed | 100% water reticulation supply constructed | 60% construction of water supply constructed | Achieved | Overall progress 65% | None | None | Completion certicicates | 424668.45
To construct reticulation network in Ga- Phaahla by June 2019 | Ga- Phaahla water supply | 40% construction constructed | Percentage of water supply constructed | 100% water reticulation supply constructed | 60% construction of water supply constructed | Not achieved | Physical progress= 84% | None | None | Completion certicicates | 6721314.72
To construct Fetakgomo Tubatse LM VIP Sanitation units by June 2019 | VIP Sanitation programme phase 2.2 | 15 180 VIP Units constructed | Number of VIP sanitation units constructed | 715 VIP Sanitation units constructed | No activity | No activity | 1. Evaluation for Emerging contractors development concluded about R5m allocated for the program. 2. Bid closed on the 02 October 2018 and the other is closing on the 16 October 2018. | Appointment of Emerging contractors not yet finalised | Finalise Appointmenti of Emerging contractors and establish PSC | Progress Report | 9805283.89
To construct completion of bulk water reticulation in Mooiplaas and Strydkraal Supplement by June 2019 | Contract 21,22& 24 : (Bulk, Res, PS & WDM Chamber in various villages | 85% Water supply below RDP level | Percentage of bulk water reticulation in Mooiplaas and Strydkraal Supplement constructed | 100% completion of bulk water reticulation in Mooiplaas and Strydkraal Supplement constructed | 90% completion of bulk water reticulation in Mooiplaas and Strydkraal Supplement constructed | Achieved | Overall progress 95% | None | None | Completion certicicates | 9000000
To complete Concrete reservoirs; Bulk Water Supply;and Reticulation at Nkadimeng: Phase 9 to 11 by June 2019 | Nkadimeng RWS Extension 2( Phase 9 to 11) (Fetakgom o) Ga- Mmela to Mashilavele , Ga- Pahla, Molapong, Ga- Magolego, Mankontu and Masehleng | 40% Nkadimeng WTW, Command Reservoir, reticulation and bulk line below RDP level constructed | Percentage Completion of Concrete reservoirs; Bulk Water Supply; Reticulation. | 100% Completion of Concrete reservoirs; Bulk Water Supply; Reticulation at Nkadimeng: Phase 9 to 11 | 60% Completion of Concrete reservoirs; Bulk Water Supply; Reticulation at Nkadimeng: Phase 9 to 11 | Not achieved | Overall progress = 57%. | The lack of commitment by the main contractor on the project. | To initiate termination process for poor performance | Completion certicicates | 15937980.32
To construct VIP Sanitation units by June 2019 (Fetakgomo Greater Tubatse LM) | VIP Sanitation programme phase 2.2 | 15 180 VIP Units constructed | Number of VIP sanitation units constructed | 1 630 VIP Sanitation units constructed | No Activity | no activity | 1. Evaluation for Emerging contractors development concluded about R10m allocated for the program. 2. Bid closed on the 2 October 2018 and the other is closing on the 16 October 2018 | Appointment of Emerging contractors not yet finalised | Finalise Appointmenti of Emerging contractors and establish PSC | Progress Report | 25311841.99
To construct command reservoir, pump station and pipelines at GaMaphopha by June 2019 | Ga - Maphopha Command Reservoir | 20% completion of Maphopha Command Reservoir constructed | Percentage completion of command reservoir, pump station and pipelines at Ga-Maphopha constructed | 100% completion of command reservoir, pump station and pipelines at Ga-Maphopha constructed | 40% completion of command reservoir, pump station and pipelines at Ga-Maphopha constructed | Achieved | pump station is at 99% and the command reservoir and pipeline is at 77% complete | None | None | Completion certicicates | 9000000
To construct connector pipe network in Lebalelo South by June 2019 | Lebalelo South connector pipes | 30% connector pipes constructed | Percentage of connector pipe network constructed | 100% of connector pipe network constructed | 40% of connector pipe network constructed | Achieved | For the Bulk Pipelines The overall progress is at 40%. System 1 - Busy with excavations, bedding, pipe laying, Backfilling and compaction – Progress 33% System 2 - currently busy with the excavations, Bedding, Pipe laying, back filling and compaction -Progress 33% System 3 - Currently Busy with the excavations, Bedding, pipe laying, Backfilling and compaction -Progress 59% | Community from ward 19 stopping the project indicating that they were not consulted during the formation of PSC and the appointment of labourers. Business forum stopping the contractor None | The issue has since been resolved. The issue has since been resolved. None | Progress Report | 70558516.71
To construct reticulation network and reservoirs in Lebalelo South phase 2 by June 2020 | Lebalelo South reticulation pipe & water storages | Project advertised and waiting procurement of Contractors | Percentage completion of reticulation network & reservoirs in Lebalelo South phase 2 | 50% of reticulation network and reservoirs in Lebalelo South phase 2 constructed | No Activity | no activity | System 1 – Contractor has been appointed and recently introduced to the community. System 2 - Contractor has been appointed and recently introduced to the community. System 3 - Contractor has been appointed and recently introduced to the community. For the Reservoir At tender evaluation stage. | None | None | Progress Report | 195614540.39 | ,
MUNICIPAL HEALTH SERVICES
To render effective and efficient Environmental pollution prevention by June 2019 | Environmental Pollution Prevention | 07 Awareness Campaigns on Air Quality | Number of air quality awareness campaigns conducted. | 12 Awareness Campaigns on Air Quality | 3 air quality awareness campaigns conducted. | Achieved | 3 Awareness campaigns conducted | None | None | Attendance register | 220000
To render effective and efficient Water quality monitoring by June 2019 | Water quality monitoring | 147 Water quality samples collected | Number of water quality samples collected | 300 Water quality samples collected | 75 water samples collected | Achieved | 75 Water samples collected | None | None | Samples results | 41820
To render effective and efficient Food Safety control by June 2019 | Foof Safety control | 914 Evaluated food premises | Number of food premises evaluated | 1400 Food Premises evaluated | 350 food Premises evaluated | Achieved | 379 Food Premises evaluated | None | None | Evaluation Report | 40800
To render effective and efficient Health Survailance of premises by June 2019 | Waste Management | 69 Health care risk waste monitored | Number of health care risk waste monitored | 100 Health care risk waste monitored | 25 Health care risk waste monitored | Achieved | 31 Health care risk waste monitored | None | None | Evaluation Report | 0
To render effective and efficient Health Survailance of premises by June 2019 | Health Survailance of premises | 668 Premises evaluated | Number of premises evaluated | 1200 Premises evaluated | 300 premises evaluated | Achieved | 332 Premises evaluated | None | None | Evaluation Reports | 0
To render effective and efficient communicable diseases outbreak control by June 2019 | Communicable Diseases outbreak Control | 142 communicble diseases outbreak traced | Number of communicable diseases investigated and controlled | All communicable diseases investigated and controlled | 4 Kilometers of bulk water pipeline constructed | Achieved | 30 Communicable diseases investigated and controlled | None | None | Reports | 50000
To render effective and efficient Survaillance and prevention of communicable deseases by June 2019 | Survaillance and prevention of communicable deseases | 142 communicable diseases traced | Number of Communicable diseases awareness campaigns held | 100 Communicable diseases awareness campaigns held | 25 Communicable diseases awareness campaigns held | Achieved | 26 Communicable diseases awareness campaigns held | None | None | Attendance registeres | 20400
To render effective and efficient Vector control by June 2019 | Vector Control | 774 Premises monitored | Number of vector on premises monitored | 1000 Premises monitored | 250 premises monitored | Achieved | 290 Premises monitored | None | None | Evaluation Reports | R0,000.00
To render effective and efficient Disposal of the dead by June 2019 | Disposal of the dead | 58 Disposal of the dead facilities evaluated | Number of disposal of the dead facilities evaluated | 100 Disposal of the dead facilities evaluated | 25 Disposal of the dead facilities evaluated | Achieved | 29 Disposal of the dead facilities evaluated | None | None | Evaluation Reports | 0
To render effective and efficient chemical safety by June 2019 | Chemical safety | 202 Chemical handling premises evaluated | Number of chemical handling premises evaluation conducted | 300 Chemical handling premises evaluations conducted | 75 chemical handling premises evaluations conducted | Achieved | 89 Chemical handling premises evaluations conducted | None | None | Evaluation Report | 0
EMERGENCY MANAGEMENT SERVICES
To render effective and efficient Fire and rescue operation by June 2019 | Fire and Rescue Operations | 489 responses to all emergency services incidents attended. | Number of reported Emergency Services incidents attended | All reported Emergency Services incidents attended | All reported Emergency Services incidents attended | Achieved | 257 of all reported Emergency Services incidents attended | None | None | Report | 0
To render an effective and efficient Emergency Management Services Training Academy by June 2019 | Emergency Management Services Training Academy | 6 firefighting training activities conducted | Number of firefighting courses facilitated | 5 firefighting courses facilitated | 1 firefighting course facilitated | Achieved | 3 firefighting courses facilitated. (First-Aid Level 3, Assessor training course and Fire Safety and Prevention training course) | None | None | Report | 31200
To render an effective and efficient Fire Safety and Prevention by June 2019 | Fire Safety and Prevention | 897 Fire Safety and Prevention activities conducted | Number of reported fire safety and prevention services conducted | All reported fire safety and prevention services conducted | All reported fire safety and prevention services conducted | Achieved | 164 of all reported fire safety and prevention services conducted | None | None | Report | R0 00
To render an effective and efficient EMS Equipment by June 2019 | EMS Equipment | 77 hydraulic rescue equipment’s | Number of required supply to stations facilitated | All required supplies to stations facilitated | All required supplies to stations facilitated | Achieved | *29 of all the required supply to stations facilitated. (fire service fleet for service, 1 new set jaws-life awaited delivery & a set jaws-life repairs with psp) | None | None | Report | R180 471,00
To render an effective and efficient Calibrations, Accreditation and South African National Standards Licenses by June 2019 | Calibrations, Accreditation and South African National Standards Licenses | 70 Self Contained Breathing Apparatus (SCBA) and 2 flow meters. | Number of renewed licenses, calibrated tools and accredited services facilitated | All renewed licenses, calibrated tools and accredited services facilitated | All renewed licenses, calibrated tools and accredited services facilitated | Achieved | 138 of renewed South African National Standard Codes tool kit and calibrated tools facilitated. (135 SANS codes+3 RFC Portable Flow & Pressure test Meters) | None | None | Report | R30 000.00
DISASTER MANAGEMENT SERVICES
To render effective and efficient Disaster risk assessment by June 2019 | Disaster risk assessment | 166 disaster management incidents | Number of reported disaster management incidents attended | All reported disaster management incidents attended | All reported disaster management incidents attended | Achieved | 56 disaster management incidents attended | None | None | Attendance registers | 350000
To render effective and efficient Disaster risk reduction by June 2019 | Disaster risk reduction | 6 public education, training and awareness campaigns conducted | Number of disaster risk reduction awareness campaigns conducted | 24 disaster risk reduction awareness campaigns conducted | 6 disaster risk reduction awareness campaigns conducted | Achieved | 13 disaster risk reduction awareness campaigns conducted | None | None | Attendance registers
To render effective and efficient Disaster response and recovery by June 2019 | Disaster response and recovery | 346 blankets and 126 mattresses provided to all disaster affected victims | Number of relief material to all affected disaster victims coordinated and provided | All relief material to all affected disaster victims coordinated and provided | All relief material to all affected disaster victims coordinated and provided | Achieved | 256 blankets, 140 sponges and 04 temporary shelters coordinated and provided to all disaster affected victims. | None | None | Report
To render effective and efficient Disaster management plan and framework review by June 2019 | Disaster management plan and framework review | Disaster Management plan and framework reviewed in 2015/2016 | Number of Disaster management plan and framework reviewed | 1 Disaster management plan and framework reviewed | Risk assessments in all four local municipalities done | Achieved | Risk assessments in all four local municipalities done | None | None | Reviewed disaster management plan and Framework | R0 00
To render effective and efficient Special Operations by June 2019 | Special Operations | 03 Arrive Alive campaigns | Number of special operations on high density days campaigns conducted | 03 special operations on high density days campaigns conducted | 1 special operations high density campaigns conducted | Achieved | 01 special operations high density campaigns conducted for September Moria operations | None | None | Operational plan, attendance register and minutes | 30000
INTERGOVERNMENTAL RELATIONS
To render effective and efficient IGR for the department by June 2019 | Municipal Health Services Fora and Environmental management Forums | *4 Municipal Health Services Fora and *2 Environmental Management Forums coordinated | Number of Municipal Health Services Fora coordinated | *4 Municipal Health Services Fora and *2 Environmental Management Forums coordinated | 1 Municipal Health Services Forum coordinated *1 Environmental Management Forum coordinted | Achieved | 1 Municipal Health Services Forum coordinated *1 Environmental Management Forum coordinted | None | None | Minutes and attendance register | R10 000
| Community Safety forum | (2017/2018) 5 District Community Safety Forum coordinated (midterm) | Number of Community Safety Forum coordinated | 10 Community Safety Forum coordinated | 2 Community Safety Forum coordinated | Achieved | 3 Community Safety Forum coordinated. (2 for the district and 1 for the provincial CSF board). | None | None | Minutes and attendance register
| District Disaster Advisory Forum meetings | 2 Advisory forum coordinated | Number of Advisory fora coordinated | 4 Advisory fora coordinated | 1 Disaster advisory forum coordinated | Achieved | 1 District Disaster advisory forum coordinated | None | None | Minutes and attendance register