## Sheet1
2018/2019 SERVICE DELIVERY BUDGET AND IMPLEMENTATION PLAN: CORPORATE SERVICES
STRATEGIC OBJECTIVE | INPUT | OUTPUT | OUTCOME | PROJECT | BASELINE 2017/2018 | INDICATORS | ANNUAL TARGET 2018/2019 | Q1 | Q2 | Q3 TARGETS | PROGRESS (Achieved/ Not achieved) | ACTUAL PROGRESS | CHALLENGE | REMEDIAL ACTIONS | EVIDENCE | BUDGET 2018-2019
LABOUR RELATIONS
To facilitate 12 Local Labour Forum (LLF) meetings by June 2019 | Human and financial resources | Meetings | Improved employer/employee relationship | Local Labour Forum | 7 LLF meetings held | Number of Local Labour Forum meetings facilitaed | 12 Local Labour Forum meetings facilitated | 3 LLF meetings facilitated | 3 LLF meetings facilitated | 3 LLF meetings facilitated | Not Achieved. | 2 LLF Meetings facilitated. | Failure to meet quorum by the management. | To solicit the intervention of the MMC of Corporate Services | Minutes and attandence registers | 50000
To issue 4 Labour Relations Publications by Jne 2019 | Human and financial resources | Publications | Informed workforce | Labour Relations Publications | 2 Labour relations publication issued | Number of Labour relations publication issued | 4 labour relations publications issued | 1 Labour Relations Publication issued | 1 Labour Relations Publication issued | 1 Labour Relations Publication issued | Achieved. | 1 Labour relations publication issued. | None | None | Labour Relations Publications issued | 0
To facilitate 100% resolution of grievance cases by June 2019 | Human and financial resources | Grievance facilitation | Speedy resolution of disputes | Grievance cases | 2 resolution of grievance cases facilitated | Number of resolution of grievance cases facilitated | All resolution of grievance cases facilitated | All resolution of grievance cases facilitated | All resolution of grievance cases facilitated | All resolution of grievance cases facilitated | Achived. | All resolution of grievance cases facilitated | None. | None. | Grievance register | 0
To facilitate 100% resolution of misconduct cases by June 2019 | Human and financial resources | Misconduct facilitation | Adherence to policies, processes and rules | Misconduct cases | 8 resolution of misconduct cases facilitated | Number of resolution of misconduct cases facilitated | All resolution of misconduct cases facilitated | All resolution of misconduct cases facilitated | All resolution of misconduct cases facilitated | All resolution of misconduct cases facilitated | Achieved. | All resolution of misconduct cases facilitated | None. | None. | Misconduct case register | 0
Information & Communication Technology
To enhance service delivery through optimal use of information technology by June 2019 | Human and Financial Resources | Disaster Recovery Site | Enabling business environment | ICT Infrastructure upgrade and maintenance | All five (5) sites in Groblersdal area have fully fledged LAN and WAN network infrastructure | Number of DRP site managed | 1 DRP site established | Appointment of service provider, signing of SLA and handing over of site. | No activity | No activity | N/A | N/A | N/A | NA | * Award Letter * Signed SLA * Hand over report * Tax invoices | R1 200 000
| Human and Financial Resources | Audio Recording System | Improved information management |  | Offsite data storage location | Number of Council audio recording system purchased | 1 Council digital audio recording system installed | Appointment of service provider, signing of SLA. | No Activity | 1 Council digital audio-recording sytem installed | Achieved | 1 Council digital audio-recording sytem installed | None | None | * Award Letter * Signed SLA * Hand over report * Tax invoices | 150000
| Human and Financial Resources | Servers and desktop computers with their related peripherals | Improved ICT infrastructure |  | 17 Servers and 400 desktops /laptops | % of ICT hardware replaced | 100% ICT hardware replaced as and when required | 100% ICT hardware replaced as and when required | 100% ICT hardware replaced as and when required | 100% ICT hardware replaced as and when required | Achieved | 100% ICT hardware and consumables repalced as an when requested | None | None | * Tax invoice * Hardware * Distribution Register | 402650
| Human and Financial Resources | Wide Area Network Connectivity links | Improved ICT infrastructure |  |  | Number of WAN sites supported | 5 WAN sites supported | Terms of Reference for 5 WAN sites submitted to the Bid Specifications Committee | No Activity | Appointment of service provider, signing of SLA. | Achieved | Service provider appointed and SLA signed | None | None | * Awad Letter * Project Plan * Tax Invoice | 770000
To manage information services by June 2019 | Human and Financial Resources | SLA Reports, Latest Software updates | Compliance and Accountability | ICT Service Management | 12 Service Level Agreement meetings held with Telkom, Unics, Open Kingdom Technologies and BCX | Number of SLA performance service standards managed | 8 SLA performance service standards managed | 2 SLA performance service standards managed | 2 SLA performance service standards managed | 2 SLA performance service standards managed | Achieved | 4 SLA performance standards managed | None | None | • SLA reports * Tax invoices | R4 000 000
[5 empty] | 11 approved software licenses renewed | Number of approved software licenses renewed | 9 approved software licenses renewed | 2 approved software licenses renewed | 2 approved software licenses renewed | 2 approved software licenses renewed | Achieved | 3 approved software licences renewed (SSL certificate, Teammate and VIP) | None | None | • Tax invoices | R2 500 000
Organizational Efficiency and Development
To facilitate the development and implementation of benchmark framework by June 2019 | Human and Financial Resources | Bechmark Framework Developed | Efficiency & effectiveness | Benchmark Framework | None | Number of benchmark framework developed | 1 Benchmark framework developed | *Gather information & analyse | * Develop a draft framework . | *Consult with relevant stakeholders * Submit final benchmark framework for approval. | Not Achieved | Consultation with relevant stakeholders done (Internal Audit). | Final Draft Benchmark Framework not approved | Fastrack the approval of the Final Draft Bechmark in Q4 | Approved Benchmark Framework | 300000
To facilitate 4 change management sessions by june 2019. | Human and Financial Resources | Advocacy sessions facilitated | Improved Productivity | Change Management Program | Change management strategy for placement in place | Number of change management sessions held with employees facilitated | *4 change management sessions facilitated. | *1 change management sessions facilitated | *1 change management sessions facilitated | *1 change management sessions facilitated | Achieved | *1 Change management facilitated in IWS & BTO respectively | None | none | Change management report
To facilitate re-evaluation of 116 jobs by June 2019 | Human and Financial Resources | Evaluated Jobs | Eqaul pay for equal jobs | Job Evaluation | 143 jobs evaluated | Number of jobs re- evaluated | 116 jobs re- evaluated | Re- evaluate (58) jobs & submit to SALGA for moderation | Re- evaluate (58) jobs & submit to SALGA for moderation | Interpretation of results and submit for Council approval: Publish the results | Not Achieved | 58 Jobs evaluated and submitted to SALGA for moderation | Moderation is done but results cannot be interpreted due to non approval of Wage Curve | SALGA Limpopo province to consult with SALG BC to approve the long awaited Wage Curve | Job evaluation report and minutes.
To facilitate 2 organisational development interventions/ assessment by June 2019 | Human and Financial Resources | Employee satisfaction survey reports | Improved Productivity | Employee Satisfaction Survey | Report of Employee satisfaction survey | Number of feedback sessions facilitated with employees | 2 feedback sessions facilitated with employees | No activity | 1 feedback sessions facilitated with employees | No activity | N/A | None | None | None | Report and attendance register
AUXILIARY SERVICES
To facilitate 4 awareness campaigns for records management by June 2019. | Human and financial resorces | Records management | Improved records management | Records management | 4 Records awareness programme | Number of awareness campaigns on records management facilitated | Four (4) records awareness campaigns facilitated | One (1) records awareness campaigns facilitated | One (1) records awareness campaigns facilitated | One (1) records awareness campaigns facilitated | Achieved | Three (3) awareness records campaingns facilitated | None | None | Report and attendance register | 2300000
To update personnel files by June 2019 | Human and financial resorces | Personnel files | Availability of documents of files |  | 920 personnel files updated | Number of personnel files updated | 920 personnel files updated | No activity | 306 personnel files updated | 306 personnel files updated | Achieved | 306 personnel files updated | None | None | List of updated files
To facilitate disposal of inactive records by June 2019 | Human and financial resorces | Inactive records | Improved records |  | 3 750 inactive records listed | Number of disposal of inactive files listed | 2500 inactive records listed for disposal | 625 inactive records listed for disposal | 625 inactive records listed for disposal | 625 inactive records listed for disposal | Achieved | 1162 inactive records listed for disposal done | None | None | Register of listed inactive records
To institutionalise document management services by June 2019 | Human and financial resorces | Document management | Improved photocopy and printing services |  | Tender, 920 personnel files, leave files, travel claims recorded | Number of departments provided with document management services | 3 departments provided with document management services( IWS, PED & CPS) | No activity | 1 department provided with document management services (CPS) | 1 department provided with document management services (IWS) | Achieved | 1 department provided with document management services (IWS)56244 water documents, 1357 tenders, 12592 mail, 512574 copies & 3689 claims recorded | None | None | Report and register
To manage leased fleet by June 2019 | Human and financial resorces | Leased vehicles | Improved management of fleet | Fleet management | 150 fleet managed | Number of fleet managed | 167 fleet managed ( 33 SDM owned, 102 Leased IWS, 27 Leased CMS, 3 Leased BTO, 2 Leased CPS) | 167 fleet managed | 167 fleet managed | 167 fleet managed | Achieved | 167 fleet managed | None | None | Payment register of leased fleet | 50235951
To facilitate security of municipal fleet by June 2019 |  |  |  |  | 25 municipal fleet provided with tracking system | Number of municipal owned fleet with tracking system managed | 33 municipal owned fleet with tracking system managed | 33 municipal owned fleet with tracking system managed | 33 municipal owned fleet with tracking system managed | 33 municipal owned fleet with tracking system managed | Achieved | 33 municipal owned fleet with tracking system managed | None | None | Payment register for tracking ,fleet tracking reports
To facilitate the purchsae of 4 water tankers by June 2019 |  |  |  |  | New Project | Number of water tankers purchased | 4 water tankers purchased | Procurement process | Delivery of four (4) water tankers | No activity | N/A | N/A | N/A | N/A | Delivery note | 4500000
To ensure payment of licenses subscriptions by June 2019. | Human and financial resorces | Licenses | Improved management of fleet |  | 25 payment of licenses paid | Number of fleet licenses renewed | 33 fleet licenses renewed | 18 fleet licenses renewed | 15 fleet licenses renewed | No activity | N/A | N/A | N/A | N/A | Payment register of licenses | 102000
To facilitate maintenance and repairs of fleet by June 2019 | Human and financial resorces | Repairs and maintanance | Secured vehicles |  | 25 fleet provided with maintanance. | Number of fleet provided with maintainance. | All fleet provided with maintainance. | All fleet provided with maintainance. | All fleet provided with maintainance. | All fleet provided with maintainance. | Achieved | All fleet provided with maintainance. | None | None | Register maintenance and repairs | 600000
To ensure management of fuel by June 2019 | Human and financial resources | Vehicle maintanance | Secured vehicles |  | R7,200 000 of fuel purchased | Rand value of fuel limit managed | R6,600 000 of fuel limit managed | R1,650 000 of fuel limit managed | R1,650 000 of fuel limit managed | R1,650 000 of fuel limit managed | Not Achieved | R2 617 362,72 of fuel managed. | Fuel budget insufficient | Fuel budget to be increased. | Monthly bank statement | 6600000
To ensure provision of office furniture by June 2019 | Human and financial resorces | Office equipments | Safe working environment | Facility Management | Lekgotla boardroom furniture, couches and boardroom chairs for 4 fire stations | Number of offices to be provided with office furniture | 8 offices to be provided with office furniture (6 managers offices, 1 ICT and 1 canteen) | No activity | 1 ICT and 1 canteen provided with furniture | No activity | N/A | N/A | N/A | N/A | Delivery note | 578600
To ensure management of leased and SDM owned facilities by June 2019 | Human and financial resorces | Office rental | Safe working environment |  | 5 offices leased, 41 owned facilities managed | Number of facilities managed | 5 leased and 41 owned facilities managed | 5 leased and 41 owned facilities managed | 5 leased and 41 owned facilities managed | 5 leased and 41 owned facilities managed | Achieved | 5 leased and 41 owned facilities managed | None | None | Register of payment for office rental and municipal services. | 8000000
Human Resources Development
To manage and provide human capital development to capacitate the SDM by June 2019 | Human and Financial Resources | Organizational Training Plan | Strategic human capital development | Organizational Training Plan for 2019 | 2017/18 Training Plan (Workplace Skills Plan ) | Number of Organizational Training Plans for 2019/2020 financial year developed | 1 Organizational Training Plans for 2019/2020 financial year developed | No Activity | No activity | Facilitate Training Committee and Staff information siting to communicate Training Plan | Achieved | Training Committee facilitated and the training plan communicated | None | None | Training Plan | 0
| Human and Financial Resources | Awarded bursaries | Improved human capital development | External Bursaries | 3 external bursaries awarded in 2017/18 | Number of bursaries maintained in 2018 | 16 external bursraies maintained | Maintain 16 external bursaries | Maintain 16 external bursaries | Maintain 16 External Bursaries | Achieved | 16 Bursaries Maintained | None | None | Bursary Letters and Contracts | 1900000
| Human and Financial Resources | Awarded bursaries | Improved human capital development | Internal Bursaries | 10 internal bursaries awarded in 2017/18 | Number of bursaries maintained in 2018 | 10 bursaries maintained | Maintain 10 internal bursaries | Maintain 10 internal bursaries | Maintain 10 internal Bursaries | Achieved | 10 internal Bursaries Maintained | None | None | Bursary Letters | 1202000
Human Resources Management
To facilitate filling of funded and vacant posts by June 2019 | Human and Financial resources | Reduced Vacancy rate | Improved Productivity | Recruitment and retention | 24 Employees appointed | Number of vacant and funded posts filled | All vacant and funded posts filled | All vacant and funded posts filled | All vacant and funded posts filled | All vacant and funded posts filled | Achieved | All vacant and funded posts were filled(8) | None | None | Appointment Letters, adverts and memo signed by MM. | 250000
To ensure compliance submission of Employment Equity (EE) plan by June 2019 | Human resources | Employment Equity Report | Compliance and Accountability | Employment Equity (EE) | EE plan in place | Number of EE reports compiled and submitted | 1 EE report compiled and submitted to the Department of Labour | No Activity | Consultation with Employment Equity Forum | 1 EE report submitted | Achieved | 1 EE report submitted | None | None | Proof of submission of EE report | 0
To implement Human Resource plan by June 2019 | Human resources | HR Plan | Improved Productivity | Human resources Plan | 2017-2020 HR plan available | Number of HR Plan implemented | 1 Human Resource plan implemented | 1 HR Plan implemented | 1 HR Plan implemented | 1 HR Plan implemented | Achieved | 1 HR Plan implemented(Induction and Recruitment) | None | None | HR Plan report | 0
EMPLOYEE WELLNESS AND OCCUPATIONAL HEALTH AND SAFETY
To conduct wellness and counselling programmes by June 2019 | Human and Financial Resourcese | Healthy Life Style | Improved Work Performance and Productivity | Employee Wellness and counselling programmes | 15 *Wellness and counselling programme conducted (2 stress and trauma management programmes, conducted 12 wellness awareness programmes, 1 Wellnes day done). | Number of wellness and counselling programmes conducted | 29 wellness and counselling programmes conducted (12 wellness awareness campaign, 12 Fun walks, 2 stress and trauma management, 1 SAIMSA, 1 IMMSA, 1 wellness day | 7 Wellness and counselling programme conducted (3 wellness awareness campaign, 3 Fun walks, 1 SAIMSA) | 7Wellness and counselling programme conducted (3 wellness awareness campaign, 3 Fun walks, 1 stress and trauma management) | 7 Wellness and counselling programme conducted (3 wellness awareness campaign, 3 Fun walks, 1 stress and trauma management | Achieved | 7 Wellness and counselling programmes conducted (3 wellness awareness campaigns, 3 Fun walks, 1 stress and trauma management) | None | None | *Wellness and counselling reports *Attendance Registers * SAIMSA report *IMMSA report Substance abuse programme and attendance registers | 760000
To facilitate substance abuse programme by June 2019 |  |  |  | Substance abuse programme | 12 substance abuse programme facilitated | Number of substance abuse programme facilitated | 12 substance abuse programme facilitated | 3 substance abuse programme facilitated | 3 substance abuse programme facilitated | 3 substance abuse programme facilitated | Achieved | 3 Substance abuse programme conducted (3 group counselling for substance abusers done) | None | None
To conduct occupational health and safety elements by June 2019. | Human and Financial Resources | Healthy and Safe Enviroment | Improved Healthy and Safe Enviroment | Occupational Health and Safety elements | 60 Occupational Health and Safety elements conducted (Project audits, Work place and tools inspection, Servicing of fire extiquishers, provision of PPE and Health and Safety Committee meetings). | Number of Occupational Health and Safety elements conducted. | 69 Occupational Health and Safety elements conducted. | 17 Occupational Health and Safety elements conducted. | 17 Occupational Health and Safety elements conducted. | 18 Occupational Health and Safety elements conducted. | Achieved | 21 Occupational Health and Safety elements conducted (13 workplace inspections, 4 projects audits, 3 safety awareness campaigns held and 1 safety committee meeting held). | None | None | * Occupational Health and Safety elements *Reports *Attendance Registers | 2800000
To conduct medical surveillance programme by June 2019 | Human and Financial Resources | Healthy employees and Healthy and Safe Enviroment | Improved health of employees and Healthy and Safe Enviroment | Medical Surveillance programme | 0 employees were subjected to medical surveillance programmes | Number of employees undergone medical surveillance programme | 1 Medical surveillance programme conducted | No Activity | No Activity | No activity | N/A | N/A | N/A | N/A | No activity
|  |  |  | DIRECTOR: CORPORATE SERVICES | [7 empty] | DATE