## Sheet1
2018/2019 SERVICE DELIVERY BUDGET AND IMPLEMENTATION PLAN: MUNICIPAL MANAGER'S OFFICE
STRATEGIC OBJECTIVE | PROJECT | BASELINE 2017/2018 | INDICATORS | ANNUAL TARGET 2018/2019 | QUARTER 1 TARGET | ACHIEVED/NOT ACHIEVED | ACTUAL PROGRESS | CHALLENGES | REMEDIAL ACTION | EVIDENCE | BUDGET 2018-2019
INTERNAL AUDIT
To provide internal audit services to SDM and SDA by June 2019 | Development of 2018-2021 Three Year Internal audit rolling plan | 100% approved 2017-2019 Three Year Rolling plan | Percentage development of the Three(3) Years rolling Plan | 100% development and implementation of the Three(3) Years rolling Plan | 100% development of Three Year rolling Plan | Achieved | 100% development of Three Year rolling Plan | None | None | Approved Three Year rolling Plan | 0
To conduct review of internal control systems for SDA and SDM by June 2019 | Conduct Regularity audits | 38 Regularity audits issued | Number of regularity audit conducted | 38 Regularity audits conducted | 8 Regularity audits conducted | Achieved | 8 Regularity audits conducted | None | None | Regularity Audit Reports | 900000
To perform management requests/ investigations by June 2019 | Management / investigation requests | 4 Management / investigation performed | Percentage Management requests/ investigations performed as and when required | 100% Management requests/ investigations performed as and when required | 100% Management requests/ investigations performed as and when required | Achieved | 100% Management requests/ investigations performed as and when required | None | None | Management /Investigation reports | 0
To evaluate and assess information and communication technology by June 2019 | Conduct ICT Audits | 4 ICT Audit reports conducted | Number of ICT audits conducted | 4 ICT Audit reports conducted | 1 ICT Audit report conducted | Achieved | 1 ICT Audit report conducted | None | None | ICT Audit Reports | 0
To evaluate and assess municipal performance information by conducting Performance Audit by June 2019 | Conduct performance audits | 4 Performance Audit conducted | Number of Performance Audit conducted | 4 Performance Audit conducted | 1 Performance Audit conducted | Achieved | 2Performance Audit conducted | None | None | Performance Audit Reports | 0
To monitor implementation of AG Action Plan for 2017/2018 financial year by June 2019 | Monitoring implementation of AG Action Plan | 2016/17 Unqualified external audit report issued | Percentage monitoring of implementation of AG action plan for 2017/18 financial year | 100% monitoring of implementation of AG action plan for 2017/18 financial year | 100% monitoring of implementation of AG action plan for 2017/18 financial year | Achieved | 100% monitoring of implementation of AG action plan for 2017/18 financial year | None | None | Audit Action plan,Agenda/Minutes/Reports | 0
To facilitate external audit fees payments for 2017/18 financial year by December 2018 | Facilitation of External audit fees payments for 2017/18 financial year | 100% 2016/17 financial year external audit fees paid | Percentage external audit fees for 2017/18 financial year facilitated | 100% external audit fees for 2017/2018 financial year facilitated | 100% external audit fees for 2017/2018 financial year facilitated | Achieved | 100% external audit fees for 2017/2018 financial year facilitated | None | None | Claim schedule Register/Proof of payments | 4691150
To coordinate the activities of the audit committee and performance audit committee by June 2019 | Coordination of activities of Audit Committee and Performance audit Committee | 6 Audit and Performance activities coordinated | Number of activities of audit and performance committees coordinated | 4 activities of audit and performance committees coordinated | 1 activity of audit and performance committees coordinated | Achieved | 3 activity of audit and performance committees coordinated | None | None | Minutes/Agenda/AC Reports | 400000
RISK MANAGEMENT
To conduct and review Strategic Risk Assessment by June 2019 | Conduct and review Strategic Risk Assessment | Approved 2017/2018 FY strategic Risk Register | Number of Strategic Risk Assessment and reviews conducted | *1 Strategic Risk Assessment conducted * 4 Strategic Risk Registers reviewed | 1 Strategic Risk register reviewed | Achieved | 1 Strategic Risk Register reviewed | None | None | Strategic Risk Register and Reviewed Risk register | 0
To conduct Operational Risk Assessment by June 2019 | Conduct Operational Risk Assessment | Approved 2017/2018 FY Operational Risk Registers | No of Operational Risk Assessment and reviews conducted | *1 Operational Risk Assessments Conducted *4 Operational Risk Registers reviewed | *1 Operational Risk review conducted | Achieved | 1 Operational Risk Register review conducted | None | None | Operational Risk Registers Reviewed Risk Registers | 0
To conduct Infrastructure and Water Services Projects Risk Assessment by June 2019 | Conduct Infrastructure and Water Services Projects Risk Assessment | 2017/2018 FY Projects Risk assessment Reports in place. | All IWS Projects risk assessments conducted | All IWS Projects risk assessments conducted | All Projects risk assessments conducted | Achieved | All Projects risk assessments conducted | None | None | Projects Risk Asessment report | 0
To conduct Processes Risk Assessments by June 2019 | Conduct Processes Risk Assessments | 2011/12 risk assessments | Number of processes risk assessments conducted | 7 x Processes risk assessments conducted | 2 Processes risk assessment conducted | Not Achieved | None | Capacity constraint due to staff shortage | To conduct assessments in the 2nd Quarter | Processes risk registers | 0
To facilitate placement of insurance coverage for municipal assets by June 2019 | Facilitation of placement insurance coverage for municipal assets | 2017/2018 FY Assets Insurance Policy contract in place. | Number of insurance coverage for municipal assets facilitated. | All insurance coverage for municipal assets facilitated | All insurance coverage for municipal assets facilitated | Achieved | Insurance coverage for municipal assets facilitated | None | None | Assets Insurance Policy Contract | R2 200 000
To facilitate of Assets Insurance Claims and payments by June 2019 | Facilitation Assets Insurance Claims and payments | 2017/2018FY insurance claims report in place. | Number of assets insurance claims processing and payments facilitated. | All assets insurance claims processing and payments facilitated | All assets insurance claims processing and payments facilitated | Achieved | All assets insurance claims processed. | None. | None | Quarterly Insurance Claims Report | 350000
To Manage Security operations and SLA by June 2019 | Management of Security operations and SLA | 4 Security Contracts and SLAs in place. | Number of Security operations and contracts managed | 4 Security operations and contracts managed | 4 Security operations and contracts managed | Achieved | 4 Security operations and contracts managed | None | None | Quarterly Physical security report | 35000000
| Fencing of Operational sites | 2017/2018FY Security Assessment report | Number of Operational Sites fenced | Five (5) Operational sites fenced | No activity | Not Applicable | N/A | N/A | N/A | Security fencing report
To Ccnduct Security Operational sites Assessments by June 2019 | Conduct Security Operational sites Assessments | 2017/2018 Security Operational sites Assessments reports in place | Number of security operational sites assessments conducted | Forty (40) Security Operational sites assessments conducted | 10 Operational sites assessed | Not Achieved | Four ( 4) Security operational sites assessessments conducted | Competing work commitments that leads to capacity constraint | Coordinate the expediting of placement of the new Senior Risk Officer to create capacity Conduct outstanding assessment in the 2nd Quarter | Security operational sites report | 0
To provide VIP Security protection by June 2019 | Provide VIP Security protection | Government Gazette No. 41335, SALGA Circular 36/2017 and COGHSTA Notice - 08/01/2018 | Percentage VIP Security protection provided | 100% personal VIP security protection to SDM provided. | 100% personal VIP security protection to SDM provided | Achieved | 100% personal VIP security protection to SDM provided | None | None | Quartely Physical security report | 0
To have an Improved accountability and transparency by June 2019 | Facilitation of Anti-Fraud & Corruption hotline | 2017/2018FY Fraud cases reported for referral and investigation. | Percentage fraud and corruption allegations cases reported for referral and investigations facilitated | 100% fraud and corruption allegation cases reported for referral and investigations facilitated | 100% fraud and corruption allegation cases reported for referral and investigations facilitated | Not Applicable | Report received from Delottee only reflects prank calls and dropped calls | No incidents reported due to possible lack of interest and unfamiliarity of the Disclosure Hotline | Popularise the Disclosure Hotline through workshops | Quarterly Disclosure Hotline report | 190000
| Monitor compliance management | 2017/2018 FY Compliance Report in place | Number of Compliance Management activities monitored | 4 x Compliance management activities monitored | 1x Compliance management activities monitored | Achieved | 1x Compliance management activities monitored | None | None | Quarterly Compliance management report | 0
To improve risk management culture by June 2019 | Undertaking of Risk Management trainings | 2017/2018FY Risk Management training report in place. | Number of Risk Management trainings undertaken | 3 x Risk Management training undertaken. | 1 Risk Management training conducted | Not Achieved | Training module developed | Capacity constraint due to staff shortage | Reschedule training for the Second (2) quarter | Training module and Workshop attendance register | 0
To improve governance by June 2019 | Facilitation of Risk Management Committee activities | 4 Risk management committee meetings facilitated and coordinated. | Number of risk management committee meetings facilitated | 4 x Risk Management Committee meetings facilitated | 1 x Risk Management Committee meeting facilitated | Achieved | 1 x Risk Management Committee meeting facilitated | None | None | Quarterly Risk Management reports | 0
| Conduct Blue and Green Drop Risk Assessments | Risk Management Framework in place | No of Blue and Green Drop Risk Assessments conducted | 8 x Blue Drop and 7 x Green drop assessment conducted | 2 x Blue Drop and 2 x Green drop assessment conducted | Not Achieved | None | Capacity constraint due to staff shortage | Coordinate the expediting of placement of the new Senior Risk Officer | Quarterly Blue and Green drop assessment reports | 0
To facilitate the development of Business Continuity Management Plan by June 2019 | Develop BCM plan | 2015/2016 Risk Assessment report in place | Percentage development of BCM Plan facilitated | 100% development of BCM Plan facilitated | 100% development of BCM Plan facilitated | Achieved | 100% development of BCM Plan facilitated BIA conducted | None | None | BCM phases report | 0
LEGAL SERVICES
To attend to the letigations by June 2019 | Litigations | 8 Litigations cases attended | Number of litigations attended | All litigations attended | All litigations attended | Achieved | 02 cases attended to, which are: 1. Rendeals Four Consulting case, 2. Waterskills (Pty) Ltd case | None | None | Summons and Court Judgments | 3000000
To draft requested Contracts by June 2019 | Contracts | 50 Contracts and Services level Agreement drafted | Number of contracts requested and drafted | All contracts requested and drafted | All contracts requested and drafted | Achieved | 10 contracts drafted and 06 contracts vetted | None | None | Contract Register and drafted contratcs and service level agreements | 0
To draft requested legal opinions by June 2019 | Legal opinions | 10 legal Opinions drafted | Number of Requested Legal Opinions drafted | All requested Legal Opinions drafted | All requested Legal Opinions drafted | Achieved | 02 Legal Advisory services provided.1. Legal Advice on legal repercussion of the Municipality water pipelines encroached by the communities; and how to protect the Municipality against any possible litigation by community members who built on or near the waterlines. 2. Legal Advice on whether the Municipality should deduct the cost of outstanding service of establishment of the Disaster Recovery Infrastructure prior to effecting payment of outstanding invoices to Dimension Data. | None | None | Drafted legal opinions register | 0
To capture claims by and against the municipality by June 2019 | Compilation of litigation Register | 2017/18 Litigation register | Number of cases by and against the municipality captured | All cases by and against the municipality captured | All cases by and against the municipality captured | Achieved | 02 Litigations matters recorded | None | None | Litigation register, copies of court judgments and Settlements agrements | 0
To record Contracts by June 2019 | Compilation of contract register | 300 contracts recorded | Number of contracts recorded | All contracts recorded | All contracts recorded | Achieved | 16 Contracts recorded in Contract register | None | None | Contracts Register
PERFORMANCE MANAGEMENT SYSTEM (PMS)
To facilitate performance Makgotla by June 2019 | Facilitation of Makgotla | 4 Performance Makgotla Sessions held | Number of Performance Lekgotla Sessions facilitated | 4 Performance makgotla Sessions facilitated | 1 Performance Lekgotla Session facilitated | Achieved | 1 Performance Lekgotla facilitated (02 August 2018) | None | None | *Performance Lekgotla Sessions resolutions *attendence registers | R100 000. 00
To develop 2019/2020 Institutional SDBIP | Development of 2018/19 Institutional SDBIP | 2017/2018 Institutional SDBIP in place | Number of 2018/2019 Institutional SDBIP developed | 01 2018/2019 Institutional SDBIP developed | No activity | N/A | N/A | N/A | N/A | Signed 2018/2019 Institutional SDBIP by Executive Mayor | 0
To compile 2017/2018 Institutional Annual Report by 31 January 2019 | Compilation of 2017/2018 Annual report | 2017/2018 Annual Report in place | Number of 2017/2018 Annual Report developed | 01 2017/2018 Annual Report developed | No activity | N/A | N/A | N/A | N/A | *2016/2017 Annual Report *Attendance Registers | 0
To develop 2018/2019 Performance Agreements for senior managers, managers and Performance commitment for level 4 & 5 officials | Development of 2018/2019 Performance Agreements for Senior Managers, Managers and Performance commitments for level 4 & 5 officials | 2017/2018 Performance agreements and Performance commitments in place | Number of 2018/2019 Performance Agreements for Senior Managers, managers and Performance Commitments for level 4 & 5’s developed | 07 2018/2019 performance agreements for Senior Managers, 32 managers and 80 performance commitments for level 4 & 5’s developed | 07 2018/2019 performance agreements for Senior Managers, 32 managers and 80 performance commitments for level 4 & 5’s developed | not achieved | *07 2018/2019 performance agreements for Senior Managers developed, signed and submitted to Coghsta *21 of 32 managers developed and signed *49 of 80 performance commitments for level 4 & 5’s developed, signed and submitted | *The following PAs are still oiutstanding to-date; 11 *Income, Planning & Regulations, DD(IWS), O&M X2, OD, EAP, HRM, Risk,(Labour & Legal appointed done in Sept. & Oct) *The following PCs are still outstanding, Risk- x 2, Legal- x2, All PCs from IWS, Office of the Chief-Whip- x1, HRM- x4, HRD- x2, ICT- x1, Auxiliary-x2 | Continuous engagement with departments through dashboard as a reminder to submit outstanding information is done | Signed Performance Agreements and Performance commiitments | 0
To facilitate the performance assessment for senior managers and managers by June 2019 | Facilitation of performance Assessments | 2017/2018 performance assessment for senior managers conducted | Number of performance assessment for senior managers conducted | 2 performance assessment (2017/18 Annual and 2018/19 Mid year) for senior managers conducted | No activity | N/A | N/A | N/A | N/A | Performance assessments reports | 0
To review PMS policy by June 2019. | PMS Policy and Framework Review | 2017/2018 PMS Policy and Framework in place | Percentage Review of PMS Policy and Framework | 100% Review of PMS Policy and Framework | No activity | N/A | N/A | N/A | N/A | Council resolution | 0
To coordinate quarterly Back to Basics reports by June 2019 | Coordination of B2B reports | 2017/2018 B2B reports in place | Number of quarterly B2B reports coordinated | 4 quarterly B2B reports coordinated | 1 quarterly back to basics reports coordinated | Achieved | 1 quarterly back to basics reports coordinated and submitted to Coghsta | None | None | Quarterly Reports | 0
PUBLIC PARTICIPATION; MPAC SUPPORT; SECRETARIAT AND SUPPORT
To have functional Council and Committees of Council by June 2019. | IGR Forums | 08 Fora | Number of fora facilitated | 16 fora facilitated | 1 Speakers' Forum , 1 Chief Whips' Forum and 1 public participation forum facilitated | Achieved | 1 Speakers' Forum held on 11/09/18, 1 Chief Whips' Forum held on 13/09/18, 1 Public participation forum held on 23/08/18 | None | None | Attendance registers & signed notices | 15000
| Public participation consultations | 16 public participation sessions | Number of public consultation meetings facilitated | 18 public participation consultation meetings facilitated | No activity | No activity | No activity | No activity | No activity | Attendance registers & signed notices | 0
| Section 79 Committees strategic planning | 2 strategic planning sessions facilitated | Number of strategic planning session facilitated | 2 strategic planning sessions facilitated | 1 strategic planning sessions facilitated | Achieved | 1 strategic planning session held on 01 - 02/08/18 | None | None | Exit Report | 0
| Capacity building workshop for councillors | 3x capacity building workshops held | Number of workshops facilitated | 3 Workshops facilitated. (2 Income Tax and 1 Code of conduct) | 1 capacity building workshop on Rules of Order and Standing Orders of Council/Code of Conduct facilitated | Achieved | 1 capacity building workshop on Code of Conduct was facilitated on 5 September 2018. | None | None | Exit Report | R120 000.00
| Training of councillors | 3 Councilors trained | Number of Councilors identified for training | 5 Councilors identified for training | No activity | No activity | No activity | No activity | No activity | Exit Report | 0
| Councillors’ welfare | 5 X queries 12 X assistance on claims attended. | Percentage queries of Cllrs facilitated | 100% queries of Councillors facilitated. (Recording queries 10%, submission and attending to the queries 70%, Feedback 20%) | 100% queries of Councillors facilitated. (Recording queries 10%, submission and attending to the queries 70%, Feedback 20%) | Achieved | 100% Quiries attended to and claims submitted. | None | none | Exit Report | 0
| Oversight visit | 4 oversights visits facilitated | Number of oversight visits facilitated | 4 oversight visits facilitated *pre-oversight visit *sessions with project managers *compile pre-oversight report | 1 oversight visit facilitated | Achieved | 1 oversight visit facilitated. Oversight visits conducted to Bulk water supply at Ga Thokoane,Mampuru,Zaaiplaas and Ga Moretsele were conducted in September 2018. | None | None | Oversight report | 100000
| Implementation of Schedule of Council Activities | 22 Council and portfolio committee meetings held | Number of council activities facilitated | 24 council activities facilitated | 6 meetings facilitated (1 council meeting and 5 portfolio committee meetings) | Achieved | 17 meetings facilitated. *4 council meeting, *13 portfolio committee meetings | None | None | Attendance registers & signed notices | 665000
| Compilation of Council resolution register | 4 Council resolution register compiled | Number of Council resolution register compiled | 4 Council resolution register compiled | 1Council resolution register compiled | Achieved | 1 Council Resolution register compiled | None | None | Council resolution registers | 0
| Facilitation of SODA and Budget day | 1 SODA and Budget day facilitated | Number SODA and Budget day facilitated | 1 SODA and Budget day facilitated | No activity | No activity | No activity | No activity | No activity | Attendance registers & signed notices | 200000
| Councillors study groups | New | Number of study groups facilitated | 1 study group for councillors facilitated | No activity | No activity | No activity | No activity | No activity | Exit Report | 0
| Council whippery meetings | 4 council whippery meetings held | Number of council whippery meetings facilitated | 4 council whippery meetings facilitated | 1 council whippery facilitated | Achieved | 1 council whippery held on 16/08/18 | None | None | Attendance registers & signed notices | 0
| MPAC Working sessions | 8 working sessions held | Number of working sessions facilitated | 8 working sessions facilitated | 2 MPAC working sessions facilitated | Achieved | 5 MPAC working sessions failitated on 01,15 Aug 18 and 11 - 13/09/18, | None | None | Attendance registers and Notices | 180000
| MPAC Public hearings | 1 public hearing held | Number of public hearing facilitated | 2 MPAC public hearings facilitated | No activity | No activity | No activity | No activity | No activity | Attendance registers & signed notices | 120000
| Review of Public Participation Policies | 1 public participation policy reviewed | Number of public participation policy review facilitated | 1 public participation policy review facilitated | Circulate public participation policy to SDM personnel and local municipalities for inputs | Achieved | Public participation policies prepared and circulated to SDM staff and local municipalities for inputs | None | None | Signed Council Resolution Certificate | 0
COMMUNICATIONS; ADVOCACY, SOCIAL FACILITATION; SPECIAL PROGRAMMES AND ARTS AND CULTURE
To facilitate stakeholder engagement /Mayoral outreaches by June 2019 | Mayoral Outreaches and Stakeholder Engagements | 12 Mayoral Outreaches Programmes/Mayoral outreaches facilitated | Number of stakeholder engagement/mayoral outreaches facilitated | 8 stakeholder engagement/mayoral outreaches facilitated | 2 Stakeholder engagement/Mayoral Outreaches Facilitated | Achieved | 5 Stakeholder engagement Facilitated. *Ga-Komane water Hand-over 05/07/18.*Water and House Handover at Maseven 31/07/18. *VIDP Project Hand-over at Ga-Moretsele 30/08/18. *House Furniture and Grocery Handover at Maseven 31/08/2018. *Water summit held 20/09/18 at Loskop Dam | None | None | Exit reports&Attedence registers | 2263200
To provide support to Mayoral Committee meetings by June 2019. | Executive Support to Mayoral Committee | 12 Mayoral Committee meetings held | Number of logistical supports provided to Mayoral Committee meetings. | 12 logistical supports provided to Mayoral Committee meetings. | 3 Logistical Supports provided to Mayoral Committee Meetings. | Achieved | 7 Logistical support provided to the Mayoral Committee.* 2 ordinary Mayoral Committee Meetings held on the 19\07\18 and 27\08\18* 5 Special Mayoral Committee Meetings held on the 10\07\18, 27\07\18, 19\08\18, 19\09\18, and 18\09\18. | None | None | Minutes and attendance registers
To promote art and culture activities by June 2019 | Cultural Heritage Celebrations and Language Promotions | 3 Art & Culture programmes promoted | Number of art and culture activities promoted | 3 Art and Culture activities promoted | 1 Art and Culture Activities Promoted | Achieved | 2 Art and Culture Activities Promoted. *Language Promotion facilitated 24/09/18 at Tjate Heritage Site.* Heritage Celebration held at Tjate on the 24/09/18 | None | None | Exit reports/attedence registers | 0
To produce news letters by June 2019 | Newsletter | 4 internal, 2 Special and 1200 diaries produced | Number of newsletters produced | 15 News letters produced. | 2 Internal , 1 Special, and 1 External Newsletter | Not Achieved | 1 Internal newsletter, 1 Special and 1 External news letters produced. 1 Internal newsletter only produced electronically. | 1 Internal newsletter not produced due to delays by SITA to upload on the wesbite for staff members. | 1 Internal newsletter would be uploaded by SITA soon as they deal with their internal backlog | copies of newsletters, diaries and calenders | 500000
To market the district by June 2019 | Media Relations and Marketing | 10 Events Branded | Number of Events Branded & procurment of material done | 12 Events Branded & procurment of material done | 3 Events Branded * procument of DVD Material done | Achieved | 3 Events marketed and branded.*Mandela Day 18/07/2018 at Apel. *Water and House Hand-over 31/07/2018 at Maseven. *House and Grocery Hand-over at Ma-Seven and VIDP Sanitation Hand Over 31/08/18 at Moretsele. | None | None | pictures & exit reports | 225000
To update the website by June 2019 | Website Management | 20 Updates | Number of Website Updates undertaken | 20 Updates undertaken | 5 Websites updates under taken | Achieved | 7 Websites updates under taken.*Tenders, *Adverts*Planning-Tribal Land Application, *Water and House Handover VIDP Sanitation at Ga-Moretsele, *House and Grocery Handover at Ma-Seven on 31/08/18, *Water Summit Event *Tjate Heritage 24/09/18 . | None | None | Exit reports&screen shots | R81 000.00
To manage business of the executive arm and systematic support to Traditional Leaders by June 2019 | Executive Support and Traditional Leadership Affairs | 2 SPLUMA meeting supported | Number of Traditional Leaders meetings coordinated | 4 meetings coordinated | 1 Meeting coordinated | Achieved | 1 Meeting coordinated. *Heritage Event harmonising with Magoshi and Mangaka (Heritage Rituals) at Tjate on the 24 Sept 2018. | None | None | Exit reports | 550000
To coordinate special Mayoral events by June 2019 | Special Mayoral strategic Events | 5 strategic events Facilitated | Number of Strategic Events facilitated | 7 Strategic Events facilitated | 2 Strategic events held (King Sekhukhune, Heritage day | Achieved | 2 Strategic events held.*King Sekhukhune I Commemoration held on the18/08/18 at Mohlaletse.*1 Mayoral Special Projects. Heritage Celebration held at Tjate on the 24 Sept 2018 | None | None | Exit reports | 1135000
To facilitate Moral Regeneration Movement (MRM) programmes by June 2019. | Strengthening of Moral Regeneration Movement Committee | MRM committee established | Number of programmes for MRM committee facilitated | 2 MRM committee programme facilitated | 1 MRM committee programme facilitated | Not Achieved | The district unsuccessfully co-ordinated MRM meeting in Ephraim Mogale Municipality on the 9th October 2018. | Non functionality of the local municipalities committees due to lack of resources | Co-ordinate the local municipaltie to organise their committees in the second quarter and impress upon them to include MRM in their SDBIP | Exit report
To facilitate HIV/AIDS programmes by June 2019 | AIDS Council Activities | District Aids and Health Council activities | Number of HIV/AIDS Programmes facilitated | 4 HIV/AIDS programmes facilitated | No activity | None | None | None | None | Exit reports/attedence registers | 100000
To conduct youth programmes by June 2019. | Youth Opportunities Expo | 3 Programmes | Number of Youth Programmes conducted. Support to youth council provided | 3 Youth Programmes conducted. 3 Support to youth council provided | 1 Career expo conducted | Achieved | 1 Career Expo Conducted on the 21 Sept 2018 at Molepane H. School (Makhuduthamaga Local Municipality) | None | None | Exit reports | 218000
To facilitate sport activities by June 2019 | Facilitation of Mayoral Sports activities | 3 Programmes facilitated | Number of Sport activities facilitated | 2 Sport activities facilitated (1 Indigenous games, 1 Mayors cup) | 1 Indigenous games facilitated | Achieved | 1 Indigenous Games facilitated. Event held 18/07/2018 at Matlebjane Old Aged Centre. Apel | None | None | Exit reports | R150 000.00
To inculcate the culture of people first and friendly customer frontline services by June 2019 | Customer Care Services | 24 reports generated | Number of reports generated | 24 queries/ complains reports on customer care generated | 6 x Reports generated (3 sdm, 3 premier & presidential ) | Achieved | 6 x Reports on customer care generated. 3 Call Centre reports generated and 3 President/Premier report received | None | None | Reports | 200000
| Batho pele | 6 Programmes conducted | Number of Batho Pele Programmes conducted | 5 Batho Pele Programmes conducted | 1 Batho Pele Programmes conducted | Achieved | 4 Batho Pele Programmes conducted. 13/08/18 at Burgesfort, 17/08/18 at Fetakgomo Tubatse ( Apel) Batho Pele Build up event:/26/08/18 at Spitspunt, 27 /09/18 at Phathanswana | None | None | Reports | 50000
| Institutional Social Development Services | 6 Programmes | Number of ISD reports generated | 12 ISD reports generated | 3 ISD reports generated | Achieved | 3 ISD projects reports for August, July and September 2018 generated | None | None | Exit reports | 0
To facilitate awareness programmes for people with disability by June 2019 | People with disability | 3 awareness programmes | Number of awareness programmes facilitated | 3 Awareness programmes facilitated | 1 Deaf/Albinism awarness campaign facilitated | Achieved | 1 Deaf awarenes compaign facilitated on 27/09/18 at Dicheung(Ephraim Mogale L. Municipality. | None | None | Exit reports&Attedence registers | R51 000.00
To facilitate women deveelopment programmes by June 2019 | Woman Development Initiative | 4 women activities coordinated | Number of women development programmes facilitated | 4 Women development programmes facilitated | 1 Launching of womens month programme facilitated | Achieved | 1 Launching of womens month programme facilitated. Women 's Day Celebrated at Ga-Maloma Moshate on the 30/08/18 | None | None | Exit repors/attedence registers | 130000
To facilitate children activities by June 2019 | Children’s Care | 2 childrens acvities facilitated | Number of children's activities facilitated | 2 Children activities facilitated | No activity | None | None | None | None | Exit reports/attedence registers | 40800
To coordinate aged care programmes by June 2019 | Aged care | 2 aged care programmes coordinated | number of aged care programmes coordinated | 2 Aged Care programmes coordinated | 1 Mandela day programme coordinated | Achieved | 1 Mandela day programme coordinated. Mandela Day Celebration held 18/07/18 at Matlebjane Old Aged Centre.Apel | None | None | Exit reports/attedence registers | 200000
To coordinate State of the District Address (SODA) by June 2019 | SODA | 2017/2018 SODA held | Number of SODA organised | 1 SODA coordinated | No activity | None | None | None | None | Exit Report | 10200