## Sheet1
2018/2019 SERVICE DELIVERY BUDGET AND IMPLEMENTATION PLAN: CORPORATE SERVICES
STRATEGIC OBJECTIVE | PROJECT | BASELINE 2017/2018 | INDICATORS | ANNUAL TARGET 2018/2019 | Q1 | ACHIEVED/NOT ACHIEVED | ACTUAL PROGRESS | CHALLENGES | REMEDIAL ACTION | EVIDENCE | BUDGET 2018-2019
LABOUR RELATIONS
To facilitate 12 Local Labour Forum (LLF) meetings by June 2019 | Local Labour Forum | 7 LLF meetings held | Number of Local Labour Forum meetings facilitaed | 12 Local Labour Forum meetings facilitated | 3 LLF meetings facilitated | Not achieved | 1 meeting held | Conflicting Schedule of Meetings | Improve thorough Communication and prioritize LLF Meetings | Minutes and attandence registers | 50000
To issue 4 Labour Relations Publications by Jne 2019 | Labour Relations Publications | 2 Labour relations publication issued | Number of Labour relations publication issued | 4 labour relations publications issued | 1 Labour Relations Publication issued | Achieved | 1 article issued/publication ( Absenteeism in the workplace) | None | None | Labour Relations Publications issued | 0
To facilitate 100% resolution of grievance cases by June 2019 | Grievance cases | 2 resolution of grievance cases facilitated | Number of resolution of grievance cases facilitated | All resolution of grievance cases facilitated | All resolution of grievance cases facilitated | Achieved | All resolution of grievance cases facilitated (2 grievance cases received and resolved) | None | None | Grievance register | 0
To facilitate 100% resolution of misconduct cases by June 2019 | Misconduct cases | 8 resolution of misconduct cases facilitated | Number of resolution of misconduct cases facilitated | All resolution of misconduct cases facilitated | All resolution of misconduct cases facilitated | Achieved | All resolution of misconduct cases facilitated ( 3 misconduct cases received and facilitated) | None | None | Misconduct case register | 0
INFORMATION & COMMUNICATION TECHNOLOGY
To enhance service delivery through optimal use of information technology by June 2019 | ICT Infrastructure upgrade and maintenance | All five (5) sites in Groblersdal area have fully fledged LAN and WAN network infrastructure | Number of DRP site managed | 1 DRP site established | Appointment of service provider, signing of SLA and handing over of site. | Achieved | Service provider apponited (Dimension Data), SLA signed (with Dimension Data) and site (Tubatse Fire Station DRP Server room) handed over | None | None | * Award Letter * Signed SLA * Hand over report * Tax invoices | R1 200 000
|  | 18 depots connected to the Main Office | Number of telephone infrastructure developed | 11 telephone infrastructure developed | Appointment of service provider, signing of SLA and handing over of site. | Not Achieved | Initiated the appointment of a service provider for provision of VoIP Telephone services with Capricorn District Municipality (CDM) through Regulation 32 of the MFMA | CDM sent incomplete VoIP Telephone Tender documents and as such SDM is unable to apply Regulation 32 of the MFMA for appointment of CDM's VoIP Service Provider | Tender for development of 11 telephone inftastructure to be readvertised | * Award Letter * Signed SLA * Hand over report * Tax invoices | 1270000
|  | 6x dicta phones recordings devices in place | Number of access control infrastructure developed | 1 CCTV and Access Control system developed | Appointment of service provider, signing of SLA and handing over of site. | Not Achieved | Service provider appointed (FHIMA Consultancy and Projects) | FHIMA Consultancy and Projects (appointed service provider) hasn’t signed the SLA | Expedite signing of the SLA (FHIMA Consultancy and Projects committed to sign the SLA on 12 October 2018) | * Award Letter * Signed SLA * Hand over report * Tax invoices | 400000
|  | Offsite data storage location | Number of Council audio recording system purchased | 1 Council digital audio recording system installed | Appointment of service provider, signing of SLA. | Achieved | Service provider appointed (New Deal Engineering), SLA signed (with New Deal Engineering) | None | None | * Award Letter * Signed SLA * Hand over report * Tax invoices | 150000
|  | 17 Servers and 400 desktops /laptops | % of ICT hardware replaced | 100% ICT hardware replaced as and when required | 100% ICT hardware replaced as and when required | Achieved | 100% ICT hardware replaced as and when required (61 hardware requested and 61 distributed) | None | None | * Tax invoice * Hardware * Distribution Register | 402650
|  |  | Number of WAN sites supported | 5 WAN sites supported | Terms of Reference for 5 WAN sites submitted to the Bid Specifications Committee | Achieved | Terms of Reference for 5 WAN sites submitted to the Bid Specifications Committee | None | None | * Awad Letter * Project Plan * Tax Invoice | 770000
To manage information services by June 2019 | ICT Service Management | 12 Service Level Agreement meetings held with Telkom, Unics, Open Kingdom Technologies and BCX | Number of SLA performance service standards managed | 8 SLA performance service standards managed | 2 SLA performance service standards managed | Achieved | 2 SLA performance service standards managed (Telkom SA, Open Kingdom Technology Consulting) | None | None | • SLA reports * Tax invoices | R4 000 000
|  | 11 approved software licenses renewed | Number of approved software licenses renewed | 9 approved software licenses renewed | 2 approved software licenses renewed | Achieved | 2 approved software licenses renewed (Adobe Creative Cloud for Teams, Caseware) | None | None | • Tax invoices | R2 500 000
|  | 1 Information Security tool managed | Number of Information Security tools purchased and managed | 2 Information Security tools purchased and managed | No Activity | None | None | None | None | • Tax invoices * Information Security Reports | 350000
| Enterprise information Management | *MunAdmin (electronic document management system) in place *Microsoft SharePoint commissioned | Number of Case Management System deployed. | 1 Case Management System deployed. | No Activity | None | None | None | None | Tax Invoice | 350000
ORGANIZATIONAL EFFICIENCY AND DEVELOPMENT
To facilitate the development and implementation of benchmark framework by June 2019 | Benchmark Framework | None | Number of benchmark framework developed | 1 Benchmark framework developed | *Gather information & analyse | Achieved | Research has been conducted towards development of Benchmark framework. Draft benchmark framework in place | None | None | Approved Benchmark Framework | 300000
To facilitate 4 change management sessions by June 2019. | Change Management Program | Change management strategy for placement in place | Number of change management sessions held with employees facilitated | *4 change management sessions facilitated. | *1 change management sessions facilitated | Not Achieved | Change management focus areas documented & plan in place | The change management programme cannot be launched due to conflicting time schedule with the Misa support | The programme will be launched in October 2018 | Change management report
To facilitate re-evaluation of 116 jobs by June 2019 | Job Evaluation | 143 jobs evaluated | Number of jobs re- evaluated | 116 jobs re- evaluated | Re- evaluate (58) jobs & submit to SALGA for moderation | Not Achieved | 57Job descriptions redeveloped, 48 jobs evaluated for Ephraim Mogale, Elias Motsoaledi and Makhuduthamaga Local Municipalities | The district job evaluation programme was amended to focus on problematic municipalities | Jobs for SDM will be evaluated in October 2018 as per the amended approved programme for 2018-19. | Job evaluation report and minutes.
To facilitate 2 organisational development interventions/ assessment by June 2019 | Employee Satisfaction Survey | Report of Employee satisfaction survey | Number of feedback sessions facilitated with employees | 2 feedback sessions facilitated with employees | No activity | None | None | None | None | Report and attendance register
AUXILIARY SERVICES
To facilitate 4 awareness campaigns for records management by June 2019. | Records management | 4 Records awareness programme | Number of awareness campaigns on records management facilitated | Four (4) records awareness campaigns facilitated | One (1) records awareness campaigns facilitated | Achieved | One (1) records awareness campaigns facilitated ( 28 September 2018) | None | None | Report and attendance register | 2300000
To update personnel files by June 2019 |  | 920 personnel files updated | Number of personnel files updated | 920 personnel files updated | No activity | None | None | None | None | List of updated files
To facilitate disposal of inactive records by June 2019 |  | 3 750 inactive records listed | Number of disposal of inactive files listed | 2500 inactive records listed for disposal | 625 inactive records listed for disposal | Achieved | 766 inactive records listed for disposal | None | None | Register of listed inactive records
To institutionalise document management services by June 2019 |  | Tender, 920 personnel files, leave files, travel claims recorded | Number of departments provided with document management services | 3 departments provided with document management services( IWS, PED & CPS) | No activity | None | None | None | None | Report and register
To manage leased fleet by June 2019 | Fleet management | 150 fleet managed | Number of fleet managed | 167 fleet managed ( 33 SDM owned, 102 Leased IWS, 27 Leased CMS, 3 Leased BTO, 2 Leased CPS) | 167 fleet managed | Achieved | 167 fleet managed ( 33 SDM owned, 102 Leased IWS, 27 Leased CMS, 3 Leased BTO, 2 Leased CPS) | None | None | Payment register of leased fleet | 50235951
To facilitate security of municipal fleet by June 2019 |  | 25 municipal fleet provided with tracking system | Number of municipal owned fleet with tracking system managed | 33 municipal owned fleet with tracking system managed | 33 municipal owned fleet with tracking system managed | Achieved | 33 Municipal fleet installed the tracking system | None | None | Payment register for tracking ,fleet tracking reports
To facilitate the purchsae of 4 water tankers by June 2019 |  | New Project | Number of water tankers purchased | 4 water tankers purchased | Procurement process | Achieved | 4 Water Tankers delivered | None | None | Delivery note | 4500000
To ensure payment of licenses subscriptions by June 2019. |  | 25 payment of licenses paid | Number of fleet licenses renewed | 33 fleet licenses renewed | 18 fleet licenses renewed | Achieved | 19 fleet license renewed during the month July | None | None | Payment register of licenses | 102000
To facilitate maintenance and repairs of fleet by June 2019 |  | 25 fleet provided with maintanance. | Number of fleet provided with maintainance. | All fleet provided with maintainance. | All fleet provided with maintainance. | Achieved | All fleet provided with maintenance (Fleet requird Repaires; BLX 492 L and fitted new tyres on BYL 688 L) | None | None | Register maintenance and repairs | 600000
To ensure management of fuel by June 2019 |  | R7,200 000 of fuel purchased | Rand value of fuel limit managed | R6,600 000 of fuel limit managed | R1,650 000 of fuel limit managed | Not Achieved | Total Spent =R2 655 656.86 July = R 871 122.74 August =R885 377.78 September = R 899 156.34 | Due to the fuel price hikes that are happening every month, it is imposible to spend R550 000 as budgeted | End-user departments to assist in the management of fuel | Monthly bank statement | 6600000
To ensure provision of office furniture by June 2019 | Facility Management | Lekgotla boardroom furniture, couches and boardroom chairs for 4 fire stations | Number of offices to be provided with office furniture | 8 offices to be provided with office furniture (6 managers offices, 1 ICT and 1 canteen) | No activity | None | None | None | None | Delivery note | 578600
To ensure management of leased and SDM owned facilities by June 2019 |  | 5 offices leased, 41 owned facilities managed | Number of facilities managed | 5 leased and 41 owned facilities managed | 5 leased and 41 owned facilities managed | Achieved | 5 leased and 41 owned facilities managed | None | None | Register of payment for office rental and municipal services. | 8000000
HUMAN RESOURCES DEVELOPMENT
To manage and provide human capital development to capacitate the SDM by June 2019 | Skills Audit | None | Number of Skills Audit Report for 2018 developed | 1 Skills Audit Report for 2018/2019 financial year developed | Conduct information campaign with management and staff. | Achieved | Information campaign with staff and management conducted (Employees profiling forms distributed and 250 forms captured) | None | None | Skills Audit Report | 0
| Organisational Training Needs analysis | None | Number of Training Needs Report developed | 1 organisational Training Needs Report developed | No Activity | None | None | None | None | Training Needs report | R1 000 000
| Organizational Training Plan for 2019 | 2017/18 Training Plan (Workplace Skills Plan ) | Number of Organizational Training Plans for 2019/2020 financial year developed | 1 Organizational Training Plans for 2019/2020 financial year developed | No Activity | None | None | None | None | Training Plan | 0
| External Bursaries | 3 external bursaries awarded in 2017/18 | Number of bursaries maintained in 2018 | 16 external bursraies maintained | Maintain 16 external bursaries | Achieved | All 16 burasries are maintained ( 4 external bursaries processed) | None | None | Bursary Letters and Contracts | 1900000
| Internal Bursaries | 10 internal bursaries awarded in 2017/18 | Number of bursaries maintained in 2018 | 10 bursaries maintained | Maintain 10 internal bursaries | Achieved | 10 internal bursaries are maintained (Two) 2 internal bursaries processed) | None | None | Bursary Letters | 1202000
HUMAN RESOURCES MANAGEMENT
To facilitate filling of funded and vacant posts by June 2019 | Recruitment and retention | 24 Employees appointed | Number of vacant and funded posts filled | All vacant and funded posts filled | All vacant and funded posts filled | Achieved | All vacant and funded posts filled ( 111 posts were vacant and funded; All 111 vacant and funded posts were filled | None | None | Appointment Letters, adverts and memo signed by MM. | 250000
To ensure compliance submission of Employment Equity (EE) plan by June 2019 | Employment Equity (EE) | EE plan in place | Number of EE reports compiled and submitted | 1 EE report compiled and submitted to the Department of Labour | No Activity | None | None | None | None | Proof of submission of EE report | 0
To implement Human Resource plan by June 2019 | Human resources Plan | 2017-2020 HR plan available | Number of HR Plan implemented | 1 Human Resource plan implemented | 1 HR Plan implemented | Achieved | 14 Employees are attending Adult Education and Training; OHS Committess are in place | None | None | HR Plan report | 0
EMPLOYEE WELLNESS AND OCCUPATIONAL HEALTH AND SAFETY
To conduct wellness and counselling programmes by June 2019 | Employee Wellness and counselling programmes | 15 *Wellness and counselling programme conducted (2 stress and trauma management programmes, conducted 12 wellness awareness programmes, 1 Wellnes day done). | Number of wellness and counselling programmes conducted | 29 wellness and counselling programmes conducted (12 wellness awareness campaign, 12 Fun walks, 2 stress and trauma management, 1 SAIMSA, 1 IMMSA, 1 wellness day | 7 Wellness and counselling programme conducted (3 wellness awareness campaign, 3 Fun walks, 1 SAIMSA) | Achieved | Seven (7) wellness and counselling programmes conducted (3 wellness awareness campaigns, 3 Fun walks, 1 SAIMSA games) | None | None | *Wellness and counselling reports *Attendance Registers * SAIMSA report *IMMSA report | 760000
To facilitate substance abuse programme by June 2019 | Substance abuse programme | 12 substance abuse programme facilitated | Number of substance abuse programme facilitated | 12 substance abuse programme facilitated | 3 substance abuse programme facilitated | Achieved | Three (3)Substance abuse programme facilitated ( 24/07/2018; 29/08/2018 and 13/09/2018) | None | None | Substance abuse programme reports and attendance registers
To conduct occupational health and safety elements by June 2019. | Occupational Health and Safety elements | 60 Occupational Health and Safety elements conducted (Project audits, Work place and tools inspection, Servicing of fire extiquishers, provision of PPE and Health and Safety Committee meetings). | Number of Occupational Health and Safety elements conducted. | 69 Occupational Health and Safety elements conducted. | 17 Occupational Health and Safety elements conducted. | Achieved | 17 Occupational Health and Safety elements conducted (11 work place and tools inspections, 4 project audits,1 provision of PPE and 1health and safety committee meeting). | None | None | * Occupational Health and Safety elements Reports, * Attendance registers | 2800000
To conduct medical surveillance programme by June 2019 | Medical Surveillance programme | 0 employees were subjected to medical surveillance programmes | Number of employees undergone medical surveillance programme | 1 Medical surveillance programme conducted | No Activity | None | None | None | None | Medical Surveillance Reports,
LEGAL SERVICES
To attend to the letigations by June 2019 | Litigations | 8 Litigations cases attended | Number of litigations attended | All litigations attended | All litigations attended | Achieved | 02 cases attended to, which are: 1. Rendeals Four Consulting case, 2. Waterskills (Pty) Ltd case | None | None | Summons and Court Judgments | 3000000
To draft requested Contracts by June 2019 | Contracts | 50 Contracts and Services level Agreement drafted | Number of contracts requested and drafted | All contracts requested and drafted | All contracts requested and drafted | Achieved | 10 contracts drafted and 06 contracts vetted | None | None | Contract Register and drafted contratcs and service level agreements | 0
To draft requested legal opinions by June 2019 | Legal opinions | 10 legal Opinions drafted | Number of Requested Legal Opinions drafted | All requested Legal Opinions drafted | All requested Legal Opinions drafted | Achieved | 02 Legal Advisory services provided.1. Legal Advice on legal repercussion of the Municipality water pipelines encroached by the communities; and how to protect the Municipality against any possible litigation by community members who built on or near the waterlines. 2. Legal Advice on whether the Municipality should deduct the cost of outstanding service of establishment of the Disaster Recovery Infrastructure prior to effecting payment of outstanding invoices to Dimension Data. | None | None | Drafted legal opinions register | 0
To capture claims by and against the municipality by June 2019 | Compilation of litigation Register | 2017/18 Litigation register | Number of cases by and against the municipality captured | All cases by and against the municipality captured | All cases by and against the municipality captured | Achieved | 02 Litigations matters recorded | None | None | Litigation register, copies of court judgments and Settlements agrements | 0
To record Contracts by June 2019 | Compilation of contract register | 300 contracts recorded | Number of contracts recorded | All contracts recorded | All contracts recorded | Achieved | 16 Contracts recorded in Contract register | None | None | Contracts Register
PERFORMANCE MANAGEMENT SYSTEM (PMS)
To facilitate performance Makgotla by June 2019 | Facilitation of Makgotla | 4 Performance Makgotla Sessions held | Number of Performance Lekgotla Sessions facilitated | 4 Performance makgotla Sessions facilitated | 1 Performance Lekgotla Session facilitated | Achieved | 1 Performance Lekgotla facilitated (02 August 2018) | None | None | *Performance Lekgotla Sessions resolutions *attendence registers | R100 000. 00
To develop 2019/2020 Institutional SDBIP | Development of 2018/19 Institutional SDBIP | 2017/2018 Institutional SDBIP in place | Number of 2018/2019 Institutional SDBIP developed | 01 2018/2019 Institutional SDBIP developed | No activity | N/A | N/A | N/A | N/A | Signed 2018/2019 Institutional SDBIP by Executive Mayor | 0
To compile 2017/2018 Institutional Annual Report by 31 January 2019 | Compilation of 2017/2018 Annual report | 2017/2018 Annual Report in place | Number of 2017/2018 Annual Report developed | 01 2017/2018 Annual Report developed | No activity | N/A | N/A | N/A | N/A | *2016/2017 Annual Report *Attendance Registers | 0
To develop 2018/2019 Performance Agreements for senior managers, managers and Performance commitment for level 4 & 5 officials | Development of 2018/2019 Performance Agreements for Senior Managers, Managers and Performance commitments for level 4 & 5 officials | 2017/2018 Performance agreements and Performance commitments in place | Number of 2018/2019 Performance Agreements for Senior Managers, managers and Performance Commitments for level 4 & 5’s developed | 07 2018/2019 performance agreements for Senior Managers, 32 managers and 80 performance commitments for level 4 & 5’s developed | 07 2018/2019 performance agreements for Senior Managers, 32 managers and 80 performance commitments for level 4 & 5’s developed | not achieved | *07 2018/2019 performance agreements for Senior Managers developed, signed and submitted to Coghsta *21 of 32 managers developed and signed *49 of 80 performance commitments for level 4 & 5’s developed, signed and submitted | *The following PAs are still oiutstanding to-date; 11 *Income, Planning & Regulations, DD(IWS), O&M X2, OD, EAP, HRM, Risk,(Labour & Legal appointed done in Sept. & Oct) *The following PCs are still outstanding, Risk- x 2, Legal- x2, All PCs from IWS, Office of the Chief-Whip- x1, HRM- x4, HRD- x2, ICT- x1, Auxiliary-x2 | Continuous engagement with departments through dashboard as a reminder to submit outstanding information is done | Signed Performance Agreements and Performance commiitments | 0
To facilitate the performance assessment for senior managers and managers by June 2019 | Facilitation of performance Assessments | 2017/2018 performance assessment for senior managers conducted | Number of performance assessment for senior managers conducted | 2 performance assessment (2017/18 Annual and 2018/19 Mid year) for senior managers conducted | No activity | N/A | N/A | N/A | N/A | Performance assessments reports | 0
To review PMS policy by June 2019. | PMS Policy and Framework Review | 2017/2018 PMS Policy and Framework in place | Percentage Review of PMS Policy and Framework | 100% Review of PMS Policy and Framework | No activity | N/A | N/A | N/A | N/A | Council resolution | 0
To coordinate quarterly Back to Basics reports by June 2019 | Coordination of B2B reports | 2017/2018 B2B reports in place | Number of quarterly B2B reports coordinated | 4 quarterly B2B reports coordinated | 1 quarterly back to basics reports coordinated | Achieved | 1 quarterly back to basics reports coordinated and submitted to Coghsta | None | None | Quarterly Reports | 0
INTEGRATED DEVELOPMENT PLAN (IDP)
To develop the IDP Framework/ Process Plan for 2019/20 by August 2018 | Development of 2019/2020 IDP/Budget Framework/Process Plan | 2018/19 IDP/Budget Framework Process Plan in place | Number of IDP Frameworks/ Process Plans developed | 1 IDP Frameworks/ Process Plans developed | Develop the IDP Framework/Process Plan | Achieved | Framework/Process Plan developed and adopted by Council on the 27 July 2018 with resolution no. OC 14/07/2018. It was then advertised in the Sowetan on the 14 August 2018 | None | N/A | IDP Framework/Process Plan | 0
To facilitate the IDP Rep Forums by May 2019 | Facilitation of the IDP Rep Forums | 2 IDP Rep Forums held in 2017/18 | Number of IDP Rep Forums facilitated | 2 IDP Rep Forums facilitated | Review the Stakeholder list | Achieved | Stakeholder list for IDP Forum reviewed | None | N/A | Report Attendance Registers | 50000
To review the IDP/Budget by May 2019 | Review of the IDP/Budget for 2019/20 | 2018/19 IDP/Budget in place | Number of IDP/Budget reviewed | 1 IDP/Budget reviewed | Consult Sector Departments on the development backlogs | Achieved | Sector Departments consulted | None | N/A | IDP/Budget document for 2019/20 | 430000