## Sheet1
STATIAL RATIONALE
MEASURABLE OBJECTIVE | INPUT | OUTPUT | OUTCOME | PROJECT | BASELINE 2017/2018 | INDICATORS | ANNUAL TARGET 2018/2019 | Q1 | Q2 | Q3 | Q4 | ACHIEVED/NOT ACHIEVED | ACTUAL PROGRESS | CHALLENGES | REMEDIAL ACTION | EVIDENCE | BUDGET | IMPACT
2018/2019 SERVICE DELIVERY BUDGET AND IMPLEMENTATION PLAN: PLANNING AND ECONOMIC DEVELOPMENT DEPARTMENT
LOCAL ECONOMIC DEVELOPMENT
To generate reports on Municipal job creation by June 2019 | Human and financial resources | Job creation report | improved accountability | Municipal Job creation | 4 Reports generated for 2017/2018 | Number of reports generated on Municipal job creation | 4 reports generated on Municipal job creation | Generate1 report on Municipal job creation | Generate 1 report on Municipal job creation | Generate1 report on Municipal job creation | Generate1 report on Municipal job creation | Achieved | 1 report on Municipal job creation generated. 502 Jobs created through municipal initiatives | None | None | Quaterly reports | 0
To generate reports on EPWP implementation by June 2019 | Human and financial resources | EPWP Reports | Improved EPWP coordination | Implementation of EPWP | 4 Quarterly reports generated | Number of reports on EPWP implementation | 4 reports on EPWP implementation generated | Generate1 report on EPWP implementation | Generate1 report on EPWP implementation | Generate1 report on EPWP implementation | Generate1 report on EPWP implementation | Achieved | 1 report on EPWP implementation generated. 43 jobs created through EPWP Integrated Incentive grant | None | None | Quaterly reports | 0
To facilitate Trainings for SMME’s and Cooperatives by June 2019 | Human and financial resources | Increased productivity | Empowered SMME | Trainings for SMMEs and cooperatives. | 4 Trainings provided during 2017/2018 financial year | Number of Trainings to SMME’s and Cooperatives facilitated | 4 Trainings to SMME’s and Cooperatives facilitated | Facilitate 1 Trainings to SMME’s and Cooperatives | Facilitate 1 Trainings to SMME’s and Cooperatives | Facilitate 1 Trainings to SMME’s and Cooperatives | Facilitate 1 Trainings to SMME’s and Cooperatives | Achieved | 17 SMMEs trained on Start up Business Skills and Tourism capacity building workshop | None | None | *Training Report *Attedance Register | 100000
To provide support to SMME’s and Cooperatives by June 2019 | Human and financial resources | Increased productivity | Empowered SMME | SMMEs & Coperative support | None | Number of SMMEs/Cooperatives support provided | 3 SMMEs/Cooperatives support provided | Review LED Funding Policy | Provide support to 1 SMME/ Cooperative | Provide support to 1 SMME/ Cooperative | Provide support to 1 SMME/ Cooperative | Achieved | LED funding policy reviewed | None | None | Reports | 230000
To generate reports on the implementation of Enterprise and Supplier Development Programme by June 2019 | Human and financial resources | Developed SMMEs & Cooperatives | Improved local economy | Implementation of Enterprise and Supplier Development (ESD) Programme | 3 Service Providers for ESD programme appointed | Number of reports generated on the implementation of Enterprise and Supplier Development Programme | 4 reports generated on the implementation of Enterprise and Supplier Development Programme | Generate 1 report on the implementation of Enterprise and Supplier Development Programme | Generate 1 report on the implementation of Enterprise and Supplier Development Programme | Generate 1 report on the implementation of Enterprise and Supplier Development Programme | Generate 1 report on the implementation of Enterprise and Supplier Development Programme | Achieved | 1 report on implementation of Enterprise and Supplier Development Programme generated. | None | None | ESD quarterly reports. | 150000
To facilitate District Economic Development Forums(Mining. Agric & Tourism) by June 2019 | Human and financial resources | Functional District Economic Development Forums | Improved local economy | Facilitation of District Economic Development Forums (Mining, Agric & Tourism) | District Mining Forum established | Number of District Economic Development Forums facilitated | 3 District Economic Development Forums facilitated | Develop TORs for the Forums | Facilitate 1 District Economic Development Forum | Facilitate 1 District Economic Development Forum | Facilitate 1 District Economic Development Forum | Achieved | Terms of reference for the 3 forums developed | None | None | *Reports *Attendance registers | 100000
To review the LED strategy by June 2019 | Human and financial resources | Reviewed LED Strategy | Improved local economy | Review LED Strategy | 2007 LED Strategy in place | Number of LED Strategy reviewed | 1 LED Strategy reviewed | Appoint Service Provider | Inception Report | Status Quo Report | Draft LED Strategy | Achieved | Service provider appointed in July 2018. | None | None | *Draft LED Strategy | 600000
To facilitate Economic Development Summit by June 2019 | Human and financial resources | Summit held | Improved economic planning | Facilitate Economic Development Summit | None | Number of Economic Develoment Summits facilitated | 1 Economic Develoment Summit facilitated | Develop Terms of Reference | Establish Task Team | Solicit funding for the Summit | Facilitate 1 Economic development Summit | Achieved | Terms of reference developed | None | None | *Report *Attendance register | 100000