## Sheet1
STATIAL RATIONALE
MEASURABLE OBJECTIVE | INPUT | OUTPUT | OUTCOME | PROJECT | BASELINE 2017/2018 | INDICATORS | ANNUAL TARGET 2018/2019 | Q1 | Q2 | Q3 TARGET | PROGRESS (Achieved/ Not achieved) | ACTUAL PROGRESS | CHALLENGE | REMEDIAL ACTIONS | EVIDENCE | BUDGET | IMPACT
2018/2019 SERVICE DELIVERY BUDGET AND IMPLEMENTATION PLAN: PLANNING AND ECONOMIC DEVELOPMENT DEPARTMENT
SPATIAL RATIONALE
To ensure facilitation of the functionality of the Joint District Municipal Planning Tribunal (JDMPT) by June 2019 | Human and financial resources | Functional District Municipal Planning Tribunal (JDMPT) | Well planned settlements and development | Facilitation of Joint District Municipal Planning Tribunal (JDMPT) | JDMPT in place | Number of JDMPT sittings facilitated | 4 JDMPT sitting facilitated | Facilitate 1 JDMPT sitting | Facilitate 1 JDMPT sitting | Facilitate 1 JDMPT sitting | Achieved | 1 JDMPT sitting faciitated. (Held on the 07 February 2019) | None | None | *Signed reports *Attendance Registers | 400000
To support Local Municipalities(LMs) on the development of SPLUMA By laws, review of Spatial Development Frameworks (SDFs) and LUMS by June 2019 | Human and financial resources | Reviewed/implemented SDFs, LUMS and promulagated Land Use By-laws for Local Municipalities | Well planned settlements and development | Support Local Municipalities(LMs) on the development of SPLUMA By laws, review of Spatial Development Frameworks (SDFs) and LUMS | All LMs have SDFs, LUMS and Land Use By-Laws | Number of Support engagements with Local Municipalities(LMs) on the development of SPLUMA By laws, review of Spatial Development Frameworks (SDFs) and LUMS | 4 Support engagements with Local Municipalities(LMs) on the development of SPLUMA By laws, review of Spatial Development Frameworks (SDFs) and LUMS | 1 Support Engagement on SDFs, LUMS, and SPLUMA By-Laws implementation/ review | 1 Support Engagement on SDFs, LUMS and SPLUMA By-Laws implementation/ review | 1 Support engagement with Local Municipalities(LMs) on the development of SPLUMA By laws, review of Spatial Development Frameworks (SDFs) and LUMS | Achieved | 1 SPLUMA Forum facilitated (held on the 07 March 2019) | None | None | *Signed reports *Attendance Registers | 20000
To facilitate land for the development of District Municipal offices by June 2019 | Human and financial resources | Land obtained | Available land for development of municipal offices | Facilitation of land for development of District Municipal Offices | Land owned by different entities is available for development | Number of engagements for land development of District Municipal Offices facilitated | 4 engagements for land development of District Municipal Offices facilitated | Facilitate 1 engagement for land development of District Municipal Offices | Facilitate 1 engagement for land development of District Municipal Offices | Facilitate 1 engagement with Land Claims Commissioner on land development of District Municipal Offices | Achieved | 1 engagement facilitated (held coghsta and RLCC on the 30 Jan 2018). | none | None | *Signed reports *Attendance Registers | 100000
To process land development applications in line with the reviewed Spatial Development Framewok (SDF) by June 2019 | Human and financial resources | Development initiatives aligned with reviewed SDF | Improved spatial planning | Process land development applications in line with the reviewed Spatial Development Framewok (SDF) | Reviewed SDF in place | Percentage land development applications processed in line with the reviewed Spatial Development Framewok (SDF) | 100% land development applications processed in line with the reviewed Spatial Development Framewok (SDF) | 100% implementation of reviewed SDF | 100% implementation of reviewed SDF | 100% land development applications processed in line with the reviewed Spatial Development Framewok (SDF) | Achieved | 100% land development applications processed in line with the reviewed Spatial Development Framewok (SDF) | None | None | Application Register Support letters | 130000
To spatially map the IDP capital projects for 2018/19 by June 2019 | Human and financial resources | Maps | Proper spatial decisions | Spatial mapping of IDP Projects | GIS Strategy in place | Percentage of IDP capital projects for 2018/19 spatially Mapped | 100% of IDP capital projects for 2018/19 spatially Mapped | Identify IDP capital projects for mapping | Spatially map 50% of IDP capital projects | Spatially map 50% of IDP capital projects | Achieved | 100% projects mapped | none | none | Maps for IDP Capital projects for 2018/19 | 20000
To facilitate SPLUMA Workshops for Traditional Leaders and Councillors by June 2019 | Human and financial resources | SPLUMA Workshop | Understanding of SPLUMA | Facilitate SPLUMA Workshops for Traditional Leaders and Councillors | SPLUMA workshop held in 2016 | Number of SPLUMA workshops facilitated | 2 SPLUMA workshops facilitated | Engage with DRDLR, COGHSTA & SALGA | Facilitate 1 SPLUMA workshop | Engage with DRDLR, COGHSTA & SALGA | Achieved | Engaged with DRDLR, COGHSTA & SALGA through meeting held on the 07 March 2019 | None | None | * Signed report * Attendance registers | 150000
LOCAL ECONOMIC DEVELOPMENT
To generate reports on Municipal job creation by June 2019 | Human and financial resources | Job creation report | improved accountability | Municipal Job creation | 4 Reports generated for 2017/2018 | Number of reports generated on Municipal job creation | 4 reports generated on Municipal job creation | Generate1 report on Municipal job creation | Generate 1 report on Municipal job creation | Generate1 report on Municipal job creation | Achieved | 1 report on Municipal job creation generated | None | None | Signed Quaterly reports | 0
To generate reports on EPWP implementation by June 2019 | Human and financial resources | EPWP Reports | Improved EPWP coordination | Implementation of EPWP | 4 Quarterly reports generated | Number of reports on EPWP implementation generated | 4 reports on EPWP implementation generated | Generate1 report on EPWP implementation | Generate1 report on EPWP implementation | Generate1 report on EPWP implementation | Achieved | 1 report on EPWP implementation generated | None | None | Signed Quaterly reports | 0
To facilitate Trainings for SMME’s and Cooperatives by June 2019 | Human and financial resources | Increased productivity | Empowered SMME | Trainings for SMMEs and cooperatives. | 4 Trainings provided during 2017/2018 financial year | Number of Trainings to SMME’s and Cooperatives facilitated | 4 Trainings to SMME’s and Cooperatives facilitated | Facilitate 1 Trainings to SMME’s and Cooperatives | Facilitate 1 Trainings to SMME’s and Cooperatives | Facilitate 1 Trainings to SMME’s and Cooperatives | Achieved | 1 Training to SMME’s and Cooperatives facilitated | None | None | *Signed Training Report *Attedance Register | 100000
To provide support to SMME’s and Cooperatives by June 2019 | Human and financial resources | Increased productivity | Empowered SMME | SMMEs & Coperative support | None | Number of SMMEs/Cooperatives support provided | 2 SMMEs/Cooperatives support provided | Review LED Funding Policy | Provide support to 1 SMME/ Cooperative | Provide support to 1 SMME/ Cooperative | Not achieved | 2 Submissions approved by the accounting Officer | Procurement process delayed | To speed up procurement process | Signed reports | 230000
To generate reports on the implementation of Enterprise and Supplier Development Programme by June 2019 | Human and financial resources | Developed SMMEs & Cooperatives | Improved local economy | Implementation of Enterprise and Supplier Development (ESD) Programme | 3 Service Providers for ESD programme appointed | Number of reports generated on the implementation of Enterprise and Supplier Development Programme | 4 reports generated on the implementation of Enterprise and Supplier Development Programme | Generate 1 report on the implementation of Enterprise and Supplier Development Programme | Generate 1 report on the implementation of Enterprise and Supplier Development Programme | Generate 1 report on the implementation of Enterprise and Supplier Development Programme | Achieved | 1 report on the implementation of Enterprise and Supplier Development Programme generated | None | None | Signed ESD quarterly reports. | 150000
To facilitate District Economic Development Forums(Mining, Agric, Tourism and EPWP) by June 2019 | Human and financial resources | Functional District Economic Development Forums | Improved local economy | Facilitation of District Economic Development Forums (Mining, Agric, Tourism and EPWP) | District Mining Forum established | Number of District Economic Development Forums (Mining, Agric, Tourism and EPWP) facilitated | 3 District Economic Development Forums (Mining, Agric, Tourism and EPWP) facilitated | Develop TORs for the Forums | Facilitate 1 District Economic Development Forums (Mining, Agric & Tourism) | Facilitate 1 District Economic Development Forums (Mining, Agric, Tourism and EPWP) | Achieved | 1 District Economic Development forum facilitated (Agric) | N/A | N/A | *Signed reports *Attendance registers | 100000
To review the LED strategy by June 2019 | Human and financial resources | Reviewed LED Strategy | Improved local economy | Review LED Strategy | 2007 LED Strategy in place | Number of LED Strategy reviewed | 1 LED Strategy reviewed | Appoint Service Provider | Inception Report | Status Quo Report | Achieved | Draft reviewed LED report in place and submitted to council for noting | None | None | *Draft LED Strategy | 600000
To facilitate Economic Development Summit by June 2019 | Human and financial resources | Summit held | Improved economic planning | Facilitate Economic Development Summit | None | Number of Economic Develoment Summits facilitated | 1 Economic Develoment Summit facilitated | Develop Terms of Reference | Establish Task Team | No activity | N/A | N/A | N/A | N/A | *Signed report *Attendance register | 100000
INTEGRATED DEVELOPMENT PLAN (IDP)
To develop the IDP Framework/ Process Plan for 2019/20 by August 2018 | Human Resources | Process plan | Integrated planning | Development of 2019/2020 IDP/Budget Framework/Process Plan | 2018/19 IDP/Budget Framework Process Plan in place | Number of IDP Frameworks/ Process Plans developed | 1 IDP Frameworks/ Process Plans developed | Develop the IDP Framework/Process Plan | No activity | No activity | N/A | N/A | N/A | N/A | IDP Framework/Process Plan | 0
To facilitate the IDP Rep Forums by May 2019 | Human and financial Resouces | IDP Rep Forums | Improved Stakeholder participation | Facilitation of the IDP Rep Forums | 2 IDP Rep Forums held in 2017/18 | Number of IDP Rep Forums facilitated | 2 IDP Rep Forums facilitated | Review the Stakeholder list | Facilitate 1 IDP Rep Forum | No activity | N/A | 1 IDP Rep Forum was held on the 12 March 2019 at Fetakgomo Tubatse Mun. Apel Chamber | None | None | *Signed report *Attendance Registers | 50000
To review the IDP/Budget by May 2019 | Human and financial Resouces | IDP/Budget Review | Improved service delivery | Review of the IDP/Budget for 2019/20 | 2018/19 IDP/Budget in place | Number of IDP/Budget reviewed | 1 IDP/Budget reviewed | Consult Sector Departments on the development backlogs | Review Analysis Phase | Draft IDP document for 2019/20 | Achieved | Draft IDP/Budget noted by council on the 28 March 2019 (OC 11/03/19) | None | None | IDP/Budget document for 2019/20 | 430000
DIRECTOR: PLANNING AND ECONOMIC DEVELOPMENT | [10 empty] | DATE