## Sheet1
STATIAL RATIONALE
MEASURABLE OBJECTIVE | INPUT | OUTPUT | OUTCOME | PROJECT | BASELINE 2017/2018 | INDICATORS | ANNUAL TARGET 2018/2019 | Q1 | Q2 | Q3 | Q4 | ACHIEVED/NOT ACHIEVED | ACTUAL PROGRESS | CHALLENGES | REMEDIAL ACTION | EVIDENCE | BUDGET | IMPACT
2018/2019 SERVICE DELIVERY BUDGET AND IMPLEMENTATION PLAN: PLANNING AND ECONOMIC DEVELOPMENT DEPARTMENT
SPATIAL RATIONALE
To ensure facilitation of the functionality of the Joint District Municipal Planning Tribunal (JDMPT) by June 2019 | Human and financial resources | Functional District Municipal Planning Tribunal (JDMPT) | Well planned settlements and development | Facilitation of Joint District Municipal Planning Tribunal (JDMPT) | JDMPT in place | Number of JDMPT sittings facilitated | 4 JDMPT sitting facilitated | Facilitate 1 JDMPT sitting | Facilitate 1 JDMPT sitting | Facilitate 1 JDMPT sitting | Facilitate 1 JDMPT sitting | Achieved | 1 JDMPT sitting held on the 26 September 2018. | None | None | *Reports *Attendance Registers | 400000
To Support Local Municipalities on Spatial and Land Use Developments by June 2019 | Human and financial resources | Reviewed/implemented SDFs, LUMS and promulagated Land Use By-laws for Local Municipalities | Well planned settlements and development | Support to Local Municipalities on SDFs, LUMS and Land Use By-laws for Local Municipalities | All LMs have SDFs, LUMS and Land Use By-Laws | Number of Support Engagements on SDFs, LUMS and SPLUMA By-Laws implementation/review | 4 Support Engagements on SDFs, LUMS and SPLUMA By-Laws implementation/ review | 1 Support Engagement on SDFs, LUMS, and SPLUMA By-Laws implementation/ review | 1 Support Engagement on SDFs, LUMS and SPLUMA By-Laws implementation/ review | 1 Support Engagement on SDFs, LUMS and SPLUMA By-Laws implementation/ review | 1 Support Engagement on SDFs, LUMS and SPLUMA By-Laws implementation/ review | Achieved | 1 SPLUMA Forum sitting held on the 18 September 2018. Magoshi and LUS engagement meeting with EPHLM and Makhuduthamaga Magoshi Bylaw consultation meeting held. Masemola development meeting held on the 07/09/18. | none | none | *Reports *Attendance Registers | 20000
To facilitate land for the development of District Municipal offices by June 2019 | Human and financial resources | Land obtained | Available land for development of municipal offices | Facilitation of land for development of District Municipal Offices | Land owned by different entities is available for development | Number of engagement for land development of District Municipal Offices facilitated | 4 engagement for land development of District Municipal Offices facilitated | Facilitate 1 engagement for land development of District Municipal Offices | Facilitate 1 engagement for land development of District Municipal Offices | Facilitate 1 engagement for land development of District Municipal Offices | Facilitate 1 engagement for land development of District Municipal Offices | Achieved | Engagements made with Batlokwa ba Mogodumo land claimants in 7 July and 28 August 2018. Engagements were further made with Monama land claimants on 27 Agust 2018. Furhteher engagements were made with Coghsta, Limpopo Legislature and Pedi Mamone on the 13 July 2018. | None | None | Reports and attendance registers | 100000
To facilitate the implementation of the reviewed Spatial Development Framewok (SDF) by June 2019 | Human and financial resources | Development initiatives aligned with reviewed SDF | Improved spatial planning | Facilitation of implementation of the reviewed District Spatial Development Framework (SDF) | Reviewed SDF in place | Percentage implementation of reviewed SDF | 100% implementation of reviewed SDF | 100% implementation of reviewed SDF | 100% implementation of reviewed SDF | 100% implementation of reviewed SDF | 100% implementation of reviewed SDF | Achieved | 100% comprehensive report on the implementation of the SDF generated and reviewed. | None | None | Application Register Support letters | 130000
To spatially map the IDP capital projects for 2018/19 by June 2019 | Human and financial resources | Maps | Proper spatial decisions | Spatial mapping of IDP Projects | GIS Strategy in place | Percentage of IDP capital projects for 2018/19 spatially Mapped | 100% of IDP capital projects for 2018/19 spatially Mapped | Identify IDP capital projects for mapping | Spatially map 50% of IDP capital projects | Spatially map 50% of IDP capital projects | No activity | Achieved | List of 21 IDP Capital Projects identified for mapping. | None | None | Maps for IDP Capital projects for 2018/19 | 20000
To facilitate SPLUMA Workshop for Traditional Leaders and Councillors by June 2019 | Human and financial resources | SPLUMA Workshop | Understanding of SPLUMA | Facilitate SPLUMA Workshop for Traditional Leaders and Councillors | SPLUMA workshop held in 2016 | Number of SPLUMA workshops facilitated | 2 SPLUMA workshops facilitated | Engage with DRDLR, COGHSTA & SALGA | Facilitate 1 SPLUMA workshop | Engage with DRDLR, COGHSTA & SALGA | Facilitate 1 SPLUMA workshop | Achieved | Sector Departments engaged | None | None | * Report * Attendance registers | 150000