## SDBIP Q3
2018/2019 SERVICE DELIVERY BUDGET AND IMPLEMENTATION PLAN: FINANCIAL VIABILITY
MEASURABLE OBJECTIVE | STRATEGY | INPUT | OUTPUT | OUTCOME | PROJECT | BASELINE 2017/2018 | INDICATORS | ANNUAL TARGET 2018/2019 | Q1 | Q2 | Q3 TARGET | PROGRESS (Achieved/ Not achieved) | ACTUAL PROGRES | CHALLENGE | REMEDIAL ACTIONS | EVIDENCE | BUDGET 2018-2019
To finalise and implement PPP by June 2019 | By having Private Partnership Partner (Smart Metering) | By undertaking PPP process | Completed study | To have a PPP | Revenue enhancement – Billing and other sources (SMART Metering) | 100% Finalisation of PPP feasibility Study | Percentage Finalisation and implementation of PPP | 100% Finalisation and implementation of PPP | 20% finalisationand implementation of PPP.( decision by National Treasury in respect of TVR I AND TVR: IIA) | 30% finalisation and implementation of PPP (A decision by National Treasury in respect of TVR: IIB | 25% finalisation and implementation of PPP. (Appointment and Implementation of PPP) | Not Achieved | Awaiting National Treasury approval on TVRII | Delay in the review and approval of Bid document for TVRII | Review bid document and engage National Treasury to fast track the approval of TVRII | PPP agreement & reports | 2540000
To improve collection rate by June 2019 | By implementing credit control measures | By implementing credit control measures | 80% collection rate | To collect 80% revenue by June 2019 | Revenue enhancement – Billing and other sources | 66% Revenue Collection | Percentage Revenue Collection Rate | 80% Revenue Collected | Increase by 4% to 70% collection rate | Increase by 4% to 74% collection rate | Increase by 3% to 77% collection rate | Not Achieved | 66% Collection as at end of Q3 | Credit Control was not fully implemented in the affected areas in terms of cut off and restrictions of flow | Fully implemented the credit control by restriction and supply cut off | Billing reports | R7m
To create cash backed reserve fund by June 2019 | By reinvesting interest and portion of VAT refunds | Capital Replacement Reserve fund | Budget 2017/18 (R35m) | Percentage improvement in capital replacement reserve fund | Reserve fund | R10m | Rand Value invested towards CRR | R5m invested towards CRR | R1m | R1m | R2m | achieved | R2,1m has been invested in to CCR as per investment register | none | none | Acknowledgement of receipt of Section 71, 52 and 72 Report by Office of Executive Mayor, Auditor General acknowledgement receipt of AFS | 0
To develop and implement procurement plan and inventory management by June 2019 | By Implementation of forward plans | By implementing SCM regulations. | 2017/18 Procurement Plan developed | Procurement plan developed and implemented. | Logistics and inventory management | IDP/BUDGET | 1. Percentage development and implementation of procurement plans 2. Percentage accounting for inventory | 1.100% development and implementation of 2018/19 procurement plans 2. 100% accounting for inventory | *100% Finalisation of Procurement Plan. *100% accounting for inventory | *100% Monitoring and Implementation of procurement plan *100% accounting for inventory | 90% Monitoring and Implementation *100% accounting for inventory | Not Achieved | Monitoring and Implementation of procurement plan * accounting for inventory | Conflicting schedule of meetings of Committee members during Evaluation and Adjudication processes | That committee work be incorporated into perfomance agreement of Committee members and schedule of bid committee meetings be devoloped | Procurement Plan *Stock counting sheet | 0
To comply with statutory returns by June 2019 | To utilise the finance intern as compliance officer | Compliance checklist and Human Resources | Compliance reports prepared and submitted on time | Compliance to legislation and regulations | Compliance reporting | 2016/17 AFS 2016/17 Section 52; 71, 72 and SCM reports | Number of finance compliance reports generated and submitted | 30 finance compliance reports generated and submitted (12x Section 71, 4x Section 52, 12x Supply Chain, 1x Section 72, 1xAFS) | 8 (3 Sec 71, 3 SCM , 1 Sec 52 and 1 AFS) reports | 8 (3 Sec 71, 3 SCM , 1 Sec 72 and 1 Sec 52) reports | section 71 | achieved | submitting to the relevant stakeholders | none | none | Acknowledgement of receipt of Section 71, 52 and 72 Report by Office of Executive Mayor, Auditor General acknowledgement receipt of AFS | 0
To pay within 30 days | By Centralisation of invoice receipting and monitoring of the payment process by CFO | Payment control sheet | All creditors paid within 30 days | Reduction of fruitless expenditure | Creditors payments | Payment rate at 28 days | Percentage payment of creditors within 30 days of correct invoice receipt-date | 100% creditors paid within 30 days of correct invoice receipt- date. | 100% creditors paid within 30 days of correct invoice receipt- date | 100% creditors paid within 30 days of correct invoice receipt- date | 100% creditors paid within 30 days of correct invoice receipt- date | achieved | 100% creditors were paid within 30 days of correct invoice date | none | none | Creditors aging report | 0
To comply with section 66 of MFMA by June 2019 | By Centralisation of invoice receipting and monitoring of the payment process by CFO | Human Resources Payment Control | All creditors paid within 30 days | Compliance to BCEA | Salaries and third parties payments | 2017/2018 Salaries paid by 25th & 3rd Parties on or before 7th | Percentage payment of salaries and third parties by 25th & the 7th respectively | 100% payment of salaries and third parties by 25th & the 7th respectively | 100% payment of salaries and third parties by 25th & the 7th respectively | 100% payment of salaries and third parties by 25th & the 7th respectively | 100% payment of salaries and third parties by 25th & the 7th respectively | achieved | 100% payment of salaries and third parties were paid by 25th & the 7th respectively | none | none | Pay roll variance report and salary recon | 0
To prepare and monitor credible budget by June 2019. | By have a functioning budget steering committee | Budget preparation and implementation | 100% 2017/2018 approved realistic and credible budget | Percentage realistic and credible budget prepared. | Budget preparation, review of budget related policies and monitoring | 100% 2017/2018 approved budget | Percentage credible budget prepared and monitored. | 100% credible budget prepared and monitored ( 10% approved budget timetable) * 10% Roll over application * 30% Mid-year adjustment of budget *10% Review of budget related policies *20% Tabling of budget 20% approval of funded budget) | 1.10% Approved budget timetable 2. 10% Roll over application 2017/2018 . | No activity | * 30% Mid-year Adjustment of budget . * 10% Review of budget related policies(draft policies). 20% Tabling of Draft Budget. | achieved | Public consultantion on IDBP/Draft Budget for 2019/2020 is in progress as per budget schedule. | none | none | Fully funded final budget. | 0
To have GRAP compliant Fixed Asset Register by June 2019. | By Sound financial management. | human resource, Asset Management Policy | GRAP compliant asset register | Improved asset management and service delivery | Fixed Asset register | 1. Manual GRAP Compliant Fixed asset register 2. Project register | Percentage accounting of Assets | 100% accounting of assets | 100% Accounting for assets 1.Safeguarding assets and verification of assets 2.Valuation (run depreciation, update projects register) 3. Records keeping | 100% Accounting for assets 1.Safeguarding assets and verification of assets 2.Valuation (run depreciation, update projects register) 3. Records keeping | Accounting of assets. 1.Safeguarding of assets ( verification of assets) 2. Valuation (run depreciation, Update Projects register (WIP, Retention, Additions and Commitment registers), 3. Records keeping | Achieved | 1. Verification was performed 2. Valuations was performed.(quaterly depriciation posted, Project Registers are updated (WIP, Retention, Additions and Commitments Register are also updated 3. Records are kept safe. | None | None | Updated GRAP compliant Asset register, Updated Project register and reconciliation of PPE | R2 000 000
To fully comply with mSCOA implementation by June 2019. | By implementing mSCOA implementation plan | mSCOA Project | Council resolution | 100% compliance to mSCOA requirements | mSCOA implementation | Council resolution 2014/2015 & Treasury circular | Percentage unbundling of assets compliant to mSCOA | 100% unbundling of assets compliant to mSCOA | 20% appointment of service provider | 20% unbundling of assets compliant to mSCOA | 30% unbundling of assets compliant to mSCOA | achieved | Unbundling of assets | none | none | mSCOA progress report | 2489200
To achieve unqualified audit opinion without matters by June 2019 | By fully implement the audit action plan. | Human resource | Clean audit outcome | Sound financial management | Clean audit - OPCA | Unqualified audit opinion with matters of emphasis. ( 21 audit findings) | Percentage reduction in matters of emphasis and monitoring of the 17/18 audit process | 100% reduction in matters of emphasis and monitoring of the 17/18 audit process | *30% reduction of 16/17 matters of emphasis | 70% reduction in matters of emphasis and 100% monitoring of the 17/18 audit process | 100% development and monitoring of 2017/2018 action plan | Not achieved | 1.WIP reconcilliation is performed on montly basis. Unbudndling of projects completed awaiting appointment of service provider.2.Monthly reconciliations for receivables are done, however payable reconciliations are yet to be commenced. 3.The records of water supplied throuhg water tankering are kept on monthly basis 4 .The review of misallocations has commenced.5.The SCM checklist has been developed and applied to all tenders for the 2018/19 financial year.6.Payment process are being streamlined and scheduled at intervals of twice a week.7. Item has been prepared to serve at council in addressing the UIF not investigated.8. During adjustment of SDBIP targets that were not aligned as per AG report were adjusted in line with the required standard | AG 's report was received late and presented to council in February 2019. 2. Vacancies and actings in most positions in BTO created by suspensions and unfilled senior positions resulted in delay in progress in AG Action plan.3. Focus was shited from AG action plan to Mid year statutory submission and Budget adjusment. | 1.Appointment of CFO is done and appointment of other managers is in progres.2.Focus is now been given to AG action plan. | Progress report on Audit Action Plan | 142800
[5 empty] | CHIEF FINANCIAL OFFICER | [8 empty] | DATE
Mr. MJ MOFOKENG