## Sheet1
2018/2019 SERVICE DELIVERY BUDGET AND IMPLEMENTATION PLAN: INFRASTRUCTURE AND WATER SERVICES
BASIC SERVICES DELIVERY
2019-2020 SERVICE DELIVERY BUDGET AND IMPLEMENTATION PLAN
MEASURABLE OBJECTIVE | PROJECT | BASELINE 2018/2019 | INDICATORS | ANNUAL TARGET 2019/2020 | Q1 | Q3 TARGET | PROGRESS (Achieved/ Not chieved) | ACTUAL PROGRESS | CHALLENGE | REMEDIAL ACTIONS | Portfolio of Evidence | BUDGET 2019-2020
MUNICIPAL HEALTH SERVICES
To Have an improved, clean, healthy and sustainable environment through municipal health services package by June 2020 | Environmental Pollution Prevention | 12 Awareness Campaigns on Air Quality conducted | Number of Awareness Campaigns on Air Quality conducted | 24 Awareness Campaigns on Air Quality conducted | 6 air quality awareness campaigns conducted | 6 air quality awareness campaigns conducted | Achieved | 6 Air quality awareness campaigns conducted | None | None | Attendance register | 231440
| Water quality monitoring | 300 Water quality samples collected | Number of Water quality samples collected | 300 Water quality samples collected | 75 water quality samples collected | 75 water quality samples collected | Achieved | 75 Water quality samples collected | None | None | Signed Water Quality samples Reports | R44 078.28
| Food Safety control | 1400 Food Premises evaluated | Number of Food Premises evaluated | 1500 Food Premises evaluated | 350 food Premises evaluated | 375 food Premises evaluated | Achieved | 410 Food Premises evaluated | None | None | Signed Assessment forms incuding the owner signature | R21 501.60
| Waste Management | 100 Health care risk waste monitored | Number of Health care risk waste monitored | 100 Health care risk waste monitored | 25 Health care risk waste monitored | 25 Health care risk waste monitored | Achieved | 25 Health care risk waste monitored | None | None | Signed Assessment forms incuding the owner signature | R0 00
| Health Surveillance of premises | 1200 premises evaluated | Number of premises evaluated | 1500 premises evaluated | 200 premises evaluated | 375 premises evaluated | Not Achieved | 368 Premises evaluated | Covid-19 lockdown | To be attended after lockdown | Signed Assessment forms incuding the owner signature | R0 00
| Surveillance and prevention of communicable diseases | 100 Communicable diseases awareness campaigns held | Number of Communicable diseases awareness campaigns held | 100 Communicable diseases awareness campaigns held | 25 Communicable diseases awareness campaigns held | 25 Communicable diseases awareness campaigns held | Achieved | 50 Communicable diseases awareness campaigns held | None | None | Signed Assessment forms incuding the owner signature | R0 00
| Communicable diseases outbreak control | 142 communicable diseases investigated and controlled | Number of communicable diseases investigated and controlled | All communicable diseases investigated and controlled | All communicable diseases investigated and controlled | All communicable diseases investigated and controlled | Achieved | 47 Foodborne cases were investigation and controlled. | None | None | Signed Reports and Attendance register | 43003.2
| Vector Control | 1000 premises monitored on vector control | Number of premises monitored on vector control | 1400 premises monitored | 350 premises monitored | 350 premises monitored | Achieved | 390 Premises monitored | None | None | Signed Reports | R0 00
| Disposal of the dead | 100 Disposal of the dead facilities evaluated | Number of Disposal of the dead facilities evaluated | 100 Disposal of the dead facilities evaluated | 25 Disposal of the dead facilities evaluated | 25 Disposal of the dead facilities evaluated | Achieved | 26 Disposal of the dead facilities evaluated | None | None | *Signed Reports * Forms signed by Mortuaries | R0 00
| Chemical safety | 300 chemical handling premises evaluations conducted | Number of chemical handling premises evaluations conducted | 300 chemical handling premises evaluations conducted | 75 chemical handling premises evaluations conducted | 75 chemical handling premises evaluations conducted | Achieved | 78 Chemical handling premises evaluations conducted | None | None | *Signed Reports * Signed evaluation forms | R0 00
EMERGENCY MANAGEMENT SERVICES
To protect loss of life, damage to property and environment by June 2020 | Fire and Rescue Operations | 587 reported Emergency Services incidents attended | Number of reported Emergency Services incidents attended | All reported Emergency Services incidents attended | All reported Emergency Services incidents attended | All reported Emergency Services incidents attended | Achieved | All 124 reported Emergency Services incidents attended | None | None | Signed Reports | R0 00
| Emergency Management Services Training Academy | 4 fire fighting courses facilitated | Number of fire fighting courses facilitated | 3 firefighting courses facilitated | 1 firefighting course facilitated | 1 firefighting course facilitated | Achieved | 1 firefighting class facilitated. (ongoing) | Suspension of the commencement of the assessment due to covid-19 lockdown conditions | Assessment of the SDM/FF/23/2020 fire fighter class to resume post covid-19 lockdown conditions | Signed Reports and Attendance register | 32884.8
| Fire Safety and Prevention | 654 reported fire safety and prevention services conducted | Number of all fire safety and prevention services provided | All reported fire safety and prevention services conducted | All reported fire safety and prevention services conducted | All reported fire safety and prevention services conducted | Achieved | All 115 reported fire safety and prevention services conducted | Suspension of the registering of new applications and site inspections due to Covid-19 lockdown conditions | Suspension of the registering of new applications and site inspections to lifted post Covid-19 lockdown conditions | Signed Reports | R0 00
DISASTER MANAGEMENT
To protect loss of life, damage to property and environment by June 2020 | Disaster risk assessment | 580 reported disaster risk management incidents attended | Number of reported disaster risk management incidents attended | All reported disaster risk management incidents attended | All reported disaster risk management incidents attended | All reported disaster risk management incidents attended | Achieved | All 26 reported disaster risk management incidents attended | None | None | Register of disaster incidents | R0 00
| Disaster risk reduction | 24 disaster risk reduction awareness campaigns conducted | Number of disaster risk reduction awareness campaigns conducted | 24 disaster risk reduction awareness campaigns conducted | 6 disaster risk reduction awareness campaigns conducted | 6 disaster risk reduction awareness campaigns conducted | Achieved | 15 disaster risk reduction awareness campaigns conducted | None | None | Attendance Registers | R0 00
| Disaster response and recovery | (1210 Blankets, 622 sponches, 55 temporary shelters, 141 food parcels) relief material to all affected disaster victims coordinated and provided | Number of all reported disaster response and recovery operations attented to | Provide relief material to all deserving reported disaster victims | All reported disaster response and recovery operations attented to | Provide relief material to all deserving reported disaster victims | Achieved | 90 Blankets and 28 sponges were provided to all deserving reported disaster victims | None | None | Report | 268000
| Disaster management plan and framework review | 1 Disaster management plan and framework reviewed | Number of disaster management plan and framework reviewed | 01 Disaster management plan and framework reviewed | Stakeholder consultation | Consolidation of Stakeholder inputs | Achieved | Stakeholder consultation inputs have been consolidated | None | None | Reviewed disaster management plan and Council resolution | R0 00
| Special Operations | 03 special operations on high density days campaigns coordinated | Number of special high density days campaigns coordinated | 03 special operations on high density days campaigns coordinated | 1 special operations high density campaigns coordinated | 1 special operations high density campaigns coordinated | No Activity | No Activity | None | None | Operational plan, attendance register and minutes | 31 620, 00
INTERGOVERNMENTA RELATIONS
To coordinate Municipal Health services and environmental management Fora by June 2020 | Municipal Health services Forum and Environmental Management Fora | 4 Municipal Health services and 2 Environmental Management Fora coordinated | Number of Municipal Health services and Environmental Management Fora coordinated | 4 Municipal Health services and 2 Environmental Management Fora coordinated | 1 Municipal Health services and 1 Environmental Management Fora coordinated | 1 Municipal Health services and 1 Environmental Management Fora coordinated | Achieved | 1 Municipal Health services and 1 Environmental Management Fora coordinated | None | None | Attendance Register and Minutes | 10540
To coordinate Community safety Fora by June 2020 | Community safety Fora | 10 Community safety Fora coordinated | Number of Community safety Fora coordinated | 10 Community safety Fora coordinated | 2 Community safety Fora coordinated | 3 Community safety Fora coordinated | Not Achieved | 2 Community Safety Fora coordinated | Suspension of Community Safety Forum board meetings and activities due to Covid-19 lockdown conditions | Community Safety Forum board meetings and activities to resume post Covid-19 lockdown conditions | Attendance Register and Minutes
To coordinate Disater management Fora by June 2020 | Disaster management For a | 4 Disaster management Advisory Fora coordinated | Number of Disaster management Advisory Fora coordinated | 4 Disaster management Advisory Fora coordinated | 1 Disater management Advisory Forum coordinated | 1 Disaster management Advisory Forum coordinated | Achieved | 1 Disaster Management Advisory Forum coordinated | None | None | Attendance Register and Minutes