## Sheet1
2018/2019 SERVICE DELIVERY BUDGET AND IMPLEMENTATION PLAN: INFRASTRUCTURE AND WATER SERVICES
BASIC SERVICES DELIVERY
2019-2020 SERVICE DELIVERY BUDGET AND IMPLEMENTATION PLAN
MEASURABLE OBJECTIVE | PROJECT | BASELINE 2018/2019 | INDICATORS | ANNUAL TARGET 2019/2020 | Q1 | PROGRESS (ACHIEVED/ NOT ACHIEVED) | ACTUAL PROGRESS | CHALLENGE | REMEDIAL ACTION | Portfolio of Evidence | BUDGET 2019-2020
RBIG
To construct pipeline from Burgersfort to Dresden pump station by June 2020 | Construction of Mooihoek Bulk Water Supply Phase 4E | 5Km of bulk water supply pipeline phase 4D in Mooihoek completed | Number of Kilometers of bulk pipeline, of booster pump station and of reservoirs constructed | 3 Kilometers of bulk pipeline, of booster pump station and of reservoirs constructed | 1.5 Kilometers of bulk pipeline constructed,0* booster pump station constructed ,0*concrete reservoir constructed | Not achieved | 0 Kilometers of bulk pipeline constructed,0* booster pump station constructed ,0*concrete reservoir constructed | Community protests prevents the contractor from casting concrete on reservoir roof.Eskom delay installations of transformer | Social facilitator assisting to resolve the matter. | Signed Progress Report by Municipal Manager | 23250261
To construct bulk pipeline from Praktiseer to Alverton by June 2020 | Mooihoek bulk water supply phase 4G2 | 13km of bulk water supply pipeline phase 2 in Mooihoek completed | Number of Kilometers bulk water pipeline constructed | 4 Kilometers of bulk water supply pipeline constructed | 0,5 Kilometers of bulk water supply pipeline constructed | Not achieved | 0 Kilometers of bulk water supply pipeline constructed | Limited funding on the RBIG programme | Project to be implemented in the next RBIG allocation | Signed Progress Report by Municipal Manager | 35116668.5
To construct bulk pipeline from Praktiseer to Alverton by June 2020 | Mooihoek bulk water supply phase 4G1 | 1 X 5 Ml concrete reservoir completed Phase 4A | Percentage 1x5 MI concrete reservoir constructed | 70%, 1 X 5 Ml concrete reservoir constructed | 15%, 1 X 5 Ml concrete reservoir constructed | Not achieved | 0 %, 1 X 5 Ml concrete reservoir constructed | Limited funding on the RBIG programme | Project to be implemented in the next RBIG allocation | Signed Progress Report by Municipal Manager | 35116668.5
To construct bulk pipeline from Praktiseer to Motodi by June 2020 | Mooihoek bulk water supply phase 4H1 | 13 Kilometre of Mooihoek bulk water supply completed | Number of Kilometers of bulk water pipeline constructed | 4 Kilometers of bulk water pipeline constructed | Site establishment and 0.5km pipeline constructed | Not achieved | Site establishment and 0 km pipeline constructed | Limited funding on the RBIG programme | Project to be implemented in the next RBIG allocation | Signed Progress Report by Municipal Manager | 12000000
To construct bulk pipeline from Praktiseer to Alverton by June 2020 | Mooihoek bulk water supply phase 4H2 | 13 Kilometre of Mooihoek bulk water supply completed | Number of Kilometers of bulk pipeline constructed | 4 Kilometers of bulk water pipeline constructed | Site establishment and 0.5km pipeline constructed | Not achieved | Site establishment and 0 km pipeline constructed | Limited funding on the RBIG programme | Project to be implemented in the next RBIG allocation | Signed Progress Report by Municipal Manager | 12000000
To construct bulk water pipeline from T-off of Makgeru to the new 10ML reservoir at Schoonoord by June 2020 | Nebo BWS (RL19) Makgeru to Schoonoord | 18.2 Km of Schoonoord bulk water supply pipeline in Makgeru | Number of Kilometers of bulk water pipeline constructed | 5 Kilometers of bulk water supply pipeline constructed | 0,5 Kilometers of bulk water supply pipeline constructed | Not achieved | 0,1 Kilometers of bulk water supply pipeline constructed | Failure to deliver the outstanding ductile pipes by the service provider as per agreement | SDM Legal department currently finalizing termination of contract with the supplier. As way forward it is recommended that we deviate from SCM normal tendering processes and appoint a service provider with financial capacity who will be linked to a reliable supplier for the specialized material | Signed Progress Report by Municipal Manager | 15000000
To test and commissioned bulk water pipeline and main pump stations by June 2020 | Jane Furse to Lobethal bulk water supply pipeline | 18Km of bulk water supply pipeline Phase 2 from Jane to Lobethal completed | Number of Kilometers of bulk water supply pipeline assessed | 18 Kilometers of bulk water supply pipeline assessed | 2 Kilometers of bulk water supply pipeline assessed | Not achieved | 0 Kilometers of bulk water supply pipeline assessed | Contractor and consultant terminated | New consultant appointed to assess the remaining work to complete the project | Signed Progress Report by Municipal Manager | 5000000
To construct Bulk water Pipeline and test main pump stations by June 2020 | Moutse BWS Construction of Pipeline Project 7-12 | 30 Kilometre of bulk water supply pipeline constructed | Number of Kilometers of bulk water supply pipeline commissioned | 30 Kilometre of bulk water supply pipeline commissioned | 5 Kilometre of bulk water supply pipeline commissioned | Not achieved | 0 Kilometre of bulk water supply pipeline commissioned | Contractual disputes on professional services. Conclusion of fees settlement Connection into Lusaka Reservoir require Engineers supervision | Project Quality and quantity Management report submitted to MM for recommendation | Signed Progress Report by Municipal Manager | 10515156.78
To install mechanical and Electrical (M & E) for the extensions to the Groblersdal Water Treatment Works by June 2020 | Moutse BWS Extension of Groblersdal WTW Project 1 | 1 WTW in Groblersdal extended | Number of extended WTW tested and commissioned | One extended WTW tested and commissioned | No activity | N/A | No activity | Contractual disputes on professional services. Litigations against SDM. Delays in procuring of material by DWS National. Project on hold. No expenditure for 2 years | The project is currently under evaluation by Engineering specialist and the report will provided to the Municipality to make recommendations | Signed Progress Report by Municipal Manager | 3608238
To construct Bulk water Pipeline and test main pump stations by June 2020 | Moutse BWS Installation of Mechanical and Electrical Project 13&14 | 1 WTW in Groblersdal extended in Project 1 and 1 pump station constructed in Project 6 | Number of mechanical and Electrical (M & E) components installed for the extensions to the Groblersdal Water Treatment Works and pump station | Two mechanical and Electrical (M & E) components installed for the extensions to the Groblersdal Water Treatment Works and pump station | No activity | N/A | No activity | Contractual disputes on professional services. Conclusion of fees settlement Connection into Lusaka Reservoir require Engineers supervision | Project Quality and quantity Management report submitted to MM for recommendation | Signed Progress Report by Municipal Manager | 39135545.22
To construct Bulk water Pipeline and test main pump stations by June 2020 | Moutse BWS Construction bulk water Pipeline Project 2 – 4 | 19 Kilometres of bulk water supply pipeline and constructed | Number of km of bulk water supply pipeline assessed and refurbished | 19 Kilometers of bulk water supply pipeline assessed and refurbished | No activity | N/A | No activity | Contractual disputes on professional services. Conclusion of fees settlement Connection into Lusaka Reservoir require Engineers supervision | Project Quality and quantity Management report submitted to MM for recommendation | Signed Progress Report by Municipal Manager | 15257462
To construct Bulk water Pipeline and test main pump stations by June 2020 | Moutse BWS Construction Pipeline Project no 5 | 5 Kilometres of bulk water supply pipeline and constructed | Number of km of bulk water supply pipeline assessed and refurbished | 5 Kilometers of bulk water supply pipeline assessed and refurbished | No activity | N/A | No activity | Contractual disputes on professional services. Conclusion of fees settlement Connection into Lusaka Reservoir require Engineers supervision | Project Quality and quantity Management report submitted to MM for recommendation | Signed Progress Report by Municipal Manager | 9000000
WATER QUALITY
To generate Water Quality Reports by June 2020 | Generation of Water Quality Reports | 12 reports generated | Number of Water Quality Reports generated | 12 Water Quality Reports generated | 3 Water Quality Reports generated | Achieved | 3 Water Quality Reports generated | None | None | Signed Progress Report by Municipal Manager | 7150000
To conduct Full SANS 241 Analysis by June 2020 | Full SANS 241 Water Quality Analysis | 4 Full SANS 241 analysis report conducted through accredited laboratory | Number of Full SANS 241 Analysis conducted through accredited laboratory | 4 Full SANS 241 analysis conducted through accredited laboratory | 1 Full SANS 241 analysis conducted through accredited laboratory | Achieved | 1 Full SANS 241 analysis conducted through accredited laboratory | None | None | Signed Progress Report by Municipal Manager
To purchase Laboratories chemical by June 2020 | Purchase of LAB Chemicals | 90% of LAB chemical purchased | Percentage of LAB chemical purchased | 100% of LAB chemical purchased | 25% of LAB chemical purchased | Achieved | 25% of LAB chemical purchased | None | None | Signed Progress Report by Municipal Manager
To participate in Blue and Green Drops Certification Programme by June 2020 | Plants participation in Blue and Green Drops Certification Programme | 15 Water Treatment Works (WTW) participated in Blue Drop Certification programme and 15 Waste Water Treatment Works (WWTW) participated in Green Drop Certificate | Number of Plants participating in Blue and Greed Drops Certification Programme | 15 WTW participating in Blue Drop and 15 WWTW Participating in Green Drop Certification Programme | 15 WTW participating in Blue Drop and 15 WWTW Participating in Green Drop Certification Programme | Achieved | 15 WTW participating in Blue Drop and 15 WWTW Participating in Green Drop Certification Programme | None | None | Signed Progress Report by Municipal Manager
O & M EXPENDITURE
To resolve registered sanitation incidents within 14 days. | Sanitation incidents | 700 registered sanitation incidents resolved within 14 days | Number of registered sanitation incidents resolved within 14 days | All registered sanitation incidents resolved within 14 days | All registered sanitation incidents resolved within 14 days | Achieved | All registered sanitation incidents resolved within 14 days | None | None | Signed Progress Report by Municipal Manager | 39487845
To resolve registered water incidents within 14 days. | Water incidents | 5000 registered water incidents resolved within 14 days | Number registered water incidents resolved within 14 days | All registered water incidents resolved within 14 days | All registered water incidents resolved within 14 days | Achieved | All registered water incidents resolved within 14 days | None | None | Signed Progress Report by Municipal Manager
To render tankering services by June 2020 | Delivery of portable water through tankering | 9.6 Ml of Potable Water delivered in Jane Furse Hospital and Buffelshoek | Number of Ml of potable Water delivered in Jane Furse Hospital and Buffelshoek | 9.6 Ml of Potable Water delivered in Jane Furse Hospital and Buffelshoek | 2,4 Ml of Potable Water delivered in Jane Furse Hospital and Buffelshoek | Achieved | 5.76Ml of Potable Water delivered in Jane Furse Hospital and Buffelshoek | None | None | Signed Progress Report by Municipal Manager | 17950108.3
To provide diesel consistently to diesel driven machines by June 2020 | Supply of diesel | 40 000ℓ of diesel supplied annually. | Number of required litres of diesel supplied | All required litres of diesel supplied | All required litres of diesel supplied | Achieved | All required litres of diesel supplied | None | None | Signed Progress Report by Municipal Manager | 1787808
To provide petrol consistently to petrol driven machines by June 2020 | Supply of petrol | 400ℓ of petrol supplied annually. | Number of required Litres petrol supplied | All required litres of petrol supplied | All required litres of petrol supplied | Achieved | All required litres of petrol supplied | None | None | Signed Progress Report by Municipal Manager
To provide oil consistently to diesel and petrol driven machines by June 2020 | Supply of oil | 300ℓ of oil supplied annually. | Number of Litres of oil supplied | All required litres of oil supplied | All required litres of oil supplied | Achieved | All required litres of oil supplied | None | None | Signed Progress Report by Municipal Manager
To resolve registered M & E incidents within 14 days. | Mechanical & Electrical Services | 450 of registered M & E incidents within 14 days | Number of registered M & E incidents resolved within 14 days | All registered M & E incidents resolved within 14 days | All registered M & E incidents resolved within 14 days | Achieved | All registered M & E incidents resolved within 14 days | None | None | Signed Progress Report by Municipal Manager | 9620000
To install Bulk Water Meters by June 2020 | Installation of Bulk Water Meters | New project | Number of Bulk Meters installed | 8 Bulk Water Meters installed | 2 Bulk Water Meters installed | Not Achieved | 0 Bulk Water Meters installed | Delays in assesement of bulk metres took long | The assement of the bulk metres has concluded | Signed Progress Report by Municipal Manager | 5000000
To purchase Mℓ Bulk portable water by June 2020 | Ml of Bulk portable Water Purchases | 10 062Mℓ of bulk portable water purchased | Number of Mℓ of bulk portable water purchased | 2515,5Mℓ of bulk portable water purchased | 2515,5Mℓ of bulk portable water purchased | Achieved | 3079 Mℓ of water purchased | None | None | Signed Progress Report by Municipal Manager | 93664588.51
PLANNING & DESIGN AND REGULATIONS & GOVERNANCE
To develop Water Conservation /Water Demand Management Strategy for SDM by June 2020 | Water Conservation and Water Demand Management Plan | No WC/WDM plan in place | Number of WC/WDM plan developed | One WC/WDM plan developed | No activity | N/A | No activity | None | None | Draft WC/WDM strategy | 0
To develop and review Water & Sanitation Master Plan by June 2020 | Development of Water & Sanitation Master Plan (WSMP) | 1 Draft Water Master Plan and no sanitation Master Plan | Number of Water & Sanitation Master Plan developed | One Water & Sanitation Master Plan developed | No activity | N/A | No activity | None | None | Draft WSMP/WSDP | 500000
To upgrade Groblersdal sewer pump- station by June 2020 | Conditional assessment of Groblersdal sewer network | 50% Conditional assessment for Groblersdal sewer network. | Number of conditional assessment report for Groblersdal sewer network conducted. | One conditional assessment report for Groblersdal sewer network conducted | No activity | N/A | No activity | None | None | Signed Progress Report by Municipal Manager | 2500000
To improve the provision of operations & maintenance efficiently by June 2020 | Development of Operation and Maintenance Plan (O&M) | Draft O&M plan completed | Number of O & M Plan completed and approved | One O & M Plan completed and approved | No activity | N/A | No activity | None | None | Approved O & M plan | 375000
To Conduct Feasibility Studies and develop Technical Report by June 2020 | Conduct Feasibility Studies and develop Technical reports | Water Services Master Plan and WSDP developed in 2014/15 and 2015/16 FY respectively | Number of Feasibility Studies conducted and technical Reports developed | 9 Feasibility Studies conducted and technical Reports developed. | 2 Feasibility Studies conducted and technical Reports developed | Achieved | 2 Feasibility Studies conducted and technical Reports developed | None | None | Signed Progress Report by Municipal Manager | 2500000
To ensure effective infrastructure planning & development by June 2020 | Update Water Service Development Plan. | Water Services Master Plan and WSDP developed in 2014/15 and 2015/16 FY respectively | Number of updated Water Service Development Pan. | 1 Water Service Development Pan updated. | No activity | N/A | No activity | None | None | Updated Water Service Development Pan . | 500000
To ensure compliance with water services policies by June 2020 | Registration of servitude for bulk water infrastructure. | Report for bulk water service in place | Number of bulk water infrastructure servitude registered | 1 bulk water infrastructure servitude registered | No activity | N/A | No activity | None | None | water infrastructure servitude register certificate | 1000000
To ensure compliance with water services policies by June 2020 | Formulation of Bulk contribution policy | Draft bulk contribution policy in place | Number of bulk water contribution policy promulgated | 1 bulk water contribution policy promulgated | No activity | N/A | No activity | None | None | Approved policy | 500000
To review water services policies by June 2020 | Review of water and sanitation by-law | Water & Sanitation by-laws in place | Number of Water & Sanitation By-Laws reviewed | 1 Water & Sanitation By-Laws reviewed | No activity | N/A | No activity | None | None | Approved water and sanitation by-laws | 250000
WSIG PROJECTS
To complete Tukakgomo water reticulation by June 2020 | Tukakgomo water intervention and refurbishment. | 14,5 km of reticulation network | Number of Kilometers of water reticulation network completed | 4 Kilometers of water reticulation network completed | 0,5 Kilometers of water reticulation network completed | Not Achieved | 0 Kilometers of water reticulation network completed | Delayed transfer of WSIG funds by DWS to Sekhukhune District Municipality. | DWS send the correspondence indicating that the funds will be transferred by the 22nd November 2019. | Signed close-out report by Municipal Manager and Completion certificate | 4000000
To develop water source by June 2020 | Phokwane Brooklyn water supply | There is existing bulk water supply line from Flag Boshielo without formal reticulation. | *Number of water source developed *Number of km of rising main and storage tank completed | *1 water source developed *0,8 km of rising main and 1 storage tank completed | 1 water source developed | Not Achieved | 0 water source developed | Delayed transfer of WSIG funds by DWS to Sekhukhune District Municipality. | DWS send the correspondence indicating that the funds will be transferred by the 22nd November 2019. | Signed close-out report by Municipal Manager and Completion certificate | 1000000
To construct water supply pipeline by June 2020 | Manganeng and Madirane water supply | There is existing distribution reservoir without gravity line. | Number of Kilometers of water supply pipeline constructed | 1.5 Kilometers of water supply pipeline constructed | No activity | N/A | No activity | No activity | No activity | Signed close-out report by Municipal Manager and Completion certificate | 2000000
To complete water supply pipeline and water storage by June 2020 | Uitspanning Water Supply Intervention | Groblersdal WTW and Moutse bulk pipeline in progress | *Number of km of water supply pipeline, water storage and package plant completed | *4 km of water supply pipeline, 1 water storage and 1 package plant completed | *0,5 km of water supply pipeline and 1 water storage completed | Not Achieved | 0 km of water supply pipeline and 0 water storage completed | Delayed transfer of WSIG funds by DWS to Sekhukhune District Municipality. | DWS send the correspondence indicating that the funds will be transferred by the 22nd November 2019. | Signed close-out report by Municipal Manager and Completion certificate | 10802000
To develop water source, complete reticulation and install storage tank by June 2020 | Mapulaneng drilling and equipping of borehole | Informal water infrastructure . | Number of water source developed, km of reticulation completed and storage tank installed. | 1 water source developed, 2.6 km of reticulation completed and 1 storage tank installed. | 1 water source developed. | Not Achieved | 0 water source developed. | Delayed transfer of WSIG funds by DWS to Sekhukhune District Municipality. | DWS send the correspondence indicating that the funds will be transferred by the 22nd November 2019. | Signed close-out report by Municipal Manager and Completion certificate | 3000000
To complete reticulation and installation of water meters by June 2020 | Flag Boshielo Water Conservation Water Demand Management | Partially reticulated village without water meters. | Number of km of reticulation completed and water meters installed. | 6 km of reticulation completed and 810 water meters installed. | 1 km of reticulation completed. | Not Achieved | 0 km of reticulation completed. | Delayed transfer of WSIG funds by DWS to Sekhukhune District Municipality. | DWS send the correspondence indicating that the funds will be transferred by the 22nd November 2019. | Signed close-out report by Municipal Manager and Completion certificate | 10000000
To develop water source, complete reticulation and installation of storage tank by June 2020 | Mabulela drilling and equipping of borehole | Informal water infrastructure . | Number of water source developed, km of reticulation completed and storage tank installed. | 1 water source developed, 1.2 km of reticulation completed and 1 storage tank installed. | 1 water source developed. | Not Achieved | 0 water source developed. | Delayed transfer of WSIG funds by DWS to Sekhukhune District Municipality. | DWS send the correspondence indicating that the funds will be transferred by the 22nd November 2019. | Signed close-out report by Municipal Manager and Completion certificate | 1413600
To complete reticulation network & storage by June 2020 | Seokodibeng construction reticulation network | Informal water infrastructure . | Number of km of reticulation completed and storage tank installed. | 1.3km of reticulation completed and 1 storage tank installed. | 0.5km of reticulation completed. | Not Achieved | 0 km of reticulation completed. | Delayed transfer of WSIG funds by DWS to Sekhukhune District Municipality. | DWS send the correspondence indicating that the funds will be transferred by the 22nd November 2019. | Signed close-out report by Municipal Manager and Completion certificate | 2000000
To develop water source, complete reticulation and install package plant by June 2020 | Maebe/Mohlaletsi interventions | Informal water infrastructure . | Number of water source developed, reticulation completed and package plant installed. | 1 water source developed, 2km of reticulation completed and 1 package plant installed. | 1 water source developed. | Not Achieved | 0 water source developed. | Delayed transfer of WSIG funds by DWS to Sekhukhune District Municipality. | DWS send the correspondence indicating that the funds will be transferred by the 22nd November 2019. | Signed close-out report by Municipal Manager and Completion certificate | 8000000
To develop water source, complete rising main and seal concrete reservoir by June 2020 | Mashikwe drilling and equipping of borehole | Informal water infrastructure . | Number of water source develop, rising main completed and concrete reservoir sealed | 1 water source developed, 0.8 km rising main completed and 1 concrete reservoir sealed. | 1 water source developed. | Not Achieved | 0 water source developed. | Delayed transfer of WSIG funds by DWS to Sekhukhune District Municipality. | DWS send the correspondence indicating that the funds will be transferred by the 22nd November 2019. | Signed close-out report by Municipal Manager and Completion certificate | 2000000
To construct VIDP Sanitation units by June 2020. | Construction of Legolaneng VDIP | New Infrastructure | Number of VDIP sanitation units constructed | 334 VDIP Sanitation units constructed | 34 VDIP Sanitation units constructed | Not Achieved | 0 VDIP Sanitation units constructed | Delayed transfer of WSIG funds by DWS to Sekhukhune District Municipality. | DWS send the correspondence indicating that the funds will be transferred by the 22nd November 2019. | Signed close-out report by Municipal Manager and Completion certificate | 7500000
To construct reticulation network by June 2020 | Rutseng Water Intervention | Informal water infrastructure in place | Number of Kilometers of water supply pipeline constructed | 7km of water supply pipeline constructed | 1km of water supply pipeline constructed | Not Achieved | 0 km of water supply pipeline constructed | Delayed transfer of WSIG funds by DWS to Sekhukhune District Municipality. | DWS send the correspondence indicating that the funds will be transferred by the 22nd November 2019. | Signed close-out report by Municipal Manager and Completion certificate | 3000000
To complete testing and commissioning of pipeline by June 2020. | Nebo Phase 1A testing and commissioning(Jane Furse WC/WD Management) | Nebo Phase1A completed but not commissioned | Number of Kilometers of bulk water supply pipeline tested and commissioned | 33km bulk water supply pipeline tested and commissioned | 6km bulk water supply pipeline tested and commissioned | Not Achieved | 0 km bulk water supply pipeline tested and commissioned | Delayed transfer of WSIG funds by DWS to Sekhukhune District Municipality. | DWS send the correspondence indicating that the funds will be transferred by the 22nd November 2019. | Signed close-out report by Municipal Manager and Completion certificate | 15284400
MUNICIPAL INFRASTRUCTURE GRANT (MIG)
To construct Ephraem Mogale VIP Sanitation units by June 2020 | Ephram Mogale VIP Sanitation Programme Phase 2.3 | 15 180 VIP units constructed | Number of VIP sanitation units constructed | 3000 VIP sanitation units constructed | 750 VIP Sanitation toilets constructed | Not Achieved | 0 VIP Sanitation toilets constructed | Contractors Development Programme stagnant because of administration issues. Contractors cannot be given sites because of the unavailability of the beneficiary list. | The request for beneficiary list letters has been done and letters are dispatched to local municipalities and we waiting for their response | Signed Progress Report by Municipal Manager | 12000000
To construct Elias Motsoaledi VIP Sanitation units by June 2020 | Elias Motsoaledi VIP Sanitation Programme Phase 2.3 | 15 180 VIP units constructed | Number of VIP sanitation units constructed | 3000 VIP sanitation units constructed | 750 VIP Sanitation toilets constructed | Not Achieved | 0 VIP Sanitation toilets constructed | Contractors Development Programme stagnant because of administration issues. Contractors cannot be given sites because of the unavailability of the beneficiary list. | The request for beneficiary list letters has been done and letters are dispatched to local municipalities and we waiting for their response | Signed Progress Report by Municipal Manager | 12000000
To complete Zaaiplaas bulk pipeline, command reservior and pump station by June 2020 | Zaaiplaas Village Reticulation Phase 2 ( Vlakfontein, Slovo and remaining village ) - CO | 80% construction of Dindela Reservoir. Commissioning of bulk pipeline and pump station completed | Number of Kilometres of Zaaiplaas bulk water supply pipeline commissioned, command reservoir constructed and pump station installed | 3 Kilometres of Zaaiplaas bulk water supply pipeline commissioned, 1 command reservoir constructed and 1 pump station installed | 1 Kilometres of Zaaiplaas bulk water supply pipeline commissioned and 1 pump station installed | Not Achieved | 0 Kilometres of Zaaiplaas bulk water supply pipeline commissioned and 0 pump station installed | General delays due to technical support requirement, procurement of materials. New estimate completion date end Nov 2019. Requires confirmation on testing conducted on pumps. Poor attendance to contractual concerns and matters by the Contractor. Concern that some variation, minor additional scope work items and extension of time consideration could exceed contingency allowance and value | Recommend Engineer be afforded opportunity to develop alternative solution for direct supply to 10 downstream reservoirs. SDM to consider extending H&H (and subcontractors) contract to include commissioning of the pipeline on alternative solution. | Signed Progress Report by Municipal Manager | 5472297
To construct Makhuduthamaga VIP Sanitation units by June 2020 | Makhuduthamaga VIP Sanitation programme phase 2.3 | 15 180 VIP units constructed | Number of VIP sanitation units constructed | 3000 VIP sanitation units constructed | 750 VIP sanitation units constructed | Not Achieved | 0 VIP Sanitation toilets constructed | Contractors Development Programme stagnant because of administration issues. Contractors cannot be given sites because of the unavailability of the beneficiary list. | The request for beneficiary list letters has been done and letters are dispatched to local municipalities and we waiting for their response | Signed Progress Report by Municipal Manager | 12000000
To construct reticulation network in Ga- Mashabela by June 2020 | Ga- Mashabela water reticulation supply | 60% of water reticulation constructed | Kilometres of pipeline constructed, number of reservoir constructed, number of boreholes drilled and equiped | 30km of pipeline constructed , 4* Reservoir constructed 7*boreholes drilled and equiped | 15km of pipeline constructed , | Not Achieved | 5km of pipeline constructed , | Delays in approval of the VO | The VO is finally approved and the project to be fast track | Signed Progress Report by Municipal Manager | 1000000
To construct Bulk water supply network in Ga- Marishane by June 2020 | Ga- Marishane water reticulation supply | 30% Bulk water supply constructed | Kilometres of pipeline constructed, number of reservoir constructed and WTW refurbished | 3.4km of bulk pipeline constructed , 1 reservoir constructed and 1 WTW refurbished | 1,7km of bulk pipeline constructed | Achieved | 3.3km of bulk pipeline constructed , 0 reservoir completed and 0 WTW completed | None | None | Signed Progress Report by Municipal Manager | 1000000
To construct reticulation network in Ga -Mogashoa(Senkapudi) and Ga- Mogashoa(Manamane) by June 2020 | Ga -Mogashoa(Senkapudi) and Ga- Mogashoa(Manamane) | 200kl reservoir constructed | kilometres of pipeline constructed | 53 kilometres of pipeline constructed | No activity | N/A | No activity | No activity | No activity | Signed Progress Report by Municipal Manager | 60000000
To construct concrete reservoirs and bulk water pipeline, NSD07 RWS Schoonoord by June 2020 | NSD07 Regional Water Scheme Construction of Concrete Reservoirs | 10ML reservoir and the bulk water pipeline constructed | Kilometre of pipeline constructed and number of reservoir constructed | 1 Kilometre of pipeline constructed and 1 reservoir constructed | No activity | N/A | No activity | No activity | No activity | Signed Progress Report by Municipal Manager | 40000000
To construct Fetakgomo Tubatse VIP Sanitation units by June 2020 | Fetakgomo Tubatse VIP Sanitation programme phase 2.3 | 15 180 VIP Units constructed | No of VIP sanitation units constructed | 1500 VIP sanitation units constructed | 375 VIP sanitation units constructed | Not Achieved | 0 VIP Sanitation toilets constructed | Contractors Development Programme stagnant because of administration issues. Contractors cannot be given sites because of the unavailability of the beneficiary list. | The request for beneficiary list letters has been done and letters are dispatched to local municipalities and we waiting for their response | Signed Progress Report by Municipal Manager | 10000000
To complete Concrete reservoirs; Bulk Water Supply;and Reticulation at Nkadimeng: Phase 9 to 11 by June 2020 | Nkadimeng RWS Extension 2( Phase 9 to 11) (Fetakgomo) Ga- Mmela to Mashilavele , Ga- Pahla, Molapong, Ga- Magolego, Mankontu and Masehleng | 2 x 500kl reservoir constructed and 67km pipeline installed | km of pipeline constructed, number of reservoir and street taps constructed | 38km of pipeline constructed, 1* 500kl reservoir and 98 street taps constructed | 2km of pipeline constructed | Achieved | 2 km of pipeline constructed, 0* 500kl reservoir and 0 street taps | None | None | Signed Progress Report by Municipal Manager | 1000000
To construct Fetakgomo Tubatse VIP Sanitation units by June 2020 | Fetakgomo Tubatse VIP Sanitation programme phase 2.3 | 15 180 VIP Units constructed | No of VIP sanitation units constructed | 3000 VIP sanitation units constructed | 750 VIP sanitation units constructed | Not Achieved | 0 VIP Sanitation toilets constructed | Contractors Development Programme stagnant because of administration issues. Contractors cannot be given sites because of the unavailability of the beneficiary list. | The request for beneficiary list letters has been done and letters are dispatched to local municipalities and we waiting for their response | Signed Progress Report by Municipal Manager | 12000000
To construct reticulation network in Malekana by June 2020 | Malekana Regional Water Scheme | 10ML Water Treatment Plant constructed | Kilometres of pipeline and number of reservoirs constructed | 10 kilometres of pipeline and 4 reservoirs constructed | No activity | N/A | No activity | No activity | No activity | Signed Progress Report by Municipal Manager | 81021375.64
To construct connector pipe network in Lebalelo South by June 2020 | Lebalelo South connector pipes | 10ML Mooihoek Water Treatment Works, Mooihoek Bulk pipeline constructed | km pipeline and number of reservoirs constructed | 190km pipeline and 3 reservoirs constructed | 40km pipeline constructed | Achieved | 40km pipeline constructed | None | None | Signed Progress Report by Municipal Manager | 107957451
| Lebalelo South phase 3 (Ga-Maroga and Motlolo Bulk and Reticulation infrastructure) | 10ML Mooihoek Water Treatment Works, Mooihoek Bulk pipeline constructed | Kilometres of pipeline and number of reservoirs coonstructed | 55 kilometres of pipeline and 3 reservoirs constructed | No activity | N/A | No activity | No activity | No activity | Signed Progress Report by Municipal Manager | 100765251.93
MUNICIPAL HEALTH SERVICES
To Have an improved, clean, healthy and sustainable environment through municipal health services package by June 2020 | Environmental Pollution Prevention | 12 Awareness Campaigns on Air Quality conducted | Number of Awareness Campaigns on Air Quality conducted | 24 Awareness Campaigns on Air Quality conducted | 6 Air quality awareness campaigns conducted | Achieved | 6 Air quality awareness campaigns conducted | None | None | Attendance register | 231440
| Water quality monitoring | 300 Water quality samples collected | Number of Water quality samples collected |  | 75 Water quality samples collected | Achieved | 75 Water quality samples collected | None | None | Signed Water Quality samples Reports | R44 078.28
| Food Safety control | 1400 Food Premises evaluated | Number of Food Premises evaluated | 1400 Food Premises evaluated | 350 Food Premises evaluated | Achieved | 366 Food premises evaluated | None | None | Signed Assessment forms incuding the owner signature | R21 501.60
| Waste Management | 100 Health care risk waste monitored | Number of Health care risk waste monitored | 100 Health care risk waste monitored | 25 Health care risk waste monitored | Achieved | 27 Health care risk waste monitored | None | None | Signed Assessment forms incuding the owner signature | R0 00
| Health Surveillance of premises | 1200 premises evaluated | Number of premises evaluated | 750 Premises evaluated | 200 Premises evaluated | Achieved | 217 Premises evaluated | None | None | Signed Assessment forms incuding the owner signature | R0 00
| Surveillance and prevention of communicable diseases | 100 Communicable diseases awareness campaigns held | Number of Communicable diseases awareness campaigns held | 100 Communicable diseases awareness campaigns held | 25 Communicable diseases awareness campaigns held | Achieved | 44 Communicable diseases awareness campaigns held | None | None | Signed Assessment forms incuding the owner signature | R0 00
| Communicable diseases outbreak control | 142 communicable diseases investigated and controlled | Number of communicable diseases investigated and controlled | All communicable diseases investigated and controlled | All communicable diseases investigated and controlled | Achieved | All 10 Diarrhoea cases reported were investigated | None | None | Signed Reports and Attendance register | 43003.2
| Vector Control | 1000 Premises monitored on vector control | Number of premises monitored on vector control | 1400 Premises monitored | 350 Premises monitored | Achieved | 366 Premises monitored | None | None | Signed Reports | R0 00
| Disposal of the dead | 100 Disposal of the dead facilities evaluated | Number of Disposal of the dead facilities evaluated | 100 Disposal of the dead facilities evaluated | 25 Disposal of the dead facilities evaluated | Achieved | 27 Disposal of the dead facilities evaluated | None | None | *Signed Reports * Forms signed by Mortuaries | R0 00
| Chemical Safety | 300 Chemical handling premises evaluations conducted | Number of chemical handling premises evaluations conducted | 300 Chemical handling premises evaluations conducted | 75 Chemical handling premises evaluations conducted | Achieved | 80 Chemical handling premises evaluations conducted | None | None | *Signed Reports * Signed evaluation forms | R0 00
EMERGENCY MANAGEMENT SERVICES
To protect loss of life, damage to property and environment by June 2020 | Fire and Rescue Operations | 587 reported Emergency Services incidents attended | Number of reported Emergency Services incidents attended | All reported Emergency Services incidents attended | All reported Emergency Services incidents attended | Achieved | All 276 reported emergency sevices incidents attended | None | None | Signed Reports | R0 00
| Emergency Management Services Training Academy | 4 Fire fighting courses facilitated | Number of fire fighting courses facilitated | 3 Firefighting courses facilitated | 1 Firefighting course facilitated | Achieved | 3 Firefighting course facilitated | None | None | Signed Reports and Attendance register | 32884.8
| Fire Safety and Prevention | 654 reported fire safety and prevention services conducted | Number of all fire safety and prevention services provided | All reported fire safety and prevention services conducted | All reported fire safety and prevention services conducted | Achieved | All 220 reported fire safety prevention services conducted | None | None | Signed Reports | R0 00
| EMS Equipment | 31 required supplies to stations delivered | Number of all provision of EMS Equipment delivered | All required supplies to stations delivered | All required supplies to stations delivered | Achieved | All 5 required supplies to stations delivered | None | None | Delivery note | 221776.43
DISASTER MANAGEMENT
To protect loss of life, damage to property and environment by June 2020 | Disaster risk assessment | 580 reported disaster risk management incidents attended | Number of reported disaster risk management incidents attended | All reported disaster risk management incidents attended | All reported disaster risk management incidents attended | Achieved | All (51) Disaster risk management incidents attended | None | None | Register of disaster incidents | 368200
| Disaster risk reduction | 24 Disaster risk reduction awareness campaigns conducted | Number of disaster risk reduction awareness campaigns conducted | 24 Disaster risk reduction awareness campaigns conducted | 6 Disaster risk reduction awareness campaigns conducted | Achieved | 15 Disaster risk reduction awareness campaigns conducted | None | None | Signed Reports * Register of disaster incidents | R0 00
| Disaster response and recovery | (1210 Blankets, 622 sponches, 55 temporary shelters, 141 food parcels) relief material to all affected disaster victims coordinated and provided | Number of all reported disaster response and recovery operations attented to | All reported disaster response and recovery operations attented to | All reported disaster response and recovery operations attented to | Achieved | All (51) reported disaster response and recovery operations attented to | None | None | Register of incidents attented to | R0 00
| Disaster management plan and framework review | 1 Disaster management plan and framework reviewed | Number of disaster management plan and framework reviewed | 01 Disaster management plan and framework reviewed | Stakeholder consultation | Achieved | Stakeholder consulted | None | None | Reviewed disaster management plan and Council resolution | R0 00
| Special Operations | 03 Special operations on high density days campaigns coordinated | Number of special high density days campaigns coordinated | 03 Special operations on high density days campaigns coordinated | 1 Special operations high density campaigns coordinated | Achieved | 1 Special operations high density campaigns coordinated | None | None | Operational plan, attendance register and minutes | 31 620, 00
INTERGOVERNMENTA RELATIONS
To coordinate Municipal Health services and environmental management Fora by June 2020 | Municipal Health services Forum and Environmental Management Fora | 4 Municipal Health services and 2 Environmental Management Fora coordinated | Number of Municipal Health services and Environmental Management Fora coordinated | 4 Municipal Health services and 2 Environmental Management Fora coordinated | 1 Municipal Health services and 1 Environmental Management Fora coordinated | Achieved | 1 Municipal Health services and 1 Environmental Management Fora coordinated | None | None | Attendance Register and Minutes | 10540
To coordinate Community safety Fora by June 2020 | Community safety Fora | 10 Community safety Fora coordinated | Number of Community safety Fora coordinated | 10 Community safety Fora coordinated | 2 Community safety Fora coordinated | Achieved | 2 Community safety Fora coordinated | None | None | Attendance Register and Minutes
To coordinate Disater management Fora by June 2020 | Disater management Fora | 4 Disater management Advisory Fora coordinated | Number of Disater management Advisory Fora coordinated | 4 Disater management Advisory Fora coordinated | 1 Disater management Advisory Forum coordinated | Achieved | 1 Disater management Advisory Forum coordinated | None | None | Attendance Register and Minutes