## PED
PLANNING AND ECONOMIC DEVELOPMENT
2019-2020 SERVICE DELIVERY BUDGET AND IMPLEMENTATION PLAN
MEASURABLE OBJECTIVE | INPUT | OUTPUT | OUTCOME | PROJECT | BASELINE 2018/2019 | INDICATORS | ANNUAL TARGET 2019/2020 | Q1 | Q2 | Q3 | Q4 | EVIDENCE | BUDGET 2019-2020
SPATIAL RATIONALE
To ensure sustainable spatial and land use development within the District by 2020 |  |  |  | Facilitate Joint District Municipal Planning Tribunal | 4 JDMPT sittings facilitated | Number of JDMPT facilitated | 4 Joint District Municipal Planning Tribunals facilitated | [5 empty] | 400000
|  |  |  | Facilitate Land Acquisition for District Municipal Offices | Land owned by different entities is available for development | Number of hectares of land acquired for development of District Municipal Offices | 10ha of land land for District Municipal Offices facilitated | [5 empty] | R50 000
|  |  |  | Process Land Development applications in line with the reviewed SDF | Processed 100% Land Development applications in line with the reviewed SDF | Percentage Land Development applications processed in line with reviewed SDF | 100% Land Development applications processed in line with reviewed SDF | [5 empty] | 0
|  |  |  | Formalisation of Informal Settlements | None | Number of Informal Settlements within the District formalised | 1 informal Settlement within the District formalised | [5 empty] | 0
|  |  |  | Develop Precinct Plans in Nodal points/Growth points with required economic resources | Reviewed Spatial Development Framework | Number of Precinct Plans in Nodal points/Growth points with required economic resources developed | 1 Precinct Plans in Nodal points/Growth points with required economic resources developed | [5 empty] | 200000
|  |  |  | Integrate Municipal Geographic Information System (GIS), Finance, Asset Management System and WSMP | GIS strategy in place | Percentage integration of Municipal Geographic Information System (GIS), Finance, Asset Management and WSMP | 100% integration of Municipal Geographic Information System (GIS) Finance, Asset Management and WSMP | [5 empty] | R1 000 000
LOCAL ECONOMIC DEVELOPMENT
To promote Job Creation Opportunities through EPWP by June 2022 |  |  |  | Implementation of EPWP | 912 | Number of jobs created through EPWP | 6 1 80 jobs created through EPWP | [5 empty] | R2 665 000
To empower 60 SMMEs by 2020 |  |  |  | Facilitate Enterprise and Supplier Development Programme | 3 Service Providers appointed | Number of SMMEs capacitated | 60 SMMEs capacitated | [5 empty] | 150000
|  |  |  | Trainings for SMMEs and cooperatives | 20 SMMEs trained during 2018/19 | Number of SMMEs trained | 30 SMMEs trained | [5 empty] | 100000
|  |  |  | Support to SMMEs and Co-operatives | 1 SMME and 1 Co-operative supported during 2019 | Number of SMMEs/Co-operative support provided | 2 SMMEs/Co-operatives supported | [5 empty] | 250000
|  |  |  | Feasibility Study on the development of a formal District Flea Market within the District | No formal Flea market within the District | Number of feasibility studies conducted on the development of a Flea Market within the District | 1 feasibility study conducted on the development of a Flea Market within the District | [5 empty] | 300000
To enhance growth of farmers production by June 2020 |  |  |  | Facilitate development of Farmer Support Production Unit (Agri-Park) | Agri Park Business Plan in place | Number of Farmer Support Production Unit (Agri-Park) developed | 1 Farmer Support Production Unit (Agri-Park) developed | [5 empty] | 1 000 000
|  |  |  | Facilitate Rehabilitation of Irrigation Schemes | None | Number of Irrigation Schemes rehabilitated | 1 irrigation scheme rehabilitated | [5 empty] | 0
| Develop Feasibility Study on Marula Processing Plant(Women, Youth and People with disability to be prioritised) |  |  | Develop Feasibility Study on Marula Processing Plant(Women, Youth and People with disability to be prioritised) | Marula Processing Plant business plan in place | Number of feasibility studies conducted | 1 Feasibility Study on Marula Processing Plant conducted | [5 empty] | 0
| Develop Industrial Development Master Plan for the Special Economic Zone (SEZ) |  |  | Develop Industrial Development Master Plan for the Special Economic Zone (SEZ) | SEZ Business Plan in place | Number of Regional Industrial Development Master Plan developed | 1 Regional Industrial Development Master Plan developed | [5 empty] | 500000
| Monitoring of the implementation of Mining Social and Labour Plans (for water & sanitation) |  |  | Monitoring of the implementation of Mining Social and Labour Plans (for water & sanitation) | 4 Mining Social and Labour Plans monitored | Number of Mining Social and Labour Plans monitored | 4 Mining Social and Labour Plans monitored | [5 empty] | 0
| Facilitate Economic Development Forums (Mining, Tourism & Agric) |  |  | Facilitate Economic Development Forums (Mining, Tourism & Agric) | Economic Development Forums (Mining, Tourism & Agric) | Number of Economic Development Forums (Mining, Tourism & Agric) facilitated | 3 Economic Development Forums (Mining, Tourism & Agric) facilitated | [5 empty] | 100000
Enhance the Tourism attraction within the District by 2020 |  |  |  | Develop Business Plan for Tjate Heritage Site | Dilapidated Tjate Heritage Site | Number of Business Plans for Tjate Heritage Site developed | 1 Business Plans for Tjate Heritage Site developed | [5 empty] | 150000
|  |  |  | Tourism Signage for Tourism Establishments (Manche Masemola, King Nyabela and Tjate) by 2020 | 3 existing District Tourism Signage for Tourism Establishments (Manche Masemola, King Nyabela and Tjate) | Number of District Tourism Signage for Tourism Establishments (Manche Masemola, King Nyabela and Tjate) installed | 3 District Tourism Signage for Tourism Establishments (Manche Masemola, King Nyabela and Tjate) installed | [5 empty] | R 500 000
INTEGRATED DEVELOPMENT PLAN
To ensure integrated development planning by June 2020 |  |  |  | Develop 2020/2021 IDP Framework/Process Plan | 2019/2020 IDP Framework/Process Plan in place | Number of IDP Frameworks/Process Plans developed | 1 IDP Framework/Process Plan developed | [5 empty] | 0
|  |  |  | Review of legally compliant Integrated Development Planning(IDP) | 1 legally compliant Integrated Development Planning(IDP) reviewed | Number of legally compliant Integrated Development Planning(IDP) reviewed | 1 legally compliant Integrated Development Planning(IDP) reviewed | [5 empty] | 320000
|  |  |  | Facilitate the IDP Rep Forums | Facilitated 2 IDP Rep Forums | Number of IDP Rep Forums facilitated | 2 IDP Rep Forums facilitated | [5 empty] | 50000

## MMs OFF
GOOD GOVERNANCE AND PUBLIC PARTICIPATION
2019-2020 SERVICE DELIVERY BUDGET AND IMPLEMENTATION PLAN
MEASURABLE OBJECTIVE | PROJECT | BASELINE 2018/2019 | INDICATORS | ANNUAL TARGET 2019/2020 | Q2 | Q4 | PROGRESS: ACHIVED/NOT ACHIEVED | ACTUAL PROGRESS | CHALLENGES | REMEDIAL ACTION | POE | BUDGET 2019/2020
INTERNAL AUDIT
To ensure improved internal controls and clean governance in the municipality by June 2020 | Development of the Three(3) Years rolling Plan | 2 approved 3 years rolling plan. | Number of development of 3 years rolling plan | 2 (SDM &SDA) 3 years rolling plan developed | No activity | No activity | Not applicable | Not applicable | None | None | Approved 3 Year rolling Plan for SDM and SDA | 900000
| Conduct Regularity audits | 38 Regularity audits conducetd | Number of regularity audits conducted | 20 Regularity Audit conducted | 5 regularity audit conducted | 5 regularity audit conducted | Not achieved | 5 regularity audit conducted | Slow implementation of the audit projects due Covid-19 and lack of cooperation from the auditee. | Fast track the finanlisation of the Audit Projects.Escalate the matter to the accounting officer for lack of cooperation | Signed Regularity Audit Reports
| Conduct Ad hoc Audits | 10 Ad hoc reports conducted | Percentage of Management / investigation conducted | 100% Management requests/ investigations conducted as and when required | 100% Management requests/ investigations conducted as and when required | 100% Management requests/ investigations conducted as and when required | Achieved | 100% Management requests/ investigations conducted as and when required | None | None | Signed Management /Investigation reports
| Conduct ICT Audits | 4 ICT Audit conducted | Number of ICT Audit conducted | 4 ICT Audit conducted | 1 ICT Audit conducted | 1 ICT Audit conducted | No activity | Not applicable | None | None | Signed ICT Audit Reports
| Conduct Perfomance Audits | 8 (4 SDM &4 SDA)PMS Audit and 8(4 SDM & SDA) Audit of Perfomance of Information conducted | Number of Performance Audit conducted | 8 PMS Audit (4 SDM & 4 SDA) 8 (4 SDM &SDA) AOPI conducted | 2 PMS and 2 AOPI conducted | 2 PMS Conducted 2 AOPI Audit conducted | Not achieved | 2 PMS Conducted 2 AOPI Audit not conducted | Slow implementation of audit projects due to Covid-19 and Non submission of portfolio by the audittee | Fast track the finanlisation of the audits.Escalate the matter to the Acting Accounting Officer.Issue a scope limitation report.Issue a scope limitation report | Signed PMS and AOPI Audit Report
| Monitoring of implementation of auditor general activities | 100% monitoring of implementation of AG activities for 2018/2019 financial year | Percentage monitoring of implementation of AG activities for 2019/20 financial year | 100% monitoring of implementation of AG activities | 100% monitoring of implementation of AG activities | 100% monitoring of implementation of AG activities | Not achieved | 0% monitoring of implementation of AG activities | Weekly Meetings to be take place in the month of August 2020. | Audit Steering Committee meetings not held to monitor the implementation of the audit action plan | Audit Action plan,Agenda,Signed Minutes,proof of payments | R5 691 150.00
| Coordination of Audit Committee and Perfomance Audit Committee | 4 meetings of audit and performance committees coordinated | Number of meetings of audit and performance committees coordinated | 4 meetings of audit and performance committees coordinated | 1 meetings of audit and performance committees coordinated | 1 meetings of audit and performance committees coordinated | Not achieved | 1 meetings of audit and performance committees not coordinated | The Audit Committee were appointed from the 1st April 2020 and and due to Corona break the Induction was done in June . | The Audit Committee for the third quarter is scheduled for the 08th August 2020 and fourth quarter in the month of September 2020. | Signed Minutes/Agenda/Signed AC Reports | R550 000.00
RISK MANAGEMENT
To assess, identify, manage risks and uncertainty in order to safeguard assets, enhance performance and ensure sustainability of operations by June 2020. | Conduct and review Strategic Risk Assessment | Strategic Risk Register in place | Number of Strategic Risk Assessment conducted and Strategic Risk Registers reviewed | *1 Strategic Risk Assessment conducted * 4 Strategic Risk Registers reviewed | 1 x Strategic Risk Register reviewed | 1 x Strategic Risk Register reviewed | Not Achieved | 1 x Strategic Risk Assessment conducted 3 x Strategic Risk Registers reviewed | Third Quarter Reviews not completed due to non-availability of role players as the results of Covid 19 Pandamec | N/A | Signed Strategic Risk Register | R0,00
| Conduct Operational Risk Assessment | Operational Risk Registers in place | Number of Operational Risk Assessment Conducted and Operational Risk Registers reviewed | *1 Operational Risk Assessment Conducted *4 Operational Risk Registers reviewed | 1 x Operational Risk Register reviewed | 1 x Operational Risk Register reviewed | Not Achieved | 1 x Operational Risk Assessment conducted 3 x Operational Risk register reviewed | Third Quarter Reviews not completed due to non-availability of role players as the results of Covid 19 Pandamec | N/A | Signed Operational Risk Register | R0,00
| Conduct Infrastructure and Water Services Projects Risk Assessment | 8 Projects Risk assessment conducted | Number of IWS Projects risk assessments conducted | 10 IWS Projects risk assessments conducted | 3 Projects risk assessments conducted | 2 Projects risk assessments conducted | Not Achieved | None | Inadequate capacity | The function is to be moved to PMU. | Signed Projects risk assessments report | R0,00
| Conduct Processes Risk Assessments | 2 Process risk assessment conducted | Number of Processes risk assessments conducted | 7 x Processes risk assessments conducted | 2 x Processes risk assessments conducted | 1 x Processes risk assessments conducted | Not Achieved | Two ( 02- OEM -Customer Services and BTO) Process Risk Assessment conducted | Inadequate capacity | Assessment to be conducted in 2020/2021FY | Signed Processes Risk Register | R0,00
| Facilitate insurance coverage for municipal assets | Assets Insurance Policy contract facilitaed | Number of insurance coverage for municipal assets facilitated | All insurance coverage for municipal assets facilitated | All insurance coverage for municipal assets facilitated | All insurance coverage for municipal assets facilitated | Achieved | All insurance coverage for municipal assets facilitated | None | N/A | Signed Assets Insurance Policy contract and endorsements | R4 603 344.00
| Facilitate Assets Insurance Claims and payments | Insurance claims report facilitated | Percentage processing and facilitation of insurance claims and payments | 100% insurance claims processing and payments facilitated | 100% insurance claims processing and payments facilitated | 100% insurance claims processing and payments facilitated | Achieved | 100% insurance claims processing and payments facilitated | None | N/A | Signed Insurance Claims report and Claim register | 222183
| Manage Security operations and SLA | 8 Security operations and SLAs managed | Number of incidents occurred reported | All incidents occurred reported | All incidents occurred reported | All incidents occurred reported | Achieved | All incidents occurred reported | None | N/A | Signed Security Management report | R 36 000 000
| Conduct Security Operational sites Assessments | Operational Sites Assessment report conducted | Number of Security Operational sites assessments conducted | Forty (40) Security Operational sites assessments conducted | 10 x Security Operational sites assessments conducted | 10 x Security Operational sites assessments conducted | Achieved | 40 x Security Operational sites assessments conducted | None | N/A | Signed Security Operational sites assessment reports | R0,00
| Facilitate Anti-Fraud & Corruption hotline | 1 Fraud cases investigation | Number of fraud and corruption allegation cases reported for referral and investigations facilitated | All fraud and corruption allegation cases reported for referral and investigations facilitated | All fraud and corruption allegation cases reported for referral and investigations facilitated | All fraud and corruption allegation cases reported for referral and investigations facilitated | Achieved | All fraud and corruption allegation cases reported for referral and investigations facilitated | None | N/A | Signed Fraud and Corruption report Signed Disclosure Hotline report | R0,00
| Facilitate Risk Management Committee activities | Risk Management training report facilitated | Number of Risk Management Committee(RMC) meetings facilitated | 4 x Risk Management Committee(RMC) meetings facilitated | 1 x Risk Management Committee(RMC)meeting facilitated | 1 x Risk Management Committee(RMC) meeting facilitated | Not Achieved | 3 x Risk Management Committee(RMC)meeting facilitated | Third Quarter (3rd Q) meeting did not take place due to non-availability of role players as the results of Covid 19 Pandamec. | Reschedule the meeting for the 1st Q of 2020/2021FY | Signed Risk Management report | Fees paid from Line item - 33052270320EQMRCZZHO - C&PS: B&A AUDIT COMMITTEE
COMMUNICATIONS; ADVOCACY; SOCIAL FACILITATION; SPECIAL PROGRAMMES AND ARTS & CULTURE
o provide communications, stakeholders relations and strategic partnerships by June 2020 | Mayoral Outreaches and Sectoral Engagements | 12 Programmes facilitated | Number of community & sectoral engagements facilitated | 6 stakeholder & sectoral engagements facilitated |  | 2 stakeholder engagement/mayoral outreach facilitated | Not Achieved | No Activity | Lockdown | Cancelled | Signed Exit Report and Attendance Register | 1400000
| Executive Support to Mayoral Committee | 12 Mayoral Committee meetings supported | Number of Mayoral Committee meetings supported | 9 Mayoral Committee meetings supported |  | 3 Mayoral Committee meetings supported. | Not Achieved | No Activity | Lockdown | Cancelled | Signed Minutes and attendance registers | 0
| Media Relations and Marketing | 12 Media Relations & marketing done. | Number of media Relations | 9 Media Relations |  | 3 media relations facilitated | Not Achieved | No Activity | Lockdown | Cancelled | Copies of newsletters and puplications | 0
| Newsletter& Publications produced | 16 Programmes produced | Number of news letters and Publications produced | 4 newsletters and publications produced. |  | 1 special and 1 ertenal newsletter produced | Not Achieved | No Activity | Lockdown | Cancelled | copies of newsletters and puplications | 400000
| Website Management | 20 Website Updates undertaken | Number of Website Updates undertaken | 11 Websites Updates undertaken |  | 3 Websites Updates undertaken (Qarter 3 SDBIP report, Finance report, approved IDP and Budget, | Not Achieved | No Activity | Lockdown | Cancelled | Screen short reports | 85212
| Traditional Leadership Affairs | 2 SPLUMA meeting supported | Number of Traditional Leaders hip meetings coordinated | 3 Traditional Leadership meeting coordinated |  | 1 Traditional Leadership meeting coordinated | Not Achieved | No Activity | Lockdown | Cancelled | Signed minutes and Attendance Register | 30000
| Special Mayoral strategic Events | 5 strategic events Facilitated | Number of Strategic Events facilitated | 7 Strategic Events facilitated |  | 1x2 Strategic Events ( Bapedi Kings and Bakgaga Bakopa) facilitated | Not Achieved | No Activity | Lockdown | Cancelled | Attendance register and pictures | 400000
| Moral Regeneration Movement Committee | MRM committee established | Number of programmes for MRM committee facilitated | 2 Moral Regeneration Movement Committee facilitated |  | 1 Moral Regeneration Movement Committee facilitated | Not Achieved | No Activity | Lockdown | Cancelled | Signed Exit Report and Attendance Register | 33156
| Customer Care Services | 24 reports generated | Number of reports generated | 24 queries/ complains reports on customer care generated |  | 6 Reports generates (3 SDM, 3 Premier and Presidential) generated | Not Achieved | No Activity | Lockdown | Cancelled | Signed reports | 0
| Batho Pele | 6 Programmes conducted | Number of Batho Pele Programmes conducted | 5 Batho Pele Programmes conducted |  | 2 Bathopele Programme conducted | Not Achieved | No Activity | Lockdown | Cancelled | Signed Exit Report and Attendance Register | 60000
| SODA | 2018/2019 SODA held | Number of SODA coordinated | 1 SODA coordinated |  | No activity | No Target | No Activity | Lockdown | N/A | Signed exit report and attendance reister | 240000
| Aged care | 2 aged programmes facilitated | Number of Aged Care programmes facilitated | 1 Aged Care programme facilitated |  | No activity | No Target | No Activity | Lockdown | N/A | Signed exit reports and attendance registers | 90000
| Children’s Care | 2 children’s activities facilitated | Number of children's activities facilitated | 1 children's activities facilitated |  | No activity | No Target | No Activity | Lockdown | N/A | Signed exit reports and attendance registers | R20 520
| Woman Development Initiative | 4 Women Programme initiatives facilitated | Number of woman development initiatives facilitated | 1 woman development initiatives facilitated |  | No activity | No Target | No Activity | Lockdown | NA | Signed exit reports and attendance registers | 20000
| People with disability | 3 awareness campaigns facilitated | Number of awareness campaigns for people with disability facilitated | 2 awareness campaigns for people with disability facilitated |  | No activity | No Target | No Activity | Lockdown | N/A | Signed exit reports and attendance registers | 20000
| Cultural Heritage Celebrations and Language Promotions | 3 Programmes facilitated | Number of promotions of art and culture programmes facilitated | 1 promotions of art and culture programmes facilitated |  | No activity | No Target | No Activity | Lockdown | N/A | Signed exit reports and attendance registers | 220000
| Health calendar days activities | 3 health calendar days activities conducted | Number of health calendar days activities coordinated | 3 Health calendar days activities coordinated |  | 1 Canlde light coordinated | Not Achieved | No Activity | Lockdown | Cancelled | Signed exit reports and attendance registers | 20000
| Youth Opportunities Expo | 3 Programmes facilitated | Number of Youth development programmes facilitated | 2 Youth development programmes facilitated |  | 1 launching of Youth Council | Not Achieved | No Activity | Lockdown | Cancelled | Signed exit reports and attendance registers | 100000
| Mayoral Sports activities | 3 Programmes facilitated | Number of Mayoral Sport activities facilitated | 1 Mayoral Sport activities facilitated |  | 1 Executive Mayor's Cup Facilitated | Not Achieved | No Activity | Lockdown | Cancelled | Signed exit reports and attendance registers | 180000
PUBLIC PARTICIPATION, MPAC SUPPORT SECRETARIAT AND SUPPORT
To provide secretarial support to 10 Council structures to ensure accountability by June 2020 | FORA | 08 FORA facilitated | Number of fora facilitated | 16 Fora facilitated |  | 1 Speakers' Forum, 1 Chief Whips' Forum, 1 Public participation Forum, 1 MPAC forum 1 Secretariat Forum facilatated. | Not achieved | *1 Speakers' Forum facilitated on 11/06/2020, *1 Chief Whips' Forum not facilitated, *1 Public participation Forum facilitated on 04/06/2020, *1 MPAC forum not facilitated, *1 Secretariat Forum not facilatated. | Covid 19 Regulations prohibiting public gatherings | The meetings will be facilitated during the 1st quarter of 2020/2021 F/Y | Attendance Register and Signed Notices. | 15000
| Public participation sessions. | 16 public participation sessions facilitated | Number of public consultation meetings facilitated | 15 public consultation meetings facilitated |  | 7 public consultation meetings on the IDP/Budget, 1 District Ward Committee Conference facilitated. | Not achieved | *7 public consultation meetings on the IDP/Budget and 1 District Ward Committee Conference not facilitated. | Covid 19 Regulations prohibiting public gatherings | 7 public consultation meetings on the IDP/Budget and 1 District Ward Committee Conference cancelled | Attendance Register and Signed Notices. | 350000
| SODA & Budget day. | 1 SODA 1 Budget day facilitated. | Number of SODA and Budget days facilitated | 1 SODA and 1 Budget day facilitated |  | 1 Extra Special Council Meeting (Budget Speech) Facilitated. | Not achieved | 1 Extra Special Council Meeting (Budget Speech) not facilitated. | Covid 19 Regulations prohibiting public gatherings | 1 Extra Special Council Meeting (Budget Speech) cancelled. | Attendance Register and Signed Notices. | 200000
| Council and portfolio committee meetings. | 22 Council and portfolio committee meetings facilitated. | Number of schedule of council activities facilitated | 4 Ordinary Council Meetings and 20 Portfolio Committee Meetings facilitated |  | 1 Ordinary Council Meetings and 5 Portfolio Committee Meetings facilitated | Achieved | *2 Special Council Meetings facilitated on 28/05/2020 & 12/06/2020. *5 Portfolio Committee Meetings facilitated | None | None | Attendance Register and Signed Notices. | 425 000. 00
| Study group. | New | Number of study groups facilitated | 4 study groups facilitated |  | 1 Study Group Facilitated. | Not achieved | 1 Study Group not facilitated. | Covid 19 Regulations prohibiting public gatherings | 1 Study Group cancelled | Attendance Register and Signed Notices.
| Council whippery meetings | 4 council whippery meetings facilitated | Number of council whippery meetings facilitated | 4 council whippery meetings facilitated |  | 1 Council Whippery meeting Facilitated. | Not achieved | 1 Council Whippery meeting not facilitated. | Covid 19 Regulations prohibiting public gatherings | 1 Council Whippery meeting cancelled | Attendance Register and Signed Notices.
| Capacity building workshops | 3 capacity building workshops held | Number of capacity building workshops facilitated | 2 workshops facilitated |  | 1 capacity building Workshop on Income tax facilitated. | Not achieved | 1 capacity building workshop on Income Tax not facilitated | Covid 19 Regulations prohibiting public gatherings | 1 capacity building workshop on Income Tax cancelled | Signed Exit Report. | 0
| Training and development programmes for Cllrs. | 2 X training and development programmes facilitated | Number of Cllrs identified for training programmes facilitated | 2 Cllrs identified for training programmes facilitated |  | No Activity | No activity | No activity | No activity | No activity | Signed Exit Report. | 90000
| Oversight visits | 4 oversight visits facilitated | Number of oversight visits facilitated | 4 oversight visits facilitated |  | 1 Oversight visit facilitated. | Not achieved | Oversight visit not facilitated | Covid 19 | Oversight visit cancelled | Signed Oversights Report. | 0
| Council Resolution registers | 4 Resolution registers developed and implemented | Number of Council Resolution registers compiled and coordinated | 4 Council Resolution registers compiled and coordinated |  | 1 council resolution register compiled and cordinated. | Achieved | 1 council resolution register compiled and cordinated. | None | None | Council Resolution Register. | 0
| Public participation policy. | 1 public participation policy reviewed | Number of review of public participation policy facilitated | 1 review of public participation policy facilitated |  | submit draft review policy to council for approval. | Not achieved | Draft review policy not submitted to Council for approval | Council meeting postponed due to covid 19 case | Submit draft review policy to the next Council meeting Q1 2020/2021 F/Y | Council Resolution Certificate. | 0
| MPAC Working sessions for Cllrs. | 8 MPAC working sessions facilitated | Number of MPAC working sessions for Cllrs held | 8 MPAC working sessions for Cllrs held |  | 2 MPAC working sessions facilitated. | Not achieved | 2 MPAC working sessions not facilitated | Covid 19 Regulations prohibiting public gatherings | 2 MPAC working sessions will be facilitated when items are received from Council | Attendance Register and Signed Notices. | 180000
| MPAC Public hearings | 2 MPAC public hearing facilitated | Number of MPAC public hearing facilitated | 2 MPAC public hearing facilitated |  | 1 MPAC Public Hearing Facilitated. | Not achieved | MPAC public hearing not facilitated | Covid 19 Regulations prohibiting public gatherings | MPAC public hearing cancelled | Attendance Register and Signed Notices.