## SDA
SEKHUKHUNE DEVELOPMENT AGENCY
DRAFT 2019-2020 SERVICE DELIVERY BUDGET AND IMPLEMENTATION PLAN
SEKHUKHUNE DEVELOPMENT AGENCY
2019-2020 SERVICE DELIVERY BUDGET AND IMPLEMENTATION PLAN
MEASURABLE OBJECTIVE | PROJECT | BASELINE 2018/2019 | INDICATORS | ANNUAL TARGET 2019/2020 | Q4 | PROGRESS: ACHIVED/NOT ACHIEVED | ACTUAL PROGRESS | CHALLENGES | REMEDIAL ACTION | EVIDENCE | BUDGET 2019/2020
To act as an engine for economic growth by diversifying and expanding local economic base by June 2020 | Mining Input Supplier Park MISP) | MISP report | Number of sessions conducted | 3 sessions conducted with stake holders (LEDET, Glencor and LEDA) | 1 sessions conducted with stakeholder (GLENCOR) | Not Achieved | Could not meet with stakeholders under lockdown | Lockdown due to Covid 19 pandemic | Meeting to be schedulled after lockdown | Signed Minutes* attedance register *Occupancy report | 0
| Wild-Life Empowerment programmes | Signed MOU | Number of Wild Life partnerships made with Ekim | 1 Wild Life partnership with Ekim | Funding application | Not Achieved | Could not meet with stakeholders under lockdown | Lockdown due to Covid 19 pandemic | Meeting to be schedulled after lockdown | Copy of Action Plan* Business plan | 0
| Tourism Route | Report | Number of district tourisn route marketed | 3 district tourism route marketed | Paricipating in global tourism indaba | Not Achieved | Tourism Indaba Suspended | Lockdown due to Covid 19 pandemic | Tourism Indaba to be held after Lockdown | *Report *Tourism guide map* Brochure | 0
| Agri-Park | Business Plan | Number of partership with Famers production support unit (FPSU) | 1 FPSU Partnership | Proposal developed for 1 FPSU | Not Achieved | Could not meet with stakeholders under lockdown | Lockdown due to Covid 19 pandemic | Meeting to be schedulled after lockdown | Attendance register and minutes* Proposal | 0
| Mining Beneficiation | Mining Beneficiation Study | Number of business plan developed | 1 business plan developed | 1 Business plan Developed | Not Achieved | no business plan developed | Lockdown due to Covid 19 pandemic | Businessplan to be developed after lock down | Attendance register* Project Report *Business plan | 0
| Digital Economy | MOU with Limpopo Connexion (LCX) | 1 Partnership established | x1 Partnership established by MOU | Application for funding | Not Achieved | Applicatio for funding not developed | Lockdown due to Covid 19 pandemic | To be developed ater lockdown | copy of the draft MOU* Proposal *Funding application | 0
| Cotton Industry Revitilisation Program | Outlook Report on cotton textile Industry in SA | 1 Partnership established | x1 Partnership established by MOU | Business plan for cotton production | Not Achieved | no business plan developed | Lockdown due to Covid 19 pandemic | Businessplan to be developed after lock down | Draft MOU* Business plan | 100000
| Youth Entrepreneurship Development and Support | MOU with Youth Entrepreneuship project (YEP) | Number of proposals developed | x 3 proposals developed | 1x proposal on Agriculture | Not Achieved | proposal on Agriculture not in place | Could not meet with service provider during lockdown | Re-schedulle a meeting with SP after lockdown | Signed MOU *Proposals | 50000
| Limpopo 6000 ( Manufacturing of electrical vehicles) | Draft MOU with EISOWAVE (PTY) LTD | Number of strategic partner | x1 Partnership established by signed MOU | Business Plan | Achieved | *Signed MOU in place * Proposal developed | None | None | Signed MOU * Business plan | 0
Strategic objective 2: To secure a stable and sustainable financial base for the future of the agency & Support Business Plan funding by June 2020
To secure a stable and sustainable financial base for the future of the agency and support business plan funding by June 2020 | Financial Mobilisation | Contracts with 3 appointed companies | Number of proposals | 3 Proposals Developed | 2 Proposal Developed | Not Achieved | Proposal not in place | Could not meet with service provider during lockdown | Re-schedulle a meeting with SP after lockdown | Proposal | 0
| Amaloloo - MOU implimentation | Signed MOU | Number of VIP sanitation Top structure supplied | Supply of 670 Units of VIP top structure supplied | 1 report generated on supply of VIP sanitation top structure and proof of payment provided | Not Achieved | no report generated on supply of VIP sanitation top structure | Supply of VIP sanitation is put on hold due to negotiations with Service provider | Re-schedulled the meeting between the service provider, SDA management and SDM MM after lockdown | Proof of payment and report | 0
| Small Business Support | Draft MOU | Number of business supported | 10 SMME’s supported | Application for funding and support to SMME projects | Not Achieved | Application for funding not developed | Lockdown due to Covid 19 pandemic | to be developed afer lockdown | Signed MOU. List of identified SMME s and report | R 100 00
| Small Business Development Fund | Draft Funding Policy | Number of SMME's & Cooperatives supported financially | 4 SMME's/Cooperatives supported financially | Disbursements of funding | Not Achieved | Advert for proposals delayed | Advert for proposal delayed due to lockdown | Advert after lockdown | *Funding Policy * Funding Approval Letters | 320000
| RAL-MOU (Steel Bridge) | Signed MOU | Number of engagements held with RAL & other partners | 2 proposals developed | Funding commitments by partners | Achieved | letters of commitment in place | None | None | 2 signed proposal reports * Commitment letters | 0
To develop/ ficilitate businesses that create sustainable jobs by June 2020 | BEE Keeping | 1 Informal project | Number of cooperatives supported | 1 cooperative supported | sourcing of materials for the cooperative | Not Achieved | Training for the cooperative could not heppen due to lockdown | Lockdown due to Covid 19 pandemic | re-schedulled training after lockdown | Registration certificate, attendance registers | 0
| Skills Development | Agri Seta Accredidation Application lodged | Number of accreditation certificates | 1 Agri-SETA accreditation certificate obtained | Application for funding | Achieved | Application for funding in place | None | None | Signed MOU and Application for Funding | 50000
| LED lights manufacturing | Benchmarking exercise | Number of partnership created | 1 LED Lights partnership created | Application for funding | Not Achieved | Application for funding not in place | Lockdown due to Covid 19 pandemic | Re-schedulled meeting after lockdown | Draft MOU* Concept Document*Application for Funding | 0
| Aquaculture farming | Feasibility study reports | Number of Aquaculture project implemented | 1 Aquaculture project implemented | Application for funding | Not Achieved | Application for funding not in place | Could not meet with service provider during lockdown | Re-schedulled meeting after lockdown | Minutes and attendance registers Businedd Plan*Application for Funding | R 100 00
| Solar Energy | Signed SLA | Number of proposals developed | 1 proposal on solar energy | Implemetation plan | Not Achieved | Implementation plan not in place | Could not meet with service provider during lockdown | Re-schedulled meeting after lockdown | proposal* Business plan* Implementation plan | 0
Strategic Objective 4: To enhance SDA Internal Capacity by June 2022
To enhance SDA Internal Capacity by June 2020 | Marketing and Promotional materials | Investment booklet | Number of marketing material developed | 4 SDA Marketing Material developed (Banners, brochures, folders, business cards) | Distribution of marketing material | Achieved | Communication and Marketing Strategy developed | None | None | SDA Marketing brochure | 180000
| SDA website development & maintenance | Previous website | Number of website developed | *1 functional website developed | 1 website update | Not Achieved | Service provider briefed and content sent to service provider to develop a dummy webside | Lockdown due to Covid 19 pandemic | website to be revamped after lockdown | Appointment letter * Functional website | 130000
| Stakeholder management | 2018/19 AGM Report | Number of public meetings & engagement held | 1 AGM and stakeholder engagement | 1 AGM held | Not Achieved | 2019-20 AGM not held | Due to lapse of term of board | Appoint new board | AGM Minutes/attedance registers *SDA Presentation