## SDA
SEKHUKHUNE DEVELOPMENT AGENCY
DRAFT 2019-2020 SERVICE DELIVERY BUDGET AND IMPLEMENTATION PLAN
SEKHUKHUNE DEVELOPMENT AGENCY
2019-2020 SERVICE DELIVERY BUDGET AND IMPLEMENTATION PLAN
MEASURABLE OBJECTIVE | PROJECT | BASELINE 2018/2019 | INDICATORS | ANNUAL TARGET 2019/2020 | Q1 | PROGRESS (ACHIEVED/ NOT ACHIEVED) | ACTUAL PROGRESS | CHALLENGE | REMEDIAL ACTION | EVIDENCE | BUDGET 2019/2020
To act as an engine for economic growth by diversifying and expanding local economic base by June 2020 | Mining Input Supplier Park MISP) | MISP report | Number of sessions conducted | 2 sessions conducted with stake holders (LEDET, Glencor and LEDA) | 1 sessions conducted with stake holders (LEDET, Glencor and LEDA) | Achieved | Meeting held with GLENCO on the 5th August 2019 on the partnerhip proposal model. | None | None | Signed Minutes and attedance register | 0
| Wild-Life Empowerment programmes | Signed MOU | Number of Wild Life partnerships made with Ekim & Tompi-Seleka | 1 Wild Life partnership with Ekim & Tompi-Seleka | MOU implementation Action Plan | Achieved | MOU Implementaton Plan in place | None | None | Copy of Action Plan | 0
| Tourism Route | Report | Number of facilities promoted | 5 facilities promoted | Packaging of tourism Guide Map | Achieved | Tourism Guide and booklet in place | None | None | *Report *Tourism guide map | 0
| Fresh Produce Market | Signed MOU | Number of engagements held | 2 engagements with strategic parter and funders | 1 Engagaments with strategic partner | Achieved | Meeting held with the Ambasador of United Emarates on the 3rd July 2019 | None | None | Signed progress report | 0
| Agri-Park | Business Plan | Number of farmers/cooperatives assisted | 1 cooperatives assisted | 1 enagagement with co-operatives | Not Achieved | Ongoing discussions with DRDLR about the establishment of FPSU | Merging of DRDLR and Department of Agriculture | Continous engagement with DALRRD | Attendance register and minutes | 0
| Mining Research/Study | Signed MOU with MINTEK | Number of reports generated | 1 report on Mining study | Engagement with MINTEK | Not Achieved | Communications done with Mintek to e a meeting with SDA board and Mintek Board to clear out conflicting issues | Challenge in securing a meeting with MINTEK | Emails follows up exchnaged with MINTEK on the need to have a formal meeting. | Signed report on Mining study | 0
Strategic objective 2: To secure a stable and sustainable financial base for the future of the agency & Support Business Plan funding by June 2020
To secure a stable and sustainable financial base for the future of the agency and support business plan funding by June 2020 | Contract management | 3 appointed companies | Number of SLA signed | 3 SLA’s signed | Evaluation of existing Business Plans | Not Achieved | Letters sent to 3 SP'S to request progress on mobilisation of funding for SDA Pojects | only 1 Service provider responded | Followup to be done with other service providers | Progress Report from SP | 0
| Amaloloo - MOU implimentation | Signed MOU | Number of engagements held with SDM & Amaloloo to supply VIP sanitation Top structure and finalise payment agreement | 2 engagements held with SDM & Amaloloo to supply VIP sanitation Top structure and finalise payment agreement | 1 report generated on supply of VIP sanitation top structure and proof of payment provided | Achieved | 1 report generated on supply of VIP sanitation top structure and proof of payment in place. | None | None | Signed payment agreement and close out report | 0
| Small Business Support | Draft MOU | Number of business supported | 10 SMME’s supported | Draft MOU*Signed MOU | Achieved | MOU SEDA in place | None | None | Signed MOU. List of identified SMM s and report | R 100 00
| RAL-MOU | Signed MOU | Number of engagements held with RAL & other partners | 2 roads partneship proposals | 1 proposal submitted to funding agencies | Achieved | Proposal submitted to Mining houses for funding commitment to steelbridge. | None | None | 2 signed proposal reports | 0
To develop/ ficilitate businesses that create sustainable jobs by June 2020 | BEE Keeping | 1 Informal project | Number of cooperatives supported | 1 cooperative supported | Finalisation of registration for the cooperative | Achieved | Registration of Malope BEE Keeping cooperative finalised | None | None | Registration certificate, attendance registers and minutes | 0
| Skills Development | Application lodged | Number of accreditation certificates | 1 accreditation certificate obtained | Identify strartegic partner and sign MOU | Achieved | 2x MOU signed with strategic partners on skills development . | None | None | Signed MOUand Funding proposals | 50000
| LED lights manufacturing | Benchmarking exercise | Number of partnership created | 1 LED Lights partnership created | Concept proposal | Achieved | LED Light manufacturing Concept proposal in place | None | None | signed MOU | 0
| Aquaculture farming (Da-Hoop& Flag Boshielo Dams | 2 Feasibility study reports | Number of Aquaculture project implemented | 1 Aquaculture project implemented | 1 engagement with stakeholders (SDM, DWS and dehoop/Flag Boshielo community | Achieved | Meeting held with SDM and DWS on the 01 August 2019. | None | None | Minutes and attendance registers | R 100 00
| Solar Energy | Appointment letter for investigation | Number of studies conducted | 1 Investigation/research report on solar energy | Proposal for solar project | Achieved | Proposa for solar energy in place amd submitted to SDM for concurance. | None | None | Concept proposal and signed report | 0
Strategic Objective 4: To enhance SDA Internal Capacity by June 2022
To enhance SDA Internal Capacity by June 2020 | Marketing brochure & Promotional materials | Investment booklet | Number of brochures developed | 1 SDA Marketing brochure | Collect information for the brochure | Achieved | Information for marketing brochure collected | None | None | SDA Marketing brochure | 180000
| SDA website development & maintenance | Previous website | Number of website developed and number of website updates | *1 functional website developed *3 website updates | Appointment service provider | Not Achieved | Re-submission made to SDM Bid specificiation committee | Delay in SCM processes due to clashes of dates and other commitments | Bid to be advertised during october 2019. | Appointment letter * photos of Functional website | 130000
| Stakeholder management | 2017/18 AGM Report | Number of public meetings & engagement held | 1 AGM and stakeholder engagement | Stakeholder enegament | Achieved | 2 days tourism capacity building workshop attended. X 1 benchmarking vist to KZN | None | None | AGM Minutes/attedance registers
ACTING CEO: KGOPELO PHASHA |  |  |  |  | DATE