## Sheet1
2018/2020 SERVICE DELIVERY BUDGET AND IMPLEMENTATION PLAN: BASIC SERVICE DELIVERY
MEASURABLE OBJECTIVE | INPUT | OUTPUT | OUTCOME | PROJECT | BASELINE 2019/2020 | INDICATORS | ANNUAL TARGET 2019/2020 | Q1 | Q2 TARGET | Q3 | Q4 | PROGRESS (ACHIEVED/ NOT ACHIEVED) | ACTUAL PROGRESS | CHALLENGE | REMEDIAL ACTION | Portfolio of Evidence | BUDGET 2019-2020
RBIG
To construct pipeline from Burgersfort to Dresden pump station by June 2020 | Financial and Human Resource | Bulk supply line | Improved water supply | Construction of Mooihoek Bulk Water Supply Phase 4E | 5Km of bulk water supply pipeline phase 4D in Mooihoek completed | Number of Kilometers of bulk pipeline constructed , booster pump station constructed ,and reservoirs constructed | 3 Kilometers of bulk pipeline constructed,1 booster pump station constructed ,1concrete reservoir constructed | 1.5 Kilometers of bulk pipeline constructed,0* booster pump station constructed ,0*concrete reservoir constructed | 1,5 Kilometers of bulk pipeline constructed, ,0* booster pump station constructed ,0*concrete reservoir constructed | No activity | No activity | Not achieved | 0 Kilometers of bulk pipeline constructed,0* booster pump station constructed ,0*concrete reservoir constructed | Community protests prevents the contractor from casting concrete on reservoir roof.Eskom delay installations of transformer | Social facilitator assisting to resolve the matter. | Progress Report | 23250261
To construct bulk pipeline from Praktiseer to Alverton by June 2020 | Financial and Human Resource | Bulk supply line | Improved water supply | Mooihoek bulk water supply phase 4BB | 13Km of bulk water supply pipeline phase 2 in Mooihoek completed | Number of Kilometers bulk water pipeline constructed | 4 Kilometers of bulk water supply pipeline constructed | 0,5 Kilometers of bulk water supply pipeline constructed | 1 Kilometers of bulk water supply pipeline constructed | 1,5 Kilometers of bulk water supply pipeline constructed | 1 Kilometers of bulk water supply pipeline constructed | Not achieved | 0 Kilometers of bulk water supply pipeline constructed | Limited funding on the RBIG programme | Project to be implemented in the next RBIG allocation | Progress Report | 24116668.5
To construct bulk pipeline from Praktiseer to Alverton by June 2020 | Financial and Human Resource | Bulk supply line | Improved water supply | Mooihoek bulk water supply phase 4F2 | 1 X 5 Ml concrete reservoir completed Phase 4A | Percentage concrete reservoir constructed | 70%, 1 X 5 Ml concrete reservoir constructed | 15%, 1 X 5 Ml concrete reservoir constructed | 15%, 1 X 5 Ml concrete reservoir constructed | 20%, 1 X 5 Ml concrete reservoir constructed | 20%, 1 X 5 Ml concrete reservoir constructed | Not achieved | 0 %, 1 X 5 Ml concrete reservoir constructed | Limited funding on the RBIG programme | Project to be implemented in the next RBIG allocation | Progress Report | 28633070.5
To construct bulk pipeline from Praktiseer to Motodi by June 2020 | Financial and Human Resource | Bulk supply line | Improved water supply | Mooihoek bulk water supply phase 4F1 | 13 Kilometre of Mooihoek bulk water supply completed | Number of Kilometers of bulk water pipeline constructed | 4 Kilometers of bulk water pipeline constructed | 0.5km pipeline bulk water constructed | 1km pipeline bulk water constructed | 1.5km pipeline bulk water constructed | 1 km pipeline bulk water constructed | Not achieved | Site establishment and 0 km pipeline constructed | Limited funding on the RBIG programme | Project to be implemented in the next RBIG allocation | Progress Report | 14000000
To construct bulk water pipeline from T-off of Makgeru to the new 10ML reservoir at Schoonoord by June 2020 | Financial and Human Resource | Bulk supply line | Improved water supply | Nebo BWS (RL19) Makgeru to Schoonoord | 18.2 Km of Schoonoord bulk water supply pipeline in Makgeru | Number of Kilometers of bulk water pipeline constructed | 5 Kilometers of bulk water supply pipeline constructed | 0,5 Kilometers of bulk water supply pipeline constructed | No activity | 2 Kilometers of bulk water supply pipeline constructed | 2,5 Kilometers of bulk water supply pipeline constructed | Not achieved | Site establishment and 0 km pipeline constructed | Limited funding on the RBIG programme | Project to be implemented in the next RBIG allocation | Progress Report | 45000000
To test and commissioned bulk water pipeline and main pump stations by June 2020 | Financial and Human Resource | Bulk supply line | Improved water supply | Jane Furse to Lobethal bulk water supply pipeline | 18Km of bulk water supply pipeline Phase 2 from Jane to Lobethal completed | Number of Kilometers of bulk water supply pipeline assessed | 18 Kilometers of bulk water supply pipeline assessed | 2 Kilometers of bulk water supply pipeline assessed | 4 Kilometers of bulk water supply pipeline assessed | 6 Kilometers of bulk water supply pipeline assessed | 6 Kilometers of bulk water supply pipeline assessed | Not Achieved | Status quo report complete | Financial model outstanding | Finalise the report before end of February 2020 | Progress Report | 5000000
To construct Bulk water Pipeline and test main pump stations by June 2020 | Financial and Human Resource | Bulk supply line | Improved water supply | Moutse BWS Construction of Pipeline Project 7-12 | 30 Kilometre of bulk water supply pipeline constructed | Number of Kilometers of bulk water supply pipeline testing | 20 Kilometre of bulk water supply pipeline testing | 5 Kilometre of bulk water supply pipeline testing | 5 Kilometre of bulk water supply pipeline testing | 5 Kilometre of bulk water supply pipeline testing | 5 Kilometre of bulk water supply pipeline testing | Not achieved | 0km of bulk water supply pipeline testing | Contractor was stopped by community stakeholders (Business forum) | Engagement with communities & business forum to ensure that project continue | Progress Report | 10515156.78
To install mechanical and Electrical (M & E) for the extensions to the Groblersdal Water Treatment Works by June 2020 | Financial and Human Resource | Bulk supply line | Improved water supply | Moutse BWS Extension of Groblersdal WTW Project 1 | 1 WTW in Groblersdal extended | Number of extended WTW refurbished | One extended WTW refurbished | No activity | No activity | No activity | One extended WTW refurbished | N/A | None | None | None | Progress Report | 3608238
To construct Bulk water Pipeline and test main pump stations by June 2020 | Financial and Human Resource | Bulk supply line | Improved water supply | Moutse BWS Installation of Mechanical and Electrical Project 13&14 | 1 WTW in Groblersdal extended in Project 1 and 1 pump station constructed in Project 6 | Number of mechanical and Electrical (M & E) components installed for the extensions to the Groblersdal Water Treatment Works and pump station | Two mechanical and Electrical (M & E) components installed for the extensions to the Groblersdal Water Treatment Works and pump station | No activity | No activity | One mechanical and Electrical (M & E) components installed for the extensions to the Groblersdal Water Treatment Works and pump station | One mechanical and Electrical (M & E) components installed for the extensions to the Groblersdal Water Treatment Works and pump station | N/A | None | None | None | Progress Report | 39135545.22
To construct Bulk water Pipeline and test main pump stations by June 2020 | Financial and Human Resource | Bulk supply line | Improved water supply | Moutse BWS Construction bulk water Pipeline Project 2 – 4 | 19 Kilometres of bulk water supply pipeline and constructed | Number of km of bulk water supply pipeline assessed and refurbished | 14 Kilometers of bulk water supply pipeline assessed and refurbished | No activity | No activity | 10 Kilometers of bulk water supply pipeline assessed and refurbished | 4 Kilometers of bulk water supply pipeline assessed and refurbished | N/A | None | None | None | Progress Report | 12741060
To construct Bulk water Pipeline and test main pump stations by June 2020 | Financial and Human Resource | Bulk supply line | Improved water supply | Moutse BWS Construction Pipeline Project no 5 | 5 Kilometres of bulk water supply pipeline and constructed | Number of km of bulk water supply pipeline assessed and refurbished | 5 Kilometers of bulk water supply pipeline assessed and refurbished | No activity | No activity | 2,5 Kilometers of bulk water supply pipeline assessed and refurbished | 2,5 Kilometers of bulk water supply pipeline assessed and refurbished | N/A | None | None | None | Progress Report | 9000000
WATER QUALITY
To generate Water Quality Reports by June 2020 | WSDP and Water Master Plan | Regulatory Compliance | Improved service delivery | Generation of Water Quality Reports | 12 reports generated | Number of Water Quality Reports generated | 12 Water Quality Reports generated | 3 Water Quality Reports generated | 3 Water Quality Reports generated | 3 Water Quality Reports generated | 3 Water Quality Reports generated | Achieved | 3 Water Quality Reports generated | None | None | Progress Report | 6150000
To conduct Full SANS 241 Analysis by June 2020 | WSDP and Water Master Plan | Regulatory Compliance | Improved service delivery | Full SANS 241 Water Quality Analysis | 4 Full SANS 241 analysis report conducted through accredited laboratory | Number of Full SANS 241 Analysis conducted | 4 Full SANS 241 analysis conducted through accredited laboratory | 1 Full SANS 241 analysis conducted through accredited laboratory | 1 Full SANS 241 analysis conducted through accredited laboratory | 1 Full SANS 241 analysis conducted through accredited laboratory | 1 Full SANS 241 analysis conducted through accredited laboratory | Achieved | 1 Full SANS 241 analysis conducted through accredited laboratory | None | None | Progress Report
To purchase Laboratories chemical by June 2020 | WSDP and Water Master Plan | Regulatory Compliance | Improved service delivery | Purchase of LAB Chemicals | 90% of LAB chemical purchased | Number of % of LAB chemical purchased | 100% of LAB chemical purchased | 25% of LAB chemical purchased | 25% of LAB chemical purchased | 25% of LAB chemical purchased | 25% of LAB chemical purchased | Achieved | 25% of LAB chemical purchased | None | None | Progress Report
To participate in Blue and Green Drops Certification Programme by June 2020 | WSDP and Water Master Plan | Regulatory Compliance | Improved service delivery | Plants participation in Blue and Green Drops Certification Programme | 15 Water Treatment Works (WTW) participated in Blue Drop Certification programme and 15 Waste Water Treatment Works (WWTW) participated in Green Drop Certificate | Number of Plants participating in Blue and Greed Drops Certification Programme | 15 WTW participating in Blue Drop and 15 WWTW Participating in Green Drop Certification Programme | 5 WTW participating in Blue Drop and 4 WWTW Participating in Green Drop Certification Programme | 5 WTW participating in Blue Drop and 4 WWTW Participating in Green Drop Certification Programme | 2 WTW participating in Blue Drop and 4 WWTW Participating in Green Drop Certification Programme | 3 WTW participating in Blue Drop and 4 WWTW Participating in Green Drop Certification Programme | Achieved | 5 WTW participating in Blue Drop and 4 WWTW Participating in Green Drop Certification Programme | None | None | Progress Report
O & M EXPENDITURE
To resolve registered sanitation incidents within 14 days. | Financial and Human Resource | Reduced sewer spillage and environmental pollution | Improved green drop status | Sanitation incidents | 700 registered sanitation incidents resolved within 14 days | Number of registered sanitation incidents resolved within 14 days | 800 registered sanitation incidents resolved within 14 days | 200 registered sanitation incidents resolved within 14 days | 200 registered sanitation incidents resolved within 14 days | 200 registered sanitation incidents resolved within 14 days | 200 registered sanitation incidents resolved within 14 days | Achieved | 250 registered sanitation incidents resolved within 14 days | None | None | Progress Report | 29987845
To resolve registered water incidents within 14 days. | Financial and Human Resource | Reduced non-revenue water losses | Improved no drop status. | Water incidents | 5000 registered water incidents resolved within 14 days | Number registered water incidents resolved within 14 days | 5500 registered water incidents resolved within 14 days | 1000 registered water incidents resolved within 14 days | 1500 registered water incidents resolved within 14 days | 1500 registered water incidents resolved within 14 days | 1500 registered water incidents resolved within 14 days | Not Achieved | 1352registered water incidents resolved within 14 days | Shortage of material for repair and maintanance | Prioritise the required material to be purchased | Progress Report
To render tankering services by June 2020 | Financial and Human Resource | Consistent supply of water | Improved water supply | Delivery of portable water through tankering | 9.6 Ml of Potable Water delivered in Jane Furse Hospital and Buffelshoek | Number of Ml of potable Water delivered in Jane Furse Hospital and Buffelshoek | 9.6 Ml of Potable Water delivered in Jane Furse Hospital and Buffelshoek | 2,4 Ml of Potable Water delivered in Jane Furse Hospital and Buffelshoek | 2,4 Ml of Potable Water delivered in Jane Furse Hospital and Buffelshoek | 2,4 Ml of Potable Water delivered in Jane Furse Hospital and Buffelshoek | 2,4 Ml of Potable Water delivered in Jane Furse Hospital and Buffelshoek | Achieved | 33.46Ml of Potable Water delivered in Jane Furse Hospital and Buffelshoek | None | None | Progress Report | 15950108.3
To provide diesel consistently to diesel driven machines by June 2020 | Financial and Human Resource | Consistant water supply. | Reliable water supply. | Supply of diesel | 40 000ℓ of diesel supplied annually. | Number of Litres of diesel supplied annually | 34 000ℓ of diesel supplied annually. | 10 000ℓ of diesel supplied annually. | 8 000ℓ of diesel supplied Quarterly. | 8 000ℓ of diesel supplied Quarterly. | 8 000ℓ of diesel supplied Quarterly. | Achieved | 11910.5ℓ of diesel supplied | None | None | Progress Report | 1787808
To provide petrol consistently to petrol driven machines by June 2020 | Financial and Human Resource | Consistant water supply. | Reliable water supply. | Supply of petrol | 400ℓ of petrol supplied annually. | Number of Litres petrol supplied annually. | 400ℓ of petrol supplied annually. | 100ℓ of petrol supplied annually. | 100ℓ of petrol supplied Quarterly. | 100ℓ of petrol supplied Quarterly. | 100ℓ of petrol supplied Quarterly. | Achieved | 751ℓ of petrol supplied | None | None | Progress Report
To provide oil consistently to diesel and petrol driven machines by June 2020 | Financial and Human Resource | Consistant water supply. | Reliable water supply. | Supply of oil | 300ℓ of oil supplied annually. | Number of Litres of oil supplied annually. | 300ℓ of oil supplied annually. | 75ℓ of oil supplied annually. | 100ℓ of petrol supplied Quarterly. | 75ℓ of oil supplied Quarterly. | 75ℓ of petrol supplied Quarterly.. | Achieved | 179.5ℓ of oil supplied | None | None | Progress Report
To resolve registered M & E incidents within 14 days. | Financial and Human Resource | Consistent supply of water | Improved water supply | Mechanical & Electrical Services | 450 of registered M & E incidents within 14 days | Number of registered M & E incidents resolved within 14 days | 450 of registered M & E incidents within 14 days | 113 of registered M & E incidents within 14 days | 113 of registered M & E incidents within 14 days | 113 of registered M & E incidents within 14 days | 111 of registered M & E incidents within 14 days | Achieved | 370 of registered M & E incidents within 14 days | None | None | Progress Report | 8620000
To install Bulk Water Meters by June 2020 | Financial and Human Resource | Consistent supply of water | Improved water supply | Installation of Bulk Water Meters | No bulk metres installed | Number of Bulk Meters installed | 6 Bulk Water Meters installed | 2 Bulk Water Meters installed | No activity | installation 3 Bulk Water Meters | 3 Bulk Water Meters installed | N/A | N/A | N/A | N/A | Progress Report | 1500000
To purchase Mℓ Bulk water by June 2020 | Financial and Human Resource | Consistent supply of water | Improved water supply | Ml of Bulk Water Purchases | 10 062Mℓ of water purchased | Number of Mℓ of bulk portable water purchased | 2515,5Mℓ of water purchased | 2515,5Mℓ of water purchased | 2515,5Mℓ of water purchased | 2515,5Mℓ of water purchased | 2515,5Mℓ of water purchased | Achieved | 4076Mℓ of water purchased | None | None | Progress Report | 115589588.51
PLANNING
To develop Water Conservation /Water Demand Management Strategy for SDM by June 2020 | WSDP and Water Master Plan | Document on Water Conservation and Demand Management | Strategy on Water Conservation and Demand Management | Water Conservation and Water Demand Management Plan | No WC/WDM plan in place | Number of WC/WDM Strategy developed | One WC/WDM Strategy developed | No activity | No activity | No activity | One WC/WDM Strategy developed | N/A | None | None | None | Draft WC/WDM strategy | 0
To develop and review Water & Sanitation Master Plan by June 2020 | Existing Water Master Plan | Effective Water & Sanitation Infrastructure Plans | Reviewed Water and Sanitation Master Plan | Development of Water & Sanitation Master Plan (WSMP) | 1 Draft Water Master Plan and no sanitation Master Plan | Number of Water & Sanitation Master Plan reviewed | One Water & Sanitation Master Plan reviewed | No activity | No activity | No activity | One Water & Sanitation Master Plan reviewed | N/A | None | None | None | Draft WSMP | 500000
To upgrade Groblersdal sewer pump- station by June 2020 | Bulk sewer intervention plan | Upgraded Sewer infrastructure | Enhanced sewer system | Conditional assessment of Groblersdal sewer network | 50% Conditional assessment for Groblersdal sewer network. | Number of conditional assessment report for Groblersdal sewer network conducted. | One conditional assessment report for Groblersdal sewer network conducted | No activity | No activity | No activity | One conditional assessment report for Groblersdal sewer network conducted | N/A | None | None | None | Progress Report | 800000
To improve the provision of operations & maintenance efficiently | Draft O&M Plan | Effective Maintenance & Operation of Existing Infrastructure | Operation & Maintenance Plan | Development of Operation and Maintenance Plan (O&M) | Draft O&M plan completed | Number of O & M Plan completed and approved | One O & M Plan completed and approved | No activity | No activity | One O & M Plan completed and approved | No activity | N/A | None | None | None | Progress Report | 375000
To Conduct Feasibility Studies and develop Technical Report by June 2020 | Assignment of a PSP to do the Technical Reports | Technical Reports | MIG registered Projects | Conduct Feasibility Studies and develop Technical reports | Water Services Master Plan and WSDP developed in 2014/15 and 2015/16 FY respectively | Number of Feasibility Studies conducted and technical Reports developed | 7 Feasibility Studies conducted and technical Reports developed. | 2 Feasibility Studies conducted and technical Reports developed | 2 Feasibility Studies conducted and technical Reports developed | 3 Feasibility Studies conducted and technical Reports development | No activity | Achieved | 2 Feasibility Studies conducted and technical Reports developed | None | None | Progress Report | 1308480
To ensure effective infrastructure planning & development. | Assignment of a PSP to Update Water Service Development Plan | Updated Water Service Development Plan | Improved service delivery | Update Water Service Development Plan. | Water Services Master Plan and WSDP developed in 2014/15 and 2015/16 FY respectively | Number of updated Water Service Development Pan. | One Water Service Development Pan updated. | No activity | No activity | No activity | One Water Service Development Pan updated. | N/A | None | None | None | Progress Report | 0
To ensure compliance with water services policies | Assignment of a PSP to perform registration of servitude for bulk water infrastructure | Registration of servitude for bulk water infrastructure | To protect municipal assets | Registration of servitude for bulk water infrastructure. | Report for bulk water service | Number of bulk water infrastructure servitude | 1 bulk water infrastructure servitude registered | No activity | No activity | No activity | 1 bulk water infrastructure servitude registered | N/A | None | None | None | Progress Report | 0
To ensure compliance with water services policies | Bulk Contribution Policy | Promulgation of Bulk contribution policy | Implement development charges | Promulgation of Bulk contribution policy | Draft bulk contribution policy. | Number of bulk water contribution policy promulgated | One bulk water contribution policy promulgated | No activity | No activity | No activity | One bulk water contribution policy promulgated | N/A | None | None | None | Progress Report | 175000
To ensure compliance with water services policies | Water and sanitation by-law | Reviewed water and sanitation by-law | Enforcement of by-laws | Review of water and sanitation by-law | Water & Sanitation by-laws in place | Number of Water & Sanitation By-Laws reviewed | One Water & Sanitation By-Laws reviewed | No activity | No activity | No activity | One Water & Sanitation By-Laws reviewed | N/A | None | None | None | Progress Report | 175000
WSIG PROJECTS
To complete Tukakgomo water reticulation by June 2020 | Financial and human resource | Reticulated water supply | Improved access to safe, reliable drinking water. | Tukakgomo water intervention and refurbishment. | 1 borehole drilled and equipped. | Number of Kilometers of water reticulation network completed | 4 Kilometers of water reticulation network completed | 0,5Kilometers of water reticulation network completed | 1.6 Kilometers of water reticulation network completed | 1,5 Kilometers of water reticulation network completed | 1Kilometers of water reticulation network completed | Achieved | 2.46 Kilometers of water reticulation network completed | None | None | Project close-out report or completion certificate. | 5309205.8
To complete Tswaing water reticulation by June 2020 | Financial and human resource | Refurbished package plant. | Improved access to safe, reliable drinking water. | Tswaing village Water intervetion Project. | 1 Package plant | Number of package plant refurbished. | 1 package plant and 1 Abstraction point refurbished. | 1 Abstraction point refurbished | 1 package plant and 1 Abstraction point refurbished. | 1 package plant refurbished. | No activity | Achieved | 1 package plant and 1 Abstraction point refurbished. | None | None | Progress Report | 2288308.28
To construct water storage and equip the 2 existing boreholes by June 2020 | Financial and human resource | Reticulated water supply | Improved access to safe, reliable drinking water. | Uitspanning Water Supply Intervention | Groblersdal WTW and Moutse bulk pipeline in progress | Number of water supply pipeline and water storage completed | 4 Kilometres of water supply pipeline and 1 water storage completed | 0,5 Kilometres of water supply pipeline and 0 water storage completed | 1 Kilometres of water supply pipeline and 0 water storage completed | 1,5 Kilometres of water supply pipeline and 0 water storage completed | 1 Kilometres of water supply pipeline and 1 water storage completed | Not achieved | 0 Kilometres of water supply pipeline and 0 water storage completed | Contractor was intructed to demolish the concerete base due to poor cocrete quality of work. | Revise project plan and the project team to ensure sub-contracting works to be assigned ot specialist contractors with skill and experience. | Project close-out report or completion certificate. | 8802000
To complete reticulation and installations of water meters by June 2020 | Financial and human resource | WC/WD Management Provisioning | Improved access to safe, reliable drinking water. | Flag Boshielo Water Conservation Water Demand Management | The village is fully reticulated supplied water for 24hrs without payment | Number of household meters installed and refurbished | 450 household meters Installed and 300 metres refurbished | 50 household meters Installed and 60 metres refurbished | 0. 5 km reticulation pipeline completed. 100 household meters installed. | 150 household meters Installed and 60 metres refurbished | 150 household meters Installed and 80 metres refurbished | Not achieved | 0 km reticulation pipeline completed. 0 household meters installed. | There is a dispute of claimed quantity between contractor and consultant over the submitted invoice for signature which cause the delay on the project progress. | The Contractor, Consultants and SDM project manager went to re-measure the quantities on the 12th of December 2020 to resolve the matter. | Project close-out report or completion certificate. | 5000000
To construct a rising main and source development at Maebe by June 2020 | Financial and human resource | Developed source | Improved access to safe, reliable drinking water. | Maebe/Mohlaletsi interventions | Informal water infrastructure . | Number of water source developed | 1 water sources developed | No activity | 1 150 km of bulk pipeline constructed. 0 pressed steel tanks installed.0 generator's room constructed | No activity | No activity | Achieved | 2.35 km of bulk pipeline constructed. 0 pressed steel tanks installed. 0 generator's room constructed | Project was on halt to allow consultant company to review the design to incorporate Mapulaneng in the Maebe project. | The consultants completed and presented their design to SDM committee for approval. Review the project programme. | Project close-out report or completion certificate. | 12000000
To construct reticulation network by June 2020 | Financial and human resource | Reticulated water supply | Improved access to safe, reliable drinking water. | Rutseng Water Intervention | Informal water infrastructure in place | Number of Kilometers of water supply pipeline constructed | 7km of water supply pipeline constructed | 1km of water supply pipeline constructed | No activity | 2km of water supply pipeline constructed | 2km of water supply pipeline constructed | N/A | No Activity | No Activity | No Activity | Project close-out report or completion certificate. | 2000000
To test & commission the bulk water supply by June 2020. | Financial and human resource | WC/WD Management Provisioning | Improved access to safe, reliable drinking water. | Nebo Phase 1A testing and commissioning(Jane Furse WC/WD Management) | Nebo Phase1A completed but not commissioned | Number of Kilometers of bulk water supply pipeline tested and commissioned | 24km bulk water supply pipeline tested and commissioned | 6km bulk water supply pipeline tested and commissioned | No activity | 9km bulk water supply pipeline tested and commissioned | 9km bulk water supply pipeline tested and commissioned | N/A | 0 km bulk water supply pipeline tested and commissioned | The project was long time on halt, the appoitment of the contractors and consultants elapse. We are on the process to terminate them. | The Municiaplity will utilise the term contractor to fast-track commission the project. | Project close-out report or completion certificate. | 15284400
To construct reticulation and standpipes by June 2020 | Financial and human resource | Reticulated water supply | Improved access to safe, reliable drinking water. | Mahlwakwena to Mapodile pipeline(Tukakgomo Extension) | 1,8km of rising main from the highlift pumpstation to the Elevated Steel tank costructed | Number of Kilometers of reticulation network and standpipes constructed | 6.3Km of reticulation network and 29 standpipes completed | No activity | 6.3Km of reticulation network and 29 standpipes completed | No activity | 6.3Km of reticulation network and 29 standpipes completed | Achieved | 6.3Km of reticulation network and 29 standpipes completed | None | None | Progress Report | 1231298.81
To complete water reticulation, storage and source development by June 2020 | Financial and human resource | Reticulated water supply | Improved access to safe, reliable drinking water. | Phiring Water Intervention(Leboeng) | Borehole refurbished and connected to the existing steel pipeline. Elevated steel tank constructed. | Number of Kilometer of water reticulation constructed, storage tanks constructed and borehole refurbished. | 1,5 Kilometer of water reticulation constructed, 1 storage tanks constructed and 1 borehole refurbished. | No activity | 1,5 Kilometer of water reticulation constructed, 1 storage tanks constructed and 1 borehole refurbished. | No activity | 1,5 Kilometer of water reticulation constructed, 1 storage tanks constructed and 1 borehole refurbished. | Achieved | 1.5 Kilometer of water reticulation constructed, 1 pressed steel tank installed and 1 borehole refurbished. | The contractor accept his appointment to execute work at phiring and later claims that he cnnot go back to site since well he didn’t sign an SLA with the client.The contractor didn’t pay the worker . | The SLA and bid document signed. So he expected to resume to site on the 13th January 2020. | Progress Report | 3440332.8
To complete Package Plant in by June 2020. | Financial and human resource | Packaged plant | Improved access to safe, reliable drinking water. | Jane Furse RDP Package plant | 70% completion of Package Plant , risnig main and storage in Jane Furse RDP | Number of Package Plant installed | 1 Package Plant installed | No activity | No activity | No activity | 1 Package Plant installed | N/A | None | None | None | Progress Report | 7059495.36
To construct VIDP Sanitation units by June 2020. | Financial and human resource | Onsite sanitation, health hygiene & user education | Improved access to safe, reliable sanitation service | Construction of Moretsele VIDP | 200 VIDP units completed | Number of VIDP Sanitation units constructed | 170 VIDP Sanitation units constructed | No activity | No activity | 70 VIDP Sanitation units constructed | 100 VIDP Sanitation units constructed | N/A | None | None | None | Progress Report | 714962.24
To package plant in by June 2020. | Financial and human resource | Packaged plant | Improved access to safe, reliable drinking water. | REFURBISHMENT OF TJIBENG PACKAGE PLANT | The package plant is dilapitated. | Number of package plant installed. | 1 package plant installed. | No activity | No activity | 1 package plant installed. | No activity | N/A | None | None | None | Progress Report | 3000000
To construct water source development and bulk infrastructure development by June 2020 | Financial and human resource | Developed source | Improved access to safe, reliable drinking water. | Laesdrift Water Source Development and Bulk Infrastructure Development | New Infrastructure | Number of Infrastucture Business Plan developed | 1 Infrastucture Business Plan developed | No Activity | 1 Infrastucture Business Plan developed | No activity | 1 of water source development and bulk infrastructure development completed | Achieved | 1 Infrastucture Business Plan developed | None | None | Progress Report | 500000
To construct water source development ,rising main and water storage by June 2020 | Financial and human resource | Developed source | Improved access to safe, reliable drinking water. | Riba Cross Water Source Development with Bulk Services | New Infrastructure | Number of Infrastucture Business Plan developed | 1 Infrastucture Business Plan developed | No Activity | 1 Infrastucture Business Plan developed | 1 Infrastucture Business Plan developed | No Activity | Achieved | 1 Infrastucture Business Plan developed | None | None | Progress Report | 300000
To construct water source development and bulk services by June 2020 | Financial and human resource | Developed source | Improved access to safe, reliable drinking water. | Mpita Water Source Development with bulk services infrastructure | New Infrastructure | Number of Infrastucture Business Plan developed | 1 Infrastucture Business Plan developed | No Activity | 1 Infrastucture Business Plan developed | 1 Infrastucture Business Plan developed | No Activity | Achieved | 1 Infrastucture Business Plan developed | None | None | Progress Report | 700000
To construct water source development and bulk services by June 2020 | Financial and human resource | Developed source | Improved access to safe, reliable drinking water. | Shakung Water Supply and source development with package plant | New Infrastructure | Number of Infrastucture Business Plan developed | 1 Infrastucture Business Plan developed | No Activity | 1 Infrastucture Business Plan developed | 1 Infrastucture Business Plan developed | No Activity | Achieved | 1 Infrastucture Business Plan developed | None | None | Progress Report | 300000
To Investigate and remove of illigal water connections, install water meters and replace old water pipelines to reduce water losses by 2020 | Financial and human resource | Developed source | Improved access to safe, reliable drinking water. | Mapodile WC/WDM | New Infrastructure | Number of Infrastucture Business Plan developed | 1 Infrastucture Business Plan developed | No Activity | 1 Infrastucture Business Plan developed | 1 Infrastucture Business Plan developed | No Activity | Achieved | 1 Infrastucture Business Plan developed | None | None | Progress Report | 500000
To do source development, refurbishment of package plant and water reticulation by 2020. | Financial and human resource | Packaged plant | Improved access to safe, reliable drinking water. | Nkosini Water Supply with package plant | New Infrastructure | Number of Infrastucture Business Plan developed | 1 Infrastucture Business Plan developed | No Activity | 1 Infrastucture Business Plan developed | 1 Infrastucture Business Plan developed | No Activity | Achieved | 1 Infrastucture Business Plan developed | None | None | Progress Report | 600000
To drill boreholes and construct rising main and storage steel tank. | Financial and human resource | Developed source | Improved access to safe, reliable drinking water. | Magoroane Water Supply | New Infrastructure | Number of Infrastucture Business Plan developed | 1 Infrastucture Business Plan developed | No Activity | 1 Infrastucture Business Plan developed | 1 Infrastucture Business Plan developed | No Activity | Achieved | 1 Infrastucture Business Plan developed | None | None | Progress Report | 469996.71
To install Package plant and construct rising main by 2020 | Financial and human resource | Packaged plant | Improved access to safe, reliable drinking water. | Strydkraal Water Intervention | New Infrastructure | Number of Infrastucture Business Plan developed | 1 Infrastucture Business Plan developed | No Activity | 1 Infrastucture Business Plan developed | 1 Infrastucture Business Plan developed | No Activity | Achieved | 1 Infrastucture Business Plan developed | None | None | Progress Report | 500000
MUNICIPAL INFRASTRUCTURE GRANT (MIG)
To construct VIP Sanitation units by June 2020 within Ephraim Mogale Municipality | Financial and Human Resource | 1 020 VIP Sanitation toilets completed | Improved health and hygiene | VIP Sanitation Programme Phase 2.3 | 15 180 VIP units constructed | Number of VIP sanitation units completed | 1510 VIP sanitation units completed | 750 VIP Sanitation toilets constructed | 300 VIP Sanitation toilets constructed | 230 VIP Sanitation toilets constructed | 230 VIP Sanitation toilets constructed | Not Achieved | Learner contractors appointed and to commence with project in February 2020 | None | None | Progress Report | 15572062.82
To construct VIP Sanitation units by June 2020 within Elias Motsoaledi Municipality | Financial and Human Resource | 1 630 VIP Sanitation toilets completed | Improved health and hygiene | VIP Sanitation Programme Phase 2.3 | 15 180 VIP units constructed | Number of VIP sanitation units completed | 2481 VIP sanitation units completed | 750 VIP Sanitation toilets constructed | 400 VIP Sanitation toilets constructed | 750 VIP Sanitation toilets constructed | 581 VIP Sanitation toilets constructed | Not Achieved | Learner contractors appointed and to commence with project in February 2020 | None | None | Progress Report | 17000000
To complete Zaaiplaas bulk pipeline, command reservior and pump station by June 2020 | Financial and Human Resource | Completed BWS | Improved water supply to Zaaiplaas | Zaaiplaas Village Reticulation Phase 2 ( Vlakfontein, Slovo and remaining village ) - CO | 80% construction of Dindela Reservoir. Commissioning of bulk pipeline and pump station completed | Number of Kilometres Zaaiplaas bulk water supply pipeline commissioned, command reservoir constructed and pump station installed | 2 Kilometres of Zaaiplaas bulk water supply pipeline commissioned, 1 command reservoir constructed and 1 pump station installed | 1 Kilometres of Zaaiplaas bulk water supply pipeline commissioned, 0 command reservoir constructed and 1 pump station installed | No activity | No activity | 1 Kilometres of Zaaiplaas bulk water supply pipeline commissioned, 1 command reservoir constructed and0 pump station installed | N/A | None | None | None | Progress Report | 5472297
To construct VIP Sanitation units by June 2020 within Makhuduthamaga Municipality | Financial and Human Resource | 1 835 VIP Sanitation toilets completed | Improved health and hygiene | VIP Sanitation programme phase 2.3 | 15 180 VIP units constructed | No of VIP sanitation units completed | 2745 VIP sanitation units constructed | 750 VIP sanitation units constructed | 500 VIP sanitation units constructed | 750 VIP sanitation units constructed | 745 VIP sanitation units constructed | Not Achieved | Learner contractors appointed and to commence with project in February 2020 | None | None | Progress Report | 16390676.03
To construct reticulation,water storage and water source development in Ga- Mashabela by June 2020 | Completed Ga-Mashabela water reticulation network | Improved water supply to Ga-Mashabela | Ga-Mashabela water reticulation supply | Ga- Mashabela water reticulation supply | 60% of water reticulation constructed | Kilometres of pipeline constructed, number of reservoir completed, number of boreholes completed | 30km of reticulation pipeline constructed , 4* Reservoir completed, 7*boreholes completed | 15km of rericulation pipeline constructed , 0* Reservoir completed, 0*boreholes completed | 15km of reticulation pipeline constructed , 4* Reservoir completed, 7*boreholes completed | No activity | No activity | Not Achieved | 15km of reticulation pipeline constructed , 4* Reservoir completed, 5*boreholes completed | 2 boreholes not energised by ESKOM | Engagement with ESKOM to fast track the energising | Progress Report | 3000000
To construct reticulation and water storage in Ga- Marishane by June 2020 | Financial and Human Resource | Completed Ga-Marishane water reticulation network | Improved water supply to Ga-Marishane | Ga- Marishane water reticulation supply | 30% water reticulation constructed | Kilometres of reticulation pipeline constructed, number of reservoir and WTW completed | 3.4km of reticulation pipeline constructed , 1 reservoir completed and 1 WTW completed | 1,7km of reticulation pipeline constructed , 0 reservoir completed and 0 WTW completed | No activity | 1,7km of reticulation pipeline constructed , 1 reservoir completed and 1 WTW completed | No activity | N/A | None | None | None | Progress Report | 5915286.3
To construct water pipeline in Ga -Mogashoa(Senkapudi) and Ga- Mogashoa(Manamane) by June 2020 | Financial and Human Resource | Completed Ga -Mogashoa(Senkapudi) and Ga- Mogashoa(Manamane)water reticulation network | Improved water supply to Ga -Mogashoa(Senkapudi) and Ga- Mogashoa(Manamane) | Ga -Mogashoa(Senkapudi) and Ga- Mogashoa(Manamane) | 200kl reservoir constructed | Kilometres of water pipeline completed | 53 Kilometres of pipeline completed | No activity | 17.6 kilometres of pipeline completed | 17.6 kilometres of pipeline completed | 17.6 kilometres of pipeline completed | Not Achieved | 12 kilometres of pipeline completed | Slow progress due to late start of construction work | Contractor to beef-up on manpower and plant during the month of January 2020 to recover time lost and will be monitored closely by the Engineer | Progress Report | 51000000
To construct concrete reservoirs and bulk water pipeline, NSD07 RWS Schoonoord by June 2020 | Financial and Human Resource | Completed concrete reservoirs and bulk water pipeline | Improved water supply to Ga -Mogashoa(Senkapudi) and Ga- Mogashoa(Manamane) | NSD07 Regional Water Scheme Construction of Concrete Reservoirs | 10ML reservoir and the bulk water pipeline constructed | Kilometres of bulk pipeline completed and number of reservoirs completed | 1 Kilometre of bulk pipeline completed and 1 reservoir completed | No activity | 0.5 kilometre of bulk pipeline completed and 0 reservoir completed | 0.5 Kilometre of bulk pipeline completed and 0 reservoir completed | 0 Kilometre of bulk pipeline completed and 1 reservoir completed | Not Achieved | 0 kilometre of bulk pipeline completed and 0 reservoir completed | Slow progress due to late start of construction work | Contractor to beef-up on manpower and plant during the month of January 2020 to recover time lost and will be monitored closely by the Engineer | Progress Report | 25000000
To construct Fetakgomo Tubatse LM VIP Sanitation units by June 2020 (Fetakgomo area) | Financial and Human Resource | 715 VIP Sanitation toilets completed | Improved health and hygiene | VIP Sanitation programme phase 2.3 | 15 180 VIP Units constructed | No of VIP sanitation units completed | 769 VIP sanitation units constructed | 375 VIP sanitation units constructed | 394 VIP sanitation units constructed | 0 VIP sanitation units constructed | 0 VIP sanitation units constructed | Not Achieved | Learner contractors appointed and to commence with project in February 2020 | None | None | Progress Report | 14700000
To complete Concrete reservoirs and Water pipeline at Nkadimeng: Phase 9 to 11 by June 2020 | Financial and Human Resources | Nkadimeng: Phase 9 to 11 (Makhuduthamaga) - | Improved Living standards. | Nkadimeng RWS Extension 2( Phase 9 to 11) (Fetakgom o) Ga- Mmela to Mashilavele , Ga- Pahla, Molapong, Ga- Magolego, Mankontu and Masehleng | 2 x 500kl reservoir constructed and 67km pipeline installed | Kilometres of water pipeline completed and number of reservoirs completed | 38km of water pipeline constructed, 1* 500kl reservoir and 98 street taps | 2km of water pipeline constructed, 0* 500kl reservoir and 0 street taps | 12km of water pipeline constructed, 0* 500kl reservoir and 30 street taps | 12km of water pipeline constructed, 0* 500kl reservoir and 34 street taps | 12km of water pipeline constructed, 1* 500kl reservoir and 34 street taps | Not Achieved | 9km of water pipeline constructed, 0* 500kl reservoir and 30 street taps | Limited funding t complete the project | Additional own funding allcoated to complete the project | Progress Report | 940850.77
To construct Fetakgomo Tubatse LM VIP Sanitation units by June 2020 (Tubatse area) | Financial and Human Resource | 1630 VIP Sanitation toilets completed | Improved health and hygiene | VIP Sanitation programme phase 2.3 | 15 180 VIP Units constructed | No of VIP sanitation units completed | 2689 VIP sanitation units constructed | 750 VIP sanitation units constructed | 1500 VIP sanitation units constructed | 200 VIP sanitation units constructed | 239 VIP sanitation units constructed | Not Achieved | Learner contractors appointed and to commence with project in February 2020 | None | None | Progress Report | 15300000
To construct water pipeline in Malekana Regional Water Scheme by June 2020 | Financial and Human Resource | Completed Malekana Regional Water Scheme water reticulation network | Improved water supply to Malekana Regional Water Scheme | Malekana Regional Water Scheme | 10ML Water Treatment Plant constructed | Kilometres of water pipeline and number of reservoirs completed | 10 kilometres of water pipeline and 4 reservoirs completed | No activity | 2 kilometres of water pipeline and 0 reservoirs completed | 4 kilometres of water pipeline and 0 reservoirs completed | 4 kilometres of water pipeline and 4 reservoirs completed | Not Achieved | 0 kilometres of water pipeline and 0 reservoirs completed | Delays in site project hand over | Fast track the site establishment of the project | Progress Report | 81000000
To construct connector pipe, reticulations network & reservior in Lebalelo South by June 2020 | Improved water supply | Lebalelo South connector pipes & reticulation network, reservior completed | Improved Living standards. | Lebalelo South connector pipes & reticulation network | 10ML Mooihoek Water Treatment Works, Mooihoek Bulk pipeline constructed | Kilometres of connector and reticulation pipelines and number of reservoirs completed | 190km of connector and reticulation pipelines constructed and 3 reservoirs completed | 40km of connector and reticulation pipelines constructed and 0 reservoirs completed | 50km of connector and reticulation pipelines constructed and 0 reservoirs completed | 50km of connector and reticulation pipelines constructed and 0 reservoirs completed | 50km of connector and reticulation pipelines constructed and 3 reservoirs completed | Achieved | 50km of connector and reticulation pipelines constructed and 0 reservoirs completed | None | None | Progress Report | 107957451
To construct water pipeline & reserviors in Lebalelo South Phase 3 (Ga Maroga & Motlolo by June 2020 | Improved water supply | Lebalelo South connector pipes completed | Improved Living standards. | Lebalelo South Phase 3 (Ga Maroga & Motlolo ) Bulk & reticulation innfrastructure | 10ML Mooihoek Water Treatment Works, Mooihoek Bulk pipeline constructed | Kilometres of water pipeline and number of reservoirs completed | 20 kilometres of water pipeline and 1 reservoirs completed | No activity | 5 kilometres of water pipeline and 0 reservoirs completed | 10 kilometres of water pipeline and 0 reservoirs completed | 5 kilometres of water pipeline and 1 reservoirs completed | Not Achieved | 0 kilometres of water pipeline and 0 reservoirs completed | Delays in site project hand over | Fast track the site establishment of the project | Progress Report | 87570251.93
To construct water pipeline, reservior and pump station in Ga Maphopha by 2020 | Improved water supply | Ga Maphopha Bulk water pipeline completed | Improved Living standards. | GaMaphopha Command Reservoir | 12ML Ga-Malekana Water Treatment Works, Malekana Bulk pipeline constructed | Kilometres of water pipeline,number of reservoirs & pump station completed | 5 kilometres of water pipeline,1 reservoirs & 1 pump station completed | No activity | 3 kilometres of water pipeline,0 reservoirs & 0 pump station completed | 2 kilometres of water pipeline,1 reservoirs & 0 pump station completed | 0 kilometres of water pipeline,0 reservoirs & 1 pump station completed | Achieved | 3 kilometres of water pipeline,0 reservoirs & 0 pump station completed | None | None | Progress Report | 3897499.72
To upgrade & extend the WWTW in Roosenekaal by June 2020 | Improved waste water provision | Roosenekaal WWTW | Improved Living standards. | Roosenekal WWTW | Existing WWTW in Roosenekaal | Number of WWTW updraded and extended | One WWTW upgraded and extented | No activity | No activity | One WWTW upgraded and extented | No activity | N/A | None | None | None | Progress Report | 500000
To construct reticulation network in De Hoop/Nebo plateau/schoonoord water scheme villages makgeru.Ga-ratau &Matekane by June | Improved water supply | Schoonoord Makgeru reticulation network | Improved Living standards. | De Hoop/Nebo plateau/schoonoord water scheme villages mkgeru.Ga-ratau &Matekane | 12ML Ga-Malekana Water Treatment Works, Malekana Bulk pipeline constructed | Number of design report and bid documents completed | One design report and two bid documents completed | No activity | One design report and 0 bid documents completed | 0 design report and 2 bid documents completed | No activity | Achieved | One design report and 0 bid documents completed | None | None | design report & bid document | 5000000
MUNICIPAL HEALTH SERVICES
To Have an improved, clean, healthy and sustainable environment through municipal health services package by June 2020 |  |  |  | Environmental Pollution Prevention | 12 Awareness Campaigns on Air Quality conducted | Number of Awareness Campaigns on Air Quality conducted | 24 Awareness Campaigns on Air Quality conducted |  | 6 Air quality awareness campaigns conducted |  |  | Achieved | 6 Air quality awareness campaigns conducted | None | None | Attendance register | 231440
|  |  |  | Water quality monitoring | 300 Water quality samples collected | Number of Water quality samples collected | 300 Water quality samples collected |  | 75 Water quality samples collected |  |  | Achieved | 75 Water quality samples collected | None | None | Signed Water Quality samples Reports | R44 078.28
|  |  |  | Food Safety control | 1400 Food Premises evaluated | Number of Food Premises evaluated | 1500 Food Premises evaluated |  | 375 Food Premises evaluated |  |  | Achieved | 390 Food Premises evaluated | None | None | Signed Assessment forms incuding the owner signature | R21 501.60
|  |  |  | Waste Management | 100 Health care risk waste monitored | Number of Health care risk waste monitored | 100 Health care risk waste monitored |  | 25 Health care risk waste monitored |  |  | Achieved | 37 Health care risk waste monitored | None | None | Signed Assessment forms incuding the owner signature | R0 00
|  |  |  | Health Surveillance of premises | 1200 premises evaluated | Number of premises evaluated | 1500 premises evaluated |  | 375 Premises evaluated |  |  | Achieved | 533 Premises evaluated | None | None | Signed Assessment forms incuding the owner signature | R0 00
|  |  |  | Surveillance and prevention of communicable diseases | 100 Communicable diseases awareness campaigns held | Number of Communicable diseases awareness campaigns held | 100 Communicable diseases awareness campaigns held |  | 25 Communicable diseases awareness campaigns held |  |  | Achieved | 31 Communicable diseases awareness campaigns held | None | None | Signed Assessment forms incuding the owner signature | R0 00
|  |  |  | Communicable diseases outbreak control | 142 communicable diseases investigated and controlled | Number of communicable diseases investigated and controlled | All communicable diseases investigated and controlled |  | All communicable diseases investigated and controlled |  |  | Achieved | All 18 communicable diseases were reported for investigation and controlled | None | None | Signed Reports and Attendance register | 43003.2
|  |  |  | Vector Control | 1000 premises monitored on vector control | Number of premises monitored on vector control | 1400 premises monitored |  | 350 Premises monitored |  |  | Achieved | 382 Premises monitored | None | None | Signed Reports | R0 00
|  |  |  | Disposal of the dead | 100 Disposal of the dead facilities evaluated | Number of Disposal of the dead facilities evaluated | 100 Disposal of the dead facilities evaluated |  | 25 Disposal of the dead facilities evaluated |  |  | Achieved | 28 Disposal of the dead facilities evaluated | None | None | *Signed Reports * Forms signed by Mortuaries | R0 00
|  |  |  | Chemical safety | 300 chemical handling premises evaluations conducted | Number of chemical handling premises evaluations conducted | 300 chemical handling premises evaluations conducted |  | 75 Chemical handling premises evaluations conducted |  |  | Achieved | 78 Chemical handling premises evaluations conducted | None | None | *Signed Reports * Signed evaluation forms | R0 00
EMERGENCY MANAGEMENT SERVICES
To protect loss of life, damage to property and environment by June 2020 |  |  |  | Fire and Rescue Operations | 587 reported Emergency Services incidents attended | Number of reported Emergency Services incidents attended | All reported Emergency Services incidents attended |  | All reported Emergency Services incidents attended |  |  | Achieved | All 167 reported Emergency Services incidents attended | None | None | Signed Reports | N
|  |  |  | Emergency Management Services Training Academy | 4 fire fighting courses facilitated | Number of fire fighting courses facilitated | 3 firefighting courses facilitated |  | No activity |  |  | N/A | No Activity | None | None | Signed Reports and Attendance register | 32884.8
|  |  |  | Fire Safety and Prevention | 654 reported fire safety and prevention services conducted | Number of all fire safety and prevention services provided | All reported fire safety and prevention services conducted |  | All reported fire safety and prevention services conducted |  |  | Achieved | All 220 reported fire safety and prevention services conducted | None | None | Signed Reports | R0 00
DISASTER MANAGEMENT
To protect loss of life, damage to property and environment by June 2020 |  |  |  | Disaster risk assessment | 580 reported disaster risk management incidents attended | Number of reported disaster risk management incidents attended | All reported disaster risk management incidents attended |  | All reported disaster risk management incidents attended |  |  | Achieved | All 45 disaster risk management incidents attended | None | None | Register of disaster incidents | R0 00
|  |  |  | Disaster risk reduction | 24 disaster risk reduction awareness campaigns conducted | Number of disaster risk reduction awareness campaigns conducted | 24 disaster risk reduction awareness campaigns conducted |  | 6 disaster risk reduction awareness campaigns conducted |  |  | Achieved | 10 disaster risk reduction awareness campaigns conducted | None | None | Attendance Registers | R0 00
|  |  |  | Disaster response and recovery | (1210 Blankets, 622 sponches, 55 temporary shelters, 141 food parcels) relief material to all affected disaster victims coordinated and provided | Number of all reported disaster response and recovery operations attented to | Provide relief material to all deserving reported disaster victims |  | Provide relief material to all deserving reported disaster victims |  |  | Achieved | 53 Blankets,21 sponges and 2 shacks were provided to all deserving reported disaster victims | None | None | Report | 268000
|  |  |  | Disaster management plan and framework review | 1 Disaster management plan and framework reviewed | Number of disaster management plan and framework reviewed | 01 Disaster management plan and framework reviewed |  | Stakeholder consultation |  |  | Achieved | Stakeholder consultation inputs have been consolidated | None | None | Reviewed disaster management plan and Council resolution | R0 00
|  |  |  | Special Operations | 03 special operations on high density days campaigns coordinated | Number of special high density days campaigns coordinated | 03 special operations on high density days campaigns coordinated |  | 1 special operation high density campaign coordinated |  |  | Achieved | 1 special operation high density campaign coordinated | None | None | Operational plan, attendance register and minutes | 31 620, 00
INTERGOVERNMENTA RELATIONS
To coordinate Municipal Health services and environmental management Fora by June 2020 |  |  |  | Municipal Health services Forum and Environmental Management Fora | 4 Municipal Health services and 2 Environmental Management Fora coordinated | Number of Municipal Health services and Environmental Management Fora coordinated | 4 Municipal Health services and 2 Environmental Management Fora coordinated |  | 1 Municipal Health services Forum coordinated |  |  | Achieved | 1 Municipal Health services Forum coordinated | None | None | Attendance Register and Minutes | 10540
To coordinate Community safety Fora by June 2020 |  |  |  | Community safety Fora | 10 Community safety Fora coordinated | Number of Community safety Fora coordinated | 10 Community safety Fora coordinated |  | 3 Community safety Fora coordinated |  |  | Not Achieved | 2 Community safety Fora coordinated | Had high profile provential activities (security summit and Swara Tsotsi) | To be covered in the next meetings | Attendance Register and Minutes
To coordinate Disater management Fora by June 2020 |  |  |  | Disater management Fora | 4 Disater management Advisory Fora coordinated | Number of Disater management Advisory Fora coordinated | 4 Disater management Advisory Fora coordinated |  | 1 Disater management Advisory Forum coordinated |  |  | Achieved | 1 Disater management Advisory Forum coordinated | None | None | Attendance Register and Minutes