## Sheet1
2021/2022 ADJUSTED SERVICE DELIVERY BUDGET AND IMPLEMENTATION PLAN
BASIC SERVICE DELIVERY
OBJECTIVES | PROJECT | BASELINE 2020/2021 | INDICATORS | ANNUAL TARGET 2021/2022 | Q3 | PROGRESS (Achieved/ Not achieved) | ACTUAL PROGRESS | CHALLENGES | REMEDIAL ACTIONS | POE | BUDGET 2021-2022 | EXPENDITURE PER Q3
INFRASTRUCTURE AND WATER SERVICES
OPERATION AND MAINTENANCE (O&M)
To resolve registered sanitation incidents within 14 days. | Sanitation incidents | 700 registered sanitation incidents resolved within 14 days | Number of registered sanitation incidents resolved within 14 days | 700 registered sanitation incidents resolved within 14 days | 175 registered sanitation incidents resolved within 14 days | Achieved | 252 registered sewer incidents resolved within 14 days | None | None | Incident Report | 52,048,895,51 | 38276576.91
To resolve registered water incidents within 14 days. | Water incidents | 5000 registered water incidents resolved within 14 days | Number of registered water incidents resolved within 14 days | 4500 registered water incidents resolved within 14 days | 1125 registered water incidents resolved within 14 days | Not Achieved | 1020 registered water incidents resolved within 14 days | shortage of material | Fastrack appointment of term contractors | Incident Report
To purchase Bulk water by June 2022 | Bulk Water Purchases | 16 500Mℓ of water purchased | Number of Mℓ water purchased | 16 500Mℓ of water purchased | 4125Mℓ of water purchased | Not Achieved | 4087Mℓ water purchased | Frequent breakdowns on the bulk pipeline due to dilapitated infrastructure. | Refurbishment of dilapitated bulk pipeline predominently on Flag boshielo scheme. | Summary Meter readings report. | 135, 330,000 | 67183244.53
To develop water sources in areas that does not have infrastructure and replace dried boreholes by June 2022 | Ground Water Development | New Program | Number of ground water source developed | 20 Ground water source developed (boreholes) | 5 Ground water source developed (boreholes) | Achieved | 5 Ground water source developed (boreholes) | None | None | Progress Reports | 10757256.78 | 3437571.96
To purchase electricity by June 2022 | Electricity Usage | 1200 KWH of Electricity used | Number of KWH electricty used | 10 000 000 KWH of Electricity used | 2,5 000 000KWH of Electricity used | Achieved | 16,333 333KWH of Electricity used | None | None | Summary Electrical Meter readings report. | 40000000 | 44633874.34
RURAL ROADS ASSET MANAGEMENT SYSTEM (RRAMS)
To Develop 80% of Road Asset Management System by June 2022 | Development of Rural Roads Asset Management System | Desk top studies and the first rounds of Visual Conditions Assessments | Number of kilometres of Roads assessed | 500 kilometres of Roads assessed | 200 kilometres of Roads assessed | Not Achieved | 0 kilometres of Roads assessed | Delayed appointment of PSP | Finalise appointment of new panel of Consultants | Progress report | 2, 437, 000. 00 | 0
|  |  | Number of traffic counting stations completed. | 200 traffic counting stations completed | 100 traffic counting stations completed | Not Achieved | 0 traffic counting stations completed |  |  |  |  | 0
REGIONAL BULK INFRASTRUCTURE GRANT (RBIG)
To reduce water services backlog with 90% by June 2022 | Mooihoek bulk water supply phase 4F1 | 1 Kilometers of bulk water pipeline and concrete reservoirs constructed | Number of km of bulk pipeline tested and commissioned | 1km of bulk pipeline tested and commissioned | Testing and commissioning of 0.15 km bulk pipeline | Achieved | Testing and commissioning of 0.75 km bulk pipeline completed | None | None | Progress report | 68640000
To reduce water services backlog with 90% by June 2022 | Construction of Mooihoek bulk water supply phase G1.1 | 1 X 5 Ml concrete reservoir completed Phase 4BA | Number of km of bulk pipeline and package plant constructed | Construction of 3 Kilometres of bulk water supply pipeline. Construction of 1 package plant type clarifier | Site establishments | Not Achieved | No Site establishments | Termination not yet finalised due to recovery of funds spent not yet completed | There is an attempt to recover the money spent from the performance guarantee which is still in process | Progress report |  | 0
To reduce water services backlog with 90% by June 2022 | Construction of Mooihoek bulk water supply phase G1.2 | 1 X 5 Ml concrete reservoir completed Phase 4BA | Number of km of bulk pipeline constructed | Construction of 4.7 Kilometers of bulk water supply pipeline. | Site establishments | Achieved | Site establishments done (Procurement of material completed. Construction has already commenced and overall progress at 40%) | None | None | Progress report |  | 19660232.17
To reduce water services backlog with 90% by June 2022 | Construction of Mooihoek bulk water supply phase G2 | 17km of bulk water supply pipeline completed | Number of km of bulk pipeline and KL of reinforced concrete rserviour constructed | Construction of 4.9 Kilometres of bulk water supply pipeline. Construction of 500KL Reinforced Concrete Reservoir | 1,5 Kilometers of bulk water supply pipeline constructed | Not Achieved | 0,343 Kilometers of bulk water supply pipeline constructed | Contractor running behind programme | Contractor instructed to submit extension of time | Progress report |  | 10077529.78
To reduce water services backlog with 90% by June 2022 | Construction of Mooihoek Reservoirs phase 4H1 | 12Ml/day Mooihoek Water Treatment Works | Number of Reservoir constructed | 1 Reservoir constructed | no activity | N/A | No activity | N/A | N/A | Progress report
To reduce water services backlog with 90% by June 2022 | Construction of Mooihoek Reservoirs phase 4H2 | 12Ml/day Mooihoek Water Treatment Works | Number of Reservoir constructed | 1 Reservoir constructed | no activity | N/A | No activity | N/A | N/A | Progress report
To reduce water services backlog with 90% by June 2022 | Nebo BWS Commission Jane Furse Pipeline | Nebo Phase1A completed and not commissioned | Number of Kilometers of bulk water supply pipeline tested and commissioned | 18 Kilometers of bulk water supply pipeline tested and commissioned | Conditional assessment 2km of pipeline | Not Achieved | Conditional assessment 0km of pipeline | Appointment of service providers not yet done | Awaiting finalisation of panel of consultants and contractors in order to appoint | Progress report | 22500000
To reduce water services backlog with 90% by June 2022 | Nebo BWS Jane Furse to Lobethal Bulk Water Supply | 18km's of bulk water supply pipe line phase two from Jane Furse to Lobethal completed | Number of km's of bulk water supply pipeline assessed | 18km of bulk water supply pipeline assessed | No activity | N/A | No activity | N/A | N/A | Progress report |  | 3316177.56
To reduce water services backlog with 90% by June 2022 | Nebo BWS Makgeru to Schoonoord BWS | 18.2 Km of Schoonoord bulk water supply pipeline in Makgeru. 10ML Command Concrete Reservoir in Schoonoord constructed | Number of Km of bulk water supply pipelines constructed | 6.4Km of bulk water supply pipeline constructed | No activity | N/A | No activity | N/A | N/A | Progress report |  | 0
To reduce water services backlog with 90% by June 2022 | Moutse BWS Project 13 & 14 | 1 WTW in Groblersdal extended in Project 1 and 1 pump station constructed in Project 6 | Number of mechanical and Electrical (M & E) components installed for the extensions to the Groblersdal Water Treatment Works and pump station | 2 mechanical and Electrical (M & E) components installed for the extensions to the Groblersdal Water Treatment Works and pump station | Refurbish 1 Clarifier | Not achieved | Refurbish 0 Clarifier | Review SLA. Review the Additional scope of work | Finalize review of SLA with legal service Submit approval of additional scope of work | Progress report | 20000000 | 7643793.88
| Moutse BWS Project (7 to 12) | 30 Kilometre of bulk water supply pipeline constructed | Number of Kilometres of bulk water supply pipeline installed and tested | 20Kilometre of bulk water supply pipeline installed and tested | Test 7.5km | Achieved | Tested 7.5km | None | None | Progress report |  | 290899.02
| Moutse BWS construction bulk water pipeline project(2-4) | 19km of bulk water supply pipeline constructed | Number of km of bulk water supply pipelines assessed and refurbished | 14 km of bulk water supply pipelines assessed and refurbished | Conditional assessment 2km of pipeline | Not achieved | Conditional assessment 0km of pipeline | Review SLA | Appoint PSP for project 2,3&4 soon after bid adjudication is complete | Progress Report |  | 0
WATER SERVICES INFRASTRUCTURE GRANT (WSIG)
To reduce water services backlog with 90% by June 2022 | Maebe Drilling and Equipping of Borehole | Three (3) drilled and equipped boreholes and bulk pipeline. | Number of pump station constructed, package plant and storage tank installed | 1 Pump station constructed and 1 Reverse Osmosis Water Treatment Package Plant and 1 storage tank installed | Installation of 1 storage tank | Not Achieved | Installation of 0 storage tank | Schedule changed to 6B. Projects reprioritised due to budget constraints | Implement in 2022/2023 FY | Progress Report / Completion Certificate | R13, 000, 000. 00 | 0
| Tukakgomo RDP Section Borehole | 3.75 Km of water distribution network constructed and 1 raw water abstraction point upgraded | Number of kilometres of network constructed and water meters installed | 7 Km of water distribution network constructed and 735 water meters installed | Installation of 410 water meters | Not Achieved | Installation of 0 water meters | Schedule changed to 6B. Projects reprioritised due to budget constraints | Implement in 2022/2023 FY | Progress Report / Completion Certificate | R9, 000, 000. 00 | 0
| Nkosini Water Supply & Package Plant | 1 scoping report and business plans | Number of kilometres of pipeline constructed and protection of abstraction point and sealing of the reservoir | 3.5km of pipeline constructed and 1 protection of abstraction and sealing of 1 reservoir | sealing of 1 reservoir | Not Achieved | 0 reservoir sealed | Schedule changed to 6B. Projects reprioritised due to budget constraints | Implement in 2022/2023 FY | Progress Report / Completion Certificate | R8, 000, 000. 00 | 0
| Laersdrift Water Supply Intervention | 1 Scoping Report and Business Plan | Number of kilometres of network constructed and stand pipes and storage tank installed | 8 km reticulation network constructed, 22 communal stand pipes and 1 storage tank installed | Construction of 1 storage tank | Not Achieved | Construction of 0 storage tank | Schedule changed to 6B. Projects reprioritised due to budget constraints | Implement in 2022/2023 FY | Progress Report / Completion Certificate | R9, 000, 000. 00 | 0
| Phokwane/Brooklyn Water Supply | Drilling, testing and equipping of 1 and rising main and 1 storage tank. | Number of kilometres of rising main and storage tank installed | 3km of rising main and 1 elevated tank | construction of 1 elevated storage tank | Not Achieved | construction of 0 elevated storage tank | Schedule changed to 6B. Projects reprioritised due to budget constraints | Implement in 2022/2023 FY | Progress Report / Completion Certificate | R4, 000, 000. 00 | 0
| Legolaneng VDIP | 410 VDIP Toilets | Number of VDIP completed | 440 VDIP completed | 70 VDIP completed | Not Achieved | 0 VDIP completed | Schedule changed to 6B. Projects reprioritised due to budget constraints | Implement in 2022/2023 FY | Progress Report / Completion Certificate | R7, 000, 000. 00 | 0
MUNICIPAL INFRASTRUCTURE GRANT(MIG)
To reduce water services backlog with 90% by June 2022 | Fetakgomo VIP Backlog Programme (Phase 2,3) | 15330 VIP units constructed | Number of VIP units constructed | 500 VIP units to be constructed | 100 VIP units to be constructed | Not Achieved | 0 VIP units to be constructed | No cession agreements were returned by learner contractors. Inflation and escalation on top structure impacted the number of units to be provided. | Learners intent to make advance payment outside cession. SDM will pay for material on site based on delivery note and cash payment. Number of units implementable after VIP unit cost adjustment 592 | Progress report | 8100000 | 533404.75
To reduce water services backlog with 90% by June 2022 | Ephraim Mogale VIP Backlog Programme (Phase2,3 ) | 15730 VIP units constructed | Number of VIP units constructed | 958 VIP units to be constructed | 500 VIP units to be constructed | Not Achieved | 0 VIP units to be constructed | The contractors commenced the construction of Vip units late due to lack of cashflow | The contractors got paid for Site Establishment to enable them to start the construction of Vip units | Progress report | 13000000 | 4661437.5
To reduce water services backlog with 90% by June 2022 | Makhuduthamaga VIP Backlog Programme | 16096 VIP units constructed | Number VIP sanitation units to be constructed | 2300 VIP sanitation units to be constructed | 500 VIP units to be constructed | Not achieved | 0 VIP units to be constructed | Delay on commencement of works due to CLOs appointment . | ISD and Social facilitators to undertake an induction workshops for CLOs and PSC members | Progress report | 32500000 | 1361527.12
To reduce water services backlog with 90% by June 2022 | De Hoop/Nebo Plateau/Schoonoord Water Scheme Villages:Ga –Mogashoa (Senkapudi) and Ga- Mogashoa (Manamane) | 94,6 kilometres of water pipeline constructed | Number of water reticulation pipeline constructed | 11Kilometers of water reticulation pipeline constructed | 1Kilometers of water reticulation pipeline constructed | Not Achieved | 0 Kilometers of water reticulation pipeline constructed | Contractor could not have access to site due to closure by sub-contractors with conflicts around payments Contract behind schedule due to insufficient material on site | Contractor met with the concerned group and social facilitator and they managed to reach an agreement to open the site Contractor procured some materials and still procuring outstanding material. Contractor also busy with pressure testing the completed pipeline sections. | Progress report | R4, 762, 404. 00 | 2805846.61
To reduce water services backlog with 90% by June 2022 | NSD07 Regional Water Scheme Construction of Concrete Reservoirs | 3km of bulk pipeline constructed 1 Reservoir completed | Kilometres of bulk pipeline constructed Number of reservoir completed | 13 Kilometres of bulk pipeline constructed, 3 reservoirs completed | 4 Kilometres of bulk pipeline constructed, 0 reservoirs completed | Not Achieved | 0 Kilometres of bulk pipeline constructed, 0 reservoirs completed | Additional funds required to complete the project due to submitted V/O from contractor | Additional funds request approved in principle during the CoGHSTA appraisal meeting held on the 21st February 2022, currently awaiting confirmation letter of approval from CoGHSTA | Progress report | 19121864.54 | 10171138.18
To reduce water services backlog with 90% by June 2022 | De Hoop/Nebo Plateau/Schoonoord Water Scheme Villages: Makgeru, Ga Ratau & Matekane | 6 Kilometres of bulk pipeline constructed. 98 km of water reticulation pipeline 2435 metered stand pipes Equipping of two boreholes | Number of Kilometres of bulk pipeline constructed. Number of kilometers of Reticulation. Number of Standpipes constructed. Number of Water Meters Installed Number of boreholes equiped. | 6 Kilometres of bulk pipeline constructed. 72 kilometers of Reticulation. 850 Standpipes constructed. 850 Water Meters Installed Equipping of two boreholes. | 1 Kilometres of bulk pipeline constructed. 25 kilometers of Reticulation. 400 Standpipes constructed. 400 Water Meters Installed. Equiping of 2 Boreholes | Achieved | 1 Kilometres of bulk pipeline constructed. 25 kilometers of Reticulation. 400 Standpipes constructed. 400 Water Meters Installed. Equiping of 2 Boreholes | None | none | Progress report | 105472953 | 80444280.83
To reduce water services backlog with 90% by June 2022 | Elias Motsoaledi VIP Backlog Programme (Phase 2,3) | 16862 VIP units constructed | Number of VIP sanitation units to be constructed | 2100 VIP sanitation units to be constructed | 500 VIP units to be constructed | Not Achieved | 0 VIP units to be constructed | The contractors commenced the construction of Vip units late due to lack of cashflow | The contractors got paid for Site Establishment to enable them to start the construction of Vip units | Progress report | 30500000 | 1845927.85
To reduce water services backlog with 90% by June 2022 | Carbonitites to Zaaiplaas PH4(Dindela Reservoir) | Dindela Pump Station, Gravity Main and Rising Main. | Number of reservoirs constructed | 1 Reservoir Constructed | No activity | N/A | N/A | N/A | N/A | Progress report | R8, 000, 000. 00 | 0
To reduce water services backlog with 90% by June 2022 | Tubatse VIP Backlog Programme (Phase 2,3) | 16830 VIP units constructed | Number of VIP sanitation units constructed | 2000 VIP sanitation units to be constructed | 500 VIP units to be constructed | Not achieved | 0 VIP units to be constructed | No cession agreements were returned by learner contractors.Inflation and escalation on top structure impacted the number of units to be provided. | Learners intent to make advance payment outside cession. SDM will pay for material on site based on delivery note and cash payment. Number of units implementable after VIP unit cost adjustment 1500 | Progress report | 28000000 | 2155467.54
To reduce water services backlog with 90% by June 2022 | Motlailana, Makgemeng Water Supply | 2,57 km of bulk pipeline constructed. 5,66 km of reticulation water pipeline constructed. 1x 100kl elevated tank erected. | Kilometers of bulk line constructed. Kilometers of reticulation constructed. Number of yard connection. Number of steel tanks erected. Number of concrete reservoirs constructed. Number of pumphouses constructed. Number of boreholes refurbished. | (5,16 Kilometers for bulk line constructed 36,87Kilometers of reticulation constructed. 520 yard connection. 1x steel tank erected. 0 x concrete reservoirs constructed. 4 pumphouses constructed. 4 boreholes refurbished) | 1Kilometers for bulk line constructed 10Kilometers of reticulation constructed. 260 yard connection. 0 concrete reservoirs constructed. 0 pumphouses constructed. 0 boreholes refurbished. | Not Achieved | 0.5 Kilometers for bulk line constructed 16.3Kilometers of reticulation constructed. 0 yard connection. 0 concrete reservoirs constructed. 3 pumphouses constructed. 3 boreholes refurbished. | Continuous stoppage by the community forum depanding work. | continuous ISD intervation and resolving the issues. | Progress report | 29409971 | 12683237.37
To reduce water services backlog with 90% by June 2022 | Malekana Regional Water Scheme | Ga-Malekana 12Ml Water Treatment Works | Kilometers of water pipeline constructed and number of reservior completed | 14 kilometres of water pipeline constructed and 4 reservoirs completed | 4 kilometres of water pipeline constructed and 4 reservoirs completed | Not Achieved | 2 kilometres of water pipeline constructed and 0 reservoirs completed | Continuous stoppage by the community/Laborers due to Late payments and allocation of work | ISD to engage with business forums | Progress report | 67458474.26 | 29762987.85
To reduce water services backlog with 90% by June 2022 | Lebalelo South connector pipes and reticulations | 100km of connector pipes and reticulation pipelines constructed and 3 steel tanks completed | Number of steel tanks erected | 11 steel tanks erected | Testing and Commissioning | Not Achieved | Testing and Commissioning not done | Continuous stoppage by the community/Laborers due to Late payments of Subcontractors/ Laborers | Cessions signed to pay the subcontractors directly from the municipality | Progress report | 32748439 | 1123772.35
To reduce water services backlog with 90% by June 2022 | Lebalelo South: Phase 3 (Ga- Maroga and Motlolo Bulk and Reticulation Infrastructure | 12,6 kilometres of bulk line constructed. 23,4km reticulation pipeline constructed. 8 reservoirs constructed. 1 package plant constructed. 6 boreholes refurbished. | Kilometers of bulk line constructed. Kilometers reticulation pipeline constructed. Number of WTW Constructed. Number of borehole refurbished. | 10 Kilometers of bulk line constructed. 50 Kilometers reticulation pipeline constructed. 1 WTW Constructed. 3 borehole refurbished. | 2 Kilometers of bulk line constructed. 16 Kilometers reticulation pipeline constructed. 0 WTW Constructed. | Achieved | 4 Kilometers of bulk line constructed. 16.54Kilometers reticulation pipeline constructed. 0 WTW Constructed. | none | none | Progress report | 76801860.18 | 60369388.54
To construct water pipeline, reservoir and pump station in Ga Maphopha by 2022 | Ga Maphopha Command reservoir | 12ML Ga-Malekana Water Treatment Works, Malekana Bulk pipeline constructed | Number of command resservoir tested and commissioned | 1 command resservoir tested and commissioned | No activity | N/A | N/A | N/A | N/A | Progress report | 400000 | 0
To reduce water services backlog with 90% by June 2022 | Legolaneng Water Supply | GEOHYDROLOGICAL REPORTS | Number of borehole drilled and equiped | 1 borehole drilled and equiped | 1 borehole drilled and equiped | Not Achieved | none | Contractor abandoned the site | Letter of intention to terminate has been issued to the contractor | Progress report | 27284034.02 | 4092479.12
| Brooklyn water supply | GEOHYDROLOGICAL REPORTS | Number of steel tank installed | 1 steel tank installed | 1 steel tank installed | Not achieved | Steel Tank not installed | Delay in installation of steel tank | Submit extension of time for end of April 2022 | Progress report
| Polaseng Water Intervetion | GEOHYDROLOGICAL REPORTS | Number of borehole installed and equiped | 1 borehole installed and equiped | 1 borehole installed and equiped | Not Achieved | Borehole installed but not equipped | Connection of electrical cable to commission the pumps | Project will be completed as soon as the pumps are connected | Progress report
| Mahlokwena (Malaeneng) water intervention | GEOHYDROLOGICAL REPORTS | Number of borehole equiped and steel tank installed | 1 borehole equiped and 1 steel tank installed | 1 borehole equiped and 1 steel tank installed | Not Achieved | Equiped borehole and install steel tank not complete | Delay in installation of steel tank | Submit extension of time for end of April 2022 | Progress report
| Kgotlopong water intervention | GEOHYDROLOGICAL REPORTS | Number of borehole equiped and pipeline distribution installed | 1 borehole equiped and 1 pipeline distribution installed | 1 borehole equiped and 1 pipeline distribution installed | Not Achieved | none | Community disruption due to request the demand that SDM extend the scope to cover other sections | PMU Support to assist with intervention | Progress report
| Tshikanoshi Water Supply | GEOHYDROLOGICAL REPORTS | Number of borehole equiped and pipeline distribution installed | 1 borehole equiped and 1 pipeline distribution installed | 1 borehole equiped and 1 pipeline distribution installed | Not Achieved | none | Source own funding | Memo for own funding | Progress report
| Sephaku Water Supply | GEOHYDROLOGICAL REPORTS | Number of borehole equiped and pipeline distribution installed | 1 borehole equiped and 1 pipeline distribution installed | 1 borehole equiped and 1 pipeline distribution installed | Not Achieved | none | Contractor under-priced | Contractor withdrew/ surrender from the project | Progress report
| Eenzaam water supply | GEOHYDROLOGICAL REPORTS | Number of borehole equiped and pipeline distribution installed | 1 borehole equiped and 1 pipeline distribution installed | 1 borehole equiped and 1 pipeline distribution installed | Not Achieved | none | Contractor under-priced | Contractor withdrew/ surrender from the project | Progress report
COMMUNITY SERVICES
MUNICIPAL HEALTH SERICES
To Have an improved, clean, healthy and sustainable environment through municipal health services package by June 2022 | Environmental Pollution Prevention | 24 Awareness Campaigns on Air Quality conducted | Number of Awareness Campaigns on Air Quality conducted | 24 Awareness Campaigns on Air Quality conducted | 6 Awareness Campaigns on Air Quality conducted | Achieved | 9 Awareness Campaigns on Air Quality conducted | None | None | Report and Attendance register | R208,200.00
| Water quality monitoring | 300 Water quality samples collected | Number of Water quality samples collected | 300 Water quality samples collected | 75 Water quality samples collected | Achieved | 122 Water quality samples collected | None | None | Water Quality samples Reports | R89,507.26
| Food Safety control | 1500 Food Premises evaluated | Number of Food Premises evaluated | 1500 Food Premises evaluated | 375 Food Premises evaluated | Achieved | 386 Food Premises evaluated | None | None | Signed Assessment forms including the agent signature | R57,932.69
| Waste Management | 100 Health care risk waste monitored | Number of Health care risk waste monitored | 100 Health care risk waste monitored | 25 Health care risk waste monitored | Achieved | 28 Health care risk waste monitored | None | None | Signed Assessment forms including the agent signature | R208,200.00
| Health Surveillance of premises | 1500 premises evaluated | Number of premises evaluated | 1500 premises evaluated | 375 premises evaluated | Achieved | 391 premises evaluated | None | None | Signed Assessment forms including the agent signature | R0.00
| Surveillance and prevention of communicable diseases | 100 awareness campaigns on Communicable diseases held | Number of awareness campaigns on Communicable diseases held | 100 awareness campaigns on Communicable diseases held | 25 awareness campaigns on Communicable diseases held | Achieved | 28 awareness campaigns on Communicable diseases held | None | None | Report and attendance register | R20,820.00
| Communicable diseases outbreak control | 127 communicable diseases investigated and controlled | Number of Communicable disease outbreaks traced | All reported Communicable disease outbreaks traced | All reported Communicable disease outbreaks traced | Achieved | All (42) Communicable disease cases reported | None | None | Reports | R2,528,423.48
| Vector Control | 1500 inspections on Vector Control on premises conducted | Number of inspections on Vector Control on premises conducted | 1500 inspections on Vector Control on premises conducted | 375 inspections on Vector Control on premises conducted | Achieved | 386 inspections on Vector Control on premises conducted | None | None | Signed Assessment forms including the agent signature | R 43,661.62
| Disposal of the dead | 100 evaluations on Disposal of the Dead facilities conducted | Number of evaluations on Disposal of the Dead facilities conducted | 100 evaluations on Disposal of the Dead facilities conducted | 25 evaluations on Disposal of the Dead facilities conducted | Achieved | 27 evaluations on Disposal of the Dead facilities conducted | None | None | Signed Assessment forms including the agent signature | R0.00
| Chemical Safety | 369 evaluations on safety to chemical handling premises conducted | Number of evaluations on safety to chemical handling premises conducted | 300 evaluations on safety to chemical handling premises conducted | 75 evaluations on safety to chemical handling premises conducted | Achieved | 90 evaluations on safety to chemical handling premises conducted | None | None | Signed Assessment forms including the agent signature | R0.00
EMERGENCY MANAGEMENT SERVICES
To protect loss of life, damage to property and environment by June 2022 | Fire and Rescue Operations | 332 reported emergency incidents attended | Number of reported emergency incidents attended | All reported emergency incidents attended | All reported emergency incidents attended | Achieved | All 96 reported Emergency Services incidents attended | None | None | Call Register and Report | R0.00
| Emergency Management Services Training Academy | 3 firefighting courses facilitated | Number of firefighting courses facilitated | 3 firefighting courses facilitated | 1 firefighting course facilitated | Achieved | All 3 firefighting course facilitated | None | None | Attendance Register and Report | R223 671,00
| Fire Prevention and Safety | 369 fire prevention and safety services provided | Number of fire prevention and safety services provided | All Fire prevention and safety services provided | All Fire prevention and safety services provided | Achieved | All 202 fire safety and prevention services provided | None | None | Call Register and Report | R0.00
DISASTER MANAGEMNET SERVICES
To protect loss of life, damage to property and environment by June 2022 | Disaster risk assessment | 198 disaster risk incidents assessed | Number of all reported disaster incidents attended | All reported disaster Management incidents | All reported disaster risk management incidents attended | Achieved | All (34) reported disaster management incidents attended | 3 | None | Register of disaster incidents | R291 480, 00
| Disaster risk reduction | 42 disaster risk reduction awareness campaigns conducted | Number of disaster risk awareness campaigns conducted | 24 disaster risk awareness campaigns conducted | 6 disaster risk reduction awareness campaigns conducted | Achieved | 14 disaster risk reduction awareness campaigns conducted | None | None | Attendance registers | R0 00
| Response and recovery | 198 disaster incidents responded | Number of all reported disaster response and recovery attended to | All reported disaster response and recovery attended to | All reported disaster response and recovery operations attented to | Achieved | All (34) reported disaster response and recovery attended to | None | None | Report | R0 00
| Disaster Management plan and framework review | Disaster management plan and framework in place | Number of disaster management plan and framework reviewed | 1 disaster management plan and framework reviewed | Consolidation of Stakeholder inputs | Achieved | Disaster Management plan and Framework review stakeholder inputs consolidated | None | None | Reviewed disaster management plan and framework | R0 00
| Special operations on high density days | 3 special operations on high density days campaigns coordinated | Number of special operations on high density days campaigns coordinated | 3 special operations on high density days campaigns coordinated | 1 special operations high density campaigns coordinated | No Activity | No Activity | None | None | Operational plan and attendance register | R0 00