## Sheet1
2021/2022 ANNUAL PERFORMANCE REPORT
BASIC SERVICE DELIVERY
OBJECTIVES | PROJECT | BASELINE 2020/2021 | INDICATORS | ANNUAL TARGET 2021/2022 | PROGRESS ACHIEVED/NOT ACHIEVED | ANNUAL ACTUAL PROGRESS | CHALLENGES | REMEDIAL | POE | BUDGET 2021-2022
INFRASTRUCTURE AND WATER SERVICES
OPERATION AND MAINTENANCE (O&M)
To resolve registered sanitation incidents within 14 days. | Sanitation incidents | 700 registered sanitation incidents resolved within 14 days | Number of registered sanitation incidents resolved within 14 days | 700 registered sanitation incidents resolved within 14 days | Achieved | 810 registered sanitation incidents resolved within 14 days | None | None | Incident Report | 52,048,895,51
To resolve registered water incidents within 14 days. | Water incidents | 5000 registered water incidents resolved within 14 days | Number of registered water incidents resolved within 14 days | 4500 registered water incidents resolved within 14 days | Not achieved | 3 817 registered water incidents resolved within 14 days | Due to non availability of funds and No spares to resolved incidents | Avail funds for new financial year, | Incident Report
To purchase Bulk water by June 2022 | Bulk Water Purchases | 16 500Mℓ of water purchased | Number of Mℓ water purchased | 16 500Mℓ of water purchased | Not achieved | 13 575Mℓ of water purchased | Due to non functionality of infrastructure as the result of non availability of funds | Avail funds for new financial year to improve water supply | Summary Meter readings report. | 135, 330,000
To develop water sources in areas that does not have infrastructure and replace dried boreholes by June 2022 | Ground Water Development | New Program | Number of ground water source developed | 20 Ground water source developed (boreholes) | Achieved | 20 Ground water source developed (boreholes) | None | None | Progress Reports | 10757256.78
To purchase electricity by June 2022 | Electricity Usage | 1200 KWH of Electricity used | Number of KWH electricty used | 10 000 000 KWH of Electricity used | Achieved | 10,8 000 000 KWH of Electricity used | None | None | Summary Electrical Meter readings report. | 40000000
RURAL ROADS ASSET MANAGEMENT SYSTEM (RRAMS)
To Develop 80% of Road Asset Management System by June 2022 | Development of Rural Roads Asset Management System | Desk top studies and the first rounds of Visual Conditions Assessments | Number of kilometres of Roads assessed | 500 kilometres of Roads assessed | Not Achieved | 0 kilometres of Roads assessed | Delay in Appointment of Professional Service Provider | Fastrack the appointment of sevice provider by end of 1st quarter of 2022/2023 financial year | Progress report | 2, 437, 000. 00
|  |  | Number of traffic counting stations completed. | 200 traffic counting stations completed | Not Achieved | 0 traffic counting stations completed | Delay in Appointment of Professional Service Provider | Fastrack the appointment of sevice provider by end of 1st quarter of 2022/2023 financial year
REGIONAL BULK INFRASTRUCTURE GRANT (RBIG)
To reduce water services backlog with 90% by June 2022 | Mooihoek bulk water supply phase 4F1 | 1 Kilometers of bulk water pipeline and concrete reservoirs constructed | Number of km of bulk pipeline tested and commissioned | 1km of bulk pipeline tested and commissioned | Achieved | 1km of bulk pipeline tested and commissioned | None | None | Progress report | R94 645 000. 00
To reduce water services backlog with 90% by June 2022 | Construction of Mooihoek bulk water supply phase G1.1 | 1 X 5 Ml concrete reservoir completed Phase 4BA | Number of km of bulk pipeline and package plant constructed | Construction of 3 Kilometres of bulk water supply pipeline. Construction of 1 package plant type clarifier | Not Achieved | Procurement of service provider not done | Project delayed due to the contractor not being able to proceed with the work caused by underpricing | The contractor surrendered the project and termination currently being finalised through SDM Legal, new contractor to be appointed in the new financial year | Progress report
To reduce water services backlog with 90% by June 2022 | Construction of Mooihoek bulk water supply phase G1.2 | 1 X 5 Ml concrete reservoir completed Phase 4BA | Number of km of bulk pipeline constructed | Construction of 4.7 Kilometers of bulk water supply pipeline. | Not Achieved | 1.88 Kilometers of bulk water supply pipeline constructed | Contractor running behind program due to cashflow problems | Revised program of works with cashflow projections has been submitted | Progress report
To reduce water services backlog with 90% by June 2022 | Construction of Mooihoek bulk water supply phase G2 | 17km of bulk water supply pipeline completed | Number of km of bulk pipeline and KL of reinforced concrete rserviour constructed | Construction of 4.9 Kilometres of bulk water supply pipeline. Construction of 500KL Reinforced Concrete Reservoir | Achieved | Construction of 4.9 Kilometres of bulk water supply pipeline. Construction of 500KL Reinforced Concrete Reservoir | None | None | Progress report
To reduce water services backlog with 90% by June 2022 | Construction of Mooihoek Reservoirs phase 4H1 | 12Ml/day Mooihoek Water Treatment Works | Number of Reservoir constructed | 1 Reservoir constructed | Not Achieved | No progress | Procurement of service provider not done | Available budget sufficient to start with this project in the 2022/2023 | Progress report
To reduce water services backlog with 90% by June 2022 | Construction of Mooihoek Reservoirs phase 4H2 | 12Ml/day Mooihoek Water Treatment Works | Number of Reservoir constructed | 1 Reservoir constructed | Not Achieved | No progress | Procurement of service provider not done | Available budget sufficient to start with this project in the 2022/2023 | Progress report
To reduce water services backlog with 90% by June 2022 | Nebo BWS Commission Jane Furse Pipeline | Nebo Phase1A completed and not commissioned | Number of Kilometers of bulk water supply pipeline tested and commissioned | 18 Kilometers of bulk water supply pipeline tested and commissioned | Not achieved | No progress | No service providers appointed yet for the refurbishment and commissioning | Tender advertised and closed. Appointment of PSP to be finaalised by end of 1st quarter 2022/2023 financial year. | Progress report | R50, 000, 000. 00
To reduce water services backlog with 90% by June 2022 | Nebo BWS Jane Furse to Lobethal Bulk Water Supply | 18km's of bulk water supply pipe line phase two from Jane Furse to Lobethal completed | Number of km's of bulk water supply pipeline assessed | 18km of bulk water supply pipeline assessed | Not achieved | No progress | Project could not implemented due to insufficient budget under the Nebo scheme | Project planned for the 2023/24 FY | Progress report
To reduce water services backlog with 90% by June 2022 | Nebo BWS Makgeru to Schoonoord BWS | 18.2 Km of Schoonoord bulk water supply pipeline in Makgeru. 10ML Command Concrete Reservoir in Schoonoord constructed | Number of Km of bulk water supply pipelines constructed | 6.4Km of bulk water supply pipeline constructed | Not achieved | 0Km of bulk water supply pipeline constructed | Additional professional fees required to complete the project exceeds 20% threshold as set by National Treasury Approximately R20 million additional funds required by contractor to complete the project Approved contract period lapsed | Request submitted to Treasury for advise which currently we awaits response from Treasury on how Council should move forward with the approval Submission needs to go through Council since the overall requested VO amount exceeds the 20% threshold Extension of time request undergoing approval processes within SDM | Progress report
To reduce water services backlog with 90% by June 2022 | Moutse BWS Project 13 & 14 | 1 WTW in Groblersdal extended in Project 1 and 1 pump station constructed in Project 6 | Number of mechanical and Electrical (M & E) components installed for the extensions to the Groblersdal Water Treatment Works and pump station | 2 mechanical and Electrical (M & E) components installed for the extensions to the Groblersdal Water Treatment Works and pump station | Not achieved | 0 Mechanical and Electrical (M & E) Groblersdal Water Treatment Work 0 clarifiers and 0 Filters refurbished | The SLA expired and could not be reviewed on time. | Approve the revised SLA by end of 1st quarter 2022/2023 financial year. | Progress report | R80, 000, 000. 00
| Moutse BWS Project (7 to 12) | 30 Kilometre of bulk water supply pipeline constructed | Number of Kilometres of bulk water supply pipeline installed and tested | 20Kilometre of bulk water supply pipeline installed and tested | Not achieved | 15 Kilometre of bulk water supply pipeline installed, tested & commissioned | The SLA expired and could not be reviewed on time. | Approve the revised SLA by end of 1st quarter 2022/2023 financial year. | Progress report
| Moutse BWS construction bulk water pipeline project(2-4) | 19km of bulk water supply pipeline constructed | Number of km of bulk water supply pipelines assessed and refurbished | 14 km of bulk water supply pipelines assessed and refurbished | Not achieved | 0 km of bulk water supply pipelines assessed and refurbished | Appoint consultant | Tender advertised and closed. Appointment of PSP to be finaalised by end of 1st quarter 2022/2023 financial year. | Progress Report
WATER SERVICES INFRASTRUCTURE GRANT (WSIG)
To reduce water services backlog with 90% by June 2022 | Maebe Drilling and Equipping of Borehole | Three (3) drilled and equipped boreholes and bulk pipeline. | Number of pump station constructed, package plant and storage tank installed | 1 Pump station constructed and 1 Reverse Osmosis Water Treatment Package Plant and 1 storage tank installed | Not Achieved | 0 Pump station constructed and 0 Reverse Osmosis Water Treatment Package Plant and 0 storage tank installed | No contractor appointed due to Insufficient budget | Project is budgeted for in 2022/2023 FY | Progress Report / Completion Certificate | R13, 000, 000. 00
| Tukakgomo RDP Section Borehole | 3.75 Km of water distribution network constructed and 1 raw water abstraction point upgraded | Number of kilometres of network constructed and water meters installed | 7 Km of water distribution network constructed and 735 water meters installed | Not achieved | 1823m of water distribution network completed and 668 water meters installed | Delay in Appointment of SDM as an implementing agent by DWS | Project is budgeted for in 2022/2023 FY | Progress Report / Completion Certificate | R9, 000, 000. 00
| Nkosini Water Supply & Package Plant | 1 scoping report and business plans | Number of kilometres of pipeline constructed and protection of abstraction point and sealing of the reservoir | 3.5km of pipeline constructed and 1 protection of abstraction and sealing of 1 reservoir | Not Achieved | 0km of pipeline constructed and 0 protection of abstraction done and 0 reservoir sealed | No contractor appointed due to Insufficient budget | Project is budgeted for in 2022/2023 FY | Progress Report / Completion Certificate | R8, 000, 000. 00
| Laersdrift Water Supply Intervention | 1 Scoping Report and Business Plan | Number of kilometres of network constructed and stand pipes and storage tank installed | 8 km reticulation network constructed, 22 communal stand pipes and 1 storage tank installed | Not Achieved | 0 km reticulation network constructed, 0 communal stand pipes and 0 storage tank installed | No contractor appointed due to Insufficient budget | Project is budgeted for in 2022/2023 FY | Progress Report / Completion Certificate | R9, 000, 000. 00
| Phokwane/Brooklyn Water Supply | Drilling, testing and equipping of 1 and rising main and 1 storage tank. | Number of kilometres of rising main and storage tank installed | 3km of rising main and 1 elevated tank | Not Achieved | 0km of rising main constructed and 0 elevated tank constructed | No contractor appointed due to Insufficient budget | Project is budgeted for in 2022/2023 FY | Progress Report / Completion Certificate | R4, 000, 000. 00
| Legolaneng VDIP | 410 VDIP Toilets | Number of VDIP completed | 440 VDIP completed | Not Achieved | 0 VDIP completed | No contractor appointed due to Insufficient budget | Project is budgeted for in 2022/2023 FY | Progress Report / Completion Certificate | R7, 000, 000. 00
MUNICIPAL INFRASTRUCTURE GRANT(MIG)
To reduce water services backlog with 90% by June 2022 | Fetakgomo VIP Backlog Programme (Phase 2,3) | 15330 VIP units constructed | Number of VIP units constructed | 500 VIP units to be constructed | Not achieved | 279 units constructed | 1. Allocated units are less than the annual target | The balance(backlog) will be implemented in the next project | Progress report | 8100000
To reduce water services backlog with 90% by June 2022 | Ephraim Mogale VIP Backlog Programme (Phase2,3 ) | 15730 VIP units constructed | Number of VIP units constructed | 958 VIP units to be constructed | Not Achieved | 747 VIP units to be constructed | 1. Allocated units are less than the annual target | The balance(backlog) will be implemented in the next project | Progress report | 13000000
To reduce water services backlog with 90% by June 2022 | Makhuduthamaga VIP Backlog Programme | 16096 VIP units constructed | Number VIP sanitation units to be constructed | 2300 VIP sanitation units to be constructed | Not Achieved | 1535 VIP units completed | Late commencement on construction due to non compliance of Supply Chain requirements | Contractors are now SARS and COIDA compliant,extention of time to be granted for completion of all the 2300 VIPs | Progress report | 32500000
To reduce water services backlog with 90% by June 2022 | De Hoop/Nebo Plateau/Schoonoord Water Scheme Villages:Ga –Mogashoa (Senkapudi) and Ga- Mogashoa (Manamane) | 94,6 kilometres of water pipeline constructed | Number of water reticulation pipeline constructed | 11 Kilometers of water reticulation pipeline constructed | Not Achieved | 4 Kilometers of water reticulation pipeline constructed | Contractor behind schedule due to insufficient material on site | Consultant to meet with the contractor to discuss issues of outstanding material and expediting procurement thereafter. Most of the outstanding material has since been procurred and construction progressing | Progress report | R4, 762, 404. 00
To reduce water services backlog with 90% by June 2022 | NSD07 Regional Water Scheme Construction of Concrete Reservoirs | 3km of bulk pipeline constructed 1 Reservoir completed | No of Kilometres of bulk pipeline constructed Number of reservoir completed | 13 Kilometres of bulk pipeline constructed, 3 reservoirs completed | Not Achieved | 0,1 Kilometres of bulk pipeline constructed, 0 reservoirs completed | Late payments of subcontractors lead to project stoppage and delays | Contractor got into an agreement with the concerned groups and managed to make outstanding payments, work has resumed on site | Progress report | 19121865
To reduce water services backlog with 90% by June 2022 | De Hoop/Nebo Plateau/Schoonoord Water Scheme Villages: Makgeru, Ga Ratau & Matekane | 6 Kilometres of bulk pipeline constructed. 98 km of water reticulation pipeline 2435 metered stand pipes Equipping of two boreholes | Number of Kilometres of bulk pipeline constructed. Number of kilometers of Reticulation. Number of Standpipes constructed. Number of Water Meters Installed Number of boreholes equiped. | 6 Kilometres of bulk pipeline constructed. 72 kilometers of Reticulation. 850 Standpipes constructed. 850 Water Meters Installed Equipping of two boreholes. | Achieved | 6 Kilometres of bulk pipeline constructed. 76.890 kilometers of Reticulation. 1285 Standpipes constructed. 1285 Water Meters Installed Equipping of two boreholes. | None | None | Progress report | 105472953
To reduce water services backlog with 90% by June 2022 | Elias Motsoaledi VIP Backlog Programme (Phase 2,3) | 16862 VIP units constructed | Number of VIP sanitation units to be constructed | 2100 VIP sanitation units to be constructed | Not achieved | 2066 VIIP units constructed | 1. Allocated units are less than the annual target | The balance(backlog) will be implemented in the next project | Progress report | 30500000
To reduce water services backlog with 90% by June 2022 | Carbonitites to Zaaiplaas PH4(Dindela Reservoir) | Dindela Pump Station, Gravity Main and Rising Main. | Number of reservoirs constructed | 1 Reservoir Constructed | Not Achieved | None | Contractor terminated | Appoint a new contractor by end of the 1st quarter 2022/2023 financial year. | Progress report | R8, 000, 000. 00
To reduce water services backlog with 90% by June 2022 | Tubatse VIP Backlog Programme (Phase 2,3) | 16830 VIP units constructed | Number of VIP sanitation units constructed | 2000 VIP sanitation units to be constructed | Not Achieved | 1731 VIP Constructed | 1. Allocated units are less than the annual target | The balance(backlog) will be implemented in the next project | Progress report | 28000000
To reduce water services backlog with 90% by June 2022 | Motlailana, Makgemeng Water Supply | 2,57 km of bulk pipeline constructed. 5,66 km of reticulation water pipeline constructed. 1x 100kl elevated tank erected. | No of Kilometers of bulk line constructed No of Kilometers of reticulation constructed. Number ofyard connecion. Number of steel tanks erected. Number of concrete reservoirs constructed. Number of pumphouses constructed. Number of boreholes refurbished. | 5,16 Kilometers for bulk line constructed 36,87 Kilometers of reticulation constructed. 520 yard connection. 1x steel tank erected. 0 x concrete reservoirs constructed. 4 pumphouses constructed. 4 boreholes refurbished) | Not Achieved | 0.5 Kilometers for bulk line constructed 44.6Kilometers of reticulation constructed. 0 yard connection. 1x steel tank erected. 0 x concrete reservoirs constructed. 4 pumphouses constructed. 4 boreholes refurbished) | ongoing disruption from the community forum or small business people demanding work | ISD attending to the issues and resolving them as and when they eminate | Progress report | R29 409 971.00
To reduce water services backlog with 90% by June 2022 | Malekana Regional Water Scheme | Ga-Malekana 12Ml Water Treatment Works | No of Kilometers of water pipeline constructed and number of reservior completed | 14 kilometres of water pipeline constructed and 4 reservoirs completed | Not Achieved | 11.61 kilometres of water pipeline constructed and 0 reservoirs completed | Delays due to social challenges on site regarding sub-contracting of work to local business forums | ISD to engage local business forums. SDM to develop sub-contracting policy. | Progress report | 67458474
To reduce water services backlog with 90% by June 2022 | Lebalelo South connector pipes and reticulations | 100km of connector pipes and reticulation pipelines constructed and 3 steel tanks completed | Number of steel tanks erected | 11 steel tanks erected | Achieved | 11 steel tanks erected | None | None | Progress report | 32748439
To reduce water services backlog with 90% by June 2022 | Lebalelo South: Phase 3 (Ga- Maroga and Motlolo Bulk and Reticulation Infrastructure | 12,6 kilometres of bulk line constructed. 23,4km reticulation pipeline constructed. 8 reservoirs constructed. 1 package plant constructed. 6 boreholes refurbished. | No of Kilometers of bulk line constructed. Kilometers reticulation pipeline constructed. Number of WTW Constructed.Number of borehole refurbished | 10 Kilometers of bulk line constructed. 50 Kilometers reticulation pipeline constructed. 1 WTW Constructed. 3 borehole refurbished. | Not Achieved | 4.2 Kilometers of bulk line constructed. 24.294 Kilometers reticulation pipeline constructed. 0 WTW Constructed. 0 borehole refurbished. | Late delivery of materials , late payments of subcontractors lead to project stoppage and delay. | ISD attending to the issues and all payments done by end of July 2022 | Progress report | 76801860
To construct water pipeline, reservoir and pump station in Ga Maphopha by 2022 | Ga Maphopha Command reservoir | 12ML Ga-Malekana Water Treatment Works, Malekana Bulk pipeline constructed | Number of command reservior tested and commissioned | 1 command reservior tested and commissioned | Not Achieved | Testing and commissioning of the command reservoir not done | Non payment due to budget constraints. Repairs to be done on the rising main | Process payment and instruct contractor to resume work | Progress report | 400000
To reduce water services backlog with 90% by June 2022 | Legolaneng Water Supply | GEOHYDROLOGICAL REPORTS | Number of borehole drilled and equiped | 1 borehole drilled and equiped | Not Achieved | 0 borehole drilled and equiped | Delay to electrify the borehole by ESKOM | Constant engagement/follow ups are being made with ESKOM | Progress report | 27284034
| Brooklyn water supply | GEOHYDROLOGICAL REPORTS | Number of steel tank installed | 1 steel tank installed | Not Achieved | 0 steel tank installed | Tank is still under construction | Tank will be installed in July 2022 | Progress report
| Polaseng Water Intervetion | GEOHYDROLOGICAL REPORTS | Number of borehole installed and equiped | 1 borehole installed and equiped | Achieved | 1 borehole installed and equiped | none | none | Progress report
| Mahlokwena (Malaeneng) water intervention | GEOHYDROLOGICAL REPORTS | Number of borehole equiped and steel tank installed | 1 borehole equiped and 1 steel tank installed | Not Achieved | 0 borehole equiped and 0 pipeline distribution installed | Contractor not competent | Contractor to be put on terms | Progress report
| Kgotlopong water intervention | GEOHYDROLOGICAL REPORTS | Number of borehole equiped and pipeline distribution installed | 1 borehole equiped and 1 pipeline distribution installed | Not Achieved | 0 borehole equiped and 0 pipeline distribution installed | community has indicated they need a project to include additional scope of works they have identified | Management is currentlying evaluating the claim | Progress report
| Tshikanoshi Water Supply | GEOHYDROLOGICAL REPORTS | Number of borehole equiped and pipeline distribution installed | 1 borehole equiped and 1 pipeline distribution installed | Not achieved | 0 borehole equiped and 0 pipeline distribution installed | no water supply source | Management is currently evaluating the claim to increase funding for addional works | Progress report
| Sephaku Water Supply | GEOHYDROLOGICAL REPORTS | Number of borehole equiped and pipeline distribution installed | 1 borehole equiped and 1 pipeline distribution installed | Not Achieved | 0 borehole equiped and 0 pipeline distribution installed | contractor withdrawal due to under quoting | Submitted a business and technical report for approval by DWS. | Progress report
| Eenzaam water supply | GEOHYDROLOGICAL REPORTS | Number of borehole equiped and pipeline distribution installed | 1 borehole equiped and 1 pipeline distribution installed | Not Achieved | 0 borehole equiped and 0 pipeline distribution installed | contractor withdrawal due to under quoting | Submitted a business and technical report for approval by DWS. | Progress report
Acting Director IWS
Date
COMMUNITY SERVICES
MUNICIPAL HEALTH SERICES
To Have an improved, clean, healthy and sustainable environment through municipal health services package by June 2022 | Environmental Pollution Prevention | 24 Awareness Campaigns on Air Quality conducted | Number of Awareness Campaigns on Air Quality conducted | 24 Awareness Campaigns on Air Quality conducted | Achieved | 29 Awareness Campaigns on Air Quality conducted | None | None | Report and Attendance register | R208,200.00 | 160255.27
| Water quality monitoring | 300 Water quality samples collected | Number of Water quality samples collected | 300 Water quality samples collected | Achieved | 322 Water quality samples collected | None | None | Water Quality samples Reports | R89,507.26 | 53800
| Food Safety control | 1500 Food Premises evaluated | Number of Food Premises evaluated | 1500 Food Premises evaluated | Achieved | 1532 Food Premises evaluated | None | None | Signed Assessment forms including the agent signature | R57,932.69 | 0
| Waste Management | 100 Health care risk waste monitored | Number of Health care risk waste monitored | 100 Health care risk waste monitored | Achieved | 105 Health care risk waste monitored | None | None | Signed Assessment forms including the agent signature | R208,200.00 | 0
| Health Surveillance of premises | 1500 premises evaluated | Number of premises evaluated | 1500 premises evaluated | Achieved | 1537 premises evaluated | None | None | Signed Assessment forms including the agent signature | R0.00 | 0
| Surveillance and prevention of communicable diseases | 100 awareness campaigns on Communicable diseases held | Number of awareness campaigns on Communicable diseases held | 100 awareness campaigns on Communicable diseases held | Achieved | 108 awareness campaigns on Communicable diseases held | None | None | Report and attendance register | R20,820.00 | 36 100.00
| Communicable diseases outbreak control | 127 communicable diseases investigated and controlled | Number of Communicable disease outbreaks traced | All reported Communicable disease outbreaks traced | Achieved | All 43 reported Communicable disease cases traced | None | None | Reports | R2,528,423.48 | 44953
| Vector Control | 1500 inspections on Vector Control on premises conducted | Number of inspections on Vector Control on premises conducted | 1500 inspections on Vector Control on premises conducted | Achieved | 1526 inspections on Vector Control on premises conducted | None | None | Signed Assessment forms including the agent signature | R 43,661.62 | 00.00
| Disposal of the dead | 100 evaluations on Disposal of the Dead facilities conducted | Number of evaluations on Disposal of the Dead facilities conducted | 100 evaluations on Disposal of the Dead facilities conducted | Achieved | 125 evaluations on Disposal of the Dead facilities conducted | None | None | Signed Assessment forms including the agent signature | R0.00 | 0
| Chemical Safety | 369 evaluations on safety to chemical handling premises conducted | Number of evaluations on safety to chemical handling premises conducted | 300 evaluations on safety to chemical handling premises conducted | Achieved | 336 evaluations on safety to chemical handling premises conducted | None | None | Signed Assessment forms including the agent signature | R0.00 | 0
EMERGENCY MANAGEMENT SERVICES
To protect loss of life, damage to property and environment by June 2022 | Fire and Rescue Operations | 332 reported emergency incidents attended | Number of reported emergency incidents attended | All reported emergency incidents attended | Achieved | All 560 reported emergency incidents attended. | None | None | Call Register and Report | R0.00 | 0
| Emergency Management Services Training Academy | 3 firefighting courses facilitated | Number of firefighting courses facilitated | 3 firefighting courses facilitated | Achieved | 3 firefighting courses facilitated. | None | None | Attendance Register and Report | R223 671,00 | 84469
| Fire Prevention and Safety | 369 fire prevention and safety services provided | Number of fire prevention and safety services provided | All Fire prevention and safety services provided | Achieved | All 714 Fire Prevention and Safety services provided. | None | None | Call Register and Report | R0.00 | 0
DISASTER MANAGEMNET SERVICES
To protect loss of life, damage to property and environment by June 2022 | Disaster risk assessment | 198 disaster risk incidents assessed | Number of all reported disaster incidents attended | All reported disaster Management incidents | Achieved | All 191 disaster management incidents attended | None | None | Register of disaster incidents | R291 480, 00 | R210 117.00
| Disaster risk reduction | 42 disaster risk reduction awareness campaigns conducted | Number of disaster risk awareness campaigns conducted | 24 disaster risk awareness campaigns conducted | Achieved | 40 disaster risk reduction awareness campaigns conducted | None | None | Attendance registers | R0 00 | 0
| Response and recovery | 198 disaster incidents responded | Number of all reported disaster response and recovery attended to | All reported disaster response and recovery attended to | Achieved | All(191) reported disaster response and recovery operations attended to | None | None | Report | R0 00 | 0
| Disaster Management plan and framework review | Disaster management plan and framework in place | Number of disaster management plan and framework reviewed | 1 disaster management plan and framework reviewed | Achieved | 1 Disaster management plan and Framework reviewed | None | None | Reviewed disaster management plan and framework | R0 00 | 0
| Special operations on high density days | 3 special operations on high density days campaigns coordinated | Number of special operations on high density days campaigns coordinated | 3 special operations on high density days campaigns coordinated | Achieved | 3 special operation on high density days campaigns coordinated | None | None | Operational plan and attendance register | R0 00 | 0
Director Community Services
Date: