## BTO
DRAFT SDBIP 2021/2022
KPA: FINANCIAL VIABILITY
2021 /2022 QUARETER 4 REPORT
FINANCIAL VIABILITY
MEASUABLE OBJECTIVES | PROJECT | BASELINE 2020/2021 | INDICATORS | ANNUAL TARGET 2021/2022 | Q4 | PROGRESS ACHIEVED/NOT ACHIEVED | ACTUAL PROGRESS | CHALLENGE | REMEDIAL | PORTFOLIO OF EVIDENCE | BUDGET 2021/2022
Manual GRAP Compliant FAR | Manual GRAP Compliant FAR | 100% accounting of assets | % accounting of assets | 100% accounting of assets | 100% fully functional fixed asset module | NOT ACHIEVED | 82% modules implemented on SOLAR | As the activities are dependent on BCX (i.e. service provider) there is only one consultant allocated to the municipality and it takes long to implement some of the activities. | Timely implementation of the outstanding modules. | Trial Balance/LG Portal Submission Reports | 4806000
| mSCOA implementation plan | 70% achievement of mSCOA implementation plan | % of activities on mSCOA implementation plan achieved | 100% of activities on mSCOA implementation plan achieved | 100% of all mSCOA modules fully operational by end of 4th Quarter | NOT ACHIEVED | 82% modules implemented on SOLAR | As the activities are dependent on BCX (i.e. service provider) there is only one consultant allocated to the municipality and it takes long to implement some of the activities. | Timely implementation of the outstanding modules. | Trial Balance/LG Portal Submission Reports | R0.00
To provide sound financial management | Functional budget steering committee | Credible budget prepared | Number of credible annual budgets prepared and implemented. | 2 Credible Annual Budgets prepared and implemented. | Credible 2022/23 Draft Annual Budget | Achieved | Credible 2022/23 Final Budget prepared and approved | None | None | Council resolutions/Draft Budget Documents | R0.00
| Procurement plan | 2020/2021 procurement plan in place | Number of procurement plan developed | 1 procurement plan developed | 1 procurement plan developed | Achieved | 1 procurement plan developed | NONE | NONE | Signed procurement plan | R0.00
| Irregular expenditure in the 2020/21 | Section 32 expenditure amount reported. | % Compliance with management of MFMA section 32 | 100% Compliance with management of MFMA section 32 | 4th Quarter reporting of UIF through Section 52 reports (Annexure A) | Achieved | 4th Quarter reporting of UIF through Section 52 reports (Annexure A) | None | None | Section 52 Report | 50000
| AFS preparations | Submission of AFS and APR to the AG within the legislated time frame | Compile AFS and APR within the legislated time frame | Compile AFS and APR within the legislated time frame | N/A | N/A | N/A | N/A | N/A | Signed AFS and APR/ Ackonwledgement of receipt by AGSA | R1 650 000
| Identification of potential areas to be billed | *Collections and Capturing of consumer Data from 5 areas identified for potential biling. *Billing of 5 identified areas for potential revenue | Number of areas with revenue potential to be billed | Collection of data and billing of 5 areas with revenue potential | Billing of 5 areas with potential to be billed | NOT ACHIEVED | Customer data have been collected in 5 areas which are potential billable | Awaiting the appointment of data cleansing provider to do cleansing before uploading in the billing system | Fast track the appointment of data cleansing provider | Data Collection report and Summary of billing reports | R5,000 000
| Meter reading | 74%% Verification and reading of 13100 customers' meters | % of customer's meters valitated and read | 75% Validation and reading of customers meters | 75% Validation and reading of customers meters | NOT ACHIEVED | 74,1% meter were validated and read | some of the copper meters were stolen in various areas | awaiting the appointment of provider to supply the plastic meters | Meter reading report | R7,500 000
| Billing of Customers | Billing of 80 % of 41133 customers | % of customers billed | 90% of 41200 customers to be billed | 90% of 41133 Customers to be billed | ACHIEVED | 91% which is 37431 customers were billed | some customers are without water meaters | awaiting the appointment of provider to supply the plastic meters | Billing report | 1500000
| Improve collection rate | Improve the collection rate to 75% | % improvement of collection rate | 75% of revenue collected against the billing | improvement of collection rate to 75% | NOT ACHIEVED | 49% revenue collection rate | Lack of internal capacity to effect disconnections of services | Appoint provider to do meter reading and disconnection | Collection rate report | 4500000
|  | R241m. debt book | % Reduction of debt book | 2% reduction of debt book | 2%reduction debt book | NOT ACHIEVED | 4% Increase in debt book | Lack of internal capacity to effect disconnections of services | Fast track appointment of provider to do meter reading and disconnection | Own revenue reports/Debtors age analysis report | R0.00
| Free basic services | Indigent register for 2020/2021 | % of indigent customers | 10% increase in indigent customers | 10%Collection of customers'indigent registration data | NOT ACHIEVED | Draft indigent register is awaiting verification | Awaiting the appointment of provider to do indigent verifiocations | Fast track the appointment of provider to do indigent verifications | Indigent register for 2021/2022 | 3000000
| Payment of creditors | 80% of valid, complete and received invoices paid ( 7 days before lapse of 30 days) | % of creditors paid within 30 days against all invoices | 100% payment of valid and complete received invoices | 100% payment of valid and complete received invoices | Achieved | 100% payment of valid and complete received invoices | None | None | Monthly Payment Report
| Personnel budget | 2020/2021 salaries paid by 25th and 3rd party payment paid on/before the 7th. | % payment of salaries 25th and 3rd party payment paid on/before the 7th. | 100% payment of salaries 25th and 3rd party payment paid on/before the 7th. | 100% payment of salaries 25th and 3rd party payment paid on/before the 7th. | Achieved | 100% payment of salaries 25th and 3rd party payment paid on/before the 7th. | None | None | Salaries Payment Vouchers
| Travel claims | 100% Travel claims paid by the 15th | % Travel claims to be paid by the 15th | 100% Travel claims to be paid by the 15th | 100% Travel claims to be paid by the 15th | Achieved | 100% Travel claims to be paid by the 15th | None | None | Payment Vouchers
13856000