## Sheet1
2021/2022 SERVICE DELIVERY BUDGET AND IMPLEMENTATION PLAN
GOOD GOVERNANCE AND PUBLIC PARTICIPATION
OBJECTIVES | PROJECT | BASELINE 2020/2021 | INDICATORS | ANNUAL TARGET 2021/2022 | Q3 TARGET | PROGRESS (Achieved/Not achieved) | ACTUAL PROGRESS | CHALLENGES | REMEDIAL ACTIONS | POE | BUDGET 2021-2022
INTERNAL AUDIT
To ensure improved internal controls and clean governance in the municipality by June 2022 | Development of the Three(3) Years rolling Plan | Development of 2020-2021 Three Year Internal audit rolling plan | Number of (SDM & SDA) 3 years rolling plans developed | 2 (SDM & SDA) 3 years rolling plans developed | No activity | N/A | N/A | None | None | Approved 3 Years and Annual Internal Audit rolling Plan for SDM and SDA by Audit Committee-Audit Committee Minutes | R0.00
| Conduct Regularity audit | 22 regularity audits conducted | Number of regularity audit conducted | 20 Regularity Audits conducted | 5 regularity audits Conducted | Not achieved | 0 regularity audit conducted | Service providers were appointed late after the budget adjustment | To fast track the regularity audit projects to be completed by the end of June 2022 | Signed Regularity Audit Reports | R884 850.00
| Conduct Ad hoc Audits | Conduct Ad Hoc Audits | Percentage Ad Hoc audits conducted | 100% Management requests/ investigations conducted as and when required | 100% Management requests/ investigations conducted as and when required | Achieved | 100% Management requests/ investigations conducted as and when required | None | None | Signed Management /Investigation reports | R 7 173 687.15
| To conduct ICT Audits | 4 ICT Audits reports conducted | Number of ICT Audits conducted | 4 ICT Audit reports conducted | 1 ICTAudits conducted | Not achieved | 0 ICT Audits conducted | Lack of skills internally.Lack of funds to appoint service provider to assist. | Services providers are appointed in March. To fast track the ICT projecsts | Signed ICT Audits Reports | R0.00
| To conduct Audits of Performance Information | 4 Audit of Performance information conducted | Number of Audit of Performance Information conducted | 4 Audit of Performance Information conducted | 1 AOPI conducted | Achieved | 1 AOPI conducted | None | None | Signed AOPI Reports | R0.00
| Monitoring of implementation of auditor general activities | 100% monitoring of implementation of AG activities | Percentage monitoring of External Audit implementation plan | 100%monitoring of external Audit Implementation plan | 100% monitoring of implementation of AG activities | Achieved | 100% monitoring of implementation of AG activities | None | None | Audit Action plan,Signed Minutes,proof of payments | R0.00
| Monitoring of Internal Audit Implementation plan | 100% monitoring of Internal Audit Implementation plan | Percentage monitoring of Internal Audit implementation plan | 100%monitoring of Internal Audit Implementation plan | 100%monitoring of Internal Audit Implementation plan | Achieved | 100%monitoring of Internal Audit Implementation plan | None | None | Internal Audit Implementation plan | R0.00
| Coordination of Audit Committee and Performance Audit Committee | 7 (4 ordinary) and (3 special ) meetings of audit and performance committees coordinated | Number of meetings of audit and performance committees coordinated | 7 (4 ordinary) and ( 3 special ) meetings of audit and performance committees coordinated | 1 meeting of audit and performance committees coordinated | Achieved | 1 ordinary meeting 2 special meetings were held in the third quarter | None | None | Signed Minutes/Agenda/Signed AC Reports | R 520 500.00
| Monitoring implementation of the operation clean audit strategy | 100% monitoring of the operation clean audit strategy | Percentage monitoring of the operation clean audit strategy | 100%monitoring of the operation clean audit strategy | 100% Implementation of the operation clean Audit Strategy | Not achieved | Implementation of the operation clean Audit Strategy | Operation Clean Audit Strategy not workshopped to Mayoral Committee | Provide workshop to Mayoral Committee on the Operational Clean Audit Strategy by the end of June 2022 | Approved operation clean Audit Strategy/Minutes of OPCA meetings/Quarterly Reports | R0.00
| Conducting external assessment review | None | Number of external quality assessment performed | 1 external quality assessment performed | No activity | N/A | N/A | N/A | N/A | External Assessment Review Report | R300 000.00
RISK MANAGEMENT
To assess, identify, and manage risks and uncertainty to safeguards assets, enhance productivity, and build resilience into the operations by June 2022 | Conduct Strategic Risk Assessment and review risk register | Strategic Risk Register in /place | Number of Strategic Risk Assessment conducted, and Strategic Risk Registers reviewed | *1 Strategic Risk Assessment conducted * 4 Strategic Risk Registers reviewed | 1.Monitor & review Risk Register | Achieved | 1.Risk Register monitored & reviewed | None | N/A | Strategic Risk Register report | R0.00
| Conduct Operational Risk Assessment and review risk register | Operational Risk Registers in place | Number of Operational Risk Assessment Conducted and Operational Risk Registers reviewed | *1 Operational Risk Assessment Conducted *4 Operational Risk Registers reviewed | 1.Monitor & review Risk Register | Achieved | 1.Risk Register monitored & reviewed | None | N/A | Operational Risk Registers report | R0.00
| Conduct Processes Risk Assessments | 2 x Processes risk assessment conducted | Number of Processes risk assessments conducted | 7 x Processes risk assessments conducted | 2 x Process Risk Assessment conducted 2.Monitor & review Processes Risk Register | Achieved | 1. Insurance coverage for municipal assets facilitated 2. Insurance policy Updated for additions and deletions | None | N/A | Processes Risk Registers report | R0.00
| Facilitate insurance coverage for municipal assets | 1 x Assets Insurance Policy contract entered into. | Number of insurance coverage for municipal assets facilitated | All insurance coverage for municipal assets facilitated | 1. Insurance coverage for municipal assets facilitated 2.Update insurance policy for additions and deletions | Achieved | 1. Insurance coverage for municipal assets facilitated 2. Insurance policy Updated for additions and deletions | None | N/A | Assets Insurance Policy contract | R6 131 490. 00
| Facilitate Assets Insurance Claims and payments | Insurance claims report facilitated | Percentage processing and facilitation of insurance claims and payments | 100% insurance claims processing, and payments of repairs, losses and excess facilitated | 100% insurance claims processing and payments facilitated | Achieved | 100% insurance claims processing and payments facilitated | None | N/A | Insurance Claims report | R 968 851,00
| Manage Security operations and SLA | All incidents occurred reported | Number of incidents occurred, and SLA managed | All occurred incidents and SLA managed | 4 x Security cluster operations and contracts managed | Achieved | 4 x Security cluster operations and contracts managed | None | N/A | Quarterly Security Report | R30 000 000. 00
| Conduct Security Operational Sites Assessments | Security operational Sites Assessment conducted | Number of Security Operational sites assessments conducted | Forty (40) Security Operational sites assessments conducted | Ten (10) Security Operational sites assessments conducted | Not Achieved | Seven (07) Security operational site assesseed | Conflicting work commitments | To assess more operatioal sites in the 4th Quarter to cover the outstanding balance of sites | Quarterly Security Operational Sites Report produced/compiled | R0.00
| Facilitate the establishment of an Anti-Fraud & Corruption hotline | Fraud and Corruption cases reported and investigated | Number of fraud and corruption allegation cases reported for referral and investigations facilitated | All fraud and corruption allegation cases reported for referral and investigations facilitated | All fraud and corruption allegation cases reported for referral and investigations | Achieved | One (01)fraud and corruption allegation cases reported for referral and investigations | None | N/A | Fraud and Corruption Cases report | R0. 00
To assist the Accounting Officer/Authority in addressing its oversight requirements of risk management and evaluating and monitoring the municipality’s performance with regards to risk management | Facilitate Risk Management Committee (RMC) meetings | One (01) Risk Management Committee held | Number of Risk Management Committee (RMC)meetings facilitated | 4 x Risk Management Committee (RMC) meetings facilitated | 1 x Risk Management Committee (RMC) meetings facilitated | Achieved | 1 x Audit Committee meeting faciliated NB. Audit Committee considered Risk Management reports | None | N/A | Risk Management Committee report | R80 000
Two (02) Audit Committee meetings held to consider Risk Management Committee report
COMMUNICATIONS; ADVOCACY; SOCIAL FACILITATION; SPECIAL PROGRAMMES AND ARTS & CULTURE
To facilitate stakeholder & sectorial engagement by June 2022 | Mayoral Outreaches and Sectorial Engagements | 12 Programmes facilitated | Number of community & sectorial engagements facilitated | 8 stakeholder & sectorial engagements facilitated | 2 stakeholder & sectoral engagement facilitated | Achieved | 5 stakeholder & sectoral engagement facilitated. 22/03/2022 Cell C Handover of LAB. Meeting with Eensaam Forum 18/01/2022 Lekgotla Boardroom. Executive Mayor and Nwaabe Community Representative Meeting 25/01/2022 at Lekgotla Boardroom. Kutullo Community Meeting with Executive Mayor. Draft Annual Report 08/02/2022 Comprehensive. 23/03/2022 Lekgotla Boardroom. Ward 6 Community Meeting 25/01/2022 Lekgotla Boardroom. | None | None | Attendace Register & Exit report | R800 000,00
To provide support to Mayoral Committee by June 2022 | Executive Support to Mayoral Committee | 12 Mayoral Committee meetings supported | Number of Mayoral Committee meetings supported | 12 Mayoral Committee meetings supported | 3 Mayoral Committee meetings supported | Achieved | 3 Mayoral Committee meetings supported. Ordinary 18/01/2022, 18/02/2022, 17/03/2022, Special 24/03/2022. | None | None | Attendace Registers | R0.00
To produce newsletters by June 2022 | Newsletter& Publications | 16 Programmes produced | Number of newsletters produced | 8 newsletters produced. | 1 external and 1 internal newsletters produced | Achieved | 1 x Internal and 1 x External News Letters Produced | None | None | Newsletters | R500 000,00
To market and brand events by June 2022 | Media Relations and Marketing | 12 Events Branded | Number of events Marketed and branded | 12 Events marketed and branded | 3 events marketed and branded | Achieved | 3 Events marketed and branded. 13/01/2022 Back to School Programme at Kgothala Sec School Elandsdoorn. Annual Draft Report - 08/02/2022 Comprehensive, Human Rights Day - 29/03/2022 | None | None | Exit reports, pictures\publications | R100 000,00
To undertake website updates by June 2022 | Website Management | 20 Updates undertaken | Number of Website Updates undertaken | 12 Website Updates undertaken | 3 Website Updates undertaken | Achieved | 5 Website Updates undertaken. Ordinary COUNCIL Meeting 27/01/2022. Draft Annual Report 01/02/2022, Special Council held 09/02/2022, Q1 BTO Report, Q1 Development Agency Report. Special Council 21/02/2022, DC47 2021-22 Adjustment Budget-Council Resolution Adjusted Budget. 2021/22 Adjusted SDBIP and 2021/22 midterm report. | None | None | Screenshots | R150 000,00
To facilitate meetings for Traditional Leaders by June 2022 | Executive Support and Traditional Leadership Affairs | 2 SPLUMA meetings supported | Number of Traditional Leadership meetings facilitated | 3 Traditional Leadership meetings facilitated | 1 Meeting facilitated | Achieved | 3 Meeting Facilitated. on the 16/02/2022 at Moshate - Mohlaletse.Executive Mayor with Moshate Bapedi Kingdom. Meeting with Magoshi at Light House Guest House 18/03/2022. Innitiation School Meeting 08/03/2022 at Ga-Nkwana Municipal Chamber. | None | None | Attendance registers and exit reports | R0. 00
To facilitate strategic events by June 2022 | Special Mayoral strategic Events | 5 strategic events Facilitated | Number of Strategic Events facilitated | 5 strategic events facilitated | 1 strategic events facilitated | Achieved | 1 strategic event facilitated. Kgoshi Mampuru Commemoration and SATMA Awards Celebration 26/03/2022 Facilitated at Mamone. | None | None | Attendance registers and exit reports | R500 000,00
To facilitate Moral Regeneration Movement committee programmes by June 2022 | Strengthening of Moral Regeneration Movement Committee | MRM committee established | Number of programmes for MRM committee facilitated | 2 MRM committee programme facilitated | No activity | N/A | N/A | N/A | N/A | Attendance registers and exit reports | R100 000,00
To generate Customer Care reports by June 2022 | Customer Care Services | 24 reports generated | Number of reports generated | 24 queries/ complains reports on customer care generated | 6 customer care reports generated | Achieved | 6 customer care reports generated | None | None | Exit reports | R0.00
To revamp the Call Centre by June 2022 | Call Centre Revamping & Maintenance | 24 hour outdated call centre system | Number of call centre revamped | 1 call centre revamped | No activity | N/A | N/A | N/A | N/A | Report | R600 000,00
To conduct Batho Pele programmes by June 2022 | Batho Pele | 6 Programmes conducted | Number of Batho Pele Programmes conducted | 4 Batho Pele Programmes conducted | 1 Batho Pele Programmes conducted | Achieved | 1 Batho Pele activity held | None | N/A | Reports | R100 000,00
To co-ordinate SODA by June 2022 | SODA | 2020/2021 SODA held | Number of SODA coordinated | 1 SODA coordinated | 1 SODA Activity Coordinated | Not Achieved | No Activity | SODA not held due to competing activities | SODA rescheduled for 13 April 2022 at Ga-Masemola Stadium. | Attendance registers and exit reports | R450 000,00
To facilitate campaigns for the elderly by June 2022 | Aged care | 2 aged care programmes facilitated | Number of Aged Care campaigns facilitated | 2 Aged Care campaigns facilitated | No activity | N/A | N/A | N/A | N/A | Attendance registers and exit reports | R200 000,00
To facilitate campaigns for the children by June 2022 | Children’s Care | 2 children’s activities facilitated | Number of children's campaigns facilitated | 2 children's campaigns facilitated | No activity | N/A | N/A | N/A | N/A | Attendance registers and exit reports | R100 000,00
To facilitate campaigns for women by June 2022 | Woman Development Initiative | 4 Women Programmes facilitated | Number of woman development initiatives facilitated | 3 woman development initiatives facilitated | No activity | N/A | N/A | N/A | N/A | Attendance registers and exit reports | R300 000,00
To facilitate Awareness campaigns for people with disability by June 2022 | People with disability | 3 Programmes facilitated | Number of awareness campaigns for people with disability facilitated | 2 awareness campaigns for people with disability facilitated | 1 campaign for people with disability facilitated | Achieved | 1 campaign for people with disabilities facilitated.Human Rights Month Celebration Disability Indaba 2022 held 29 March 2022 at Peter Nchabeleng Sport Complex Hall | None | N/A | Attendance registers and exit reports | R200 000,00
To facilitate art and culture programmes by June 2022 | Cultural Heritage Celebrations and Language Promotions | 2 Programmes facilitated | Number of Heritage and promotions of indigenous languages and theatre workshop facilitated | 1 Heritage day and 1 promotions of indigenous languages and Theatre workshop facilitated | No activity | N/A | N/A | N/A | N/A | Attendance registers and exit reports | R500 000,00
To coordinate health calendar days activities by June 2022 | Coordination of health calendar days activities | 3 health calendar days activities conducted | Number of health calendar days activities coordinated | 3 Health calendar days activities coordinated | I health calendar day co-ordinated | Achieved | 1 health calendar day cordinated. Coordinate TB Month Commemoration Campaigns held 11 - 18 March 2022. | None | N/A | Attendance registers and exit reports | R200 000,00
To coordinate district AIDS Council activities by June 2022 | Coordination of District AIDS Council activities | 4 District Aids Council activities coordinated | Number of district AIDS Council activities coordinated | 3 district AIDS Council activities coordinated | 1 district AIDS Council activity coordinated | Achieved | 1 District AIDS Council activity coordinated on the 24-25 March 2022 (LACs Support visits) | None | N/A | Attendance registers and exit reports
To facilitate Youth development programmes by June 2022 | Youth Opportunities Expo | 3 Programmes facilitated | Number of Youth development programmes facilitated | 3 Youth development programmes facilitated | 1 Youth development programme facilitated | Achieved | 1 youth development programme facilitated.Youth Council Activity -CCSA Graduation Ceremony held 18 March 2022 at Bareki Mall Council Chamber. | None | N/A | Attendance registers and exit reports | R900 000 00
To facilitate Mayor’s forum activities by June 2022 | Facilitation of Mayor’s forum | 4 Mayor’s forum facilitated | Number of Mayor’s forum facilitated | 4 Mayor’s forum facilitated | 1 Mayor’s forum facilitated | Not Achieved | No Activity | Unable to hold Mayor's Forum due to competing activities | Mayor's Forum rescheduled for next quarter (Q4). | Attendance registers and exit reports | R0.00
To facilitate Mayoral sports activities by June 2022 | Facilitation of Mayoral Sports activities | 2 Mayoral Sport activities facilitated | Number of Mayoral Sport activities facilitated | 1 Mayoral Sport activities facilitated | No activity | No Activity | No Target | None | N/A | Attendance registers and exit reports | R500 000,00
PUBLIC PARTICIPATION, MPAC SUPPORT; SECRETARIAT AND SUPPORT
Provide secretarial support to 10 council structures to ensure accountability by June 2022 | FORA | 16 Fora facilitated | Number of fora facilitated | 16 Fora facilitated | 1 Speakers' Forum, 1 Chief Whips' Forum, 1 Public participation Forum facilatated. | Achieved | 1 Speakers' Forum, 1 Chief Whips' Forum, 1 Public participation Forum facilatated on 15/03/22, 29/03/2022 and 03/03/22 & 28/03/22 respectively. | None | None | Notice & Attendance registers | R75 000.00
| Public participation sessions. | 15 public participation sessions facilitated | Number of public consultation meetings facilitated | 15 public participation facilitated | 7 public consultation meetings on 2020/2021 draft annual report facilitated. | Achieved | 7 public consultation meetings on 2020/2021 draft annual report facilitated. | None | Npne | Attendance registers and exit reports | R750 000.00
| SODA & Budget Day | 1 SODA , 1 Budget Day facilitated | Number of SODA and Budget days facilitated | 1 SODA , 1 Budget Day facilitated | 1 Extra Special Council Meeting (SODA) Facilitated. | Not achieved | 1 Extra Special Council Meeting (SODA) not Facilitated. | Challenge of supply chain procurement processes | 1 Extra Special Council Meeting (SODA) to be facilitated on 13 April 2022. | Notice and attendance registers | R0.00
| Council and portfolio committee meetings | 22 Council and portfolio committee meetings facilitated | Number Council and portfolio committee meetings facilitated | 24 Council and portfolio committee meetings facilitated | 1 Ordinary Council Meetings and 5 Portfolio Committee Meetings facilitated. | Achieved | 1 Ordinary Council Meeting facilitated on 27/01/2022, 3 Special Council Meetings on 09/02/22, 21/02/22, 30/032/22 and 5 Portfolio Committee Meetings facilitated | None | None | Notice and attendance registers | R500 000.00
| Study group | 4 study groups facilitated | Number of study groups facilitated | 4 study groups facilitated | 1 Study Group Facilitated. | Achieved | 1 study group facilitated | None | None | Notice and attendance registers | R65 000.00
| Public hearings | 2 public hearings facilitated | Number of public hearings facilitated | 2 public hearings facilitated | No activity | N/A | N/A | N/A | N/A | Notice and attendance registers | R200 000.00
| Strategic planning sessions for Section 79 Portfolio Committees & MPAC | 2 strategic planning sessions facilitated | Number of strategic planning session facilitated | 2 strategic planning sessions facilitated | No activity | N/A | N/A | N/A | N/A | Notice and attendance registers | R350 000.00
| Capacity building workshops | 2x workshops facilitated | Number of workshops facilitated | 2x workshops facilitated | No activity | N/A | N/A | N/A | N/A | Notice and attendance registers | R300 000.00
| Training and development of Cllrs | 2x councillors trained | Number of councillors trained | 10x Councillors trained | No activity | N/A | N/A | N/A | N/A | Exit report | R600 000.00
| Queries and assistance of travel claims | 100% resolution of Cllrs queries facilitated | Percentage resolution of Cllrs queries facilitated | 100% resolution of Cllrs queries facilitated | 100% resolution of Cllrs queries facilitated. | Achieved | 100% resolution of cllrs queries facilitated | None | None | Exit report | R0.00
| Resolution registers for Council implementation. | 4 Council Resolution registers compiled and coordinated | Number of Council Resolution registers compiled and coordinated | 4 Council Resolution registers compiled and coordinated | 1 council resolution register compiled and cordinated. | Achieved | 1 council resolution register compiled and cordinated. | None | None | Council resolution register | R0.00
| Council whippery meetings facilitated | 4 meetings held | Number of meetings facilitated | 4 Council Whippery meeting Facilitated. | 1 Council Whippery meeting Facilitated. | Achieved | 1 Council Whippery meeting facilitated | None | None | Notice and attendance registers | R20 000.00
| Working sessions for Cllrs. | 8 MPAC Working sessions for Cllrs facilitated | Number of MPAC working sessions for Cllrs facilitated | 8 MPAC working sessions for Cllr facilitated. | 2 MPAC working sessions for Cllr facilitated. | Achieved | 3 MPAC working sessions for Cllr facilitated. | None | None | Notice and attendance registers