## Sheet1
2021/2022 ANNUAL REPORT
GOOD GOVERNANCE AND PUBLIC PARTICIPATION
OBJECTIVES | PROJECT | BASELINE 2020/2021 | INDICATORS | ANNUAL TARGET 2021/2022 | PROGRESS ACHIEVED/NOT ACHIEVED | PROGRESS | CHALLENGE | REMEDIAL | POE | BUDGET 2021-2022 | EXPENDITURE
INTERNAL AUDIT
To ensure improved internal controls and clean governance in the municipality by June 2022 | Development of the Three(3) Years rolling Plan | Development of 2020-2021 Three Year Internal audit rolling plan | Number of (SDM & SDA) 3 years rolling plans developed | 2 (SDM & SDA) 3 years rolling plans developed | Achieved | 2 SDM & SDA) 3 years rolling plans developed | None | None | Approved 3 Years and Annual Internal Audit rolling Plan for SDM and SDA by Audit Committee-Audit Committee Minutes | R0.00
| Conduct Regularity audit | 22 regularity audits conducted | Number of regularity audit conducted | 20 Regularity Audits conducted | Not Achieved | 17 regularity audit projects are conducted and report issued. 3 Audit Projects are in progress. | Lack of human resource.Late appointment of service providers due to lack of budget.Performed more due dilligence review | CAE position be filled .Due dilligence be performed within certain threshold . | Signed Regularity Audit Reports | R4734850.00 | R2216569.35
| Conduct Ad hoc Audits | Conduct Ad Hoc Audits | Percentage Ad Hoc audits conducted | 100% Management requests/ investigations conducted as and when required | Achieved | 100% Management requests/ investigations conducted as and when required (15 reports issued) | None | None | Signed Management /Investigation reports | 7823687 | R7798710.98
| To conduct ICT Audits | 4 ICT Audits reports conducted | Number of ICT Audits conducted | 4 ICT Audit reports conducted | Achieved | 4 ICT Audit reports conducted | None | None | Signed ICT Audits Reports | R0.00
| To conduct Audits of Performance Information | 4 Audit of Performance information conducted | Number of Audit of Performance Information conducted | 4 Audit of Performance Information conducted | Achieved | 4 Audit of Performance Information conducted | None | None | Signed AOPI Reports | R0.00
| Monitoring of implementation of auditor general activities | 100% monitoring of implementation of AG activities | Percentage monitoring of External Audit implementation plan | 100% monitoring of external Audit Implementation plan | Achieved | 100% monitoring of external Audit Implementation plan | None | None | Audit Action plan,Signed Minutes,proof of payments | R0.00
| Monitoring of Internal Audit Implementation plan | 100% monitoring of Internal Audit Implementation plan | Percentage monitoring of Internal Audit implementation plan | 100% monitoring of Internal Audit Implementation plan | Achieved | 100% monitoring of Internal Audit Implementation plan | None | None | Internal Audit Implementation plan | R0.00
| Coordination of Audit Committee and Performance Audit Committee | 7 (4 ordinary) and (3 special ) meetings of audit and performance committees coordinated | Number of meetings of audit and performance committees coordinated | 7 (4 ordinary) and ( 3 special ) meetings of audit and performance committees coordinated | Achieved | 10 Ordinary Audit Committee meetings held (4 SDM,3 SDA,3 PAC) and 5 special Audit Committee meetings | None | None | Signed Minutes/Agenda/Signed AC Reports | 670500 | R625165.31
| Monitoring implementation of the operation clean audit strategy | 100% monitoring of the operation clean audit strategy | Percentage monitoring of the operation clean audit strategy | 100% monitoring of the operation clean audit strategy | Not Achieved | 0% monitoring of the operation clean audit strategy | Operation Clean Audit Strategy not presented to council for approval | Operation Clean Audit Strategy to be workshopped to Members of Mayoral committee before submssion for approval council | Approved operation clean Audit Strategy/Minutes of OPCA meetings/Quarterly Reports | R0.00
| Conducting external assessment review | None | Number of external quality assessment performed | 1 external quality assessment performed | Not Achieved | 1 external quality assessment not performed | Lack of capacity (Human Resources) in the Internal Audit | Request Human resource to provide two Interns or fill in the vacant position including the position of the CAE | External Assessment Review Report | R300 000.00
Acting Chief Audit Executive
Date:
RISK MANAGEMENT
To assess, identify, and manage risks and uncertainty to safeguards assets, enhance productivity, and build resilience into the operations by June 2022 | Conduct Strategic Risk Assessment and review risk register | Strategic Risk Register in /place | Number of Strategic Risk Assessment conducted, and Strategic Risk Registers reviewed | *1 Strategic Risk Assessment conducted * 4 Strategic Risk Registers reviewed | Achieved | *1 Strategic Risk Assessment conducted * 4 Strategic Risk Registers reviewed | None | None | Strategic Risk Register report | R0.00
| Conduct Operational Risk Assessment and review risk register | Operational Risk Registers in place | Number of Operational Risk Assessment Conducted and Operational Risk Registers reviewed | *1 Operational Risk Assessment Conducted *4 Operational Risk Registers reviewed | Achieved | *1 Operational Risk Assessment Conducted *4 Operational Risk Registers reviewed | None | None | Operational Risk Registers report | R0.00
| Facilitate insurance coverage for municipal assets | 1 x Assets Insurance Policy contract entered into. | Number of insurance coverage for municipal assets facilitated | All insurance coverage for municipal assets facilitated | Achieved | All insurance coverage for municipal assets facilitated | Values of some Assets at risk are found to be less than their market value thereby resulting in underinsurance that results in application of average during settlement of claims. | Conduct reevaluation of assets at risk and adjust the Sums Insured accordingly to reflect Current Market values. | Assets Insurance Policy contract | R6 131 490. 00
| Facilitate Assets Insurance Claims and payments | Insurance claims report facilitated | Percentage processing and facilitation of insurance claims and payments | 100% insurance claims processing, and payments of repairs, losses and excess facilitated | Achieved | 100% (52) insurance claims processed, and payments of repairs, losses and excess facilitated | None | N/A | Insurance Claims report | R 968 851,00
| Manage Security operations and SLA | All incidents occurred reported | Number of incidents occurred, and SLA managed | All occurred incidents and SLA managed | Achieved | All twenty two (22) occurred incidents and SLA managed | None | N/A | Quarterly Security Report | R30 000 000. 00
| Conduct Security Operational Sites Assessments | Security operational Sites Assessment conducted | Number of Security Operational sites assessments conducted | Forty (40) Security Operational sites assessments conducted | Achieved | Forty one (41)Security Operational sites assessments conducted | None | N/A | Quarterly Security Operational Sites Report produced/compiled | R0.00
| Facilitate the establishment of an Anti-Fraud & Corruption hotline | Fraud and Corruption cases reported and investigated | Number of fraud and corruption allegation cases reported for referral and investigations facilitated | All fraud and corruption allegation cases reported for referral and investigations facilitated | Achieved | One (01) fraud and corruption allegation case reported for referral and investigations facilitated | None | N/A | Fraud and Corruption Cases report | R0. 00
To assist the Accounting Officer/Authority in addressing its oversight requirements of risk management and evaluating and monitoring the municipality’s performance with regards to risk management | Facilitate Risk Management Committee (RMC) meetings | One (01) Risk Management Committee held | Number of Risk Management Committee (RMC)meetings facilitated | 4 x Risk Management Committee (RMC) meetings facilitated | Not Achieved | 1 Risk Management Committee meeting facilitated | Delay in the appointment of Chairperson of Risk Committee | The chairperson was appointed during the 4th quarter of 2021/2022 financial year | Risk Management Committee report | R80 000
Two (02) Audit Committee meetings held to consider Risk Management Committee report
Chief Risk Officer
Date:
PUBLIC PARTICIPATION, MPAC SUPPORT; SECRETARIAT AND SUPPORT
Provide secretarial support to 10 council structures to ensure accountability by June 2022 | FOR A | 16 Fora facilitated | Number of fora facilitated | 16 Fora facilitated | Not achieved | 15 Fora facilitated | Conflicting schedules | MPAC forum meeting rescheduled for 1st quarter | Notice & Attendance registers | R75 000.00
| Public participation sessions. | 15 public participation sessions facilitated | Number of public consultation meetings facilitated | 15 public participation facilitated | Achieved | 15 public participation facilitated | None | None | Attendance registers and exit reports | R750 000.00
| SODA & Budget Day | 1 SODA , 1 Budget Day facilitated | Number of SODA and Budget days facilitated | 1 SODA , 1 Budget Day facilitated | Achieved | 1 SODA , 1 Budget Day facilitated | None | None | Notice and attendance registers | R0.00
| Council and portfolio committee meetings | 22 Council and portfolio committee meetings facilitated | Number Council and portfolio committee meetings facilitated | 24 Council and portfolio committee meetings facilitated | Achieved | 46 Council and portfolio committee meetings facilitated | None | None | Notice and attendance registers | R500 000.00
| Study group | 4 study groups facilitated | Number of study groups facilitated | 4 study groups facilitated | Achieved | 4 study groups facilitated | None | None | Notice and attendance registers | R65 000.00
| Public hearings | 2 public hearings facilitated | Number of public hearings facilitated | 2 public hearings facilitated | Not achieved | 1 public hearings facilitated | *Term of office of Cllrs ended on the 01/11/2021. The new Cllrs were sworn in and inaugurated on 25/11/2021 and 02/12/2021. *Conflicting schedules | 1MPAC Public Hearing will be faciliated during Q1 | Notice and attendance registers | R200 000.00
| Strategic planning sessions for Section 79 Portfolio Committees & MPAC | 2 strategic planning sessions facilitated | Number of strategic planning session facilitated | 2 strategic planning sessions facilitated | Achieved | 2 strategic planning sessions facilitated | None | None | Notice and attendance registers | R350 000.00
| Capacity building workshops | 2x workshops facilitated | Number of workshops facilitated | 2x workshops facilitated | Achieved | 2x workshops facilitated | None | None | Notice and attendance registers | R300 000.00
| Training and development of Cllrs | 2x councillors trained | Number of councillors trained | 10x Councillors trained | Not Achieved | 10x Councillors identified for training and applications sent to higher learning institutions | *Term of office of Cllrs ended on the 01/11/2021. The new Cllrs were sworn in and inaugurated on 25/11/2021 and 02/12/2021. *Conflicting schedules | 10x Councillors registered to be trained during 2022/23 financial year | Exit report | R600 000.00
| Queries and assistance of travel claims | 100% resolution of Cllrs queries facilitated | Percentage resolution of Cllrs queries facilitated | 100% resolution of Cllrs queries facilitated | Achieved | 100% resolution of Cllrs queries facilitated | None | None | Exit report | R0.00
| Resolution registers for Council implementation. | 4 Council Resolution registers compiled and coordinated | Number of Council Resolution registers compiled and coordinated | 4 Council Resolution registers compiled and coordinated | Achieved | 4 council resolution registers compiled and cordinated. | None | None | Council resolution register | R0.00
| Council whippery meetings facilitated | 4 meetings held | Number of meetings facilitated | 4 Council Whippery meetings Facilitated. | Achieved | 4 Council Whippery meetings Facilitated. | None | None | Notice and attendance registers | R20 000.00
| Working sessions for Cllrs. | 8 MPAC Working sessions for Cllrs facilitated | Number of MPAC working sessions for Cllrs facilitated | 8 MPAC working sessions for Cllr facilitated. | Achieved | 21 MPAC working sessions for Cllr facilitated. | None | None | Notice and attendance registers | R180 000.00
Council Secretary
Date:
COMMUNICATIONS; ADVOCACY; SOCIAL FACILITATION; SPECIAL PROGRAMMES AND ARTS & CULTURE
To facilitate stakeholder & sectorial engagement by June 2022 | Mayoral Outreaches and Sectorial Engagements | 12 Programmes facilitated | Number of community & sectorial engagements facilitated | 8 stakeholder & sectorial engagements facilitated | Achieved | 10 stakeholder & sectoral engagement facilitated. | None | N/A | Attendace Register & Exit report | R800 000,00
To provide support to Mayoral Committee by June 2022 | Executive Support to Mayoral Committee | 12 Mayoral Committee meetings supported | Number of Mayoral Committee meetings supported | 12 Mayoral Committee meetings supported | Achieved | 14 Mayoral Committee Meetings supported. | None | N/A | Attendace Registers | R0.00
To produce newsletters by June 2022 | Newsletter& Publications | 16 Programmes produced | Number of newsletters produced | 8 newsletters produced. | Not Achieved | 4 Newsletters Produced. | Delayed Printing of News Letters resulted into none achievement. | The target will be implemented in the 2022/2023 financial year | Newsletters | R500 000,00
To market and brand events by June 2022 | Media Relations and Marketing | 12 Events Branded | Number of events Marketed and branded | 12 Events marketed and branded | Achieved | 17 Events Marketed and Branded. | None | N/A | Exit reports, pictures\publications | R100 000,00
To undertake website updates by June 2022 | Website Management | 20 Updates undertaken | Number of Website Updates undertaken | 12 Website Updates undertaken | Achieved | 18 Websites updates undertaken. | None | N/A | Screenshots | R150 000,00
To facilitate meetings for Traditional Leaders by June 2022 | Executive Support and Traditional Leadership Affairs | 2 SPLUMA meetings supported | Number of Traditional Leadership meetings facilitated | 3 Traditional Leadership meetings facilitated | Achieved | 5 Traditional leadership Meetings Facilitated. | None | N/A | Attendance registers and exit reports | R0. 00
To facilitate strategic events by June 2022 | Special Mayoral strategic Events | 5 strategic events Facilitated | Number of Strategic Events facilitated | 5 strategic events facilitated | Achieved | 5 strategic events facilitated | None | None | Attendance registers and exit reports | R500 000,00
To facilitate Moral Regeneration Movement committee programmes by June 2022 | Strengthening of Moral Regeneration Movement Committee | MRM committee established | Number of programmes for MRM committee facilitated | 2 MRM committee programme facilitated | Achieved | 2 MRM activities facilitated. | None | N/A | Attendance registers and exit reports | R100 000,00
To generate Customer Care reports by June 2022 | Customer Care Services | 24 reports generated | Number of reports generated | 24 queries/ complains reports on customer care generated | Achieved | 24 customer care reports genetated | None | N/A | Exit reports | R0.00
To revamp the Call Centre by June 2022 | Call Centre Revamping & Maintenance | 24 hour outdated call centre system | Number of call centre revamped | 1 call centre revamped | Not Achieved | 1 call centre not revamped. | Lack of Budget | The project is budgeted for implementation in the 2022/2023 financial year. | Report | R600 000,00
To conduct Batho Pele programmes by June 2022 | Batho Pele | 6 Programmes conducted | Number of Batho Pele Programmes conducted | 4 Batho Pele Programmes conducted | Achieved | 4 Batho pele Activities held. | None | None | Reports | R100 000,00
To co-ordinate SODA by June 2022 | SODA | 2020/2021 SODA held | Number of SODA coordinated | 1 SODA coordinated | Achieved | 1 SODA event coordinated | None | None | Attendance registers and exit reports | R450 000,00
To facilitate campaigns for the elderly by June 2022 | Aged care | 2 aged care programmes facilitated | Number of Aged Care campaigns facilitated | 2 Aged Care campaigns facilitated | Achieved | 2 Aged campaigns facilitated. | None | None | Attendance registers and exit reports | R200 000,00
To facilitate campaigns for the children by June 2022 | Children’s Care | 2 children’s activities facilitated | Number of children's campaigns facilitated | 2 children's campaigns facilitated | Achieved | 2 children programme facilitated. | None | N/A | Attendance registers and exit reports | R100 000,00
To facilitate campaigns for women by June 2022 | Woman Development Initiative | 4 Women Programmes facilitated | Number of woman development initiatives facilitated | 3 woman development initiatives facilitated | Achieved | 3 woman development initiatives facilitated | None | None | Attendance registers and exit reports | R300 000,00
To facilitate Awareness campaigns for people with disability by June 2022 | People with disability | 3 Programmes facilitated | Number of awareness campaigns for people with disability facilitated | 2 awareness campaigns for people with disability facilitated | Achieved | 2 awareness campaigns for people with disability facilitated | None | None | Attendance registers and exit reports | R200 000,00
To facilitate art and culture programmes by June 2022 | Cultural Heritage Celebrations and Language Promotions | 2 Programmes facilitated | Number of Heritage and promotions of indigenous languages and theatre workshop facilitated | 1 Heritage day and 2 promotions of indigenous languages and Theatre workshop facilitated | Achieved | 1 Heritage day and 2 promotions of indigenous languages and Theatre workshop facilitated | None | None | Attendance registers and exit reports | R500 000,00
To coordinate health calendar days activities by June 2022 | Coordination of health calendar days activities | 3 health calendar days activities conducted | Number of health calendar days activities coordinated | 3 Health calendar days activities coordinated | Not Achieved | 1 Health Calender Day Coordinated. | Unavailability of major stakeholders | Event planned for 2022/23 financial year | Attendance registers and exit reports | R200 000,00
To coordinate district AIDS Council activities by June 2022 | Coordination of District AIDS Council activities | 4 District Aids Council activities coordinated | Number of district AIDS Council activities coordinated | 3 district AIDS Council activities coordinated | Not Achieved | 1 District AIDS Council activity coordinated. | Tight schedule in the Office of the Executive Mayor | AIDS Council meeting rescheduled for 2022/23 financial year | Attendance registers and exit reports
To facilitate Youth development programmes by June 2022 | Youth Opportunities Expo | 3 Programmes facilitated | Number of Youth development programmes facilitated | 3 Youth development programmes facilitated | Achieved | 3 Youth Development Programme Facilitated. | None | None | Attendance registers and exit reports | R900 000 00
To facilitate Mayor’s forum activities by June 2022 | Facilitation of Mayor’s forum | 4 Mayor’s forum facilitated | Number of Mayor’s forum facilitated | 4 Mayor’s forum facilitated | Not Achieved | 1 Mayor's Forum facilitated. | Forum meeting not held due to tight schedule. | Forum meetings rescheduled for 2022/23 | Attendance registers and exit reports | R0.00
To facilitate Mayoral sports activities by June 2022 | Facilitation of Mayoral Sports activities | 2 Mayoral Sport activities facilitated | Number of Mayoral Sport activities facilitated | 1 Mayoral Sport activities facilitated | Achieved | 1 Mayoral sport activity facilitated. | None | None | Attendance registers and exit reports | R500 000,00 |  | R6,200,000.00
R55,299,378.15
Acting Deputy Director
Date