## CPS
DRAFT SDBIP 2021/2022
KPA: INSTITUTIONAL TRANSFORMATION & ORGANISATIONAL DEVELOPMENT
INSTITUTIONAL TRANSFORMATION & ORGANISATIONAL DEVELOPMENT
2021/2022 SDBIP
MEASUABLE OBJECTIVES | PROJECT | BASELINE 2020/2021 | INDICATORS | ANNUAL TARGET 2021/2022 | Q3 TARGET | PROGRESS (Achieved/ Not achieved) | ACTUAL PROGRESS | CHALLENGES | REMEDIAL ACTIONS | PORTFOLIO OF EVIDENCE | BUDGET 2021/2022
ORGANISATIONAL DEVELOPEMENT
To review the Organisational Structure by June 2022 | Organisational Structure Review | Approved Organisational Structure for 2020-2021 | Number of Organisational Structure Reviewed | 1 Organisational Structure Reviewed | Draft organisational structure in place | Achieved | Draft Organisational Structure in Place *Council Resolution | None | None | Council Resolution and Approved Organisational Structure | 0
To facilitate development of job descriptions and job evaluation by June 2022 | Job Description Development and Job Evaluation | 50 Job Descriptions Developed and Evaluated | Number of Job Descriptions Developed and facilitated for Evaluated | 50 Job Descriptions Developed and Facilitated for Evaluation | 15 Job Descriptions Developed and Facilitated for Evaluation | Achieved | 15 Job Descriptions Developed and Facilitated for Evaluation | None | None | Job Evaluation Report
INFORMATION AND COMMUNICATION TECHNOLOGY (ICT)
To establish effective network connectivity by June 2022 | ICT Infrastructure connection | 18 depots connected | Number of depots connections upgraded | 18 depots connections upgraded | Monitoring and evaluation | Achieved | Monitoring and evaluation done in 18 depos | None | None | Reports | 500000
| Implementation of security measures | 05 of Security Control implemented | Number of Security Controls implemented | 24 Security Controls Implemented | 6 Security Controls Implemented | Achieved | 6 Security Controls Implemented | None | None | Security measures | 400000
To conduct need analysis of ICT hardware and consumables by June 2022 | ICT consumables and hardware replacement | 50 ICT consumables and hardware replacement | Number of ICT consumables and Computers replaced | 30 ICT consumables and Computers replaced | 5 ICT consumables and Computers replaced | Achieved | 5 ICT consumables and Computers replaced | None | None | Laptop/Consumable Register | 1000000
To monitor expiry date of licenses by June 2022 | Software Licence renewal | 12 licenses renewed | Number of licenses renewed | 11 licenses renewed | 3 licenses renewed | Achieved | 3 licenses renewed | None | None | Licenses | 3859000
To monitor Service Level Agreements by June 2022 | Contract Monitoring | 12 SLA performance held | Number of SLA performance held | 16 SLA performance held | 4 SLA performance held | Achieved | 4 SLA performance held | None | Nonr | Reports | 3159000
LABOUR RELATIONS
To Issue four labour relations publications by June 2022 | Issue Labour Relations Publications | 4 Labour relations publications issued. | Number of Labour relations publications issued | 4 Labour relations publications issued | 1 Labour relations publication issued | Achieved. | 1 Labour relations publication issued. | None. | None. | Copies of publications | R0.00
To facilitate Labour related grievances by June 2022 | Facilitate Labour Relations Grievances | 3 Grievance cases facilitated | Number of grievances cases received facilitated | All Labour related grievances cases received facilitated | All Labour related grievances cases received facilitated | N/A | No Labour related grievance received. | None. | None. | Copies grievances | R0.00
To facilitate Labour related disciplinary cases by June 2022 | Facilitate labour related disciplinary cases | 7 disciplinary cases facilitated | Number of labour related disciplinary cases received facilitated | All labour related disciplinary cases received facilitated | All labour related disciplinary cases received facilitated | Not achieved | All (01) labour related disciplinary cases received and facilitated | Employee needed legal representative | To be finalised once the employee is represented legally | Reports and attendance registers | R0.00
To facilitate12 LLF meetings by June 2022 | Facilitate LLF Meetings | 9 LLF meetings held | Number of LLF meetings facilitated. | 12 LLF meetings facilitated | 3 LLF meetings facilitated. | Not achieved. | 1 LLF meeting facilitated. | Failure to meet quorum and non-adherence to schedule. | Adherence to scheduled meeting. | Minutes and attendance registers | R0.00
AUXILIARY SERVICES
To conduct records management awareness programme by June 2022 | Records management awareness | 2 Records management awareness facilitated | Number of Records management awareness facilitated | 02 Records management awareness facilitated | No activity | N/A | N/A | N/A | N/A | Report | R0.00
To facilitate the development of file plan by June 2022 | File plan | 1 File plan developed | Number of File plan developed | 01 File plan developed | No activity | N/A | N/A | N/A | N/A | Draft File Plan | R0.00
To facilitate implementation of records (document) management system by June 2022 | Records (documents) management system | 1 Records management system in place. (MunAdmin) | Number of document management system implemented | 01 Record management system implemented | Monitoring implementation of the system | Not achieved | Monitoring implementation of the system not done | Councilors provided with laptops but no connectivity | Councillors to be workshopped on Paperless Agenda once coonrctivity is secured for them. | Report | R300 000
To maintain and repair the fleet and facilities by June 2022 | Maintenance and repairs | 20 vehicles Maintained and repaired | Number of vehicles Maintained and repaired | 20 vehicles Maintained and repaired | 15 Vihecles maintained and repaired | Achieved | 15 Vihecles maintained and repaired | None | None | Licensing and Maintanance Report | R1 800 000
To procure fleet mangement system by June 2022 | Fleet Management system | New project | Number of fleet management system procured | 01 fleet management system procured | Implementation of the fleet management system | No Achieved | Implementation of fleet management system not done | Fleet management module not included in the mun admin | Fleet management module to be included in the mun admin in the next financial year | Report | 500000
To settle the emergency vehicles by June 2022 | Settlement of emergency vehicles | 11 emergency vehicles settled | Number of emergency vehicles settled | 15 emergency vehicles settled | No Activity | N/A | N/A | N/A | N/A | Report, proof of payment Certificate | R12 000 000
HUMAN RESOURCE MANAGEMENT
To implement the process and procedures of Human Resource (HR) policies by June 2022 | Recruitment and Selection | 05 Vacant and funded positions filled | % of vacant funded positions filled | 100% Filling of vacant and funded positions | Appointment and induction of employees | Not Achieved | Senior Managers Positions advertised | None | Process to unfold in the next quarter to allow appointment | Appointment letters | 98805.47
| Internal Bursaries | 9 Internal Bursaries maintained | Number of Internal Bursaries maintained | 09 Internal Bursaries maintained | Maintanance of internal Bursaries | Achieved | 22 Bursaries maintatined | None | None | Bursary letters | 592830.76
| External Bursaries | 3 External Bursaries maintained | Number of External Bursaries maintained | 03 External Bursaries maintained | maintanance of 3 external Bursaries | Achieved | 03 Bursaries maintained | None | None | Bursary letters | 691636.24
To implement the WSP projects by June 2022 | WSP Projects | 02 WSP Projects Implemented | Number of WSP Projects implemented | 05 WSP Projects implemented | Implementation of 01 WSP project | Achieved | 6 WSP Projects implemented | None | None | WSP training report | 210000
EMPLOYEE ASSISTANCE PROGRAMME
To conduct employee wellness programmes by June 2022 | Employee wellness and Counselling | 4 wellness and counselling programmes conducted. | Number of wellness programmes conducted | 2 wellness awareness programmes conducted | 1 employee wellnes awareness programme conducted | Achieved | 3 wellness awareness programme conducted dates,24/01/22, 24/02/22 & 17/03/22). | None | None | Wellness awareness programme attendance registers. | 571651.62
To conduct substance abuse programmes by June 2022 | Substance Abuse | 3 substance abuse programmes conducted | Number of substance abuse programmes conducted | 2 substance abuse programmes conducted | 1 substance abuse programme conducted | Achieved | 3 substance abuse programmes facilitated dates, (31/01/22,22/02/22 & 22/03/22) | None | None | Substance abuse programme registers.
To conduct Occupational Health and Safety elements by June 2022 | Occupational Health and Safety elements | 42 Occupational Health and Safety elements conducted | Number of Occupational Health and Safety elements conducted | 41 Occupational Health and Safety elements conducted (24 workplace inspections, 8 project audits, 2 safety awareness campaigns, 4 safety committee meetings, 2 servicing of fire extiquishers and hose reels). | 10 Occupational Health and Safety elements conducted (6 workplace inspections, 2 project audits, 1 safety awareness campaigns, 1 safety committee meetings1 servicing of fire extiquishers and fire hose reels). | Achieved | 14 Worplace inspection, 1 health and safety committee meeting, 3 awareness campaigns | None | None | Workplace inspections and project audits reports, safety awareness campaigns attendance registers, safety committee meeting attendance registers, servicing of fire extiquishers and fire hose reels register . | 8345586.65
To provide personal Protective equipment by June 2022 | Personal Protective Equipment | 7692 Personal Protective Equipment (fire protection PPE) provided to Emergency Services employees, IWS, and CPS | Number of Personal Protective Equipment provided to IWS, Emergency Services, Municipal Health Services, CPS, Budget and Treasury, SDA, PED, Mayors and Speakers office employees | All Personal Protective Equipment provided to IWS, Emergency Services, Municipal Health Services, CPS, Budget and Treasury, SDA, PED, Mayors and Speakers office employees | All Personal Protective Equipment provided to IWS, Emergency Services, Municipal Health Services, CPS, Budget and Treasury, SDA, Mayors Office and Speakers office employees | Achieved | All (345) PPE items distributed to IWS and CPS staff members. | None | None | Personal protective equipment issuing forms
PERFORMANCE MANAGEMENT
To facilitate Performance Makgotla by 30 June 2022 | Performance Makgotla | 3 Performance Makgotla Sessions held | Number of Performance Makgotla facilitated | 04 Performance Makgotla facilitated | 1 Performance Lekgotla facilitated | Achieved | 1 Performance Lekgotla facilitated | None | None | Attendance Registers, Makgotla Resolutions | 105141
To develop 2022/2023 Institutional SDBIP by June 2022 | 2022/2023 Institutional SDBIP | 2021/2022 Institutional SDBIP in place | Number of 2022/2023 Institutional SDBIP developed | 01 2022/2023 Institutional SDBIP developed | 01 2022/2023 draft Institutional SDBIP developed | Achieved | 01 2022/2023 draft Institutional SDBIP developed | None | None | Signed 2022/2023 Institutional SDBIP | R0.00
To compile 2020/2021 Institutional Annual Report by January 2022 | 2020/21 Annual Report | 2019/20 Annual Report in place | Number of 2020/21 Annual Reports developed | 01 2020/21 Annual Report developed | 01 2020/21 Annual Report and 1 oversight report developed | Not achieved | 01 2020/21 Annual Report in place and 1 oversight report not yet done | 2020/2021 AGSA report received late | The report to be tabled as per the legislation | Final 2020/2021 Annual Report and Oversight Report. | R0.00
To develop 2021/2022 Performance Agreements for Senior Managers by July 2021 | 2021/22 Performance Agreements for Senior Managers | 2020/21 Performance agreements and in place | Number of 2021/22 Performance Agreements for Senior Managers developed | 04 2021/22 performance agreements for Senior Managers developed | No Activity | N/A | N/A | N/A | N/A | Signed Performance Agreements of Senior Managers | R0.00
To facilitate performance assessments for senior managers by June 2022 | Individual performance assessments for senior managers | 2019/20 performance assessments for senior managers conducted | Number of performance assessments for senior managers conducted. (2020/21 Annual & 2021/22 Mid-term) | 02 performance assessments for senior managers conducted. (2020/21 Annual & 2021/22 Mid-term) | 02 performance assessments for senior managers conducted. (2020/21 Annual & 2021/22 Mid-term) | Not achieved | Performance assessments for senior managers not conducted. | Unavailability of panel membersas the result of conflicting schedule | Reschedule Assessments to fourth quarter | 2021/22 Mid-term and 2020/2021 Annual Assessment Reports | R0.00
To review PMS Policy and Framework by 30 June 2022 | Review of PMS Policy and Framework | 2020/2021 PMS Policy and Framework in place | Number of PMS Policies and Frameworks reviewed | 01 PMS Policy and Framework reviewed | Presentation of the policy to management and council committees | Achieved | Policy served at Management, LLF, Audit Committee and Mayoral Committee.It will be presented to Council in June Council seating | None | None | Reviewed PMS Policy and Framework | R0.00
To coordinate quarterly Back to Basics Reports by June 2022 | Back to Basics (B2B) | 2020/2021 B2B quarterly reports in place | Number of quarterly Back to Basics (B2B) reports coordinated | 04 quarterly B2B reports coordinated | 01 quarterly B2B report coordinated | Achieved | 01 quarterly B2B report coordinated | None. | None | 4 Quarterly B2B signed Reports | R0.00
LEGAL SERVICES
To manage litigations instituted against Sekhukhune District Municipality by June 2022 | Litigations | 15 Litigations attended to | Number of litigations attended to | 4 litigations attended to | 1 litigations attended to | Ahieved | 3 litigations attended to | None | None | Copies of Court judgments Copies of Summons Copies of Deeds of settlement | 6766500
To reduce value of contingency liability for SDM by June 2022 | Litigations | 15 Litigations attended to | Reduced percentage (%) value of contingency liability for SDM | 20% value of contingency liability reduced | 5% value of contigency liabity reduced | Ahieved | No case settled out of court | None | None | Comparitive value of contigent liability Setlements of of Court
To draft/vett service level agreements and other forms of agreements by June 2022 | Service level agreements and other forms of agreements | 310 service level agreements and other forms of agreements | Number of all service level agreements and other forms of agreements drafted or vetted | All of service level agreements or other forms of agreements drafted or vetted | All of service level agreements or other forms of agreements drfted or vetted | Ahieved | All of service level agreements or other forms of agreements drafted or vetted (14 contracts drfted and 5 vetted) | None | None | Copies of agreements
To provide legally sound advice to SDM by June 2022 | Legal opinions | 10 legal opinions | Number of legal opinions drafted | All legal opinions drafted | All legal opinions drafted | Ahieved | All legal opinions drafted (3 legal opinion Provided) | None | None | Copies of legal opinions
DISTRICT DEVELOPMENT PLAN (DDP) / INTEGRATED DEVELOPMENT PLAN (IDP)
To develop 2022/2023 IDP Framework/ Process Plan by August 2021 | Develop 2022/2023 IDP Framework/ Process Plan | 2021/2022 IDP Framework/Process Plan in place | Number of IDP Frameworks/Process Plans developed | 1 IDP Framework/ Process Plan developed | No activity | No activity | No activity | No activity | No activity | *IDP Framework/ Process Plan document for 2022/2023 *Council resolution | R0
To review the Integrated Development Plan (IDP) for 2022/2023 by June 2022 | Review of Integrated Development Plan (IDP) | 2021/22 Integrated Development Plan (IDP) developed | Number of Integrated Development Plans (IDP) reviewed | 1 Integrated Development Plan (IDP) reviewed | Draft reviewed IDP in place | Achieved | Draft reviewed IDP in place | None | None | *Final IDP 2022/2023 *Council Resolution | 60000
To facilitate the IDP Rep Forums by June 2022 | Facilitate the IDP Rep Forums | 2 IDP Rep Forums facilitated | Number of IDP Rep Forums facilitated | 2 IDP Rep Forums facilitated | 1 IDP Rep Forum facilitated | Not achieved | The IDP Rep Forum will be facilitated in April/May | The IDP Rep Forum could not be facilitated in March due to other commitments relating to IDP processes | The IDP Rep Forum will be facilitated in April/May | *Signed Minutes *attendance register | 100000
To facilitate review the District Development Plan (One Plan) by June 2022 | Review of 2022/2023 District Development Plan (DDP) | 2021/2022 District Development Plan (DDP) in place | Number of District Development Plan (DDP) reviewed | 1 District Development Plan (DDP) reviewed | Draft reviewed DDP in place | Not achieved | The DDP approved by Council in July 2021 is awaiting assessment results from CoGTA | All DDPs across the country were planned to be reviewed from May 2022 as per CoGTA directives | The review of the DDP will commence in Mat 2022 | *Final DDP 2022/2023 *Council Resolution