## CPS
DRAFT SDBIP 2021/2022
KPA: INSTITUTIONAL TRANSFORMATION & ORGANISATIONAL DEVELOPMENT
2021/2022 QUARTER 4 REPORT
2021/2022 SDBIP
MEASUABLE OBJECTIVES | PROJECT | BASELINE 2020/2021 | INDICATORS | ANNUAL TARGET 2021/2022 | Q4 | PROGRESS ACHIEVED/NOT ACHIEVED | ACTUAL PROGRESS | CHALLENGE | REMEDIAL | PORTFOLIO OF EVIDENCE | BUDGET 2021/2022
ORGANISATIONAL DEVELOPEMENT
To review the Organisational Structure by June 2022 | Organisational Structure Review | Approved Organisational Structure for 2020-2021 | Number of Organisational Structure Reviewed | 1 Organisational Structure Reviewed | 1 organisational structure reviewed and approved by Council | Achieved | 1 organisational structure reviewed and approved by Council | None | None | Council Resolution and Approved Organisational Structure | 0
To facilitate development of job descriptions and job evaluation by June 2022 | Job Description Development and Job Evaluation | 50 Job Descriptions Developed and Evaluated | Number of Job Descriptions Developed and facilitated for Evaluated | 50 Job Descriptions Developed and Facilitated for Evaluation | 10 Job Descriptions Developed and Facilitated for Evaluation | Achieved | 10 Job Descriptions Developed and Facilitated for Evaluation | None | None | Job Evaluation Report
INFORMATION AND COMMUNICATION TECHNOLOGY (ICT)
To establish effective network connectivity by June 2022 | ICT Infrastructure connection | 18 depots connected | Number of depots connections upgraded | 18 depots connections upgraded | Monitoring and evaluation | Not Achieved | Legal unit finalizing the MSA(Master Service Agreement). We received quatation to upgrade 18 depots connection | Delay in finalizing the Master Service Agreement | Expedite finalizing the Master Service Agreement | Reports | 500000
| Implementation of security measures | 05 of Security Control implemented | Number of Security Controls implemented | 24 Security Controls Implemented | 6 Security Controls Implemented | Achieved | 6 Security Controls implemented | None | None | Security measures | 400000
To conduct need analysis of ICT hardware and consumables by June 2022 | ICT consumables and hardware replacement | 50 ICT consumables and hardware replacement | Number of ICT consumables and Computers replaced | 30 ICT consumables and Computers replaced | 5 ICT consumables and Computers replaced | Achieved | 5 ICT consumables and Computers replaced | None | None | Laptop/Consumable Register | 1000000
To monitor expiry date of licenses by June 2022 | Software Licence renewal | 12 licenses renewed | Number of licenses renewed | 11 licenses renewed | No Activity | N/A | N/A | N/A | N/A | Licenses | 3859000
To monitor Service Level Agreements by June 2022 | Contract Monitoring | 12 SLA performance held | Number of SLA performance held | 16 SLA performance held | 4 SLA performance held | Achieved | 4 SLA performance held | None | None | Reports | 3159000
LABOUR RELATIONS
To Issue four labour relations publications by June 2022 | Issue Labour Relations Publications | 4 Labour relations publications issued. | Number of Labour relations publications issued | 4 Labour relations publications issued | 1 Labour relations publication issued | Achieved. | 1 Labour relations publication issued. | None. | None. | Copies of publications | R0.00
To facilitate Labour related grievances by June 2022 | Facilitate Labour Relations Grievances | 3 Grievance cases facilitated | Number of grievances cases received facilitated | All Labour related grievances cases received facilitated | All Labour related grievances cases received facilitated | N/A | No new grievances reported | None. | None. | Copies grievances | R0.00
To facilitate Labour related disciplinary cases by June 2022 | Facilitate labour related disciplinary cases | 7 disciplinary cases facilitated | Number of labour related disciplinary cases received facilitated | All labour related disciplinary cases received facilitated | All labour related disciplinary cases received facilitated | Achieved | All (1) disciplinary case facilitated. | Some Labour related disciplinary cases have moved to Legal services unit. | All Labour related disciplinary cases must brought back to Labour relations unit for proper management and accountability. | Reports and attendance registers | R0.00
To facilitate12 LLF meetings by June 2022 | Facilitate LLF Meetings | 9 LLF meetings held | Number of LLF meetings facilitated. | 12 LLF meetings facilitated | 3 LLF meetings facilitated. | Not achieved. | 1 LLF meeting facilitated. | Failure by parties to observe the annual scheduled meetings which led to failure to meet quorum. | SALGA facilitated workshop conducted for management component and hopefully there would improvement in the new financial year. | Minutes and attendance registers | R0.00
AUXILIARY SERVICES
To conduct records management awareness programme by June 2022 | Records management awareness | 2 Records management awareness facilitated | Number of Records management awareness facilitated | 02 Records management awareness facilitated | 01 Records management awareness facilitated | Achieved | 2 records management awareness facilitated, 1st held on the 9th December 2021& 2nd in March 2022 | None | None | Report, Attendance register | R0.00
To facilitate the development of file plan by June 2022 | File plan | 1 File plan developed | Number of File plan developed | 01 File plan developed | No activity | N/A | N/A | N/A | N/A | Report, Attendance register & Approved file plan | R0.00
To facilitate implementation of records (document) management system by June 2022 | Records (documents) management system | 1 Records management system in place. (MunAdmin) | Number of document management system implemented | 01 Record management system implemented | Monitoring implementation of the system. | Achieved | Monitoring implementation of the system done (Munadmin gradually been implemented i.e Legal Services.) | None | None | Signed training form. | R300 000
To maintain and repair the fleet and facilities by June 2022 | Maintenance and repairs | 20 vehicles Maintained and repaired | Number of vehicles Maintained and repaired | 20 vehicles Maintained and repaired | 20 vehicles Maintained and repaired | Not Achieved | No vehicle was maitaned and repaired during quarter 4 | Lack of Funds | Repairs to be done next financial 1st quarter | Maintanance Report | R1 800 000
To procure fleet mangement system by June 2022 | Fleet Management system | New project | Number of fleet management system procured | 01 fleet management system procured | Implementation of the fleet management system | Not Achieved | Workshop arranged with MUNADMIN on fleet management | Fleet Management Module was not included in the MUNADMIN | MUNADMIN system will include Fleet Manament module in the next financial year | Report | 500000
To settle the emergency vehicles by June 2022 | Settlement of emergency vehicles | 11 emergency vehicles settled | Number of emergency vehicles settled | 15 emergency vehicles settled | No Activity | N/A | N/A | N/A | N/A | Report, proof of payment Certificate | R12 000 000
HUMAN RESOURCE MANAGEMENT
To implement the process and procedures of Human Resource (HR) policies by June 2022 | Recruitment and Selection | 05 Vacant and funded positions filled | % of vacant funded positions filled | 100% Filling of vacant and funded positions | Appointment and induction of employees | Achieved | 30 Heavy Duty Operators employed. | None | None | Appointment letters | 98805.47
| Internal Bursaries | 9 Internal Bursaries maintained | Number of Internal Bursaries maintained | 09 Internal Bursaries maintained | Maintance of internal Bursaries | Achieved | 30 Internal Bursaries maintained | None | None | Bursary letters | 592830.76
| External Bursaries | 3 External Bursaries maintained | Number of External Bursaries maintained | 03 External Bursaries maintained | maintance of 3 external Bursaries | Achieved | 3 External Bursaries maintained | None | None | Bursary letters | 691636.24
To implement the WSP projects by June 2022 | WSP Projects | 02 WSP Projects Implemented | Number of WSP Projects implemented | 05 WSP Projects implemented | Implementation of 02 WSP projects | Achieved | 06 WSP projects implemented | None | None | WSP training report | 210000
EMPLOYEE ASSISTANCE PROGRAMME
To conduct employee wellness programmes by June 2022 | Employee wellness and Counselling | 4 wellness and counselling programmes conducted. | Number of wellness programmes conducted | 2 wellness awareness programmes conducted | No Activity | N/A | N/A | N/A | N/A | Wellness awareness programme attendance registers. | 571651.62
To conduct substance abuse programmes by June 2022 | Substance Abuse | 3 substance abuse programmes conducted | Number of substance abuse programmes conducted | 2 substance abuse programmes conducted | No Activity | N/A | N/A | N/A | N/A | Substance abuse programme registers.
To conduct Occupational Health and Safety elements by June 2022 | Occupational Health and Safety elements | 42 Occupational Health and Safety elements conducted | Number of Occupational Health and Safety elements conducted | 41 Occupational Health and Safety elements conducted (24 workplace inspections, 8 project audits, 2 safety awareness campaigns, 4 safety committee meetings, 2 servicing of fire extiquishers and hose reels). | 11 Occupational Health and Safety elements conducted (6 workplace inspections, 2 project audits, 1 safety committee meetings, 1 servicing of fire extiquishers and fire hose reels). | Not Achieved | 10 Occupational Health and Safety elements conducted (7 workplace inspections, 2 project audits, 1 safety committee meetings, 1 servicing of fire extiquishers and fire hose reels not done). | Supply hain Management processes which were witheld due to the order. | Servicing of fire extiquishers and fire hose reels will be done in the Q1 of the Financial year 2022/2023 | Workplace inspections and project audits reports, safety awareness campaigns attendance registers, safety committee meeting attendance registers, servicing of fire extiquishers and fire hose reels register . | 8345586.65
To provide personal Protective equipment by June 2022 | Personal Protective Equipment | 7692 Personal Protective Equipment (fire protection PPE) provided to Emergency Services employees, IWS, and CPS | Number of Personal Protective Equipment provided to IWS, Emergency Services, Municipal Health Services, CPS, Budget and Treasury, SDA, PED, Mayors and Speakers office employees | All Personal Protective Equipment provided to IWS, Emergency Services, Municipal Health Services, CPS, Budget and Treasury, SDA, PED, Mayors and Speakers office employees | All Personal Protective Equipment provided to IWS, Emergency Services, Municipal Health Services, CPS, Budget and Treasury, Mayors Office and Speakers office employees | Not Achieved | All Personal Protective Equipment (184 PPE items) were provided to IWS , CPS and Planning and Economic Development employees excluding EMS, MHS, BTO, Mayors office and sSpeakers office | Delay in Supply Chain Bid Committee processes | All Personal Protective Equipment will be provided to employees in Q2 of the financial year 2022/2023 | Memos, Proof of payments, Personal protective equipment issuing forms
LEGAL SERVICES
To manage litigations instituted against Sekhukhune District Municipality by June 2022 | Litigations | 15 Litigations attended to | Number of litigations attended to | 4 litigations attended to | 1 litigation attended to | Achieved | 4 litigation attended to | None | None | Copies of Court judgments Copies of Summons Copies of Deeds of settlement | 6766500
To reduce value of contingency liability for SDM by June 2022 | Litigations | 15 Litigations attended to | Reduced percentage (%) value of contingency liability for SDM | 20% value of contingency liability reduced | 5% value of contigency liability reduced | N/A | No cases settled out of court | None | None | Comparitive value of contigent liability Setlements of of Court
To draft/vett service level agreements and other forms of agreements by June 2022 | Service level agreements and other forms of agreements | 310 service level agreements and other forms of agreements | Number of all service level agreements and other forms of agreements drafted or vetted | All of service level agreements or other forms of agreements drafted or vetted | All of service level agreements or other forms of agreements drfted or vetted | Achieved | All (35) of service level agreements or other forms of agreements drfted or vetted (31 contracts drafted and 4 vetted) | None | None | Copies of agreements
To provide legally sound advice to SDM by June 2022 | Legal opinions | 10 legal opinions | Number of legal opinions drafted | All legal opinions drafted | All legal opinions drafted | Achieved | All (2) legal opinions drafted | None | None | Copies of legal opinions
PERFORMANCE MANAGEMENT
To facilitate Performance Makgotla by 30 June 2022 | Performance Makgotla | 3 Performance Makgotla Sessions held | Number of Performance Makgotla facilitated | 04 Performance Makgotla facilitated | 1 Performance Lekgotla facilitated | Achieved | 1 Performance Lekgotla facilitated | None | None | Attendance Registers, Makgotla Resolutions | 105141
To develop 2022/2023 Institutional SDBIP by June 2022 | 2022/2023 Institutional SDBIP | 2021/2022 Institutional SDBIP in place | Number of 2022/2023 Institutional SDBIP developed | 01 2022/2023 Institutional SDBIP developed | 01 2022/2023 final Institutional SDBIP developed | Achieved | 01 2022/2023 final Institutional SDBIP developed | None | None | Signed 2022/2023 Institutional SDBIP | R0.00
To compile 2020/2021 Institutional Annual Report by January 2022 | 2020/21 Annual Report | 2019/20 Annual Report in place | Number of 2020/21 Annual Reports developed | 01 2020/21 Annual Report developed | No activity | N/A | N/A | N/A | N/A | Final 2020/2021 Annual Report and Oversight Report. | R0.00
To develop 2021/2022 Performance Agreements for Senior Managers by July 2021 | 2021/22 Performance Agreements for Senior Managers | 2020/21 Performance agreements and in place | Number of 2021/22 Performance Agreements for Senior Managers developed | 04 2021/22 performance agreements for Senior Managers developed | No Activity | N/A | N/A | N/A | N/A | Signed Performance Agreements of Senior Managers | R0.00
To facilitate performance assessments for senior managers by June 2022 | Individual performance assessments for senior managers | 2019/20 performance assessments for senior managers conducted | Number of performance assessments for senior managers conducted. (2020/21 Annual & 2021/22 Mid-term) | 02 performance assessments for senior managers conducted. (2020/21 Annual & 2021/22 Mid-term) | No Activity | N/A | 01 performance assessments for senior managers conducted. (2020/21 Annual) | None | None | 2021/22 Mid-term and 2020/2021 Annual Assessment Reports | R0.00
To review PMS Policy and Framework by 30 June 2022 | Review of PMS Policy and Framework | 2020/2021 PMS Policy and Framework in place | Number of PMS Policies and Frameworks reviewed | 01 PMS Policy and Framework reviewed | 01 PMS Policy and Framework reviewed and adopted by Council | Achieved | 01 PMS Policy and Framework reviewed and adopted by Council | None | None | Reviewed PMS Policy and Framework | R0.00
To coordinate quarterly Back to Basics Reports by June 2022 | Back to Basics (B2B) | 2020/2021 B2B quarterly reports in place | Number of quarterly Back to Basics (B2B) reports coordinated | 04 quarterly B2B reports coordinated | 01 quarterly B2B report coordinated | Achieved | 01 quarterly B2B report coordinated | None | None | 4 Quarterly B2B signed Reports | R0.00
DISTRICT DEVELOPMENT PLAN (DDP) / INTEGRATED DEVELOPMENT PLAN (IDP)
To develop 2022/2023 IDP Framework/ Process Plan by August 2021 | Develop 2022/2023 IDP Framework/ Process Plan | 2021/2022 IDP Framework/Process Plan in place | Number of IDP Frameworks/Process Plans developed | 1 IDP Framework/ Process Plan developed | No activity | N/A | N/A | N/A | N/A | *IDP Framework/ Process Plan document for 2022/2023 *Council resolution | R0
To review the Integrated Development Plan (IDP) for 2022/2023 by June 2022 | Review of Integrated Development Plan (IDP) | 2021/22 Integrated Development Plan (IDP) developed | Number of Integrated Development Plans (IDP) reviewed | 1 Integrated Development Plan (IDP) reviewed | Final reviewed IDP in place | Achieved | Final reviewed IDP in place | None | None | *Final IDP 2022/2023 *Council Resolution | 60000
To facilitate the IDP Rep Forums by June 2022 | Facilitate the IDP Rep Forums | 2 IDP Rep Forums facilitated | Number of IDP Rep Forums facilitated | 2 IDP Rep Forums facilitated | 1 IDP Rep Forum facilitated | Achieved | 1 IDP Rep Forum Meeting was held on the 04 May 2022 | None | None | *Signed Minutes *attendance register | 100000
To facilitate review the District Development Plan (One Plan) by June 2022 | Review of 2022/2023 District Development Plan (DDP) | 2021/2022 District Development Plan (DDP) in place | Number of District Development Plan (DDP) reviewed | 1 District Development Plan (DDP) reviewed | Final reviewed DDP in place | Not Achieved | Review was done by CoGTA and not the municipality | Poor dissemination of information by Coghta | Improve on communication | *Final DDP 2022/2023 *Council Resolution | 100000