## BTO
DRAFT SDBIP 2021/2022
KPA: FINANCIAL VIABILITY
FINANCIAL VIABILITY
2021/2022 SDBIP
MEASUABLE OBJECTIVES | PROJECT | BASELINE 2020/2021 | INDICATORS | ANNUAL TARGET 2021/2022 | Q1 TARGET | PROGRESS (Achieved/ Not achieved) | ACTUAL PROGRESS | CHALLENGES | REMEDIAL ACTIONS | PORTFOLIO OF EVIDENCE | BUDGET 2021/2022
Manual GRAP Compliant FAR | Manual GRAP Compliant FAR | 100% accounting of assets | % accounting of assets | 100% accounting of assets | 100% fully functional fixed asset module | Not achieved | Asset module is in progress for implementation | The activity is depended on the service provider (BCX) and module is still under construction. | The module will only be installed after the testing | GRAP Compliant Fixed Asset Register/ Trial Balance | 4806000
| mSCOA implementation plan | 70% achievement of mSCOA implementation plan | % of activities on mSCOA implementation plan achieved | 100% of activities on mSCOA implementation plan achieved | 100% of all mSCOA modules fully operational by end of 1st Quarter | Not achieved | Asset module and Budget module in progress | The activity is depended on the service provider (BCX) and modules is still under construction. | The module will only be installed after the testing | Trial Balance/LG Portal Submission Reports | R0.00
To provide sound financial management | Functional budget steering committee | Credible budget prepared | Number of credible annual budgets prepared and implemented. | 2 Credible Annual Budgets prepared and implemented. | No activity | N/A | N/A | N/A | N/A | Council resolutions/Draft Budget Documents | R0.00
| Procurement plan | 2020/2021 procurement plan in place | Number of procurement plan developed | 1 procurement plan developed | Monitoring implementation of the plan | Achieved | Implementation of the plan monitored | None | None | Signed procurement plan | R0.00
| Irregular expenditure in the 2020/21 | Section 32 expenditure amount reported. | % Compliance with management of MFMA section 32 | 100% Compliance with management of MFMA section 32 | 1st Quarter reporting of UIF through Section 52 reports (Annexure A) | Achieved | UIF reported in the Sec 52 as required | None | None | Section 52 Report | 50000
| AFS preparations | Submission of AFS and APR to the AG within the legislated time frame | Compile AFS and APR within the legislated time frame | Compile AFS and APR within the legislated time frame | Submission of Annual Financial Statements and Audit Performance Report to AG | Achieved | AFS and APR subumitted to AGSA at the 31 August 2021 | None | None | Signed AFS and APR/ Ackonwledgement of receipt by AGSA | R1 650 000
| Identification of potential areas to be billed | *Collections and Capturing of consumer Data from 5 areas identified for potential biling. *Billing of 5 identified areas for potential revenue | Number of areas with revenue potential to be billed | Collection of data and billing of 5 areas with revenue potential | Data collection in 2 areas with revenue potential | Achieved | Data have been collected in 2 of the 5 areas with revenue potetial | Delay in capturing that into the billing system | BCX provider | Data Collection report and Summary of billing reports | R5,000 000
| Meter reading | 74%% Verification and reading of 13100 customers' meters | % of customer's meters valitated and read | 75% Validation and reading of customers meters | 60% Validation and reading of customers meters | Achived | 87,3% validation and readings of customers meters | Denied accessed to meter readings in some areas remain a challenge | Political intervention is required in areas refusing meter readings | Meter reading report | R7,500 000
| Billing of Customers | Billing of 80 % of 41133 customers | % of customers billed | 90% of 41200 customers to be billed | 80% of 41200 customers to be billed | Achived | 86% of customers were billed | Avarage was billed were meters could not be read | Political intervention is required in areas refusing meter readings | Billing report | 1500000
| Improve collection rate | Improve the collection rate to 75% | % improvement of collection rate | 75% of revenue collected against the billing | improvement collection rate to 65% | Not Achieved | 53,3% debtors collection rate | lack of capacity to disconnect services | Extend the meter readers scope to effect disconnections | Collection rate report | 4500000
|  | R241m. debt book | % Reduction of debt book | 2% reduction of debt book | 1%reduction debt book | Not Achieved | Debtors book have increased by 5% | lack of capacity to disconnect services | Extend the meter readers scope to effect disconnections | Own revenue reports/Debtors age analysis report | R0.00
| Free basic services | Indigent register for 2020/2021 | % of indigent customers | 10% increase in indigent customers | 5%Collection of customers'indigent registration data | Not Achieved | Indigents data have been collected and are awaiting verification | Awaiting the appointment of a provider to do verifications | Fast track the appoinment of a provider to do indigent regsiter verifications | Indigent register for 2021/2022 | 3000000
ACTING CFO: BUDGET & TREASURY
Mr. NKADIMENG HENDRICK
DATE: _________________________