## Sheet1
2021/2022 SERVICE DELIVERY BUDGET AND IMPLEMENTATION PLAN
GOOD GOVERNANCE AND PUBLIC PARTICIPATION
OBJECTIVES | PROJECT | BASELINE 2020/2021 | INDICATORS | ANNUAL TARGET 2021/2022 | Q1 TARGET | PROGRESS (Achieved/ Not achieved) | ACTUAL PROGRESS | CHALLENGES | REMEDIAL ACTIONS | POE | BUDGET 2021-2022
INTERNAL AUDIT
To ensure improved internal controls and clean governance in the municipality by June 2022 | Development of the Three(3) Years rolling Plan | Development of 2020-2021 Three Year Internal audit rolling plan | Number of (SDM & SDA) 3 years rolling plans developed | 2 (SDM & SDA) 3 years rolling plans developed | 2 (SDM & SDA) 3 years and annual Internal Audit rolling plans developed | Not Achieved | 2 (SDM & SDA) 3 years and annual Internal Audit rolling plans developed. SDA IA Plan not approved | Fourth Quarter SDA Audit Committee meeting was postponed due to time management | The Audit Committee Meetings will be held in two days to cover all the agendas. (SDM) and SDA and PAC.The SDA plan will be approved in the next Audit Committee meetings | Approved 3 Years and Annual Internal Audit rolling Plan for SDM and SDA by Audit Committee-Audit Committee Minutes | R0.00
| Conduct Regularity audit | 22 regularity audits conducted | Number of regularity audit conducted | 20 Regularity Audits conducted | 4 regularity audits Conducted | Not Achieved | 3 regularity Audits were conducted | Late approval of the IA plans | Fastrack the finalisation of the first quarter Audit Projects | Signed Regularity Audit Reports | R884 850.00
| Conduct Ad hoc Audits | Conduct Ad Hoc Audits | Percentage Ad Hoc audits conducted | 100% Management requests/ investigations conducted as and when required | 100% Management requests/ investigations conducted as and when required | Achieved | 100% Management requests/ investigations conducted as and when required - 04 due dilligence were conducted | None | None | Signed Management /Investigation reports | R 7 173 687.15
| To conduct ICT Audits | 4 ICT Audits reports conducted | Number of ICT Audits conducted | 4 ICT Audit reports conducted | 1 ICTAudits conducted | Not Achieved | 1 ICTAudits not conducted | The Three Year Rolling Plan was approved late due to late finalisation of the Risk Assessment and Backlog of the Audit Projects | ICT Audit Projects to be conducted in the second quarter | Signed ICT Audits Reports | R0.00
| To conduct Audits of Performance Information | 8 Audit of Performance information conducted | Number of Audit of Performance Information conducted | 8 Audit of Performance Information conducted | 2 AOPI conducted | Achieved | 2 AOPI conducted | None | None | Signed AOPI Reports | R0.00
| Monitoring of implementation of auditor general activities | 100% monitoring of implementation of AG activities | Percentage monitoring of External Audit implementation plan | 100%monitoring of external Audit Implementation plan | 100% monitoring of implementation of AG activities | Achieved | 100% monitoring of implementation of AG activitie | None | None | Audit Action plan,Signed Minutes,proof of payments | R0.00
| Monitoring of Internal Audit Implementation plan | 100% monitoring of Internal Audit Implementation plan | Percentage monitoring of Internal Audit implementation plan | 100%monitoring of Internal Audit Implementation plan | 100%monitoring of Internal Audit Implementation plan | Achieved | 100%monitoring of Internal Audit Implementation plan | None | None | Internal Audit Implementation plan | R0.00
| Coordination of Audit Committee and Performance Audit Committee | 7 (4 ordinary) and (3 special ) meetings of audit and performance committees coordinated | Number of meetings of audit and performance committees coordinated | 7 (4 ordinary) and ( 3 special ) meetings of audit and performance committees coordinated | 2 meetings of audit and performance committees coordinated | Achieved | 2 Special Audit Committee ( Review of AFS and Review of Consolidated AFS) Meetings and Fourth Quarter Ordinary Audit Committee Meeting for SDM were held in the month of september | None | None | Signed Minutes/Agenda/Signed AC Reports | R 520 500.00
| Monitoring implementation of the operation clean audit strategy | 100% monitoring of the operation clean audit strategy | Percentage monitoring of the operation clean audit strategy | 100%monitoring of the operation clean audit strategy | Development and approval of the operation clean Audit Strategy | Achieved | The Operation Clean Audit Strategy is developed and will be presented to council October 2021 | None | None | Approved operation clean Audit Strategy/Minutes of OPCA meetings/Quarterly Reports | R0.00
| Conducting external assessment review | None | Number of external quality assessment performed | 1 external quality assessment performed | No activity | No activity | None | None | None | External Assessment Review Report | R300 000.00 | R8,879, 037.15
RISK MANAGEMENT
To assess, identify, and manage risks and uncertainty to safeguards assets, enhance productivity, and build resilience into the operations by June 2022 | Conduct Strategic Risk Assessment and review risk register | Strategic Risk Register in /place | Number of Strategic Risk Assessment conducted, and Strategic Risk Registers reviewed | *1 Strategic Risk Assessment conducted * 4 Strategic Risk Registers reviewed | 1.1 x Strategic Risk Assessment conducted 2.Monitor & review Risk Register | Achieved | 1.1 x Strategic Risk Assessment conducted 2.Monitor & review Risk Register | None | None | Strategic Risk Register report | R0.00
| Conduct Operational Risk Assessment and review risk register | Operational Risk Registers in place | Number of Operational Risk Assessment Conducted and Operational Risk Registers reviewed | *1 Operational Risk Assessment Conducted *4 Operational Risk Registers reviewed | 1, 1 x Operational Risk Assessment conducted 1.Monitor & review Operational Risk Register | Achieved | 1, 1 x Operational Risk Assessment conducted 1.Monitor & review Operational Risk Register | None | None | Operational Risk Registers report | R0.00
| Conduct Processes Risk Assessments | 2 x Processes risk assessment conducted | Number of Processes risk assessments conducted | 7 x Processes risk assessments conducted | 1 x Process Risk Assessment conducted 2.Monitor & review Processes Risk Register | Not Achieved | 1 x Process Risk Assessment conducted 2.Monitor & review Processes Risk Register | Capacity contstraints | To be implemented in the second quarter | Processes Risk Registers report | R0.00
| Facilitate insurance coverage for municipal assets | 1 x Assets Insurance Policy contract entered into. | Number of insurance coverage for municipal assets facilitated | All insurance coverage for municipal assets facilitated | 1.Insurance coverage for municipal assets facilitated 2.Update insurance policy for additions and deletions | Achieved | 1.Insurance coverage for municipal assets facilitated 2.Update insurance policy for additions and deletions | None | None | Assets Insurance Policy contract | R6 131 490. 00
| Facilitate Assets Insurance Claims and payments | Insurance claims report facilitated | Percentage processing and facilitation of insurance claims and payments | 100% insurance claims processing, and payments of repairs, losses and excess facilitated | 100% insurance claims processing and payments facilitated | Achieved | 100% insurance claims processing and payments facilitated | None | None | Insurance Claims report | R 968 851,00
| Manage Security operations and SLA | All incidents occurred reported | Number of incidents occurred, and SLA managed | All occurred incidents and SLA managed | 4 x Security cluster operations and contracts managed | Achieved | 4 x Security cluster operations and contracts managed | None | None | Quarterly Security Report | R30 000 000. 00
| Conduct Security Operational Sites Assessments | Security operational Sites Assessment conducted | Number of Security Operational sites assessments conducted | Forty (40) Security Operational sites assessments conducted | Forty (10) Security Operational sites assessments conducted | Achieved | Ten(10) Security Operational sites assessments conducted | None | None | Quarterly Security Operational Sites Report produced/compiled | R0.00
| Facilitate the establishment of an Anti-Fraud & Corruption hotline | Fraud and Corruption cases reported and investigated | Number of fraud and corruption allegation cases reported for referral and investigations facilitated | All fraud and corruption allegation cases reported for referral and investigations facilitated | All fraud and corruption allegation cases reported for referral and investigations | N/A | No cases reported | N/A | N/A | Fraud and Corruption Cases report | R0. 00
| Facilitate the development of a Business Continuity Management plan | Business Continuity Management Framework in place | Number of phases of the Business Continuity Management plan completed | 100% completion of phase one (01) of the Business Continuity Management plan | Stage 1 of Phase 01 of the BCM Plan facilitated | Not Achieved | Stage 1 of Phase 01 of the BCM Plan not facilitated | Tight schedule | To be implemented in the second quarter | Business Impact Analysis report | R0. 00
To assist the Accounting Officer/Authority in addressing its oversight requirements of risk management and evaluating and monitoring the municipality’s performance with regards to risk management | Facilitate Risk Management Committee (RMC) meetings | One (01) Risk Management Committee held | Number of Risk Management Committee (RMC)meetings facilitated | 4 x Risk Management Committee (RMC) meetings facilitated | 1 x Risk Management Committee (RMC) meetings facilitated | Not Achieved | 1 x Risk Management Committee (RMC) meetings facilitate | Chairperson not appointed | Fastrack the appointment of chaiperson | Risk Management Committee report | R80 000
|  | Two (02) Audit Committee meetings held to consider Risk Management Committee report |  |  |  | Achieved | One Audit Committee meetings held to consider Risk Management Committee report | None | None |  |  | R37, 180,341.00
COMMUNICATIONS; ADVOCACY; SOCIAL FACILITATION; SPECIAL PROGRAMMES AND ARTS & CULTURE
To facilitate stakeholder & sectorial engagement by June 2022 | Mayoral Outreaches and Sectorial Engagements | 12 Programmes facilitated | Number of community & sectorial engagements facilitated | 8 stakeholder & sectorial engagements facilitated | 2 stakeholder & sectoral engagement facilitated | Achieved | 2 stakeholder & sectoral engagement facilitated 10/09/2021 at Ga Radingwana. Intervention meeting. Special meeting DWS, Lepelle Nothern Water and SDM with Eensaam forum members 21/09/2021 at Makhuduthamaga Chambor. | None | None | Attendace Register & Exit report | R800 000,00
To provide support to Mayoral Committee by June 2022 | Executive Support to Mayoral Committee | 12 Mayoral Committee meetings supported | Number of Mayoral Committee meetings supported | 12 Mayoral Committee meetings supported | 3 Mayoral Committee meetings supported | Achieved | 5 Mayoral committee meetings supported. Mayoral committee held 21/07/2021, 25/08/2021 ordinary and 27/08/2021 at Lekgotla Boardroom. Mayoral committee held 20/09/2021 ordinary and 23/09/2021 special at chambor. | None | None | Attendace Registers | R0.00
To produce newsletters by June 2022 | Newsletter& Publications | 16 Programmes produced | Number of newsletters produced | 8 newsletters produced. | 1 external and 1 internal newsletters produced | Achieved | 1 internal and 1 external newsletters produced | None | None | Newsletters | R500 000,00
To market and brand events by June 2022 | Media Relations and Marketing | 12 Events Branded | Number of events Marketed and branded | 12 Events marketed and branded | 3 events marketed and branded | Achieved | 17 events marketed and branded. 6 Media statements,1 heritage advert and 10 public notices. | None | None | Exit reports, pictures\publications | R100 000,00
To undertake website updates by June 2022 | Website Management | 20 Updates undertaken | Number of Website Updates undertaken | 12 Website Updates undertaken | 3 Website Updates undertaken | Achieved | 12 Website updates undertaken | None | None | Screenshots | R150 000,00
To facilitate meetings for Traditional Leaders by June 2022 | Executive Support and Traditional Leadership Affairs | 2 SPLUMA meetings supported | Number of Traditional Leadership meetings facilitated | 3 Traditional Leadership meetings facilitated | No activity | N/A | N/A | N/A | N/A | Attendance registers and exit reports | R0. 00
To facilitate strategic events by June 2022 | Special Mayoral strategic Events | 5 strategic events Facilitated | Number of Strategic Events facilitated | 5 strategic events facilitated | 1 strategic events facilitated | Achieved | 1 strategic events facilitated.Heritage and Language Promotion held 24/09/2021 at Masemola high school | None | None | Attendance registers and exit reports | R500 000,00
To facilitate Moral Regeneration Movement committee programmes by June 2022 | Strengthening of Moral Regeneration Movement Committee | MRM committee established | Number of programmes for MRM committee facilitated | 2 MRM committee programme facilitated | No activity | N/A | N/A | N/A | N/A | Attendance registers and exit reports | R100 000,00
To generate Customer Care reports by June 2022 | Customer Care Services | 24 reports generated | Number of reports generated | 24 queries/ complains reports on customer care generated | 6 customer care reports generated | Achieved | 6 customer care reports generated | None | None | Exit reports | R0.00
To revamp the Call Centre by June 2022 | Call Centre Revamping & Maintenance | 24 hour outdated call centre system | Number of call centre revamped | 1 call centre revamped | No activity | N/A | N/A | N/A | N/A | Report | R600 000,00
To conduct Batho Pele programmes by June 2022 | Batho Pele | 6 Programmes conducted | Number of Batho Pele Programmes conducted | 4 Batho Pele Programmes conducted | 1 Batho Pele Programmes conducted | Achieved | 1 Batho Pele Programmes conducted. Build up event 30/09 tsantsabela- Relegae | None | None | Reports | R100 000,00
To co-ordinate SODA by June 2022 | SODA | 2020/2021 SODA held | Number of SODA coordinated | 1 SODA coordinated | No activity | N/A | N/A | N/A | N/A | Attendance registers and exit reports | R450 000,00
To facilitate campaigns for the elderly by June 2022 | Aged care | 2 aged care programmes facilitated | Number of Aged Care campaigns facilitated | 2 Aged Care campaigns facilitated | 1 elderly campaign facilitated | Achieved | 1 elderly campaign facilitated. Mandela Day held at Bokgwaswa elderly club 26 August 2021 | None | None | Attendance registers and exit reports | R200 000,00
To facilitate campaigns for the children by June 2022 | Children’s Care | 2 children’s activities facilitated | Number of children's campaigns facilitated | 2 children's campaigns facilitated | No activity | N/A | N/A | N/A | N/A | Attendance registers and exit reports | R100 000,00
To facilitate campaigns for women by June 2022 | Woman Development Initiative | 4 Women Programmes facilitated | Number of woman development initiatives facilitated | 3 woman development initiatives facilitated | 1 programme for women facilitated | Achieved | 2 programme for women facilitated. Women month celebration at Bareki Mall 12\08\2021. Keerom Metaneng Primary School Young women dialoque in partnership with Storyline foundation and GCIS | None | None | Attendance registers and exit reports | R300 000,00
To facilitate Awareness campaigns for people with disability by June 2022 | People with disability | 3 Programmes facilitated | Number of awareness campaigns for people with disability facilitated | 2 awareness campaigns for people with disability facilitated | 1 awareness campaign for people with disability facilitated | Achieved | 1 awareness campaign for people with disability facilitated. Mandela Day held on the 26 August 2021 at Bogaswa elderly club | None | None | Attendance registers and exit reports | R200 000,00
To facilitate art and culture programmes by June 2022 | Cultural Heritage Celebrations and Language Promotions | 2 Programmes facilitated | Number of Heritage and promotions of indigenous languages and theatre workshop facilitated | 1 Heritage day and 2 promotions of indigenous languages and Theatre workshop facilitated | 1 art and culture programme facilitated | Achieved | 1 art and culture programme facilitated. Heritage and language promotion held on the 24th September 2021 at Masemola high | None | None | Attendance registers and exit reports | R500 000,00
To coordinate health calendar days activities by June 2022 | Coordination of health calendar days activities | 3 health calendar days activities conducted | Number of health calendar days activities coordinated | 3 Health calendar days activities coordinated | No activity | N/A | N/A | N/A | N/A | Attendance registers and exit reports | R200 000,00
To coordinate district AIDS Council activities by June 2022 | Coordination of District AIDS Council activities | 4 District Aids Council activities coordinated | Number of district AIDS Council activities coordinated | 4 district AIDS Council activities coordinated | No activity | N/A | N/A | N/A | N/A | Attendance registers and exit reports
To facilitate Youth development programmes by June 2022 | Youth Opportunities Expo | 3 Programmes facilitated | Number of Youth development programmes facilitated | 3 Youth development programmes facilitated | No activity | N/A | N/A | N/A | N/A | Attendance registers and exit reports | R900 000 00
To facilitate Mayor’s forum activities by June 2022 | Facilitation of Mayor’s forum | 4 Mayor’s forum facilitated | Number of Mayor’s forum facilitated | 4 Mayor’s forum facilitated | 1 Mayor’s forum facilitated | Not Achieved | Mayor's forum preparations finalised | Unable to hold Mayor's forum due to executive Mayor's tight schedule | Mayors forum rescheduled to be held on the 05 October 2021 | Attendance registers and exit reports | R0.00
To facilitate Mayoral sports activities by June 2022 | Facilitation of Mayoral Sports activities | 2 Mayoral Sport activities facilitated | Number of Mayoral Sport activities facilitated | 2 Mayoral Sport activities facilitated | No activity | N/A | N/A | N/A | N/A | Attendance registers and exit reports | R500 000,00 | R6,200,000.00
PUBLIC PARTICIPATION, MPAC SUPPORT; SECRETARIAT AND SUPPORT
Provide secretarial support to 10 council structures to ensure accountability by June 2022 | FORA | 16 Fora facilitated | Number of fora facilitated | 16 Fora facilitated | 1 Speakers' Forum, 1 Chief Whips' Forum, 1 Public participation Forum facilatated. | Achieved | 1 Speakers' Forum &1 Chief Whips' Forum facilatated on 08/09/2021 respectively. 1 Public Participation Forum facilitated on 11/08/2021 | None | None | Notice & Attendance registers | R75 000.00
| Public participation sessions. | 15 public participation sessions facilitated | Number of public consultation meetings facilitated | 15 public participation facilitated | No activity | No activity | No activity | No activity | No activity | Attendance registers and exit reports | R750 000.00
| SODA & Budget Day | 1 SODA , 1 Budget Day facilitated | Number of SODA and Budget days facilitated | 1 SODA , 1 Budget Day facilitated | No activity | No activity | No activity | No activity | No activity | Notice and attendance registers | R0.00
| Council and portfolio committee meetings | 22 Council and portfolio committee meetings facilitated | Number Council and portfolio committee meetings facilitated | 24 Council and portfolio committee meetings facilitated | 1 Ordinary Council Meetings and 5 Portfolio Committee Meetings facilitated. | Achieved | 1 Ordinary Council Meeting - 29/07/21, 2 Special Council Meetings - 30/08/21 & 29/09/21 and 15 Portfolio Committee Meetings facilitated | None | None | Notice and attendance registers | R500 000.00
| Study group | 4 study groups facilitated | Number of study groups facilitated | 4 study groups facilitated | 1 Study Group Facilitated. | Achieved | 1 study group facilitated on 28/07/21 | None | None | Notice and attendance registers | R65 000.00
| Public hearings | 2 public hearings facilitated | Number of public hearings facilitated | 2 public hearings facilitated | No activity | No activity | No activity | No activity | No activity | Notice and attendance registers | R200 000.00
| Strategic planning sessions for Section 79 Portfolio Committees & MPAC | 2 strategic planning sessions facilitated | Number of strategic planning session facilitated | 2 strategic planning sessions facilitated | 1 MPAC Startegic Planning Session facilitated. | Achieved | 1 MPAC Annual Work Planning Programme facilitated in July 2021 | None | None | Notice and attendance registers | R350 000.00
| Capacity building workshops | 2x workshops facilitated | Number of workshops facilitated | 2x workshops facilitated | 1 capacity building Workshop on Rules of order and Standing Orders of Council/ Code of Conduct facilitated. | Achieved | Capacity building workshop on Rules of Order and Standing Orders of Council/Code of Conduct facilitated in June 2021 as per request of Council | None | None | Notice and attendance registers | R300 000.00
| Training and development of Cllrs | 2x councillors trained | Number of councillors trained | 10x Councillors trained | 10 Councillors identified for training programmes facilitated. | Not achieved | 10 Cllrs identified for training programmes not facilitated | Term of office ends on the 01/11/2021 when Local Government Elections are held. | 10 Cllrs will be identified for training programmes after the inauguration of new Councillors | Exit report | R600 000.00
| Queries and assistance of travel claims | 100% resolution of Cllrs queries facilitated | Percentage resolution of Cllrs queries facilitated | 100% resolution of Cllrs queries facilitated | 100% resolution of Cllrs queries facilitated. | Achieved | 100% resolution of cllrs queries facilitated (recording queriesv10%, submission and attending to queries 70%, feedback 20%) facilitated | None | None | Exit report | R0.00
| Resolution registers for Council implementation. | 4 Council Resolution registers compiled and coordinated | Number of Council Resolution registers compiled and coordinated | 4 Council Resolution registers compiled and coordinated | 1 council resolution register compiled and cordinated. | Achieved | Council Resolution register compiled | None | None | Council resolution register | R0.00
| Council whippery meetings facilitated | 4 meetings held | Number of meetings facilitated | 4 Council Whippery meeting Facilitated. | 1 Council Whippery meeting Facilitated. | Achieved | 1 Council Whippery meeting facilitated on 26/07/2021 | None | None | Notice and attendance registers | R20 000.00
| Review of public participation policy | 1 public participation policy review facilitated | Number of public participation policy review facilitated | 1 public participation policy review facilitated | Circulate public participation policy to SDM personnel and Local Municipalities for inputs. | Achieved | Public participation policy submitted to Council for approval on 29/07/2021 | None | None | Council resolution certificate | R0.00
| Working sessions for Cllrs. | 8 MPAC Working sessions for Cllrs facilitated | Number of MPAC working sessions for Cllrs facilitated | 8 MPAC working sessions for Cllr facilitated. | 2 MPAC working sessions for Cllr facilitated. | Achieved | 10 MPAC working sessions facilitated | None | None | Notice and attendance registers | R180 000.00