## CPS
DRAFT SDBIP 2021/2022
DEPARTMENT: CORPORATE SERVICES
MEASUABLE OBJECTIVES | PROJECT | BASELINE 2020/2021 | INDICATORS | ANNUAL TARGET 2021/2022 | Q1 | Q2 | Q3 | Q4 | PORTFOLIO OF EVIDENCE | BUDGET 2021/2022
ORGANISATIONAL DEVELOPEMENT
By reviewing the Organisational Structure | Organisational Structure Review | Approved Organisational Structure for 202-2021 | Number of Organisational Structure Reviewed | 1 Organisational Structure Reviewed | [5 empty] | R0.00
By facilitating development of job descriptions and job evaluation | Job Description Development and Job Evaluation | 50 Job Descriptions Developed and Evaluated | Number of Job Descriptions Developed and Evaluated | 50 Job Descriptions Developed and Facilitated for Evaluation
By conducting change management awareness campaigns | Change Management | Approved Change Management Plan | Number of Change Management Session Facilitated | 2 Change Management Sessions Facilitated
INFORMATION AND COMMUNICATION TECHNOLOGY (ICT)
By establishing effective network connectivity | ICT Infrastructure connection | 18 depots connected | Number of depots connections upgraded | 18 depots connections upgraded | [5 empty] | 500000
| Implementation of security measures | 05 of Security Control implemented | Number of Security Controls implemented | 24 Security Controls Implemented | [5 empty] | 400000
By conducting need analysis of ICT hardware and consumables | ICT consumables and hardware replacement | 50 ICT consumables and hardware replacement | Number of ICT consumables and Computers replaced | 30 ICT consumables and Computers replaced | [5 empty] | 1000000
By monitoring expiry date of licenses | Software Licence renewal | 12 licenses renewed | Number of licenses renewed | 11 licenses renewed | [5 empty] | 3859000
By monitoring Service Level Agreements | Contract Monitoring | 12 SLA performance held | Number of SLA performance held | 16 SLA performance held | [5 empty] | 3159000
LABOUR RELATIONS
Issue four labour relations publications by June 2022 | Issue Labour Relations Publications | 4 Labour relations publications issued. | Number of Labour relations publications issued | 4 Labour relations publications issued | [5 empty] | R0.00
To facilitate Labour related grievances by June 2022 | Facilitate Labour Relations Grievances |  | % of Labour related grievances facilitated | 100% Labour related grievances facilitated | [5 empty] | R0.00
To facilitate Labour related disciplinary cases by June 2022 | Facilitate labour related disciplinary cases |  | % of Labour related disciplinary cases facilitated | 100% Labour related disciplinary facilitated. | [5 empty] | R0.00
To facilitate12 LLF meetings by June 2022 | Facilitate LLF Meetings |  | Number of LLF meetings facilitated. | 12 LLF meetings facilitated | [5 empty] | R0.00
AUXILIARY SERVICES
By conducting records management awareness programme | Records management awareness | 2 | Number of Records management awareness facilitated | 02 Records management awareness facilitated | [5 empty] | R0.00
By facilitating the development of file plan | File plan | 1 | Number of File plan developed | 01 File plan developed | [5 empty] | R0.00
By ensuring purchase of filling cabinets | Purchase of filling cabinets | 6 | Number of filling cabinets purchased | 06 filling cabinets purchased | [5 empty] | 200000
By facilitating implementation of records management system | Records management system | 1 | Number of Records management system implemented | 01 Records management system implemented | [5 empty] | R300 000
By ensuring maintenance and repairs for fleet and facilities | Maintenance and repairs | 20 | Number of vehicles Maintained and repaired | 20 vehicles Maintained and repaired | [5 empty] | R1 800 000
By ensuring that provision of facility and fleet management system is in place | Fleet management system | 1 | Number of Fleet management system developed | 01 Fleet management system developed | [5 empty] | 500000
By ensuring that emergency vehicles are settled | Settlement of emergency vehicles | 11 | Number of emergency vehicles settled | 15 emergency vehicles settled | [5 empty] | R12 000 000
HUMAN RESOURCE MANAGEMENT
By implementing the process and procedures of Human Resource (HR) policies | Recruitment and Selection | 05 Vacant and funded positions filled | % of vacant funded positions filled | 100% Filling of vacant and funded positions | [5 empty] | 120000
| Internal Bursaries | 9 Internal Bursaries maintained | Number of Internal Bursaries maintained | 09 Internal Bursaries maintained | [5 empty] | 670000
| External Bursaries | O3 External Bursaries maintained | Number of External Bursaries maintained | 03 External Bursaries maintained | [5 empty] | 664000
By conducting skills audit | WSP Projects | 02 WSP Projects Implemented | Number of WSP Projects implemented | 05 WSP Projects implemented | [5 empty] | 2100000
EMPLOYEE ASSISTANCE PROGRAMME
To conduct employee wellness programmes by June 2022 | Employee wellness and Counselling | 4 wellness and counselling programmes conducted. | Number of wellness programmes conducted | 04 wellness awareness programmes conducted | [5 empty] | R549 137.00
To conduct substance abuse programmes by June 2022 | Substance Abuse | 3 substance abuse programmes conducted | Number of substance abuse programmes conducted | 04 substance abuse programmes conducted
To conduct Occupational Health and Safety elements by June 2022 | Occupational Health and Safety elements | 42 Occupational Health and Safety elements conducted | Number of Occupational Health and Safety elements conducted | Occupational Health and Safety elements conducted (30 workplace inspections, 13 project audits, 4 safety awareness campaigns, 4 safety committee meetings, 1 servicing of fire extiquishers). | [5 empty] | R8 016 894.00
| Personal Protective Equipment | 3936 Personal Protective Equipment (fire protection PPE) provided to Emergency Services employees, IWS, and CPS | Number of Personal Protective Equipment provided to IWS, Emergency Services, Municipal Health Services, CPS, Budget and Treasury, SDA and PED employees | Personal Protective Equipment provided to IWS, Emergency Services, Municipal Health Services, CPS, Budget and Treasury, SDA, PED, Mayors and Speakers office employees

## PED
DRAFT SDBIP 2021/2022
DEPARTMENT: PLANNING AND ECONOMIC DEVELOPMENT
MEASUABLE OBJECTIVES | PROJECT | BASELINE 2020/2021 | INDICATORS | ANNUAL TARGET 2021/2022 | Q1 | Q2 | Q3 | Q4 | PORTFOLIO OF EVIDENCE | BUDGET 2021/2022
SPATIAL RATIONALE
Facilitate Joint District Municipal Planning Tribunal (JDMPT) sittings by June 2022 | Joint District Municipal Planning Tribunal sittings | 4 JDMPT sittings facilitated | Number of JDMPT sittings facilitated | 4 JDMPT sittings facilitated | [5 empty] | 500
Facilitate Land Acquisition for District Municipal Offices by June 2022 | Facilitate Land Acquisition for District Municipal Offices | Land donation letter available | Number of Land acquisition agreement Signed | 1 land acquisition Agreement signed | [5 empty] | 60
Process Land Development applications in line with reviewed SDF by June 2022 | Process Land Development applications in line with the reviewed SDF | Processed 6 Land Development applications in line with the reviewed SDF | % of received Land Development applications processed in line with reviewed SDF | 100% of received Land Development applications processed in line with reviewed SDF | [5 empty] | R0.00
Facilitate Formalisation of Informal Settlements by June 2022 | Formalisation of Informal Settlements (Jane Furse, Phokwane) | None | Number of Informal Settlements (Jane Furse, Phokwane) within the District formalised | 2 informal settlement (Jane Furse, Phokwane) within the District formalised | [5 empty] | R0.00
Develop Precinct Plans in Nodal /Growth points by June 2022 | Develop Precinct Plans in Nodal/Growth points ( Moroke-Meckleinburg and Dennilton) | None | Number of Precinct Plans in Nodal /Growth points developed( Moroke-Meckleinburg and Dennilton) | 2 Precinct Plans in Nodal/Growth points( Moroke-Meckleinburg and Dennilton) | [5 empty] | R0.00
Facilitate workshop to Traditional Leaders on land use and land allocations in terms of SPLUMA by June 2022 | Facilitate workshop to traditional Leaders on land use and land allocation in terms of SPLUMA | None | Number of Workshop facilitated | 2 Workshop to Traditional Leaders on land use and land allocation in terms of SPLUMA | [5 empty] | R0.00
Facilitate workshop to Local Municipal Officials on application processing in terms of SPLUMA by June 2022 | Facilitate workshop to Local Municipal Officials on application processing in terms of SPLUMA | None | Number of Workshop facilitated | 2 workshop to Local Municipal Officials on application processing in terms of SPLUMA | [5 empty] | R0.00
Integrate Municipal Geographic Information System (GIS), (Finance, Asset Management System) by June 2022 | Integrate Municipal Geographic Information System (GIS)- (Finance and Asset Management System) | GIS Strategy in place | Percentage integration of Municipal Geographic Information System (GIS)- (Finance and Asset Management system) | 100% integration of Municipal Geographic Information System (GIS) – (Finance and Asset Management ) | [5 empty] | R 1 000 000
To review GIS strategy by June 2022 | Review of GIS Strategy | 2009 GIS strategy in place | Percentage review of GIS strategy | 100% review of GIS strategy | [5 empty] | 500000
By spatially reference the District Development Plan (DDP) capital projects by June 2022 | Spatial referencing of District Development Plan(DDP) Capital Projects | 50 Projects spatially referenced | Number of District Development Plan (DDP) capital projects spatially referenced | 40 District Development Plan (DDP) capital projects spatially referenced | [5 empty] | 50
LOCAL ECONOMIC DEVELOPMENT
Create 2 788 job Opportunities through EPWP by 30 June 2022 | Implementation of EPWP | 2 448 job opportunities created through EPWP | Number of jobs opportunities created through EPWP | 2 788 jobs created through EPWP | [5 empty] | R8 180 000
Facilitate development of SMMEs and Cooperatives development strategy by 30 June 2022 | Facilitate development of SMMEs and Cooperatives development strategy | None | Number of SMMEs and Cooperatives development strategy developed | 1 SMMEs and Cooperatives development strategy developed | [5 empty] | R400.000.00
Facilitate Enterprise and Supplier Development (ESD) Programme by 30 June 2022 | Facilitate Enterprise and Supplier Development Programme | 114 SMMEs appointed for ESD programme | Number of trainings provided through the ESD programme | 6 trainings provided through ESD programme | [5 empty] | 250000
Provide support to SMMEs and co-operatives by 30 June 2022 | Support to SMMEs and Co-operatives | None | Number of SMMEs/Co-operative support provided | 4 SMMEs/Co-operatives supported | [5 empty] | R2,000,000 00
Facilitate establishment of Flea Market by 30 June 2022 | Facilitate the development of a District Flea Market | No formal Flea market within the District | Number of Flea Markets developed within the District | 1 feasibility study conducted on the development of a Flea Market within the District | [5 empty] | R0.00
Facilitate Entrepreneurship promotion workshops to aspiring Entrepreneurs by June 2022 | Facilitate Entrepreneurship promotion workshops to aspiring Entrepreneurs | None | Number of Entrepreneurship promotion workshops to aspiring Entrepreneurs facilitated | 2 Entrepreneurship promotion workshops to aspiring Entrepreneurs facilitated | [5 empty] | R0.00
Facilitate development of Agri Hub site (Agri-Park) by 30 June 2022 | Facilitate development of Agri Hub Site (Agri-Park) (SDA) | Agri Park Business Plan in place | Number of Agri Hub site developed | 1 Agri Hub site developed | [5 empty] | R0.00
Facilitate farmers support through Farmers Production Support Unit (Agri Park) at Vleeschboom by June 2022 | Facilitate farmers support through Farmers Production Support Unit (Agri Park) at Vleeschboom (PED) | Farmers production Support Unit in place | Number of farmers supported through Farmers Production Support Unit (Agri Park) at Vleeschboom | 500 farmers supported through Farmers Production Support Unit (Agri Park) at Vleeschboom | [5 empty] | R7 454 980
Facilitate establishment of Local Cotton Spinner by 30 June 2022 | Facilitate establishment of Local Cotton Spinner (SDA) | Cotton Farmers identified | Number of Local Cotton Spinners facilitated | 1 Local Cotton Spinner facilitated | [5 empty] | R0.00
Facilitate of Cotton Farmers support through Local Cotton Spinner by 30 June 2022 | Facilitate of Cotton Farmers support through Local Cotton Spinner (PED) | Cotton Farmers identified | Number of Cotton Farmers supported through Local Cotton Spinner | 50 Cotton Farmers supported through Local Cotton Spinner | [5 empty] | R0.00
Facilitate development of feasibility study for Poultry Abattoir facility by 30 June 2022 | Facilitate development of feasibility study for Poultry Abattoir facility | 6 poultry houses (40 000 capacity each) in place | Number of feasibility studies on Poultry Abattoir developed | 1 feasibility study on Poultry Abattoir developed | [5 empty] | R0.00
Facilitate development of Industrial Development Master Plan for the Special Economic Zone (SEZ) by 30 June 2022 | Facilitate development of Industrial Development Master Plan for the Special Economic Zone (SEZ) (PED) | SEZ Business Plan in place | Number of Regional Industrial Development Master Plan developed | 1 Regional Industrial Development Master Plan developed | [5 empty] | R1 500 000
Facilitate Small Scale Mining Seminars and Workshops by 30 June 2022 | Facilitate Small Scale Mining Seminars and Workshops | None | Number of Small Scale Mining Seminars and Workshops facilitated | 2 Small Scale Mining Seminars and Workshops facilitated | [5 empty] | 100000
Facilitate funding for 2 district wide impact projects through Mining Social and Labour Plans by 30 June 2022 | Facilitate funding for 2 district wide impact projects through Mining Social and Labour Plans by 30 June 2022 (PED) | Replacement of Malekana Steel Bridge project facilitated by SDM | Number of district wide impact projects funding facilitated through Mining Social and Labour Plans | Funding for 2 district wide impact projects facilitated through Mining Social and Labour Plans | [5 empty] | R0.00
Facilitate Economic Development Forums (Mining, Tourism, LED & Agric.) by 30 June 2022 | Facilitate Economic Development Forums (Mining, Tourism, LED & Agric.) | Economic Development Forums (Mining, Tourism, LED & Agric.) | Number of Economic Development Forums (Mining, Tourism, LED & Agric.) facilitated | 4 Economic Development Forums (Mining, Tourism, LED & Agric.) facilitated | [5 empty] | 90000
Facilitate replacement of Malekana Steel Bridge by June 2022 | Facilitate replacement of Malekana Steel Bridge (SDA) | Old Malekana Steel Bridge | Number of Malekana Steel Bridge replacement facilitated | 1 Malekana Steel Bridge replacement facilitated | [5 empty] | R72 000 000
Facilitate review of SDM Tourism Strategy by 30 June 2022 | Facilitate review of SDM Tourism Strategy | Tourism Strategy in place | Number of SDM Tourism Strategies reviewed | 1 SDM Tourism Strategy reviewed | [5 empty] | 500000
Facilitate recreational and tourism development of De Hoop and Flag Boshielo Dams by 30 June 2022 | Facilitate recreational and tourism development of De Hoop and Flag Boshielo Dams (SDA) | De Hoop and Flag Boshielo Dams Resource Management Plans (RMPs) in place | Number of recreational and tourism developments (De Hoop and Flag Boshielo Dams) facilitated | 2 Recreational and tourism developments (De Hoop and Flag Boshielo Dams) facilitated | [5 empty] | R0.00
Develop Tjate Heritage Site by 30 June 2022 | Develop Tjate Heritage Site | Tjate Heritage Site in place | Number of Tjate Heritage Site developed | 1 Tjate Heritage Site developed | [5 empty] | R0.00
Facilitate Installation of District Tourism Signage for Tourism Establishments and Products (Manche Masemola, King Nyabela and Tjate) by 30 June 2022 | Facilitate Installation of District Tourism Signage for Tourism Establishments and Products (Manche Masemola, King Nyabela and Tjate) | 3 existing District Tourism Establishments and Products (Manche Masemola, King Nyabela and Tjate) | Number of District Tourism Signage for Tourism Establishments and Products (Manche Masemola, King Nyabela and Tjate) installation facilitated | 9 District Tourism Signage for Tourism Establishments (Manche Masemola, King Nyabela and Tjate) installation facilitated | [5 empty] | R0.00
DISTRICT DEVELOPMENT PLAN / INTEGRATED DEVELOPMENT PLAN
By developing IDP Framework/ Process Plan by August 2021 | Develop 2022/2023 IDP Framework/ Process Plan | 2021/2022 IDP Framework/ Process Plan in place | Number of IDP Frameworks/ Process Plans developed | 01 IDP Framework/ Process Plan developed | [5 empty] | R0.00
Review Integrated Development Plan (IDP) by June 2022 | Review of Integrated Development (IDP) | 2021/22 Integrated Development Plan (IDP) reviewed | Number of Integrated Development Plans (IDP) reviewed | 01 Integrated Development Plan (IDP) reviewed | [5 empty] | 60
Facilitate the IDP Rep Forums by June 2022 | Facilitate the IDP Rep Forums | Facilitated 2 IDP Rep Forums | Number of IDP Rep Forums facilitated | 02 IDP Rep Forums facilitated | [5 empty] | 100000
Facilitate review of District Development Plan (One Plan) by June 2022 | Review of 2022/2023 DDP | 2020/2021 District Economic Profile | Number of District Development Plan reviewed | 01 District Development Plan reviewed | [5 empty] | 100000

## SDA
2021/2022 Q2 REPORT
SEKHUKHUNE DEVELOPMENT AGENCY
MEASUABLE OBJECTIVES | PROJECT | BASELINE 2020/2021 | INDICATORS | ANNUAL TARGET 2021/2022 | Q2 | PROGRESS(ACHIEVED/ NOT ACHIEVED) | ACTUAL PROGRESS | CHALLENGE | REMEDIAL ACTIONS | PORTFOLIO OF EVIDENCE | BUDGET 2021/2022
To Jointly Facilitate new approach to Special Economic Zone by June 2022 | Special Economic Zone | SEZ Concept Document & Implementation Plan | Number of SEZ sessions jointly facilitated | X 4 SEZ sessions jointly facilitated | X 1 SEZ Session Jointly facilitated | Achieved | X1 SEZ session facilitated (SDA jointly with LEDA,SDM and FetaKgomo-Tubatse Municipality faciliated an econom ic development summit on SEZ discussions and opportunities) | None | None | 7-8 Dec 2021 Invitationons sent | R0.00
To secure strategic partner to invest in Green Automotive Manufacturing by June 2022 | Green Automotive Manufacturing (Electrical Tuk-Tuks) | Signed MOU and Business Plan | Number of investors secured | X 1 investor secured | implement investment agreement | Achieved | Private Partner presented the implementation of the investment agreement to the SDA board at the strategic planning session held on the 26 August 2021 | None | None | signed agreement | R1 500 000.00
To facilitate Implementation of De-Hoop & Flag Boshielo Resource Management Plans by June 2022 | De-Hoop & Flag Boshielo Tourism Development -RMP’s | Draft Dam Resource Management Plan’s | Number of RMP’s sessions facilitated | X 4 RMP’s sessions faciliated | X 1 RMP session facilitated | Achieved | 1x RMP session facilitated where SDA participated in the re-ignighting tourism workshop at flag boshielo dam on the 3rd of September 2021 | None | None | *attendance register | R0.00
To conduct Minerals Research Study by June 2022 | Mineral Research Study | Signed MOU and commitment letter | Number of Mineral research study conducted | X 1 mineral research study conducted | Re-engage MINTEK to fund the study | Achieved | SDA engaged MINTEK. a letter to MINTEK to follow up on the commitment was sent |  |  | *Letters*copy of the study | R0.00
To facilitate replacement of Malekana Steel Bridge by June 2022 | Facilitate replacement of Malekana Steel Bridge (SDA) | Signed Partnership Agreement | Number of Project Implementation Reports for Malekane Steel Bridge facilitated | X 4 project implementation reports for Malekane Steelbridge facilitated | x 1 project implemntation report | Not Achieved | None | The signed MOU does not include SDA.Agreement is between RAL and Mining companies | Liaise with RAL as project owners to seek collaborationon the project. | x 4 copies of reports | R0.00
To facilitate Bi-Literal Twining Agreements with the Chinese Cities by June 2022 | International Twining Agreement | Signed Memorandum of Intend | Number of twining agreement program facilitated | X 1 twinning agreement program facilitated | need anylsis report | Achieved | Analysis report in place | None | None | *copy of letter*draft&final proposal | R100 000.00
To facilitate partnership for Supply of Dry Sanitation Top Structures by June 2022 | Dry Sanitation Top Structure Supply | Signed MOU | Number of Dry Sanitation Top Structure Supplied | X1000 Dry Sanitation Top Structure Supplied | No activity | Not applicable | N/A | N/A | N/A | Council Resolution | R0.00
To facilitate feasibility study and business plan for land Development by June 2022 | Land Development of ERF 488 | Transfer and donation letters | Number of Feasibility studies and Business plans developed | X 1 Feasibility Study and Business Plan Developed | evaluate and appoint SP | Not Achieved | Advert to solicit proposals from service provider went out. feasibility study proposals at evaluation stage | None | None. | *advert copy*appoinment letter*feasibility report | 105000
To apply for funding for Skills Development by June 2022 | Agri-Sita Funding Application | Agri-Sita Accreditation Certificate | Number of Agri-Sita Funding Application Undertaken | X1 Agri-Sita funding application undertaken | prepare documents for funding | Achieved | funding proposal and Application sent to SETA | None | None | *appoinment letter*funding proposals | 70000
To facilitate Tourism Promotion and Development by June 2022 | Tourism & Marketing | Tourism Route Development | Number of Tourism and Marketing activities Conducted | X 3 Tourism & Marketing activities conducted | x 1 tourism marketing session | Achieved | SDA partnered and participated in the opening of Tourism Month (31 August to 04 September 2021) at Flag Boshielo Dam hosted at Black Aloe Waterfront. | None | None | reports & attendance register | 235000
To partner with agencies in the SMME and Cooperatives Eco-System by June 2022 | SMME’s & Cooperatives Incubation Hub | Draft MOU’s with SEDA | Number of partnerships secured for SMME& Cooperatives Incubation | X 1 SMME’s and Cooperative Incubation partnership secured | Sign MOU | Not Achieved | Revive draft MOU in place | Non availability of representatives to sign MOU | To liase and secure meetimng to finalise and sign MOU with the SEDA Branch manager | Signed MOU | R0.00
To facilitate funding for SMME’s and Cooperatives Business Plans by June 2022 | SMME& Cooperatives Fund | SMME& Cooperatives Funding Policy | Number of SMME’s and Cooperatives Supported | X 5 SMME’s and Cooperatives Supported | Advertise for SMME support | Not Achieved | Support for SMME to be budjeted for in the next financial year | No Clear budget to sustain the programme | Support for SMME to be budjeted for in the next financial year | *form*advert*report | 0
To facilitate Youth In Business Development Program by June 2022 | Youth Business development | Signed MOU | Number of Youth Business Development Programs facilitated | X 2 Youth Business development programs facilitated | Develop concept document | Achieved | Concept document developed and in place | None | None | *Concept document | 30000
To facilitate partnership program to empower emerging farmers by June 2022 | Agang Cotton Initiative | Concept discusions | Number of Partnership facilitated for cotton initiative | X 1 partnership secured for cotton initiative | identify beneficiaries | Achieved | 15 beneficiaries identified | None | None | reports & attendance register | 0
To facilate the appointment of panel of professional fundraisers by June 2022 | Fundraising | Previous appointment letters | Number of Panel appointed for professional fundraisers | X 1 Panel of professional fundraisers appointed | No activity | N/A | N/A | N/A | N/A | *copy of TOR's and advert | R0.00
To develop SDA digital media platform by June 2022 | SDA Website | SDA website in place | Number of updates done on the website | 4 updates done on the website | 1 update done on the website | Achieved | 1 Update done on SDM website | None | None | SDA website | 121000
Establishing socio-economic internal resource information centre by June 2022 | Resource Information Centre/ Repository | New target | Number of Resource Information Centre/Repository developed | X 1 Resource Information Centre Developed | No activity | N/A | N/A | N/A | N/A | *Copy of TOR's | R0.00
To enhance SDA internal capacity by June 2022 | AGM Reports | AGM Reports | Number of AGM meetings facilitated | 1 AGM meeting facilitated | No activity | N/A | N/A | N/A | N/A | AGM Reports | 20000

## BTO
DRAFT SDBIP 2021/2022
DEPARTMENT: BUDGET AND TREASURY
MEASUABLE OBJECTIVES | PROJECT | BASELINE 2020/2021 | INDICATORS | ANNUAL TARGET 2021/2022 | Q1 | Q2 | Q3 | Q4 | PORTFOLIO OF EVIDENCE | BUDGET 2021/2022
Manual GRAP Compliant FAR | Manual GRAP Compliant FAR | % accounting of assets | % accounting of assets | 100% accounting of assets | [5 empty] | R4 806 892
| Functional budget steering committee | Credible budget prepared | Number of Credible budget prepared and monitored | 2 Credible budget prepared and monitored | [5 empty] | R0.00
| mSCOA implementation plan | 70% achievement of mSCOA implementation plan | % of activities on mSCOA implementation plan achieved | 100% of activities on mSCOA implementation plan achieved | [5 empty] | R0.00
Effective, efficient and economical supply chain management process and implementation of SCM regulations | Procurement Plan | Proper implementation of Procurement plan | % Development and implementation of procurement plans | 100% development and implementation of procurement plan(MIG,RBIG,WSIG and all other tenders) | [5 empty] | R0.00
| Irregular expenditure | Section 32 expenditure amount reported | 100% officials to be trained | Compliance with management of MFMA section 32 | [5 empty] | R50 000
100% Functionality of Bid Committees
AFS Preparation | AFS Preparation |  | AFS Preparation | AFS Preparation | [5 empty] | R1 650 000
Revenue enhancement | Identification of potential areas to be billed | *Collections and Capturing of consumer Data from 5 areas identified for potential billing. *Billing of 5 identified areas for potential revenue | Number of areas with revenue potential to be billed | Collection of data and billing of 5 areas with revenue potential
| Meter reading | 74%% Verification and reading of 41133 customers' meters | % of customer's meters validated and read | 70% Validation and reading of customers meters
| Billing of Customers | Billing of 70 % of 41133 customers | % of customers billed | 80% of 56113 customers to be billed
| Improve collection rate | Improve the collection rate to 65% | % improvement of collection rate | 70% of revenue collected against the billing
| Reduction in Debt book | R270m. debt book | % Reduction of debt book | 2% reduction of debt book
| Free basic services | Indigent register | % of indigent customers | 10% increase in indigent customers | [5 empty] | 3000000