## Sheet1
BASIC SERVICE DELIVERY
2021/2022 QUARTER 2 REPORT
OBJECTIVES | PROJECT | BASELINE 2020/2021 | INDICATORS | ANNUAL TARGET 2021/2022 | Q2 | PROGRESS(ACHIEVED/ NOT ACHIEVED) | ACTUAL PROGRESS | CHALLENGE | REMEDIAL ACTIONS | POE | BUDGET 2021-2022
OPERATION AND MAINTENANCE (O&M)
To resolve registered sanitation incidents within 14 days. | Sanitation incidents | 700 registered sanitation incidents resolved within 14 days | Number of registered sanitation incidents resolved within 14 days | 700 registered sanitation incidents resolved within 14 days | 175 registered sanitation incidents resolved within 14 days | Achieved | 253 registered sanitation incidents resolved within 14 days | None | None | Incident Report | 52,048,895,51
To resolve registered water incidents within 14 days. | Water incidents | 5000 registered water incidents resolved within 14 days | Number of registered water incidents resolved within 14 days | 4500 registered water incidents resolved within 14 days | 1125 registered water incidents resolved within 14 days | Achieved | 1263 registered water incidents resolved within 14 days | None | None | Incident Report
To purchase Bulk water by June 2022 | Bulk Water Purchases | 16 500Mℓ of water purchased | Number of Mℓ water purchased | 16 500Mℓ of water purchased | 4125Mℓ of water purchased | Not achieved | 4036Mℓ of water purchased | Frequent breakdowns of bulk supply | Improve turn around time of attending break downs | Summary Meter readings report. | 135, 330,000
To develop water sources in areas that does not have infrastructure and replace dried boreholes by June 2022 | Ground Water Development | New Program | Number of ground water source developed | 20 Ground water source developed (boreholes) | 10 Ground water source developed (boreholes) | Achieved | 08 Procurement of Geo-Hydrologist | None | None | Progress Reports | 10757256.78
To purchase electricity by June 2022 | Electricity Usage | 1200 KWH of Electricity used | Number of KWH electricty used | 10 000 000 KWH of Electricity used | 2,5 000 000KWH of Electricity used | Achieved | 8,333 333KWH of Electricity used | None | None | Summary Electrical Meter readings report. | 40000000
RURAL ROADS ASSET MANAGEMENT SYSTEM (RRAMS)
To Develop 80% of Road Asset Management System by June 2022 | Development of Rural Roads Asset Management System | Desk top studies and the first rounds of Visual Conditions Assessments | Number of kilometres of Roads assessed | 500 kilometres of Roads assessed | 200 kilometres of Roads assessed | Not achieved | Develop draft tender document | Delay in the development of draft tender document | Complete the tender document and submit to specification for approval by 21/01/2022 | Progress report | 2, 437, 000. 00
|  |  | Number of traffic counting stations completed. | 200 traffic counting stations completed | 100 traffic counting stations completed | Not achieved
REGIONAL BULK INFRASTRUCTURE GRANT (RBIG)
To reduce water services backlog with 90% by June 2022 | Mooihoek bulk water supply phase 4F1 | 1 Kilometers of bulk water pipeline and concrete reservoirs constructed | Number of km of bulk pipeline tested and commissioned | 1km of bulk pipeline tested and commissioned | Testing and commissioning of 0.15km bulk pipeline | Not achieved | Testing and commissioning of 0.15km bulk pipeline not done | Non-achievement of quarterly target | Annual target already achieved in Quarter 1 | Progress report | R94 645 000. 00
To reduce water services backlog with 90% by June 2022 | Construction of Mooihoek bulk water supply phase G1.1 | 1 X 5 Ml concrete reservoir completed Phase 4BA | Number of km of bulk pipeline and package plant constructed | Construction of 3 Kilometres of bulk water supply pipeline. Construction of 1 package plant type clarifier | Contractor appointed | Achieved | Contractor appointed | None | None | Progress report
To reduce water services backlog with 90% by June 2022 | Construction of Mooihoek bulk water supply phase G1.2 | 1 X 5 Ml concrete reservoir completed Phase 4BA | Number of km of bulk pipeline constructed | Construction of 4.7 Kilometers of bulk water supply pipeline. | Contractor appointed | Achieved | Contractor appointed | None | None | Progress report
To reduce water services backlog with 90% by June 2022 | Construction of Mooihoek bulk water supply phase G2 | 17km of bulk water supply pipeline completed | Number of km of bulk pipeline and KL of reinforced concrete rserviour constructed | Construction of 4.9 Kilometres of bulk water supply pipeline. Construction of 500KL Reinforced Concrete Reservoir | 1,5 Kilometers of bulk water supply pipeline constructed | Not achieved | 0 Kilometers of bulk water supply pipeline constructed | Contractor running behind programme | Contractor applied for extension of time till end February 2022 | Progress report
To reduce water services backlog with 90% by June 2022 | Construction of Mooihoek Reservoirs phase 4H1 | 12Ml/day Mooihoek Water Treatment Works | Number of Reservoir constructed | 1 Reservoir constructed | Procurement of service provider for construction of 10ML concrete reservoir | Not achieved | Procurement of service provider for construction of 10ML concrete reservoir not done | Contractor not procured | Contractor procurement planned for the last quarter of 2021/22 FY | Progress report
To reduce water services backlog with 90% by June 2022 | Construction of Mooihoek Reservoirs phase 4H2 | 12Ml/day Mooihoek Water Treatment Works | Number of Reservoir constructed | 1 Reservoir constructed | Procurement of service provider for construction of 10ML concrete reservoir | Not achieved | Procurement of service provider for construction of 10ML concrete reservoir not done | Contractor not procured | Contractor procurement planned for the last quarter of 2021/22 FY | Progress report
To reduce water services backlog with 90% by June 2022 | Nebo BWS Commission Jane Furse Pipeline | Nebo Phase1A completed and not commissioned | Number of Kilometers of bulk water supply pipeline tested and commissioned | 18 Kilometers of bulk water supply pipeline tested and commissioned | Test 9km pipeline | Not achieved | 0km of pipeline tested | awaiting panel of consultant. | Scope of work to be allocated to selected electro mechanic & civil contractors from panel | Progress report | R50, 000, 000. 00
To reduce water services backlog with 90% by June 2022 | Nebo BWS Jane Furse to Lobethal Bulk Water Supply | 18km's of bulk water supply pipe line phase two from Jane Furse to Lobethal completed | Number of km's of bulk water supply pipeline assessed | 18km of bulk water supply pipeline assessed | No activity | N/A | N/A | N/A | N/A | Progress report
To reduce water services backlog with 90% by June 2022 | Nebo BWS Makgeru to Schoonoord BWS | 18.2 Km of Schoonoord bulk water supply pipeline in Makgeru. 10ML Command Concrete Reservoir in Schoonoord constructed | Number of Km of bulk water supply pipelines constructed | 6.4Km of bulk water supply pipeline constructed | 2.5 Km of bulk water supply pipeline constructed | Not achieved | 0 Km of bulk water supply pipeline constructed | Additional professional fees required to complete the project exceeds 20% threshold as set by National Treasury Approximately R22 million additional funds required by contractor to complete the project Approved contract duration of project has lapsed | SDM to await the appointment of new panel of consultants in order to finalize the appointment of service provider DWS to assist in terms of additional funds application process Extension of time application for contractor at MM’s office for final approval | Progress report
To reduce water services backlog with 90% by June 2022 | Moutse BWS Project 13 & 14 | 1 WTW in Groblersdal extended in Project 1 and 1 pump station constructed in Project 6 | Number of mechanical and Electrical (M & E) components installed for the extensions to the Groblersdal Water Treatment Works and pump station | 2 mechanical and Electrical (M & E) components installed for the extensions to the Groblersdal Water Treatment Works and pump station | Test mechanical and Electrical (M & E) hosted in new GWT pump house and filters | Not achieved | Project is at 90% and awaits testing (Testing of mechanical and Electrical (M & E) hosted in new GWT pump house and filters not done) | Testing of pumps and motors in Groblersdal WTW depends on civil work repair (clarifier and filters structures) | Consultant has approved variation order for contractor to repair the civil works (clarifier and filters structures) | Progress report | R80, 000, 000. 00
| Moutse BWS Project (7 to 12) | 30 Kilometre of bulk water supply pipeline constructed | Number of Kilometres of bulk water supply pipeline installed and tested | 20Kilometre of bulk water supply pipeline installed and tested | 10Kilometre of bulk water supply pipeline installed and tested | Not achieved | Project 11 is 75% Project 12 is 70% | Extension of timeline | Contractor has submitted request for extension of time to Engineer | Progress report
| Moutse BWS construction bulk water pipeline project(2-4) | 19km of bulk water supply pipeline constructed | Number of km of bulk water supply pipelines assessed and refurbished | 14 km of bulk water supply pipelines assessed and refurbished | No activity | Not achieved | none | none | Scope of work to be allocated to selected electro mechanic & civil contractors from panel. Project may be completed under WSIG | Progress Report
WATER SERVICES INFRASTRUCTURE GRANT (WSIG)
To reduce water services backlog with 90% by June 2022 | Maebe Drilling and Equipping of Borehole | Three (3) drilled and equipped boreholes and bulk pipeline. | Number of pump station constructed, package plant and storage tank installed | 1 Pump station constructed and 1 Reverse Osmosis Water Treatment Package Plant and 1 storage tank installed | Manufacturing and installation of 1 Reverse Osmosis Treatment Package Plant | Not achieved | Manufacturing and installation of 1 Reverse Osmosis Treatment Package Plant not done | Project budget to be reprioritsed and re-allocated to complete 2020/2021 projects on rollover | Submit business plans for approval to DWS and go -out on tender as soon as approval is granted | Progress Report / Completion Certificate | R13, 000, 000. 00
| Tukakgomo RDP Section Borehole | 3.75 Km of water distribution network constructed and 1 raw water abstraction point upgraded | Number of kilometres of network constructed and water meters installed | 7 Km of water distribution network constructed and 735 water meters installed | Construction of 4km distribution network | Not achieved | Construction of 4km distribution network not done | Project budget to be reprioritsed and re-allocated to complete 2020/2021 projects on rollover | Submit business plans for approval to DWS and go -out on tender as soon as approval is granted | Progress Report / Completion Certificate | R9, 000, 000. 00
| Nkosini Water Supply & Package Plant | 1 scoping report and business plans | Number of kilometres of pipeline constructed and protection of abstraction point and sealing of the reservoir | 3.5km of pipeline constructed and 1 protection of abstraction and sealing of 1 reservoir | 1 protection of abstraction | Not achieved | 1 protection of abstraction not done | Project budget to be reprioritsed and re-allocated to complete 2020/2021 projects on rollover | Submit business plans for approval to DWS and go -out on tender as soon as approval is granted | Progress Report / Completion Certificate | R8, 000, 000. 00
| Laersdrift Water Supply Intervention | 1 Scoping Report and Business Plan | Number of kilometres of network constructed and stand pipes and storage tank installed | 8 km reticulation network constructed, 22 communal stand pipes and 1 storage tank installed | Construction of 3km network | Not achieved | Construction of 3km network not done | Project budget to be reprioritsed and re-allocated to complete 2020/2021 projects on rollover | Submit business plans for approval to DWS and go -out on tender as soon as approval is granted | Progress Report / Completion Certificate | R9, 000, 000. 00
| Phokwane/Brooklyn Water Supply | Drilling, testing and equipping of 1 and rising main and 1 storage tank. | Number of kilometres of rising main and storage tank installed | 3km of rising main and 1 elevated tank | Construction of 1.5km of rising main | Not achieved | Construction of 1.5km of rising main not done | Project budget to be reprioritsed and re-allocated to complete 2020/2021 projects on rollover | Submit business plans for approval to DWS and go -out on tender as soon as approval is granted | Progress Report / Completion Certificate | R4, 000, 000. 00
| Legolaneng VDIP | 410 VDIP Toilets | Number of VDIP completed | 440 VDIP completed | 150 VDIP completed | Not achieved | 150 VDIP not completed | Project budget to be reprioritsed and re-allocated to complete 2020/2021 projects on rollover | Submit business plans for approval to DWS and go -out on tender as soon as approval is granted | Progress Report / Completion Certificate | R7, 000, 000. 00
MUNICIPAL INFRASTRUCTURE GRANT(MIG)
To reduce water services backlog with 90% by June 2022 | Fetakgomo VIP Backlog Programme (Phase 2,3) | 15330 VIP units constructed | Number of VIP units constructed | 154 VIP units to be constructed | 40 VIP units to be constructed | NOT ACHIEVED | ISD has provided beneficiary list | Budget needs to be increased Consultants needs to be appointed Learner contractors are still to be allocated scope of work | Appoint consultant Allocate scope to learner contractors within the budget Increase (up adjust) budget to cover work to be assigned to other learner contractors | Progress report | R2, 000, 000. 00
To reduce water services backlog with 90% by June 2022 | Ephraim Mogale VIP Backlog Programme (Phase2,3 ) | 15730 VIP units constructed | Number of VIP units constructed | 1308 VIP units to be constructed | 440 VIP units to be constructed | NOT ACHIEVED | ISD has provided beneficiary list | Budget needs to be increased Consultants needs to be appointed Learner contractors are still to be allocated scope of work | Appoint consultant Allocate scope to learner contractors within the budget Increase (up adjust) budget to cover work to be assigned to other learner contractors | Progress report | R17, 000, 000. 00
To reduce water services backlog with 90% by June 2022 | Makhuduthamaga VIP Backlog Programme | 16096 VIP units constructed | Number VIP sanitation units to be constructed | 1308 VIP sanitation units to be constructed | 440 VIP units to be constructed | NOT ACHIEVED | ISD has provided beneficiary list | Budget needs to be increased Consultants needs to be appointed Learner contractors are still to be allocated scope of work | Appoint consultant Allocate scope to learner contractors within the budget Increase (up adjust) budget to cover work to be assigned to other learner contractors | Progress report | R17, 000, 000. 00
To reduce water services backlog with 90% by June 2022 | Upgrading of De Hoop Water Treatment Works | Ga-Malekana 12Ml Water Treatment Works | Number of WTW registered. | 01 WTW registered. | Registration | Not achieved | Overall progress = 0%. | 5 Year Reliability Plan Outstanding to motivate registration with MIG. | Finalize and approve 5 Year Reliability Plan. | Progress report | R60, 505, 976. 00
To reduce water services backlog with 90% by June 2022 | De Hoop/Nebo Plateau/Schoonoord Water Scheme Villages:Ga –Mogashoa (Senkapudi) and Ga- Mogashoa (Manamane) | 94,6 kilometres of water pipeline constructed | Number of water reticulation pipeline constructed | 11Kilometers of water reticulation pipeline constructed | 5 Kilometers of water reticulation pipeline constructed | Not achieved | 0 Kilometers of water reticulation pipeline constructed | Project behind schedule due to limited material on site | Contractor instructed to procure outstanding material in order to complete the project | Progress report | R4, 762, 404. 00
To reduce water services backlog with 90% by June 2022 | NSD07 Regional Water Scheme Construction of Concrete Reservoirs | 3km of bulk pipeline constructed 1 Reservoir completed | Kilometres of bulk pipeline constructed Number of reservoir completed | 13 Kilometres of bulk pipeline constructed, 3 reservoirs completed | 4 Kilometres of bulk pipeline constructed, 0 reservoirs completed | Not achieved | 0 Kilometres of bulk pipeline constructed, 0 reservoirs completed | Project behind schedule due to stoppages relating to non-payments of sub-contractors and other project related services | Meeting was scheduled on the 7th December with no success between Engineer, Contractor, Social Facilitator and SDM PM to try and resolve outstanding items causing delay to the project | Progress report | R28, 686, 829. 00
To reduce water services backlog with 90% by June 2022 | De Hoop/Nebo Plateau/Schoonoord Water Scheme Villages: Makgeru, Ga Ratau & Matekane | 6 Kilometres of bulk pipeline constructed. 98 km of water reticulation pipeline 2435 metered stand pipes Equipping of two boreholes | Number of Kilometres of bulk pipeline constructed. Number of kilometers of Reticulation. Number of Standpipes constructed. Number of Water Meters Installed Number of boreholes equiped. | 6 Kilometres of bulk pipeline constructed. 42 kilometers of Reticulation. 850 Standpipes constructed. 850 Water Meters Installed Equipping of two boreholes. | 2 Kilometres of bulk pipeline constructed. 12 kilometers of Reticulation. 0 Standpipes constructed. 0 Water Meters Installed. | Achieved | 6.7 Kilometres of bulk pipeline constructed. 67,047 kilometers of Reticulation. 0 Standpipes constructed. 0 Water Meters Installed. | None | None | Progress report | R85, 472 953. 08
To reduce water services backlog with 90% by June 2022 | Elias Motsoaledi VIP Backlog Programme (Phase 2,3) | 16862 VIP units constructed | Number of VIP sanitation units to be constructed | 1308 VIP sanitation units to be constructed | 440 VIP units to be constructed | NOT ACHIEVED | ISD has provided beneficiary list | Budget needs to be increased Consultants needs to be appointed Learner contractors are still to be allocated scope of work | Appoint consultant Allocate scope to learner contractors within the budget Increase (up adjust) budget to cover work to be assigned to other learner contractors | Progress report | R17, 000, 000. 00
To reduce water services backlog with 90% by June 2022 | Carbonitites to Zaaiplaas PH4(Dindela Reservoir) | Dindela Pump Station, Gravity Main and Rising Main. | Number of reservoirs constructed | 1 Reservoir Constructed | No activity | N/A | None | Contractors terminated, no activity on site | MISA together with our planning enginners have been requested to assess the works and material on site and prepare a status quo which will then map a wayforward | Progress report | R8, 000, 000. 00
To reduce water services backlog with 90% by June 2022 | Tubatse VIP Backlog Programme (Phase 2,3) | 16830 VIP units constructed | Number of VIP sanitation units constructed | 1308 VIP sanitation units to be constructed | 440 VIP units to be constructed | NOT ACHIEVED | ISD has provided beneficiary list | Budget needs to be increased Consultants needs to be appointed Learner contractors are still to be allocated scope of work | Appoint consultant Allocate scope to learner contractors within the budget Increase (up adjust) budget to cover work to be assigned to other learner contractors | Progress report | R17, 000, 000. 00
To reduce water services backlog with 90% by June 2022 | Motlailana, Makgemeng Water Supply | 2,57 km of bulk pipeline constructed. 5,66 km of reticulation water pipeline constructed. 1x 100kl elevated tank erected. | Kilometers of bulk line constructed Kilometers of reticulation constructed Number of steel tanks erected. Number of concrete reservoirs constructed. Number of pumphouses constructed. Number of boreholes refurbished. | 5,16 Kilometers for bulk line constructed 36,87Kilometers of reticulation constructed 1 steel tank erected 2 concrete reservoirs constructed. 4 pumphouses constructed. 4 boreholes refurbished. | 2 Kilometers for bulk line constructed 10Kilometers of reticulation constructed 0 concrete reservoirs constructed. 0 pumphouses constructed. 0 boreholes refurbished. | Not achieved | 0 Kilometers for bulk line constructed 3 kilometers of reticulation constructed 0 concrete reservoirs constructed. 0 pumphouses constructed. 0 boreholes refurbished. | Late submission of returnable document by the contractor. Stopages now and again which are coursing delays by the community and the local business forum | ISD is continueasly attending to the arising issues and the contractor to have a fasttracking program | Progress report | R29 409 971.00
To reduce water services backlog with 90% by June 2022 | Malekana Regional Water Scheme | Ga-Malekana 12Ml Water Treatment Works | Kilometers of water pipeline constructed and number of reservior completed | 14 kilometres of water pipeline and 4 reservoirs completed | 4 kilometres of water pipeline and 0 reservoirs completed | Achieved | 7 kilometres of water pipeline and 0 reservoirs completed | None | None | Progress report | R60 973 427.00
To reduce water services backlog with 90% by June 2022 | Lebalelo South connector pipes and reticulations | 100km of connector pipes and reticulation pipelines constructed and 3 steel tanks completed | Number of steel tanks erected | 11 steel tanks erected | 5 steel tanks erected | Achieved | 7 Steel tanks erected | None | None | Progress report | R32, 748, 439. 30
To reduce water services backlog with 90% by June 2022 | Lebalelo South: Phase 3 (Ga- Maroga and Motlolo Bulk and Reticulation Infrastructure | 12,6 kilometres of bulk line constructed. 23,4km reticulation pipeline constructed. 8 reservoirs constructed. 1 package plant constructed. 6 boreholes refurbished. | Kilometers of bulk line constructed. Kilometers reticulation pipeline constructed. Number of WTW Constructed. | 10 Kilometers of bulk line constructed. 46Kilometers reticulation pipeline constructed. 1 WTW Constructed. | 3 Kilometers of bulk line constructed. 10Kilometers reticulation pipeline constructed.6 concrete reserviors constructed, 0 WTW Constructed. | Not achieved | 1 Kilometers of bulk line constructed. 7 Kilometers reticulation pipeline constructed.3 concrete reserviors constructed 0 WTW Constructed. | late delivery of steel pipe due to NUMSA strike . | the contractor was granted extention of time . | Progress report | R63, 000, 000. 00
To reduce water services backlog with 90% by June 2022 | Mampuru Bulk Water Scheme | Ga-Malekana 12Ml Water Treatment Works | Kilometres of bulk line constructed. Number of reservoirs constructed. Number of booster pumpstations constructed. Number boreholes drilled. | 68,26 Kilometers of bulk line constructed. 10 reservoirs constructed. 3 booster pumpstations constructed. 8 boreholes drilled. | Design and tender | Not achieved | Overall progress = 0%. Project not MIG registered | 5 Year Reliability Plan Outstanding to motivate registration with MIG. | Finalize and approve 5 Year Reliability Plan. | Progress report | R40,000,000.00
MUNICIPAL HEALTH SERICES
To Have an improved, clean, healthy and sustainable environment through municipal health services package by June 2022 | Environmental Pollution Prevention | 24 Awareness Campaigns on Air Quality conducted | Number of Awareness Campaigns on Air Quality conducted | 24 Awareness Campaigns on Air Quality conducted | 6 Awareness Campaigns on Air Quality conducted | Achieved | 8 Awareness Campaigns on Air Quality conducted | None | None | Report and Attendance register | R208,200.00
| Water quality monitoring | 300 Water quality samples collected | Number of Water quality samples collected | 300 Water quality samples collected | 75 Water quality samples collected | Achieved | 75 Water quality samples collected | None | None | Water Quality samples Reports | R89,507.26
| Food Safety control | 1500 Food Premises evaluated | Number of Food Premises evaluated | 1500 Food Premises evaluated | 375 Food Premises evaluated | Achieved | 386 Food Premises evaluated | None | None | Signed Assessment forms including the agent signature | R57,932.69
| Waste Management | 100 Health care risk waste monitored | Number of Health care risk waste monitored | 100 Health care risk waste monitored | 25 Health care risk waste monitored | Achieved | 25 Health care risk waste monitored | None | None | Signed Assessment forms including the agent signature | R208,200.00
| Health Surveillance of premises | 1500 premises evaluated | Number of premises evaluated | 1500 premises evaluated | 375 premises evaluated | Achieved | 389 premises evaluated | None | None | Signed Assessment forms including the agent signature | R0.00
| Surveillance and prevention of communicable diseases | 100 awareness campaigns on Communicable diseases held | Number of awareness campaigns on Communicable diseases held | 100 awareness campaigns on Communicable diseases held | 25 awareness campaigns on Communicable diseases held | Achieved | 25 awareness campaigns on Communicable diseases held | None | None | Report and attendance register | R20,820.00
| Communicable diseases outbreak control | 127 communicable diseases investigated and controlled | Number of Communicable disease outbreaks traced | All reported Communicable disease outbreaks traced | All reported Communicable disease outbreaks traced | Not applicable | No Communicable disease cases reported | None | None | Reports | R2,528,423.48
| Vector Control | 1500 inspections on Vector Control on premises conducted | Number of inspections on Vector Control on premises conducted | 1500 inspections on Vector Control on premises conducted | 375 inspections on Vector Control on premises conducted | Achieved | 385 inspections on Vector Control on premises conducted | None | None | Signed Assessment forms including the agent signature | R 43,661.62
| Disposal of the dead | 100 evaluations on Disposal of the Dead facilities conducted | Number of evaluations on Disposal of the Dead facilities conducted | 100 evaluations on Disposal of the Dead facilities conducted | 25 evaluations on Disposal of the Dead facilities conducted | Achieved | 28 evaluations on Disposal of the Dead facilities conducted | None | None | Signed Assessment forms including the agent signature | R0.00
| Chemical Safety | 369 evaluations on safety to chemical handling premises conducted | Number of evaluations on safety to chemical handling premises conducted | 300 evaluations on safety to chemical handling premises conducted | 75 evaluations on safety to chemical handling premises conducted | Achieved | 79 evaluations on safety to chemical handling premises conducted | None | None | Signed Assessment forms including the agent signature | R0.00
EMERGENCY MANAGEMENT SERVICES
To protect loss of life, damage to property and environment by June 2022 | Fire and Rescue Operations | 332 reported emergency incidents attended | Number of reported emergency incidents attended | All reported emergency incidents attended | All reported emergency incidents attended | Achieved | All (88) reported Emergency Services incidents attended | None | None | Call Register and Report | R0.00
| Emergency Management Services Training Academy | 3 firefighting courses facilitated | Number of firefighting courses facilitated | 3 firefighting courses facilitated | 1 firefighting course facilitated | Achieved | 2 firefighting course facilitated | None | None | Attendance Register and Report | R223 671,00
| Fire Prevention and Safety | 369 fire prevention and safety services provided | Number of fire prevention and safety services provided | All Fire prevention and safety services provided | All Fire prevention and safety services provided | Achieved | All (113) fire safety and prevention services provided | None | None | Call Register and Report | R0.00
DISASTER MANAGEMENT SERVICES
To protect loss of life, damage to property and environment by June 2022 | Disaster risk assessment | 198 disaster risk incidents assessed | Number of all reported disaster incidents attended | All reported disaster Management incidents | All reported disaster risk management incidents attended | Achieved | All (97) reported disaster management incidents attended | None | None | Register of disaster incidents | R291 480, 00
| Disaster risk reduction | 42 disaster risk reduction awareness campaigns conducted | Number of disaster risk awareness campaigns conducted | 24 disaster risk awareness campaigns conducted | 6 disaster risk reduction awareness campaigns conducted | Achieved | 12 disaster risk reduction awareness campaigns conducted | None | None | Attendance registers
| Response and recovery | 198 disaster incidents responded | Number of all reported disaster response and recovery attended to | All reported disaster response and recovery attended to | All reported disaster response and recovery operations attented to | Achieved | All (97) reported disaster response and recovery attended to | None | None | Report
| Disaster Management plan and framework review | Disaster management plan and framework in place | Number of disaster management plan and framework reviewed | 1 disaster management plan and framework reviewed | Stakeholder consultation | Achieved | Stakeholder Consultation done on the 14 October 2021 | None | None | Reviewed disaster management plan and framework
| Special operations on high density days | 3 special operations on high density days campaigns coordinated | Number of special operations on high density days campaigns coordinated | 3 special operations on high density days campaigns coordinated | 1 special operations high density campaigns coordinated | Achieved | 1 special operations high density campaigns coordinated | None | None | Operational plan and attendance register