## BTO
DRAFT SDBIP 2021/2022
KPA: FINANCIAL VIABILITY
FINANCIAL VIABILITY
2021/2022 Q2 REPORT
MEASUABLE OBJECTIVES | PROJECT | BASELINE 2020/2021 | INDICATORS | ANNUAL TARGET 2021/2022 | Q2 | PROGRESS(ACHIEVED/ NOT ACHIEVED) | ACTUAL PROGRESS | CHALLENGE | REMEDIAL ACTIONS | PORTFOLIO OF EVIDENCE | BUDGET 2021/2022
Manual GRAP Compliant FAR | Manual GRAP Compliant FAR | 100% accounting of assets | % accounting of assets | 100% accounting of assets | 100% fully functional fixed asset module | Not achieved | The activity is in progress, the municipality is being assisted by BCX for full compliance on asset and budget module. | As this activity dependent on assistance by service provider. In the previous meeting it was reported that the modules is being piloted in another municipality is only after the success of that pilot project to fully implement the budget and asset module | Timely communication with the service provider to speed up the process | GRAP Compliant Fixed Asset Register/ Trial Balance | 4806000
| mSCOA implementation plan | 70% achievement of mSCOA implementation plan | % of activities on mSCOA implementation plan achieved | 100% of activities on mSCOA implementation plan achieved | 100% of all mSCOA modules fully operational by end of 2nd Quarter | Not achieved | The activity is in progress, the municipality is being assisted by BCX for full compliance on asset and budget module. | As this activity dependent on assistance by service provider. In the previous meeting it was reported that the modules is being piloted in another municipality is only after the success of that pilot project to fully implement the budget and asset module | Timely communication with the service provider to speed up the process | Trial Balance/LG Portal Submission Reports | R0.00
To provide sound financial management | Functional budget steering committee | Credible budget prepared | Number of credible annual budgets prepared and implemented. | 2 Credible Annual Budgets prepared and implemented. | No activity | N/A | N/A | N/A | N/A | Council resolutions/Draft Budget Documents | R0.00
| Procurement plan | 2020/2021 procurement plan in place | Number of procurement plan developed | 1 procurement plan developed | Monitoring implementation of the plan | Achieved | Monitoring implementation of the plan done | none. | none | Signed procurement plan | R0.00
| Irregular expenditure in the 2020/21 | Section 32 expenditure amount reported. | % Compliance with management of MFMA section 32 | 100% Compliance with management of MFMA section 32 | 2nd Quarter reporting of UIF through Section 52 reports (Annexure A) | Achieved | 1st and 2nd Quarter reporting of UIF through Section 52 reports in place (Annexure A) | none | none | Section 52 Report | 50000
| AFS preparations | Submission of AFS and APR to the AG within the legislated time frame | Compile AFS and APR within the legislated time frame | Compile AFS and APR within the legislated time frame | No activity | N/A | N/A | N/A | N/A | Signed AFS and APR/ Ackonwledgement of receipt by AGSA | R1 650 000
| Identification of potential areas to be billed | *Collections and Capturing of consumer Data from 5 areas identified for potential biling. *Billing of 5 identified areas for potential revenue | Number of areas with revenue potential to be billed | Collection of data and billing of 5 areas with revenue potential | Data collection in 5 areas with revenue potential | Achieved | Data have been collected in 5 areas with revenue potential | None | None | Data Collection report and Summary of billing reports | R5,000 000
| Meter reading | 74%% Verification and reading of 13100 customers' meters | % of customer's meters valitated and read | 75% Validation and reading of customers meters | 65% Validation and reading of customers meters | Achieved | 70% of meters were read and validated | in some areas access to meter reading is denied , and meters are being stolen | Political intervention is required | Meter reading report | R7,500 000
| Billing of Customers | Billing of 80 % of 41133 customers | % of customers billed | 90% of 41200 customers to be billed | 85% of 41200 customers to be billed | Achieved | 90% of 41200 customers were billed | Were meter could not be read avarage were billed | Acess to meter reading will reduce avarage billing | Billing report | 1500000
| Improve collection rate | Improve the collection rate to 75% | % improvement of collection rate | 75% of revenue collected against the billing | improvement of collection rate to 70% | Not Achieved | 64% Collection was achieved | Lack of capacity to do disconnection internally | Lack of capacity to do disconnection internally | Collection rate report | 4500000
|  | R241m. debt book | % Reduction of debt book | 2% reduction of debt book | 1,5%reduction debt book | Not Achieved | 11% increase in Debt book | Lack of capacity to do disconnection internally | Lack of capacity to do disconnection internally | Own revenue reports/Debtors age analysis report | R0.00
| Free basic services | Indigent register for 2020/2021 | % of indigent customers | 10% increase in indigent customers | 7%Collection of customers'indigent registration data | Not Achieved | Data has been collected and not verified | Awaiting appointment of provider to do Indigent register verification | Fast Track the appointment of Provider to do indigent register verifications | Indigent register for 2021/2022 | 3000000
13856000