## CPS
DRAFT SDBIP 2021/2022
KPA: INSTITUTIONAL TRANSFORMATION & ORGANISATIONAL DEVELOPMENT
GOOD GOVERNANCE AND PUBLIC PARTICIPATION
2021/2022 Q2 REPORT
MEASUABLE OBJECTIVES | PROJECT | BASELINE 2020/2021 | INDICATORS | ANNUAL TARGET 2021/2022 | Q2 | PROGRESS(ACHIEVED/ NOT ACHIEVED) | ACTUAL PROGRESS | CHALLENGE | REMEDIAL ACTIONS | PORTFOLIO OF EVIDENCE | BUDGET 2021/2022
INTERNAL AUDIT
To ensure improved internal controls and clean governance in the municipality by June 2022 | Development of the Three(3) Years rolling Plan | Development of 2020-2021 Three Year Internal audit rolling plan | Number of (SDM & SDA) 3 years rolling plans developed | 2 (SDM & SDA) 3 years rolling plans developed | No activity | N/A | N/A | N/A | Audit Committee meetings will be divided | Approved 3 Years and Annual Internal Audit rolling Plan for SDM and SDA by Audit Committee-Audit Committee Minutes | R0.00
| Conduct Regularity audit | 22 regularity audits conducted | Number of regularity audit conducted | 20 Regularity Audits conducted | 5 regularity audits Conducted | Not Achieved | 4 regularity audits conducted | Performed more due dilligence | To fastrack the audits projects | Signed Regularity Audit Reports | R884 850.00
| Conduct Ad hoc Audits | Conduct Ad Hoc Audits | Percentage Ad Hoc audits conducted | 100% Management requests/ investigations conducted as and when required | 100% Management requests/ investigations conducted as and when required | Achieved | 100% (05) Management requests/ investigations conducted as and when required | None | None | Signed Management /Investigation reports | R 7 173 687.15
| To conduct ICT Audits | 4 ICT Audits reports conducted | Number of ICT Audits conducted | 4 ICT Audit reports conducted | 1 ICTAudits conducted | Not achieved | 1 ICT Audits not conducted | Lack of skill internally | To be outsourced in the third quarter | Signed ICT Audits Reports | R0.00
| To conduct Audits of Performance Information | 4 Audit of Performance information conducted | Number of Audit of Performance Information conducted | 4 Audit of Performance Information conducted | 1 AOPI conducted | Achieved | 1 AOPI conducted | None | None | Signed AOPI Reports | R0.00
| Monitoring of implementation of auditor general activities | 100% monitoring of implementation of AG activities | Percentage monitoring of External Audit implementation plan | 100%monitoring of external Audit Implementation plan | 100% monitoring of implementation of AG activities | Achieved | 100% monitoring of implementation of AG activities | None | None | Audit Action plan,Signed Minutes,proof of payments | R0.00
| Monitoring of Internal Audit Implementation plan | 100% monitoring of Internal Audit Implementation plan | Percentage monitoring of Internal Audit implementation plan | 100%monitoring of Internal Audit Implementation plan | 100%monitoring of Internal Audit Implementation plan | Achieved | 100%monitoring of Internal Audit Implementation plan | None | None | Internal Audit Implementation plan | R0.00
| Coordination of Audit Committee and Performance Audit Committee | 7 (4 ordinary) and (3 special ) meetings of audit and performance committees coordinated | Number of meetings of audit and performance committees coordinated | 7 (4 ordinary) and ( 3 special ) meetings of audit and performance committees coordinated | 2 meetings of audit and performance committees coordinated | Not Achieved | 2 meetings of audit and performance committees not coordinated | Auditor General (SA) audit not finalised and backlog from the previous meetings | Audit Committee meetings to be conducted in January 2022 will be separated | Signed Minutes/Agenda/Signed AC Reports | R 520 500.00
| Monitoring implementation of the operation clean audit strategy | 100% monitoring of the operation clean audit strategy | Percentage monitoring of the operation clean audit strategy | 100%monitoring of the operation clean audit strategy | Implementation of operation clean Audit Strategy | Not achieved | Operation Clean Audit Strategy is developed presented to Management,Municipal Managers forum and Mayors forum but not approved by council | First quarter council meeting did not take place due to transitions of the council | The Operation clean Audit Strategy to be presented in the next council meeting | Approved operation clean Audit Strategy/Minutes of OPCA meetings/Quarterly Reports | R0.00
| Conducting external assessment review | None | Number of external quality assessment performed | 1 external quality assessment performed | No activity | N/A | N/A | None | None | External Assessment Review Report | R300 000.00
RISK MANAGEMENT
To assess, identify, and manage risks and uncertainty to safeguards assets, enhance productivity, and build resilience into the operations by June 2022 | Conduct Strategic Risk Assessment and review risk register | Strategic Risk Register in /place | Number of Strategic Risk Assessment conducted, and Strategic Risk Registers reviewed | *1 Strategic Risk Assessment conducted * 4 Strategic Risk Registers reviewed | 1.Monitor & review Risk Register | Achieved | 1 x Strageic Risk Register monitored & reviewed | None | N/A | Strategic Risk Register report | R0.00
| Conduct Operational Risk Assessment and review risk register | Operational Risk Registers in place | Number of Operational Risk Assessment Conducted and Operational Risk Registers reviewed | *1 Operational Risk Assessment Conducted *4 Operational Risk Registers reviewed | 1.Monitor & review Operational Risk Register | Achieved | 1 x Operational Risk Register monitored & reviewed | None | N/A | Operational Risk Registers report | R0.00
| Conduct Processes Risk Assessments | 2 x Processes risk assessment conducted | Number of Processes risk assessments conducted | 7 x Processes risk assessments conducted | 2x Process Risk Assessment conducted 2.Monitor & review Processes Risk Register | Not achieved | None | Delays in perusing documents and systems for corelation with modules and work processes | Undertake assess- ment in the 3rdQ | Processes Risk Registers report | R0.00
| Facilitate insurance coverage for municipal assets | 1 x Assets Insurance Policy contract entered into. | Number of insurance coverage for municipal assets facilitated | All insurance coverage for municipal assets facilitated | 1.Insurance coverage for municipal assets facilitated 2.Update insurance policy for additions and deletions | Achieved | Insurance coverage for municipal assets facilitated. I nsurance policy updated for additions and deletions | None | N/A | Assets Insurance Policy contract | R6 131 490. 00
| Facilitate Assets Insurance Claims and payments | Insurance claims report facilitated | Percentage processing and facilitation of insurance claims and payments | 100% insurance claims processing, and payments of repairs, losses and excess facilitated | 100% insurance claims processing and payments facilitated | Achieved | 100% (13) insurance claims processed and payments facilitated | None | N/A | Insurance Claims report | R 968 851,00
| Manage Security operations and SLA | All incidents occurred reported | Number of incidents occurred, and SLA managed | All occurred incidents and SLA managed | 4 x Security cluster operations and contracts managed | Achieved | Four (04) Security cluster operations and contracts managed | None | N/A | Quarterly Security Report | R30 000 000. 00
| Conduct Security Operational Sites Assessments | Security operational Sites Assessment conducted | Number of Security Operational sites assessments conducted | Forty (40) Security Operational sites assessments conducted | Ten (10) Security Operational sites assessments conducted | Achieved | Thirteen (13)Security Operational sites assessments conducted | None | N/A | Quarterly Security Operational Sites Report produced/compiled | R0.00
| Facilitate the establishment of an Anti-Fraud & Corruption hotline | Fraud and Corruption cases reported and investigated | Number of fraud and corruption allegation cases reported for referral and investigations facilitated | All fraud and corruption allegation cases reported for referral and investigations facilitated | All fraud and corruption allegation cases reported for referral and investigations | Not applicable | No fraud cases reported | N/A | N/A | Fraud and Corruption Cases report | R0. 00
| Facilitate the development of a Business Continuity Management plan | Business Continuity Management Framework in place | Number of phases of the Business Continuity Management plan completed | 100% completion of phase one (01) of the Business Continuity Management plan | Stage 2 of Phase 01 of the BCM Plan facilitated | Not achieved | None | Delays in perusing documents and systems for alignment with Stage 1 already completed. | Faciliatet the compl etion of phase 01 of the plan in the 3rd Q | Business Impact Analysis report | R0. 00
To assist the Accounting Officer/Authority in addressing its oversight requirements of risk management and evaluating and monitoring the municipality’s performance with regards to risk management | Facilitate Risk Management Committee (RMC) meetings | One (01) Risk Management Committee held | Number of Risk Management Committee (RMC)meetings facilitated | 4 x Risk Management Committee (RMC) meetings facilitated | 1 x Risk Management Committee (RMC) meetings facilitated | Not Achieved | None | Slow turn around times due to conflicting commitments ( e.g AG enagements) | Reschedule the meeting in the 3rd Quarter. | Risk Management Committee report | R80 000
Two (02) Audit Committee meetings held to consider Risk Management Committee report
COMMUNICATIONS; ADVOCACY; SOCIAL FACILITATION; SPECIAL PROGRAMMES AND ARTS & CULTURE
To facilitate stakeholder & sectorial engagement by June 2022 | Mayoral Outreaches and Sectorial Engagements | 12 Programmes facilitated | Number of community & sectorial engagements facilitated | 8 stakeholder & sectorial engagements facilitated | 2 stakeholder & sectoral engagement facilitated | Not Achieved | 0 stakeholder & sectoral engagement facilitated | 1 Stakeholder & Sectoral Engagement not held due to uncompleted council processes. | stakeholder & sectoral engagement rescheduled for next quarter | Attendace Register & Exit report | R800 000,00
To provide support to Mayoral Committee by June 2022 | Executive Support to Mayoral Committee | 12 Mayoral Committee meetings supported | Number of Mayoral Committee meetings supported | 12 Mayoral Committee meetings supported | 3 Mayoral Committee meetings supported | Achieved | 3 Mayoral Committee meetings supported | None | None | Attendace Registers | R0.00
To produce newsletters by June 2022 | Newsletter& Publications | 16 Programmes produced | Number of newsletters produced | 8 newsletters produced. | 1 external and 1 internal newsletters produced | Not Achieved | 1 x Internal and 1 X External News Letters Produced | Delayed Printing | Rescheduled for 3rd Quarter | Newsletters | R500 000,00
To market and brand events by June 2022 | Media Relations and Marketing | 12 Events Branded | Number of events Marketed and branded | 12 Events marketed and branded | 3 events marketed and branded | Achieved | 3 Events marketed and branded. Council sitting, disability day and Arts and Culture Workshop. 16 Days of Activism against women and children abuse held 08 Dec 2021. | None | N/A | Exit reports, pictures\publications | R100 000,00
To undertake website updates by June 2022 | Website Management | 20 Updates undertaken | Number of Website Updates undertaken | 12 Website Updates undertaken | 3 Website Updates undertaken | Achieved | 6 Website Updates undertaken. Ordinary Council Meeting 26/10/2021, Acting CFO Performance Agreement, Acting COO Performance Agreement, First Council Meeting 23/11/2021, Acting CPS Performance Agreement, Ordinary Council 05/12/2021. | None | N/A | Screenshots | R150 000,00
To facilitate meetings for Traditional Leaders by June 2022 | Executive Support and Traditional Leadership Affairs | 2 SPLUMA meetings supported | Number of Traditional Leadership meetings facilitated | 3 Traditional Leadership meetings facilitated | 1 meeting facilitated | Achieved | 1 Meeting facilitated | None | N\A | Attendance registers and exit reports | R0. 00
To facilitate strategic events by June 2022 | Special Mayoral strategic Events | 5 strategic events Facilitated | Number of Strategic Events facilitated | 5 strategic events facilitated | 1 strategic events facilitated | Achieved | Kgoshi Nyabela Commemoration Day 19/12/2021 Facilitated at Mabhoko Cave. | None | N/A | Attendance registers and exit reports | R500 000,00
To facilitate Moral Regeneration Movement committee programmes by June 2022 | Strengthening of Moral Regeneration Movement Committee | MRM committee established | Number of programmes for MRM committee facilitated | 2 MRM committee programme facilitated | 1 MRM activity facilitated | Achieved | 1 MRM activity facilitated | None | N\A | Attendance registers and exit reports | R100 000,00
To generate Customer Care reports by June 2022 | Customer Care Services | 24 reports generated | Number of reports generated | 24 queries/ complains reports on customer care generated | 6 customer care reports generated | Achieved | 6 customer care reports generated | None | N/A | Exit reports | R0.00
To revamp the Call Centre by June 2022 | Call Centre Revamping & Maintenance | 24 hour outdated call centre system | Number of call centre revamped | 1 call centre revamped | 1 Call centre revamped | Not Achieved | No Activity | Due to budget constraints | To be considered during adjustment budget | Report | R600 000,00
To conduct Batho Pele programmes by June 2022 | Batho Pele | 6 Programmes conducted | Number of Batho Pele Programmes conducted | 4 Batho Pele Programmes conducted | 1 Batho Pele Programmes conducted | Achieved | 1 Batho Pele activity conducted | None | N/A | Reports | R100 000,00
To co-ordinate SODA by June 2022 | SODA | 2020/2021 SODA held | Number of SODA coordinated | 1 SODA coordinated | No activity | No Target | No Activity | None | N/A | Attendance registers and exit reports | R450 000,00
To facilitate campaigns for the elderly by June 2022 | Aged care | 2 aged care programmes facilitated | Number of Aged Care campaigns facilitated | 2 Aged Care campaigns facilitated | 1 elderly campaign facilitated | Achieved | 1 elderly campaing facilitated.Older Persons Event held 26/10/2021 at Apel | None | N/A | Attendance registers and exit reports | R200 000,00
To facilitate campaigns for the children by June 2022 | Children’s Care | 2 children’s activities facilitated | Number of children's campaigns facilitated | 2 children's campaigns facilitated | 1 children programme facilitated | Achieved | 1 children programme facilitated on the 26 December 2022 | None | N/A | Attendance registers and exit reports | R100 000,00
To facilitate campaigns for women by June 2022 | Woman Development Initiative | 4 Women Programmes facilitated | Number of woman development initiatives facilitated | 3 woman development initiatives facilitated | 1 programme for women facilitated | Achieved | Launching of 16 Days of Activism against Abuse of Women and Children held 08 Dec 2021 | None | N/A | Attendance registers and exit reports | R300 000,00
To facilitate Awareness campaigns for people with disability by June 2022 | People with disability | 3 Programmes facilitated | Number of awareness campaigns for people with disability facilitated | 2 awareness campaigns for people with disability facilitated | 1 campaign for people with disability facilitates | Achieved | Disability Day held 17 Dec 2021 at Mohlaletse Disability Centre. | None | N/A | Attendance registers and exit reports | R200 000,00
To facilitate art and culture programmes by June 2022 | Cultural Heritage Celebrations and Language Promotions | 2 Programmes facilitated | Number of Heritage and promotions of indigenous languages and theatre workshop facilitated | 1 Heritage day and 1 promotions of indigenous languages and Theatre workshop facilitated | 1 art and culture programme facilitated | Achieved | Arts and Culture Workshop held 11 Dec 2021 at Ga-Nkoane Municipal Chamber. | None | N/A | Attendance registers and exit reports | R500 000,00
To coordinate health calendar days activities by June 2022 | Coordination of health calendar days activities | 3 health calendar days activities conducted | Number of health calendar days activities coordinated | 3 Health calendar days activities coordinated | I health calendar day co-ordinated | Achieved | World AIDS Day Commemoration held 07 - 10 Dec 2021 at Loskop Dam Forever Aventura | None | N/A | Attendance registers and exit reports | R200 000,00
To coordinate district AIDS Council activities by June 2022 | Coordination of District AIDS Council activities | 4 District Aids Council activities coordinated | Number of district AIDS Council activities coordinated | 3 district AIDS Council activities coordinated | 1 district AIDS Council activity coordinated | Achieved | 1 district AIDS Council activity coordinated | None | N\A | Attendance registers and exit reports
To facilitate Youth development programmes by June 2022 | Youth Opportunities Expo | 3 Programmes facilitated | Number of Youth development programmes facilitated | 3 Youth development programmes facilitated | 1 Youth development programme facilitated | Achieved | 1 Youth development programme facilitated | None | None | Attendance registers and exit reports | R900 000 00
To facilitate Mayor’s forum activities by June 2022 | Facilitation of Mayor’s forum | 4 Mayor’s forum facilitated | Number of Mayor’s forum facilitated | 4 Mayor’s forum facilitated | 1 Mayor’s forum facilitated | Achieved | 1 Mayor's Forum facilitated on 05 Oct 2021 at Bareki Mall - Lekgotla Boardroom | None | N\A | Attendance registers and exit reports | R0.00
To facilitate Mayoral sports activities by June 2022 | Facilitation of Mayoral Sports activities | 2 Mayoral Sport activities facilitated | Number of Mayoral Sport activities facilitated | 1 Mayoral Sport activities facilitated | No activity | No Activity | No Target | None | N/A | Attendance registers and exit reports | R500 000,00 | R6,200,000.00
PUBLIC PARTICIPATION, MPAC SUPPORT; SECRETARIAT AND SUPPORT
Provide secretarial support to 10 council structures to ensure accountability by June 2022 | FORA | 16 Fora facilitated | Number of fora facilitated | 16 Fora facilitated | 1 Speakers' Forum, 1 Chief Whips' Forum,1 Public participation Forum. 1 MPAC forum, 1 Secretariat Forum facilatated. | Not achieved | 1 Speakers' Forum & 1 Chief Whips' Forum not facilitated,1 Public participation Forum held on 13/12/2021. 1 MPAC forum & 1 Secretariat Forum not facilatated. | Fora meetings were not facilitated due to the Sworn in & Inauguration of Cllrs, Election of PMT, and induction programme for Cllrs which overlap to scheduled dates for fora meetings. | 1 Speakers' Forum, Chief Whips' Forum, MPAC Forum, Secretariat Forum to be facilitated during the Q1. | Notice & Attendance registers | R75 000.00
| Public participation sessions. | 15 public participation sessions facilitated | Number of public consultation meetings facilitated | 15 public participation facilitated | No activity | No activity | No activity | No activity | No activity | Attendance registers and exit reports | R750 000.00
| SODA & Budget Day | 1 SODA , 1 Budget Day facilitated | Number of SODA and Budget days facilitated | 1 SODA , 1 Budget Day facilitated | No activity | No activity | No activity | No activity | No activity | Notice and attendance registers | R0.00
| Council and portfolio committee meetings | 22 Council and portfolio committee meetings facilitated | Number Council and portfolio committee meetings facilitated | 24 Council and portfolio committee meetings facilitated | 1 Ordinary Council Meetings and 5 Portfolio Committee Meetings facilitated. | Achieved | 2 Ordinary Council Meetings, 1 First Council Meeting (Fifth Term) and 5 Portfolio Committee Meetings facilitated on 26/10/2021, 15/12/2021, 25/11/2021 & 14-15/10/2021 respectively. | None | None | Notice and attendance registers | R500 000.00
| Study group | 4 study groups facilitated | Number of study groups facilitated | 4 study groups facilitated | 1 Study Group Facilitated. | Achieved | 1 study group facilitated 25/10/2021 | None | None | Notice and attendance registers | R65 000.00
| Public hearings | 2 public hearings facilitated | Number of public hearings facilitated | 2 public hearings facilitated | 1 MPAC Public Hearing Facilitated. | Not achieved | 1 MPAC Public Hearing not facilitated. | Term of office of Cllrs ended on the 01/11/2021. The new Cllrs were sworn in and inaugurated on 25/11/2021 and 02/12/2021. | 1MPAC Public Hearing will be faciliated during Q3 | Notice and attendance registers | R200 000.00
| Strategic planning sessions for Section 79 Portfolio Committees & MPAC | 2 strategic planning sessions facilitated | Number of strategic planning session facilitated | 2 strategic planning sessions facilitated | No activity | N/A | N/A | N/A | N/A | Notice and attendance registers | R350 000.00
| Capacity building workshops | 2x workshops facilitated | Number of workshops facilitated | 2x workshops facilitated | No activity | N/A | N/A | N/A | N/A | Notice and attendance registers | R300 000.00
| Training and development of Cllrs | 2x councillors trained | Number of councillors trained | 10x Councillors trained | No activity | N/A | N/A | N/A | N/A | Exit report | R600 000.00
| Queries and assistance of travel claims | 100% resolution of Cllrs queries facilitated | Percentage resolution of Cllrs queries facilitated | 100% resolution of Cllrs queries facilitated | 100% resolution of Cllrs queries facilitated. | Achieved | 100% resolution of cllrs queries facilitated | None | None | Exit report | R0.00
| Resolution registers for Council implementation. | 4 Council Resolution registers compiled and coordinated | Number of Council Resolution registers compiled and coordinated | 4 Council Resolution registers compiled and coordinated | 1 council resolution register compiled and cordinated. | Achieved | 1 council resolution register compiled and cordinated. | None | None | Council resolution register | R0.00
| Council whippery meetings facilitated | 4 meetings held | Number of meetings facilitated | 4 Council Whippery meeting Facilitated. | 1 Council Whippery meeting Facilitated. | Achieved | 1 Council Whippery meeting facilitated on 10/12/2021 | None | None | Notice and attendance registers | R20 000.00
| Review of public participation policy | 1 public participation policy review facilitated | Number of public participation policy review facilitated | 1 public participation policy review facilitated | No activity | No activity | No activity | No activity | No activity | Council resolution certificate | R0.00
| Working sessions for Cllrs. | 8 MPAC Working sessions for Cllrs facilitated | Number of MPAC working sessions for Cllrs facilitated | 8 MPAC working sessions for Cllr facilitated. | 2 MPAC working sessions for Cllr facilitated. | Achieved | 2 MPAC Working session facilitated. | None | None | Notice and attendance registers | R180 000.00 | R3,040,000.00