## CPS
DRAFT SDBIP 2021/2022
KPA: INSTITUTIONAL TRANSFORMATION & ORGANISATIONAL DEVELOPMENT
INSTITUTIONAL TRANSFORMATION & ORGANISATIONAL DEVELOPMENT
2021/2022 Q2 REPORT
MEASUABLE OBJECTIVES | PROJECT | BASELINE 2020/2021 | INDICATORS | ANNUAL TARGET 2021/2022 | Q2 | PROGRESS(ACHIEVED/ NOT ACHIEVED) | ACTUAL PROGRESS | CHALLENGE | REMEDIAL ACTIONS | PORTFOLIO OF EVIDENCE | BUDGET 2021/2022
ORGANISATIONAL DEVELOPEMENT
To review the Organisational Structure by June 2022 | Organisational Structure Review | Approved Organisational Structure for 2020-2021 | Number of Organisational Structure Reviewed | 1 Organisational Structure Reviewed | 2nd Assessment of organisational structure | Achieved | 2nd Assessment of Organisational Structure Conducted | None | None | Council Resolution and Approved Organisational Structure | 0
To facilitate development of job descriptions and job evaluation by June 2022 | Job Description Development and Job Evaluation | 50 Job Descriptions Developed and Evaluated | Number of Job Descriptions Developed and facilitated for Evaluated | 50 Job Descriptions Developed and Facilitated for Evaluation | 15 Job Descriptions Developed and Facilitated for Evaluation | Achieved | 15 Job Descriptions Developed and Facilitated for Evaluation | None | None | Job Evaluation Report
To conduct change management awareness campaigns by June 2022 | Change Management | Approved Change Management Plan | Number of Change Management Session Facilitated | 2 Change Management Sessions Facilitated | 1 Change Management Session Facilitated | Not Achieved | Change Management Plan Developed and Approved | Unavailibility of Budget | Request for Budget during Adjustment | Change Management Report
INFORMATION AND COMMUNICATION TECHNOLOGY (ICT)
To establish effective network connectivity by June 2022 | ICT Infrastructure connection | 18 depots connected | Number of depots connections upgraded | 18 depots connections upgraded | Monitoring and evaluation | Not Achieved | The project was not approved as a resultsthe project to be removed during adjustment of SDBIP | The extension of scope and contarct to include 18 depots was not approved | Project to be removed during adjustment of SDBIP | Reports | 500000
| Implementation of security measures | 05 of Security Control implemented | Number of Security Controls implemented | 24 Security Controls Implemented | 6 Security Controls Implemented | Achieved | 6 Security Controls implemented | None | None | Security measures | 400000
To conduct need analysis of ICT hardware and consumables by June 2022 | ICT consumables and hardware replacement | 50 ICT consumables and hardware replacement | Number of ICT consumables and Computers replaced | 30 ICT consumables and Computers replaced | 10 ICT consumables and Computers replaced | Achieved | 10 ICT consumables and Computers replaced | None | None | Laptop/Consumable Register | 1000000
To monitor expiry date of licenses by June 2022 | Software Licence renewal | 12 licenses renewed | Number of licenses renewed | 11 licenses renewed | 4 licenses renewed | Not Achieved | 3 licenses renewed | Delay in receiving invoices from service provider | Request service provider to expedite sending of invoicec on time | Licenses | 3859000
To monitor Service Level Agreements by June 2022 | Contract Monitoring | 12 SLA performance held | Number of SLA performance held | 16 SLA performance held | 4 SLA performance held | Achieved | 4 SLA performance held | None | None | Reports | 3159000
LABOUR RELATIONS
To Issue four labour relations publications by June 2022 | Issue Labour Relations Publications | 4 Labour relations publications issued. | Number of Labour relations publications issued | 4 Labour relations publications issued | 1 Labour relations publication issued | Achieved. | 1 Labour relations publications issued. | None. | None. | Copies of publications | R0.00
To facilitate Labour related grievances by June 2022 | Facilitate Labour Relations Grievances | 3 Grievance cases facilitated | Number of grievances cases received facilitated | All Labour related grievances cases received facilitated | All Labour related grievances cases received facilitated | Not applicable | No Labour related grievances cases received. | None. | None. | Copies grievances | R0.00
To facilitate Labour related disciplinary cases by June 2022 | Facilitate labour related disciplinary cases | 7 disciplinary cases facilitated | Number of labour related disciplinary cases received facilitated | All labour related disciplinary cases received facilitated | All labour related disciplinary cases received facilitated | Achieved | All (4) Labour related disciplinary received cases facilitated. | None. | None. | Reports and attendance registers | R0.00
To facilitate12 LLF meetings by June 2022 | Facilitate LLF Meetings | 9 LLF meetings held | Number of LLF meetings facilitated. | 12 LLF meetings facilitated | 3 LLF meetings facilitated. | Not Achieved | 3 LLF meetings facilitated | Failure by members to honour scheduled meetings and failure to understand their roles and responsibilities. | SALGA facilitated workshop sought on the roles and responsibilities in the forum. | Minutes and attendance registers | R0.00
AUXILIARY SERVICES
To conduct records management awareness programme by June 2022 | Records management awareness | 2 Records management awareness facilitated | Number of Records management awareness facilitated | 02 Records management awareness facilitated | 01 Records management awareness facilitated | Achieved | 01 Records management awareness facilitated on the 9th December 2021 | None | None | Report, Attendance register | R0.00
To facilitate the development of file plan by June 2022 | File plan | 1 File plan developed | Number of File plan developed | 01 File plan developed | 01 File plan developed | Achieved | 01 File plan developed. Approved by Provincial Archive | None | None | Report, Attendance register & Approved file plan | R0.00
To purchase filling cabinets by June 2022 | Purchase of filling cabinets | 6 filling cabinets purchased | Number of filling cabinets purchased | 06 filling cabinets purchased | No Activity | N/A | N/A | N/A | N/A | Delivery note | 200000
To facilitate implementation of records (document) management system by June 2022 | Records (documents) management system | 1 Records management system in place. (MunAdmin) | Number of document management system implemented | 01 Record management system implemented | Monitoring implementation of the system. | Achieved | Monitoring implementation of the system. | None | None | Signed training form. | R300 000
To maintain and repair the fleet and facilities by June 2022 | Maintenance and repairs | 20 vehicles Maintained and repaired | Number of vehicles Maintained and repaired | 20 vehicles Maintained and repaired | 10 vehicles Maintained and repaired | Achieved | 10 vehicles maintained and repaired | None | None | Maintanance Report | R1 800 000
To procure fleet mangement system by June 2022 | Fleet Management system | New project | Number of fleet management system procured | 01 fleet management system procured | Development of terms of reference | Not Achieved | Memo Developed with terms of reference. | No budget available | MunAdmin system will be utelised and implemented in the third quarter | Report | 500000
To settle the emergency vehicles by June 2022 | Settlement of emergency vehicles | 11 emergency vehicles settled | Number of emergency vehicles settled | 15 emergency vehicles settled | 15 emergency vehicles settled | Not Achieved | 15 emergency vehicles not settled | Delayed by non payment of vehicles involved in accident | Settlement to be completed next financial year | Report, proof of payment Certificate | R12 000 000
HUMAN RESOURCE MANAGEMENT
To implement the process and procedures of Human Resource (HR) policies by June 2022 | Recruitment and Selection | 05 Vacant and funded positions filled | % of vacant funded positions filled | 100% Filling of vacant and funded positions | Shortlisting and interview of funded positions | Achieved | Appointment of 20 Heavy Duty Operators,advertisement of Manager Budget,Manager ICT,Director IWS,Director Corporate Services,CAE,Financial Interns | None | None | Appointment letters | 98805.47
| Internal Bursaries | 9 Internal Bursaries maintained | Number of Internal Bursaries maintained | 09 Internal Bursaries maintained | Maintanance of internal Bursaries | Achieved | 22 Internal Bursaries awarded and amintained.Advert for 2022 Academic year released | None | None | Bursary letters | 592830.76
| External Bursaries | 3 External Bursaries maintained | Number of External Bursaries maintained | 03 External Bursaries maintained | Maintanance of 3 external Bursaries | Achieved | 03 External Bursaries maintained | None | None | Bursary letters | 691636.24
To implement the WSP projects by June 2022 | WSP Projects | 02 WSP Projects Implemented | Number of WSP Projects implemented | 05 WSP Projects implemented | Implementation of 01 WSP project | Achieved | 6 WSP Projects implemented | None | None | WSP training report | 210000
EMPLOYEE ASSISTANCE PROGRAMME
To conduct employee wellness programmes by June 2022 | Employee wellness and Counselling | 4 wellness and counselling programmes conducted. | Number of wellness programmes conducted | 2 wellness awareness programmes conducted | 1 employee wellnes awareness programme conducted | Achieved | 1 employee wellness awareness programme was conducted in Uitspaning Depot on the 21/12 2021 | None | None | Wellness awareness programme attendance registers. | 571651.62
To conduct substance abuse programmes by June 2022 | Substance Abuse | 3 substance abuse programmes conducted | Number of substance abuse programmes conducted | 2 substance abuse programmes conducted | 1 substance abuse programme conduccted | Achieved | Substance abuse programme was conducted in Uitspaning Depot on the 20/12/2021 | None | None | Substance abuse programme registers.
To conduct Occupational Health and Safety elements by June 2022 | Occupational Health and Safety elements | 42 Occupational Health and Safety elements conducted | Number of Occupational Health and Safety elements conducted | 41 Occupational Health and Safety elements conducted (24 workplace inspections, 8 project audits, 2 safety awareness campaigns, 4 safety committee meetings, 2 servicing of fire extiquishers and hose reels). | 10 Occupational Health and Safety elements conducted (6 workplace inspections, 2 project audits, 1 safety awareness campaigns, 1 safety committee meetings). | Achieved | 27 Ocupational Health and Safety elementys conducted (23 workplace inspections, 2 project audits and 1 safety committee meeting held, 1 safety awareness campaign). | None | None | Workplace inspections and project audits reports, safety awareness campaigns attendance registers, safety committee meeting attendance registers, servicing of fire extiquishers and fire hose reels register . | 8345586.65
To provide personal Protective equipment by June 2022 | Personal Protective Equipment | 7692 Personal Protective Equipment (fire protection PPE) provided to Emergency Services employees, IWS, and CPS | Number of Personal Protective Equipment provided to IWS, Emergency Services, Municipal Health Services, CPS, Budget and Treasury, SDA, PED, Mayors and Speakers office employees | All Personal Protective Equipment provided to IWS, Emergency Services, Municipal Health Services, CPS, Budget and Treasury, SDA, PED, Mayors and Speakers office employees | All Personal Protective Equipment provided to IWS, Emergency Services, Municipal Health Services, CPS, Budget and Treasury, and PED | Not Achieved | All Personal Protective Equipment provided to some employees in IWS and CPS (chest weiders, gloves, work suits) provided to some employeesin IWS, CPS, PED and Executive Myors' office(chest weiders, gloves, work suits). | PPE tender is still undergoing Supply Chain Management Bid Committee process. | Supply chain Management Unit to fastrack appoinment of the Service Provider | Memos, Proof of payments, Personal protective equipment issuing forms
PERFORMANCE MANAGEMENT
To facilitate Performance Makgotla by 30 June 2022 | Performance Makgotla | 3 Performance Makgotla Sessions held | Number of Performance Makgotla facilitated | 04 Performance Makgotla facilitated | 1 Performance Makgotla facilitated | Not achieved | 1 Performance Lekgotla not facilitated | Change of Leadership | To be facilitated in the next quarter once new Council is elected and resumed duty | Attendance Registers, Makgotla Resolutions | 105141
To develop 2022/2023 Institutional SDBIP by June 2022 | 2022/2023 Institutional SDBIP | 2021/2022 Institutional SDBIP in place | Number of 2022/2023 Institutional SDBIP developed | 01 2022/2023 Institutional SDBIP developed | No Activity | N/A | N/A | N/A | N/A | Signed 2022/2023 Institutional SDBIP | R0.00
To compile 2020/2021 Institutional Annual Report by January 2022 | 2020/21 Annual Report | 2019/20 Annual Report in place | Number of 2020/21 Annual Reports developed | 01 2020/21 Annual Report developed | Data collection | Achieved | Data collected and Draft Annual Report in place | None | None | Final 2020/2021 Annual Report and Oversight Report. | R0.00
To develop 2021/2022 Performance Agreements for Senior Managers by July 2021 | 2021/22 Performance Agreements for Senior Managers | 2020/21 Performance agreements and in place | Number of 2021/22 Performance Agreements for Senior Managers developed | 04 2021/22 performance agreements for Senior Managers developed | No Activity | N/A | N/A | N/A | N/A | Signed Performance Agreements of Senior Managers | R0.00
To facilitate performance assessments for senior managers by June 2022 | Individual performance assessments for senior managers | 2019/20 performance assessments for senior managers conducted | Number of performance assessments for senior managers conducted. (2020/21 Annual & 2021/22 Mid-term) | 02 performance assessments for senior managers conducted. (2020/21 Annual & 2021/22 Mid-term) | No Activity | N/A | N/A | N/A | N/A | 2021/22 Mid-term and 2020/2021 Annual Assessment Reports | R0.00
To review PMS Policy and Framework by 30 June 2022 | Review of PMS Policy and Framework | 2020/2021 PMS Policy and Framework in place | Number of PMS Policies and Frameworks reviewed | 01 PMS Policy and Framework reviewed | Circulation of the policy for inputs | Achieved | Policy circulated to staff for inputs | None | None | Reviewed PMS Policy and Framework | R0.00
To coordinate quarterly Back to Basics Reports by June 2022 | Back to Basics (B2B) | 2020/2021 B2B quarterly reports in place | Number of quarterly Back to Basics (B2B) reports coordinated | 04 quarterly B2B reports coordinated | 01 quarterly B2B report coordinated | Achieved | 01 quarterly B2B report coordinated | None | None | 4 Quarterly B2B signed Reports | R0.00
To procure PMS by June 2022 | Performance Management System | New | Number of Performance Management Systems procured | 01 Performance Management System procured | Appointment of Service Provider for PMS System | Not achieved | Service Provider not appointed | The bid was advertised with a period of once off (14 days)while it should be done in stages (30 days) | The bid will be readvertised for 30 days | PMS system in place and operational | R1 000 000.00
LEGAL SERVICES
To manage litigations instituted against Sekhukhune District Municipality by June 2022 | Litigations | 15 Litigations attended to | Number of litigations attended to | 4 litigations attended to | 1 litigation attended to | Achieved | 4 litigations attedned to (03 litigations attedned to) | None | None | Copies of Court judgments Copies of Summons Copies of Deeds of settlement | 6766500
To reduce value of contingency liability for SDM by June 2022 | Litigations | 15 Litigations attended to | Reduced percentage (%) value of contingency liability for SDM | 20% value of contingency liability reduced | 5% value of contigency liabity reduced | Achieved | No case settled out of court | None | None | Comparitive value of contigent liability Setlements of of Court
To draft/vett service level agreements and other forms of agreements by June 2022 | Service level agreements and other forms of agreements | 310 service level agreements and other forms of agreements | Number of all service level agreements and other forms of agreements drafted or vetted | All of service level agreements or other forms of agreements drafted or vetted | All of service level agreements or other forms of agreements drfted or vetted | Achieved | All of service level agreements or other forms of agreements drafted or vetted (26 contracts drfted and 0 vetted) | None | None | Copies of agreements
To provide legally sound advice to SDM by June 2022 | Legal opinions | 10 legal opinions | Number of legal opinions drafted | All legal opinions drafted | All legal opinions drafted | Achieved | All legal opinions drafted (1 legal opinion Provided) | None | None | Copies of legal opinions
To manage Section 57 Disciplinary Enquiries by June 2022 | Disciplinary Enquiries | 4 Disciplinary enquiries | Number of disciplinary enquiries managed | All disciplinary enquiries managed | All disciplianry enquiries managed | Not applicable | No Labour related disciplinary cases received. | None. | None. | Records of conclusion of enquiries
DISTRICT DEVELOPMENT PLAN (DDP) / INTEGRATED DEVELOPMENT PLAN (IDP)
To develop 2022/2023 IDP Framework/ Process Plan by August 2021 | Develop 2022/2023 IDP Framework/ Process Plan | 2021/2022 IDP Framework/Process Plan in place | Number of IDP Frameworks/Process Plans developed | 1 IDP Framework/ Process Plan developed | No activity | N/A | N/A | N/A | N/A | *IDP Framework/ Process Plan document for 2022/2023 *Council resolution | R0
To review the Integrated Development Plan (IDP) for 2022/2023 by June 2022 | Review of Integrated Development Plan (IDP) | 2021/22 Integrated Development Plan (IDP) developed | Number of Integrated Development Plans (IDP) reviewed | 1 Integrated Development Plan (IDP) reviewed | Status Quo Analysis completed | Achieved | Status Quo Analysis completed | None | None | *Final IDP 2022/2023 *Council Resolution | 60000
To facilitate the IDP Rep Forums by June 2022 | Facilitate the IDP Rep Forums | 2 IDP Rep Forums facilitated | Number of IDP Rep Forums facilitated | 2 IDP Rep Forums facilitated | No activity | No activity | No activity | N/A | N/A | *Signed Minutes *attendance register | 100000
To facilitate review the District Development Plan (One Plan) by June 2022 | Review of 2022/2023 District Development Plan (DDP) | 2021/2022 District Development Plan (DDP) in place | Number of District Development Plan (DDP) reviewed | 1 District Development Plan (DDP) reviewed | Review of the District Socio-economic Profile | Achieved | The District Socio-economic Profile reviewed | None | None | *Final DDP 2022/2023 *Council Resolution | 100000