## Sheet1
2022/2023 ADJUSTED SERVICE DELIVERY BUDGET AND IMPLEMENTATION PLAN
FINANCIAL VIABILITY
OBJECTIVES | PROJECT | BASELINE 2021/2022 | INDICATORS | ANNUAL TARGET 2022/2023 | Q4 TARGETS | JUNE TARGETS | PROGRESS (Achieved not achieved) | ACTUAL PROGRESS | CHALLENGES | REMEDIAL ACTIONS | POE | BUDGET 2022-2023
To ensure that valid and complete invoices are paid within 30 days | Payment of creditors | 80% of received invoices, valid and complete (paid within 30 days) | Percentage payment of valid and complete invoices received and paid within 30 days | 100% payment of valid and complete invoices received and paid within 30 days | 100% payment of valid and complete invoices received and paid within 30 days | 100% payment of valid and complete invoices received and paid within 30 days | Achieved | 100% payment of valid and complete invoices received and paid within 30 days | None | None | Invoices. Creditors age analysis and payment register. | 0
To adhere to set dates for monthly submission of salary inputs and work schedules | Salaries and Third-Party Payments | 100% of Salaries paid by the 25th and 3rd party payments by the 7th. | Percentage of salaries paid on thee 25th and 3rd party payment by the 7th. | 100% of salaries paid on thee 25th and 3rd party payment by the 7th. | 100% of salaries paid on the 25th and 3rd party payment by the 7th. | 100% of salaries paid on the 25th and 3rd party payment by the 7th. | Achieved | 100% of salaries paid on the 25th and 3rd party payment by the 7th. | None | None | Bank statements and Salary reports | 0
| Subsistence and Travel | 100% of 2020/202100% of Travel claims paid on the 15th | Percentage of Travel claims paid by the 15th | 100% Travel claims paid by the 15th | 100% Travel claims paid by the 15th | 100% Travel claims paid by the 15th | Achieved | 100% Travel claims paid by the 15th | None | None | pay slip | 0
To improve audit opinion | Clean Audit | Qualified Audit opinion | Percentage of Finance related Audit findings resolved | 100% of Finance related Audit findings resolved | 100% of Finance related Audit findings resolved | 100% of Finance related Audit findings resolved | Not achieved | 65% Finance related Audit findings resolved | Supporting documents not uploaded | All supporting documents be uploaded | AG report | 0
To ensure compliance reporting | Submission of AFS and APR to the AG within the legislated time frame | Submitted AFS and APR to AG within legislated timeframe | Number of Submission of AFS and APR by 31st August and consolidated AFS by 30th September | 01 Submission of AFS and APR by 31st August and consolidated AFS by 30th September | No activity | No activity | No activity |  |  |  | Signed AFS and APR/ Ackonwledgement of receipt by AGSA | 0
To ensure compliance reporting | National Treasury statutory reports | 17 National Treasury statutory reports | Number of National Treasury statutory reports submitted (4 sec 52, 12 sec 71 and 1 sec 72) | 17 National Treasury statutory reports submitted (4 sec 52, 12 sec 71 and 1 sec 72) | 5 National Treasury statutory reports submitted (1 sec 52, 4 sec 71) | 5 National Treasury statutory reports submitted (1 sec 52, 4 sec 71) | Achieved | 5 National Treasury statutory reports submitted (1 sec 52, 4 sec 71) | None | None | Signed report and proof of submission | R0.00
To provide sound financial management | Budget | 1 Credible (Annual and adjusted) Budget prepared and implemented. | Number of Credible (Annual and adjusted) Budget prepared and implemented. | 1 Credible (Annual and adjusted) Budget prepared and implemented. | 1 Tabled 2022/2023 Annual Budget to Council for approval by 30 May 2023 | 1 Tabled 2022/2023 Annual Budget to Council for approval by 30 May 2023 | Achieved | 1 Tabled 2022/2023 Annual Budget to Council for approval by 30 May 2023 | None | None | Annual Budget & Council resolution | R0.00
To implement revenue enhancement strategy | Improved revenue base and collection rate | Improve the collection rate to 75% | Percentage of revenue collected against the billing | 75% of revenue collected against the billing | 5% of revenue collected against the billing | 5% of revenue collected against the billing | Achieved | 49% | None | None | Collection rate report & Deptors Age analysis | R823 573.76
To implement Credit and debt collection policy | Customer Data cleansing | 25% inaccurate customer data | Number of service provider appointed for data cleasing | 1 service provider appointed for data cleasing | Data analysis by the appointed service provider | Data analysis by the appointed service provider | Not achieved | No service provider appointed | The tender was re-advertised | Prioritise appoint the service provider | Appointment letter & data cleansing report | R3 000 000.00
| Identification of potential areas to be billed | 5 areas with revenue potential identified | Collection of data and billing of areas with revenue potential | Collection of data and billing of 5 areas with revenue potential | Collection of data and billing 2 area with revenue potential | Collection of data and billing 2 area with revenue potential | Not achieved | 0 areas where collection of data and billing | The tender was re-advertised | Prioritise appoint the service provider | Data Collection report and Summary of billing reports | R3 500 000.00
| pre-paid meter installations | 287 prepaid meters installed in Tubatse | Number of service provider appointed to install prepaid meters | 1 service provider appointed to install prepaid meters | Site establishment and installation of meters | Site establishment and installation of meters | Not achieved | 0 prepaid meters installed | The tender was re-advertised | Prioritise appoint the service provider | Meter reading report and appointment letter | R3 000 000.00
| Verification of indigent register | Indigent register for 2021/2022 | Percentage increase in indigent customers | 10% increase in indigent customers | 3% increase in indigent customers | 3% increase in indigent customers | Not achieved | 0% increase in indigent customer | The tender was re-advertised | Prioritise appoint the service provider | Indigents register | R2 500 000.00
| Meter reading | 75% Verification and reading of 13100 customers' meters | Percentage of customers meter readings | 70% reading of customers meters | 70% reading of customers meters | 70% reading of customers meters | Achieved | 72% reading of customers meters | None | None | Billing report and meter reading schedule register | R8 500 000.00
To Improve accountability of Asset Management | Assets management support | 80% Accountability of Asset Management | Percentage Accountability of Asset Management | 100% Accountability of Asset Management | 100% Accountability of Asset Management | 100% Accountability of Asset Management | Achieved | 100% Accountability of Asset Management | None | None | GRAP and mSCOA compliant FAR | R5 308 134.00
To implement effective, efficient and economical supply chain management process and SCM regulations | Procurement Plan | 80% Procurement plan developed and implemented | Percentage development and implementation of procurement plan (MIG,RBIG,WSIG and all other tenders) | 100% development and implementation of procurement plan (MIG,RBIG,WSIG and all other tenders) | 100%Procurement plan developed and implemented (MIG,RBIG,WSIG and all other tenders) | 100%Procurement plan developed and implemented (MIG,RBIG,WSIG and all other tenders) | Not achieved | 100%Procurement plan developed and implemented (MIG,RBIG,WSIG and all other tenders) | None | None | Procurement plan | 0
| Unauthorised ,irregular, fruitless and wasteful expenditure (UIFW) | Section 32 expenditure amount reported | Number of reports on the Compliance with MFMA section 32 | 4 reports on the Compliance with MFMA section 32 | 1 report on the Compliance with MFMA section 32 | 1 report on the Compliance with MFMA section 32 | Achieved | 1 report on the Compliance with MFMA section 32 | None | None | 4 UIFW Reports | R0.00
| Effective and Efficient inventory management system | 90% Adherence Grap compliance | Number of reports on compliance with management of MFMA section 63(1) | 4 reports on compliance with management of MFMA section 63(1) | 1 report in compliance with management of MFMA section 63(1) | 1 report in compliance with management of MFMA section 63(1) | Achieved | 1 report in compliance with management of MFMA section 63(1) | None | None | Monthly Recons reports | 0
| Contracts and Compliance Management | 80%Compliance to SCM Policy | Number of reports on compliance to all prescribed Legislations | 4 reports on compliance to all prescribed Legislations | 1 report in compliance to all prescribed Legislations | 1 report in compliance to all prescribed Legislations | Achieved | 1 report in compliance to all prescribed Legislations | None | None | Contract register and SCM report | 0