## Sheet1
2022/2023 ADJUSTED SERVICE DELIVERY BUDGET AND IMPLEMENTATION PLAN
INSTITUTIONAL DEVELOPMENT AND ORGANIZATIONAL TRANSFORMATION
OBJECTIVES | PROJECT | BASELINE 2021/2022 | INDICATORS | ANNUAL TARGET 2022/2023 | Q1 | Q2 | Q3 | Q4 | ACTION ( Remove/ Retain/ Adjust) | Reason for Adjustment | Adjusted Budget | POE | BUDGET 2022-2023 | RESPONSIBLE MANAGER
ORGANISATIONAL DEVELOPMENT
To review the Organisational Structure by June 2023. | Organisational Structure Review | 1 Organisational Structure Reviewed | Number of Organisational Structures Reviewed. | 1 Organisational Structure Reviewed | 1st Assessment of organisational structure | 2nd Assessment of organisational structure | Gather information for organisational structure review | 1 Final organisational strucutre for approval | Retain | None | None | Council Resolution(approved Organisational Structure) | 0 | Langa Kabini
To facilitate development of job descriptions and job evaluation by June 2023 | Job Description Development and Job Evaluation | 50 Job Description Developed and Evaluated | Number Job Descriptions Developed and Evaluated. | 50 Job Descriptions Developed and Evaluated | 0 Job Descriptions Developed and Evaluated | 15 Job Descriptions Developed and Evaluated | 15 Job Descriptions Developed and Evaluated | 20 Job Descriptions Developed and Evaluated | Retain | None | None | Report | 0
To develop SOP’s and Process Maps by June 2023. | SOP’s and Process Maps | Approved SOP'S and Process Maps | Number of SOP’s and Process Maps Developed. | 20 SOP’s and Process Maps Developed | 5 SOP's and Process Maps Developed | 5 SOP's and Process Maps Developed | 5 SOP's and Process Maps Developed | 5 SOP's and Process Maps Developed. | Retain | None | None | Approved SOP's and Process Maps | 0
INFORMATION AND COMMUNICATION TECHNOLOGY (ICT)
To convene ICT steering committee meetings by June 2023. | ICT Steering Committee Meetings | 4 Quartely meetings | Number of meetings convened | 4 meetings convened | 3 Security Controls Implemented | 3 Security Controls Implemented | 1 meeting convened | 1 meeting convened | New | To comply with ICT Governance framawork | None | Attendant register/minutes | 0 | Mashaba T
To monitor Service Level Agreements by June 2023. | Contract Monitoring | New | Number of Service Providers Performance Monitoring and Evaluation meetings held | 4 ICT Service Providers Performance Monitoring and Evaluation meetings held | 1 Service Providers Performance Monintoring and Evaluation meetings held | 1 Service Providers Performance Monintoring and Evaluation meetings held | 1 Service Providers Performance Monintoring and Evaluation meetings held | 1 Service Providers Performance Monitoring and Evaluation meetings held | Adjust | Target refined | None | Attendant register/minutes | 0
To report ICT incidents resolved by June 2023. | ICT Incedent | New | Percentage of reported ICT incidents sesolved. | 90% - 100% of reported ICT incidents resolved | 90% - 100% of reported ICT incidents resolved | 90% - 100% of reported ICT incidents resolved | 90% - 100% of reported ICT incidents resolved | 90% - 100% of reported ICT incidents resolved | New | To comply with ICT Governance framawork | None | ICT Job Card | 0
To improve efficiency and effectiveness of municipal administration by June 2023. | Hardware devices | New | Percentage Hardware devices purchased. | 100 % Hardware devices purchased | 100 % Hardware devices purchased | 100 % Hardware devices purchased | 100 % Hardware devices purchased | 100 % Hardware devices purchased | New | To comply with ICT Governance framawork | 2000000 | Purchase Order/Proof of Payment | R2 000 000.00
LABOUR RELATIONS
To Facilitate Local Labour Forums by June 2023. | Local labour Forums | 7 Local Labour Forums Facilitated. | Number of LLF meetings facilitated | 12 LLF meetings facilitated | 3 LLF meetings facilitated | 3 LLF meetings facilitated | 3 LLF meetings facilitated | 3 LLF meetings facilitated | Retain | None | None | Minutes and attendance registers | R60 000.00 | Ntobeng L
To facilitate Disciplinary cases by June 2023. | Disciplinary cases. | 100% Disciplinary cases facilitated. | Percentage Disciplinary cases facilitated | 100% disciplinary cases facilitated | 100% disciplinary cases facilitated | 100% disciplinary cases facilitated | 100% disciplinary cases facilitated | 100% disciplinary cases facilitated | Retain | None | None | Disciplinary hearing rullings/reports and/or settlements and attendance registers | R205 514.40
AUXILIARY SERVICES
To implement file plan by June 2023. | File Plan | Approved File Plan | Percentage of File Plan Implementation | 100% File Plan Implemented | 100% File Plan Implemented | 100% File Plan Implemented | 100% File Plan Implemented | 100% File Plan Implemented | Retain | None | None | File plan | 0 | Boshego K
To facilitate Implementation of Electronic Filling System by June 2023. | Electronic Filling System | Electronic Filling Systems (Mun admin) implemented by 1 Department (legal services) | Number of departments to implement lectronic Filling Systems (Mun admin) | 2 departments to implement lectronic Filling Systems (Mun admin) | No activity | 1 department to implement lectronic Filling Systems (Mun admin) | 1 department to implement lectronic Filling Systems (Mun admin) | No activity | Remove | Contract expired | None | Monthly report | 0
To facilitate purchase of filling cabinets by June 2023 | Filling cabinets | 6 filing cabinets purchased | Number of filling cabinets purchased. | 06 filing cabinets purchased | No activity | No Activity | 06 filing cabinets purchased | No activity | Retain | None | 700000 | Reports delivery notes | R 316 000.00
To facilitate records management IGR structure by June 2023. | IGR cluster group | 1 IGR cluster group formed | Number of IGR cluster groups with all local municipalities facilitated | 7 IGR cluster groups with all local municipalities facilitated | 2 meeting facilitated for Records Management IGR structure | 2 meeting facilitated for Records Management IGR structure | 2 meeting facilitated for Records Management IGR structure | 1 meeting facilitated for Records Management IGR structure | Retain | None | None | attendance registers and quarterly report | 0
To facilitate the Maintenance and repairs of municipal vehicles by June 2023 | Maintenance and repairs of vehichles | 67 vehicles Maintained and repaired | Number of vehicles Maintained and repaired. | 67 vehicles Maintained and repaired | 16 vehicles Maintained and repaired | 16 vehicles Maintained and repaired | 16 vehicles Maintained and repaired | 19 vehicles Maintained and repaired | Adjust | Target reduced | None | invoices | R3 300 000.00
To facilitate purchasing of IWS manchinery by June 2023. | Purchase of IWS machinery (yellow vehicles) | 67 Vehicles | Number of Vehicles purchased | 04 Vehicles purchased (Cherry picker x1, Crane Truck 1, TLB x1, Tipper Truck x1 | No activity | 02 vehicles purchased. Cherry picker trailor x1 and TLB x1 | 02 vehicles purchased. Tipper truck x1 crane truck X1 | No activity | Remove | No budget | None | Reports delivery notes | R 3 750 000.00
To facilitate maintanance and repair of facilities by June 2023. | Maintenance and repairs of facilities | 06 Facilities Maintained and repaired | Number of Facilities Maintained and repaired | 06 Facilities Maintained and repaired | 01 Facilities Maintained and repaired | 02 Facilities Maintained and repaired | 01 Facilities Maintained and repaired | 02 Facilities Maintained and repaired | Retain | None | None | Maintanance and repairs invoices | R1 880 000.00
To purchase office furniture by June 2023 | Office furniture | 60 high back chairs | Number of high back chairs, workstation and executive chairs purchased. | 100 high back chairs, 10 workstation and 03 executive chairs purchased | 100 high back chairs and 03 executive chairs purchased | 05 workstations (table) purchased | 05 workstations (table) purchased | No activity | Remove | No budget | None | Reports delivery notes | R 1 000 000.00
HUMAN RESOURCE MANAGEMENT
To implement the process and procedures of Human Resource (HR) policies by June 2023 | Recruitment and Selection. | 38 Vacant and funded positions filled | Percentage of funded and vacant positions filled | 100% of funded and vacant positions filled | Internal advertisement | 25% of funded and vacant positions filled | 50% of funded and vacant positions filled | 25% of funded and vacant positions filled | Retain | None | None | Appointment Letters | R500 000.00 | Langa Kabini
| Internal Bursaries | 22 Internal Bursaries awarded | Number of Internal Bursaries maintained. | 22 Internal Bursaries maintained | 22 Internal Bursaries maintained | 22 Internal Bursaries maintained | 22 Internal Bursaries maintained | 22 Internal Bursaries maintained | Retain | None | None | Bursary Report and busary holder list | R 720 544.24
| External Bursaries | 03 External Bursaries awarded | Number of External Bursaries maintained | 03 External Bursaries maintained | 03 External Bursaries maintained | 03 External Bursaries maintained | 03 External Bursaries maintained | 03 External Bursaries maintained | Remove | The 3 External Bursary Holders completed their studies in 2022 Academic Year | Budget Udjusted.R200 000 to catering and R100 000 to Recruitment and Selection | Bursary Report | R 459 301.44
| WSP Training interventions | 06 WSP Projects implemented | Number of WSP projects implemented | 05 WSP projects implemented | 02 WSP projects implemented | 01 WSP projects implemented | 01 WSP projects implemented | 01 WSP projects implemented | Retain | None | None | Training and Development Report and WSP | R 825 787.04
EMPLOYEE ASSISTANCE PROGRAMME
To conduct employee wellness programmes by June 2023. | Employee wellness programme | 2 wellness and counselling programmes conducted. | Number of wellness awareness programmes conducted. | 2 wellness awareness programmes conducted | No activity | 1 wellness awareness programmes conducted | 1 wellness awareness programmes conducted | No activity | Adjust | Increased Target | Activities does not require budget | attendance registers and report | R 386 518.08 | Sekhukhune L
To conduct substance abuse programmes by June 2023 | Substance Abuse Programme | 3 substance abuse programmes conducted | Number of substance abuse programmes conducted. | 2 substance abuse programmes conducted | No activity | 1 substance abuse programmes conducted | No activity | 1 substance abuse programmes conducted | Adjust | Target Increased | Activities does not require budget | attendance registers and report
To conduct Occupational Health and Safety elements by June 2023 | Occupational Health and Safety elements | 42 Occupational Health and Safety elements conducted | Number of Occupational Health and Safety elements conducted. | 40 Occupational Health and Safety elements conducted (24 workplace inspections, 8 project audits, 2 safety awareness campaigns, 4 safety committee meetings, 2 servicing of fire extiquishers and hose reels). | 10 Occupational Health and Safety elements conducted | 10 Occupational Health and Safety elements conducted | 10 Occupational Health and Safety elements conducted | 10 Occupational Health and Safety elements conducted | Retain | None | Adjusted budget not available | Exit reports, attendance registers, minutes and invoice | R2 000 000.00
Tp provide Personal Protective Equipment by June 2023. | Personal Protective Equipment | 7692 Personal Protective Equipment (fire protection PPE) provided to Emergency Services employees, IWS, and CPS | Percentage of Personal Protective Equipment provided to employes. | 100% Personal Protective Equipment provided to employes | 100% Personal Protective Equipment provided to employes | 100% Personal Protective Equipment provided to employes | 100% Personal Protective Equipment provided to employes | 100% Personal Protective Equipment provided to employes | Retain | None | None | Reports and PPE collection register.
PERFORMANCE MANAGEMENT SYSTEM (PMS)
To facilitate Performance Makgotla sessions by | Performance Makgotla | 3 Performance Makgotla Sessions held | Number of Performance Makgotla Sessions facilitated. | 04 Performance Makgotla sessions facilitated | 01 Performance Lekgotla session facilitated | 01 Performance Lekgotla session facilitated | 01 Performance Lekgotla session facilitated | 01 Performance Lekgotla session facilitated | Retain | None | None | Attendance Registers, Makgotla Resolutions | R100 000.00 | Robinson K
To develop 2023 /2024 Institutional SDBIP by July 2023 | 2023/2024 Institutional SDBIP | 2022/2023 Institutional SDBIP in place | Number of 2023/2024 Institutional SDBIP developed. | 01 2023/2024 Institutional SDBIP developed | No Activity | No Activity | 01 2023/2024 draft Institutional SDBIP developed | 01 2023/2024 final Institutional SDBIP developed | Adjust | Target refined | None | Signed 2023/2024 Institutional SDBIP | R0.00
To compile 2021/2022 Institutional Annual Report and oversight report developed by June 2023. | 2021/22 Institutional Annual Report oversight report developed | 1 2020/21 Instituional Annual Report in place and 01 oversight report developed | Number of 2021/22 Institutional Annual Reports developed. | 01 2021/22 Institutional Annual Report developed | Data collection | Data Collection | 01 2021/22 Institutional Annual and oversight report developed | No activity | Retain | None | None | Final 2021/2022 Annual Report and Oversight Report. | R0.00
To develop 2022/2023 Performance Agreements for Senior Managers by 31 July 2023. | 2022/23 Performance Agreements for Senior Managers | 2021/22 Performance agreements for Senior Managers and in place | Number of 2022/23 Performance Agreements for Senior Managers developed | 04 2022/23 performance agreements for Senior Managers developed | 04 2022/23 performance agreements for Senior Managers developed | No Activity | No Activity | No Activity | Retain | None | None | Signed Performance Agreements of Senior Managers | R0.00
To facilitate performance assessments for senior managers June 2023. | Individual performance assessments for senior managers | Signed Performance agreement for senior managers in place | Number of performance assessments for senior managers conducted. (2021/22 Annual & 2022/23 Mid-term) | 02 performance assessments for senior managers conducted. (2021/22 Annual & 2022/23 Mid-term) | No Activity | No Activity | 02 performance assessments for senior managers conducted. (2021/22 Annual & 2022/23 Mid-term) | No Activity | Retain | None | None | 2022/23 Mid-term and 2021/2022 Annual Assessment Reports | R0.00
To review PMS Policy and Framework by June 2023. | Review of 2022/2023 PMS Policy and Framework | 2021/2022 PMS Policy and Framework in place | Number of 2022/2023 PMS Policies and Frameworks reviewed | 01 2022/2023 PMS Policy and Framework reviewed | No Activity | Circulation of the policy for inputs | Presentation of the policy to management and council committees | 01 PMS Policy and Framework reviewed and adopted by Council | Retain | None | None | Reviewed PMS Policy, Framework and Council Resolution | R0.00
To Coordinate quarterly Back to Basics Reports by June 2023. | Back to Basics (B2B) | 2021/2022 B2B reports in place | Number of quarterly Back to Basics (B2B) reports coordinated. | 04 quarterly Back to Basics (B2B) reports coordinated | 01 quarterly B2B report coordinated | 01 quarterly B2B report coordinated | 01 quarterly B2B report coordinated | 01 quarterly B2B report coordinated | Retain | None | None | 4 Quarterly B2B signed Reports | R0.00
To procure PMS by June 2023 | Performance Management System | New | Number of Performance Management Systems procured. | 01 Performance Management System procured | Development of specification and submission to SCM. | Appointment of Service Provider for PMS System | Implementation of the PMS system | Implementation of the PMS system | Retain | None | 700000 | PMS system in place and operational. Service provider appointment letter | R2 000 000.00
LEGAL SERVICES
To Manage litigations instituted against SDM by June 2023 | Litigations | 30 Litigations attended to | Percentage of litigations attended to. | 100% litigations attended to | 100% litigations attended to | 100% litigations attended to | 100% litigations attended to | 100% litigations attended to | Retain | None | N/A | 1 litigations attended to, Litigation register and Report. | R6 537 160.00 | Malatji H
To vet and or draft service level agreements and other forms of agreements by June 2023. | Service level agreements and other forms of agreements | 310 service level agreements and other forms of agreements drafted and or vetted | Percentage of service level agreements and other forms of agreements drafted and or vetted. | 100% service level agreements and other forms of agreements drafted and or vetted | 100% service level agreements and other forms of agreements drafted and or vetted | 100% service level agreements and other forms of agreements drafted and or vetted | 100% service level agreements and other forms of agreements drafted and or vetted | 100% service level agreements and other forms of agreements drafted and or vetted | Retain | None | N/A | All of service level agreements or other forms of agreements drafted or vetted. List of service providers without SLA's
To provide sound legal opinion to SDM by June 2023. | Legal opinions | 10 legal opinions | Percentage of legal opinions drafted. | 100% legal opinions drafted | 100% legal opinions drafted | 100% legal opinions drafted | 100% legal opinions drafted | 100% legal opinions drafted | Retain | None | N/A | All legal opinions drafted
DISTRICT DEVELOPMENT PLAN / INTEGRATED DEVELOPMENT PLAN
To develop IDP Framework/ Process Plan by June 2023. | 2023/2024 IDP Framework/ Process Plan | 2022/2023 IDP Framework/ Process Plan in place | Number of 2023/2024 IDP Framework/ Process Plan developed. | 01 2023/2024 IDP Framework/ Process Plan developed | 01 2023/2024 IDP Framework/ Process Plan developed | No activity | No activity | No activity | Retain | None | 42400 | *IDP Framework/ Process Plan document for 2023/2024 *Council resolution | R0.00 | Makgati R
To review Integrated Development Plan (IDP) by June 2023. | Integrated Development Plan (IDP) | 2022/23 Integrated Development Plan (IDP) developed | Number of 2023/2024 Integrated Development Plan (IDP) reviewed. | 01 2023/2024 Integrated Development Plan (IDP) reviewed | Internal and sector departments consulted on the level of development within the district. | Status Quo Analysis completed | 2023/2024 Draft reviewed IDP in place | 2023/2024 Final reviewed IDP in place | Retain | None | N/A | *Final IDP 2023/2024 *Council Resolution | R62 000.00
To facilitate the IDP Rep Forums by June 2023. | IDP Rep Forums | 1 IDP Rep Forums Facilitated | Number of IDP Rep Forums facilitated. | 02 IDP Rep Forums facilitated | No activity | 1 IDP Rep Forum facilitated | No activity | 1 IDP Rep Forum facilitated | Retain | None | N/A | *Signed Minutes *attendance register | R100 000.00
To facilitate review of District Development Plan (One Plan) by June 2023 | 2023/2024 DDP | 2022/2023 District Development Plan in place | Number of 2023/2024 District Development Plan reviewed | 01 2023/2024 District Development Plan reviewed | No activity | Review of DDP inline with Coghsta DDP analysis report | Reviewed DDP send to Coghsta and OTP for inputs | Final reviewed DDP in place | Retain | None | 104000 | *Final DDP 2023/2024 *Council Resolution | R100 000.00