## Sheet1
2022/2023 QUARTER 4 SERVICE DELIVERY BUDGET AND IMPLEMENTATION PLAN
LOCAL ECONOMIC DEVELOPMENT: Manager Nchabeleng KC
OBJECTIVES | PROJECT | BASELINE 2021/2022 | INDICATORS | ANNUAL TARGET 2022/2023 | Q4 | PROGRESS (Achieved/ Not achieved) | ACTUAL PROGRESS | CHALLENGES | REMEDIAL ACTIONS | POE | BUDGET 2022/2023
To create 2 788 job Opportunities through EPWP by June 2023. | Implementation of EPWP | 2788 job opportunities created through EPWP | Number of jobs opportunities created through EPWP. | 2788 jobs opportunities created through EPWP (Infrastructure 2564, Environment and Culture 36 and Social Sector 188) | 764 jobs opportunities created through EPWP | Achieved | 762 jobs opportunities created through EPWP | None | None | Signed & Salary report | R13 010 000.00
To provide support to SMMEs and co-operatives by June 2023. | Support to SMMEs and Co-operatives | 30 SMMEs/Co-operatives supported | Number of SMMEs / Co-operative support provided. | 20 SMMEs / Co-operatives supported | Provide support to 20 SMMEs/ Cooperatives | Not achieved | Support to 20 SMMEs/Coperatives not provided | Tender is at adjudication stage | To expedite finalisation of the procurement processes | Reports | R 2 000 000.00 | .
To facilitate development of feasibility study for establishment of Flea Market by June 2023. | District Flea Market | Feasibility study of flea market within the district | Number of feasibility studies on the development of Flea Markets facilitated within the district | 1 feasibility study on the development of a Flea Market facilitated within the District | 1 Feasibility study on development of a Flea Market within the district | Not achieved | Tender validity period expired on the 18 April 2023 | The tender could not be readvertised as development of the feasibility study require a minimum of 2 months and above. | The project to be implemented in the future financial years. | Feasibility report on development of a Flea Market within the district. Terms of reference, Inveption report and Appointment letter | R300,000.00
To facilitate farmers support through Farmers Production Support Unit (Agri Park) at Vleeschboom by June 2023. | Farmers support through Farmers Production Support Unit (Agri Park) at Vleeschboom (PED) | 879 farmers supported through Farmers Production Support Unit (Agri Park) at Vleeschboom | Number of farmers supported through Farmers Production Support Unit (Agri Park) at Vleeschboom | 1 000 farmers supported through Farmers Production Support Unit (Agri Park) at Vleeschboom | 334 farmers supported through Farmer Prodcution Support Unit | Achieved | 334 farmers supported through Farmer Prodcution Support Unit | None | None | *Signed Reports | R8 000 000 (DALRRD, LDARD)
To facilitate development of feasibility study for Poultry Abattoir facility by June 2023 | Development of feasibility study for Poultry Abattoir facility | 6 poultry houses (40 000 capacity each) in place | Number of feasibility study on Poultry Abattoir facility facilitated | 1 feasibility study on development of Poultry Abattoir facility facilitated | 1 Feasibility study on development of poultry abattoir facility facilitated | Not achieved | Tender validity period expired on the 18 April 2023 | The tender could not be readvertised as development of the feasibility study require a minimum of 2 months and above. | The project to be implemented in the future financial years. | Feasibility study report for poultry abattoir facility. Terms of refereence, Inception and Appointment letter | R400,000.00
To facilitate development of Industrial Development Master Plan for the Special Economic Zone (SEZ) by June 2023. | Development of Industrial Development Master Plan for the Special Economic Zone (SEZ) (PED) | SEZ Business Plan in place | Number of Regional Industrial Development Master Plan developed | 1 Regional Industrial Development Master Plan developed | 1 Regional Industrial Development Master Plan developed | Not achieved | Draft report on Industrial Development Master Plan not in place | Severely underbudgeted | To be implemented in the next financial year 2023/2024. | Report on Industrial Development Master Plan. Terms of refereence, Inception and Appointment letter | R900 000.00
To facilitate Economic Development Forums (Mining, Tourism, LED & Agric.) by June 2023. | Economic Development Forums (Mining, Tourism, LED & Agric.) | 4 Economic Development Forums (Mining, Tourism, LED & Agric.) facilitated | Number of Economic Development Forums (Mining, Tourism, LED & Agric.) facilitated | 4 Economic Development Forums (Mining, Tourism, LED & Agric.) facilitated | 1 Economic Development Forum facilitated | Achieved | 1 Economic Development Forum facilitated | None | None | Signed reports and attendance register | R93 600 .00
To facilitate quartely reports on replacement of Malekana Steel Bridge by June 2023. | Quarterly reports on replacement of Malekana Steel Bridge (SDA) | Old Malekana Steel Bridge in place | Number of quartely reports on Malekana Steel Bridge replacement facilitated | 4 quarterly reports on Malekana Steel Bridge replacement facilitated | 1 Quarterly Report on Malekana Steel Bridge replacement facilitated | Achieved | 1 Quarterly Report on Malekana Steel Bridge replacement facilitated | None | None | Signed reports and Progress reports | R8 100 000.00
To facilitate fencing off of Tjate Heritage Site by June 2023. | Fencing of of Tjate Heritage Site | Tjate Heritage Site in place | Number of fencing of Tjate Heritage Site developed. | 1 fencing off of Tjate Heritage Site facilitated. | 1 fencing off of Tjate Heritage Site facilitated | Not achieved | Support to 20 SMMEs/Coperatives not provided | Tender is at adjudication stage | To expedite finalisation of the procurement processes | Signed report and Progress report | R400 000.00
To facilitate farmers support with Agricultural infrastructure by June 2023. | Farmers support | Cotton farmers identified | Number of farmers supported with Agricultural infrastructure | 2 farmers supported with Agricultural infrastructure | 2 farmers supported with Agricultural infrastructure | Not achieved | Support to 20 SMMEs/Coperatives not provided | Tender is at adjudication stage | To expedite finalisation of the procurement processes | Signed report | R400 000.00
To facilitate Installation of District Tourism Signage for Tourism Establishments and Products (Manche Masemola, King Nyabela and Tjate) by June 2023. | District Tourism Signage for Tourism Establishments and Products (Manche Masemola, King Nyabela and Tjate) | 3 existing District Tourism Establishments and Products (Manche Masemola, King Nyabela and Tjate) | Number of District Tourism Signage for Tourism Establishments and Products (Manche Masemola, King Nyabela and Tjate) installation facilitated | 9 District Tourism Signage for Tourism Establishments (Manche Masemola, King Nyabela and Tjate) installation facilitated | No activity | No activity | No activity | No activity | No activity | Signed report | R100 000 .00