## Sheet1
2022/2023 QUARTER 4 SERVICE DELIVERY BUDGET AND IMPLEMENTATION PLAN
SEKHUKHUNE DEVELOPMENT AGENCY (SDA) 2022-2023 PROJECTS
Strategy (approach to achieve objective) | Project | Baseline 2021/2022 | Indicators | Annual target 2022/2023 | Q4 | PROGRESS (Achieved/ Not achieved) | ACTUAL PROGRESS | CHALLENGES | REMEDIAL ACTIONS | POE | Budget 2022/2023
To facilitate Signing of Agreement for SDA to be appointed as the FSPU Facilities Management | Appointment of SDA as the FSPU Facilities Management | Feasibility study on the FSPU conducted | Number of engagement for SDA to be appointed as the FSPU Facilities Management facilitated | 4 Engagement for SDA to be appointed as the FSPU Facilities Management facilitated | Engagenent with stakeholders fascilitated | Achieved | Meeting held with Dept of Agriculrure and Rural Development | None | None | Attendance register and report\minutes | R 0,00
To facilitate signing of agreement with local cotton Spinner | Local cotton spinner agreement with (SDA) | Concept document | Number of local cotton producers collected for database. | 14 local cotton producers collected for database. | 7 local cotton producers collected for database. | Achieved | 14 Database of Local cotton producers collected. | None | None | Database of Local cotton producers | 0
To facilitate ngagement on appointment of SDA inclusion to SEZ project | Engagement on appointment of SDA inclusion to SEZ project | Draft quadripartite agreement | Number of Engagement on appointment of SDA inclusion to SEZ project to sign MOU between SDA and FTIP facilitated | 3 Engagement on appointment of SDA inclusion to SEZ project to sign MOU between SDA and FTIP facilitated | 1 Engagement to Signed MOU with FTIP | Achieved | MOU Signed with LFTIP | None | None | Signed MOU | R 0, 00
To conduct survey on district mineral resources | Conduct Survey of District Mineral Resources (SDA) | SDA business plan | Number of engagement to revive partnership with MINTEK to conduct district mineral resourse survey | 3 engagement to revive partnership with MINTEK to conduct district mineral resourse survey | 1 engagement to revive partnership with MINTEK to conduct district mineral resource survey | Achieved | Letter written to MINTEK to revive partnership to conduct mineral resource survey | None | None | formal request, Signed MOU | R 0, 00
To conduct feasibility study and 1 Business plan | Land ERF 488 (SDA) | Council resolutionn and deed of donation | Number of draft feasibility study conducted | 1 draft feasibility study conducted | 1 draft feasibility study conducted | Achieved | 1 Draft feasibility study report in place | None | None | Signed SLA,draft feasibility study report | R0.00
To conduct tourism promotion and marketing | Promotion of District heritage sites | Concept document | Number of Marketing activites on Distrcit Heritage sites campaigns conducted | 4 Marketing activites on District Heritage sites campaigns conducted | 1 Marketing activity on District Heritage sites campaigns conducted | Achieved | 1 Marketing activity on District Heritage sites campaigns conducted | None | None | Attendance register and or report | R0.00
To facilitate skills development learning intervention programmes | District-wide Skills developmet | None | Number of skills development learning intervention programmes facilitated | 4 skills development learning intervention programmes facilitated | 1 skills development learning intervention programmes facilitated | Achieved | 1 skills development learning intervention programmes facilitated | None | None | Attendance register | R0.00
By facilitating Strategic session of SDA | Facilitation of strategic session | Business Plan | Number of strategic session | 1 Strategic Session facilitated | 1 Strategic session facilitated | Achieved | 1 Strategic session final report facilitated | None | None | Strategic session Report\ document | 50000
To develop and maintain SDM website | Website development and maintenance | None | Number of website developed and maintained | 1 website developed and maintained | Appoint service provider to develop and maintain website | Not Achieved | 1 website not developed and maintained | Service provider to develop and maintain website not appointed due to budget constraints | Service provider to develop and maintain website to be appointed in the new financial year 2023/2024 | Appointment letter and website screenshot | R.00