## Sheet1
MEASURABLE OBJECTIVE | STRATEGY | INPUT | OUTPUT | OUTCOME | PROJECT | BASELINE 2015/2016 | INDICATORS | ANNUAL TARGET 2016/2017 | Q1 | Q2 | Q3 | Q4 | EVIDENCE | BUDGET 2016/2017 | IMPACT
FINANCAL VIABILITY
To ensure sufficient reserve funds to address asset renewal by contributing R35m to CRR by end of June 2017 | Reserve VAT refunds and interest on investments for purposes of CRR |  |  |  | Capital Replacement Reserve fund | R30m | Rand value invested towards CRR | R35m by end June 2017 *Q1=R5m *Q2=R15m *Q3=R25m *Q4=R35m | [5 empty] | 0
To ensure 100% Preparation of a credible 2017/18 budget at 30 May 2017 | To have a functioning budget steering committee |  |  |  | Budget preparation and implementation | 100% 2015/2016 approved budget | Percentage credible budget prepared. | 100% credible budget prepared: 1 budget timetable(10%)2. Roll over 2014/2015 (10%) 2. 3. Functionality of budget steering committee (8%) 4.Amendment of roll overs. (10%).5.Mid-year Adjustment of budget (12%) 5.. Reviewed budget related policies(20%) 6. Draft budget (20%) 7.Cash backed budget(10%) | [5 empty] | 0
To ensure 80% improved audit opinion for 2016/17 financial year. | To fully implement the audit action plan. |  |  |  | Operation Clean Audit | Unqualified audit opinion | Percentage reduction in matters of emphasis | 100% reduction of matters of emphasis *clearance of 14/15 matters of emphasis *monitoring of the 15/16 audit process *clerance of 15/16 matters of emphasis | [5 empty] | 350000
To generate and submit 30 finance compliance reports by June 2017 | To utilise the finance intern as compliance officer |  |  |  | Finance Compliance Reports | 2014/15 AFS 2014/15 Section 52; 71 and 72 reports | Number of finance compliance reports generated and submitted | 30 finance compliance reports generated and submitted (12x Section 71, 4x Section 52, 12x Supply Chain, 1x Section 72, 1xAFS) | [5 empty] | 0
To ensure 100% implementation of SCOA activities in terms of the implementation plan by 30 June 2017 | To have a functioning Mscoa commitee |  |  |  | Municipal Standard Chart of Accounts (mSCOA) | Council resolution 2014/2015 & Treasury circular | Percentage of activities on SCOA implementation plan achieved | 100% achievement of SCOA implementation plan *scoa transaction selection 15%; building of SCOA ledger 15%; align old chart to new SCOA 20%; training and budget inputs from departments 10%; final draft on SCOA submitted to council 10%; final full SCOA release 10%; testing 20% | [5 empty] | R1 200 000
100% accounting of assets and inventory by 30 June 2017 | Sound financial management. |  |  |  | 1. Asset management 2. Asset management plan | Manual GRAP Compliant Fixed asset register | % accounting of assets and inventory | 100% accounting of assets 1) safeguarding movable assets 20%, 2) valuation 30%, 3) records keeping 10%) | Accounting for assets. 1.Safeguarding of assets ( verification of assets) 2. Valuation (run depreciation) 3.Records keeping. | Accounting for assets. 1.Safeguarding of assets ( verification of assets) 2. Valuation (run depreciation), 3.Records keeping. | Accounting for assets. 1.Safeguarding of assets ( verification of assets) 2. Valuation (run depreciation), 3.Records keeping. 4.Migration of data to electronic System. | 100% valuation, records keeping, safe Guarding & disposal 100%-activation of electronic Asset Managent Module Year end veification.Impairment tests.Review usefull lifes. Review residual values. Reconcile FAR to G/L.Update FAR Prepare notes to AFSs | Updated GRAP compliant asset register and reconciliation of PPE | R1 900 000
To achieve 75% revenue collection rate by June 2017 | Cost Recovery | human resource, functional meters, credit control policy | Revenue collection reports | Improved financial viability | Revenue management | 65% of billed customers collected | Percentage revenue collection rate achieved | 75% revenue collection rate achieved | 67% collection rate | 69% collection rate | 72% collection rate | 75% collection rate | 1)Customer payment report | 8400000
To undertake 100% feasibility study of Prepaid meters by June 2017 | By conducting feasibity study, and installation of the meters | Feasibility study report* TVR1 *TVR2 | Prepaid meters installed | Increase in revenue collection through payment received in advance | PPP project (transactional advice) | Council resolution | Percentage feasibility study of Prepaid meters done | 100% feasibility study of Prepaid meters done | 100% Feasibility study*Advert for PPP | 1) Appointment of pre paid meter contractor 2)20% Prepaid (SMART)meters installed | 1) 50% Prepaid (SMART) meters installed | 1) 80% Prepaid (SMART) meters installed | Feasibility report & Pre-paid Meter report | 8500000
To cleanse 100% customer data in the three towns (Burgersfort, Marble Hall & Groblersdal) by June 2017 | By auditing data and doing physical verification.By updating customer information on the biling system | 1. Valuation roll and deeds office report 2. Human and financial resources | 1. Updated customer database. | Improved revenue and reliable customer data | Customer Data cleansing | Current non verifiable customer data | Percentage customer data cleansed | 100% customer data cleansed | 50% customer data cleansed for three towns (Groblersdal, Burgersfort and Marble Hall) | 100% customer data cleansed for three towns (Groblersdal, Burgersfort and Marble Hall) | 1)100% updating of cleansed data on the system 2) Physical verifications done for 50% towns | 100% physical verification done on towns | Cleansed customer data report | 2000000
To ensure that 100% creditors are paid within 30 days by June 2017 | Centralisation of invoice receipting and monitoring of the payment process by CFO |  |  |  | Expenditure management | Payment rate at 43 days | Percentage payment of creditors within 30 days of correct invoice date | 100% creditors paid within 30 days of correct invoice date | [5 empty] | 0
To ensure 100% development and implementation of the procurement plan by 30 June 2017 | Implementation of forward plans |  |  |  | Procurement Plan | IDP/BUDGET | Percentage development and implementation of procurement plans | 1) 100% development and implementation of 2016/17 procurement plan *Development of procurement plan =40% * Implementation of procurement plan = 60% | [5 empty] | 350000
To ensure 100% reduction of UIF expenditure by 30 June 2017 | *Due diligence on all projects *Pool of officials for SCM commitees and training of committee members |  |  |  | Acquisition Management | R300M reported irregular expenditure | Percentage reduction of irregular expenditure from baseline | 100% reduction of irregular expenditure from baseline (adherence to full SCM policies and regulations 100%) | [5 empty] | 500000

## SDBIP
SDBIP FOR 2nd QUARTER 2017
KPA: FINANCIAL VIABILITY
MEASURABLE OBJECTIVE | INPUT | OUTPUT | OUTCOME | PROJECT | BASELINE 2016/2017 | INDICATORS | 2nd QUARTER TARGET 2017/2018 | ANNUAL 2018 TARGET | 2nd QUARTER 2017 PROGRESS (Achieved/ not achieved) | ACTUAL PROGRESS | CHALLENGE | REMEDIAL ACTION | BUDGET 2017/2018 | POE
2016/2017 SDBIP KPA: FINANCIAL VIABILITY
FINANCAL VIABILITY
To improve collection rate by June 2018 | By implementing credit control measures | 80% collection rate | To collect 80% revenue by June 2018 | Revenue Collection | 75% Revenue Collection | % Revenue Collection Rate | Increase by 3% to 78% collection rate | 80% Revenue Collected | Achieved | The total bill was R17 850 451,97 and collection was R14 348 968,53 Collection rate was at 80,38%. | None | Tighten collection processes through-out the year | R2 000 000 | Billing reports
To conduct feasibitlity study for installation of smart meters by 2018 | By undertaking PPP process | Completed study | To finalise 100% PPP feasibility study by 2018 | Conduct feasibility study for Installation of Smart Meters | 75% Feasibility Study Concluded | % Finalisation of PPP feasibility Study | N/A | 100% Finalisation of PPP feasibility Study | Achieved | No action was planned for the month | None | None | R4 500 000 | Feasibility study report
To create CRR by June 2018 | Capital Replacement Reserve fund | Budget 2016/17 (R35m) | Percentage improvement in capital replacement reserve fund | Capital Replacement Reserve (CRR) | R35m not cash backed | Rand Value invested to CRR | R10m | R30m invested towards CRR | Achieved | An amount of R12,7m reserved for CRR (Made up of FNB balance of R10,5, plus interest earned on investments of R2,1m that has been reinvested) | None | None | 0 | Investment certificates
To create cash backed CRR by June 2018 | Capital Replacement Reserve fund | Budget 2016/17 (R35m) | Percentage improvement in capital replacement reserve fund | Capital Replacement Reserve (CRR) | R35m not cash backed | Rand Value invested to CRR | R5m | R10m cash backed | Achieved | An amount of R12,7m reserved for CRR (Made up of FNB balance of R10,5, plus interest earned on investments of R2,1m that has been reinvested) | None | None | 0 | Investment certificates
To ensure preparation of fully funded 2018/19 budget by 31 May 2018 | Budget preparation and implementation | 100% 2016/2017 approved realistic and credible budget | Percentage realistic and credible budget prepared. | Fully funded Budget preparation and implementation | 2016/2017 approved budget with deficit. | 2018/2019 aproved budget fully funded | Amendment for roll overs | 2018/2019 approved fully funded budget and its related policies | Achieved | 1) Roll over application denied | None | None | 0 | Fully funded final budget.
To ensure improved audit opinion for 2016/17 financial year. | Human resource | Clean audit outcome | Sound financial management | Operation Clean Audit | 2015/2016 financial year. Unqualified audit opinion with 17 audit findings in matters of emphasis. | Number of findings reduced in matters of emphasis from 2015/2016 audit opinion | All 2015/2016 audit matters addressed. Development of audit action plan for 2016/17 audit | All the 2016/2017 audit findings addressed | Not Achieved | 15 out of 17 issues resolved (88% achieved) - for 15/16 fin yr. AGSA still auditing 16/17 finding not issued | AGSA was still auditing & finilising | To be done in January 2018 | R 140,000 | Progress report on Audit Action Plan
To generate and submit 30 finance compliance reports by June 2018 | Compliance checklist and Human Resources | Compliance reports prepared and submitted on time | Compliance to legislation and regulations | Finance Compliance Reports | 2015/16 AFS 2015/16 Section 52; 71 and 72 reports | Number of finance compliance reports generated and submitted | 8 (3 Sec 71, 3 SCM , 1 Sec 72 and 1 Sec 52) reports | 30 finance compliance reports generated and submitted (12x Section 71, 4x Section 52, 12x Supply Chain, 1x Section 72, 1xAFS) | Achieved | 8 (3 Sec 71, 3 SCM , 1 Sec 72 and 1 Sec 52) reports submitted | None | None | 0 | Acknowledgement of receipt of Section 71, 52 and 72 Report by Office of Executive Mayor, Auditor General acknowledgement receipt of AFS
To ensure implementation of mSCOA activities in terms of the implementation plan by 30 June 2017 | mSCOA Project | Council resolution | 100% compliance to mSCOA requirements | Municipal Standard Chart of Accounts (mSCOA) | Council resolution 2014/2015 & Treasury circular | Number of activities on mSCOA implementation plan achieved | All activities on mSCOA implementation plan achieved | All activities on mSCOA implementation plan achieved | Achieved | Interface with errors performed | Mapping on line items for VIP system - Interface | Manual Journal processed. Engage with VIP | R2 000 000 | mSCOA progress report
To account for assets and inventory by 30 June 2018 | human resource, Asset Management Policy | GRAP compliant asset register | Improved asset management and service delivery | Update asset register | Manual GRAP Compliant Fixed asset register | GRAP compliance asset register | Accounting for assets 1.Safeguarding assets 2.Valuation (run depreciation, update projects & inventory register) 3. Records keeping | Updated GRAP compliant asset register | Achieved | 1. Verification was performed 2. Valuations done.(monthly depriciation posted, Project Registers are updated WIP, Retention, Commitments and Additions Register are also updated. 3. Records are kept safe. | None | None | 1800000 | 1.Fixed Asset Register and Verification reports 2.GRAP Compliant Fixed Asset Register
To ensure that creditors are paid within 30 days by June 2018 | Payment control sheet and Human Resources | All creditors paid within 30 days | Reduction of fruitless expenditure | Centralisation of Invoice receiving & monitoring | Payment rate at 28 days | Number of creditors paid within 30 days of correct invoice date | All creditors paid within 30 days of correct invoice date | All creditors paid within 30 days of correct invoice date | Achieved | All creditors paid within 30 days of correct invoice date | None | None | 0 | Creditors aging report
To ensure development and implementation of the procurement plan by 31 DECEMBER 2017 | By implementing SCM regulations. | 2017 18 Procurement Plan developed | Procurement plan developed and implemented. | Procurement Plan | IDP/BUDGET | Developed and approved procurement plans | Monthly monitoring of procurement of goods and services as per Procurement Plan. | Developed and approved procurement plans | Achieved | Monitored and procured goods as per the PP. | Bulk issuing of adverts creates bottlenecks. | Better schedulling of projects / workload | 0 | Procurement Plan
To ensure 100% reduction of UIF expenditure by 30 June 2017 | Montly UIF report. | Reduction of UIF | 100% reduction of UIF | Acquisition Management | R244M reported irregular expenditure | Percentage reduction of irregular expenditure from baseline | 100% reduction of irregular expenditure from baseline (adherence to full SCM policies and regulations 100%) | No UIF incurred | Achieved | No UIF incurred | None | None | 0
[9 empty] | 0 | Not achieved
[9 empty] | 12 | Achieved
12
[9 empty] | 100% | Performance for the quarter