## Sheet1
IDP PROJECTS 2017/2018
2017/2018 Q2 PERFORMANCE REPORT
INSTITUTIONAL TRANSFORMATION
MEASURABLE OBJECTIVE | INPUT | OUTPUT | OUTCOME | PROJECT | BASELINE 2016/2017 | INDICATORS | ANNUAL TARGET 2017/2018 | Q2 TARGET TARGETS | ACHIEVED/NOT ACHIEVED | ACTUAL PROGRESS | CHALLENGES | REMEDIAL | EVIDENCE | BUDGET 2017-2018 | IMPACT
LABOUR RELATIONS
To facilitate Local Labour Forum (LLF) meetings by June 2018 | Human and financial resources | Meetings | Improved employer-employee relationship | Facilitation of Local Labour Forum | 8 LLF meetings facilitated | Number of Local Labour Forum meetings facilitated | 12 Local Labour Forum meetings facilitated | 6 Local Labour Forum meetings facilitated | Achieved | 3 Local Labour Forum meetings facilitated(6 September , October and 17 November 2017) | none | none | *Copies of LLF minutes * Attendance registers | 100000
To issue Labour Relations Publications by June 2018 | Human and financial resources | Publications | Infomed labour force | Issuing of Labour Relations Publications | 4 Labour Relations Publications issued | Number of Labour Relations Publications issued | 4 Labour Relations Publications issued | 2 Labour Relations Publications issued | Achieved | 3 Local Labour Labour Relations Publications issued on Employee perfomance ,latecoming and grievance procedure. | none | none | Copies of Publications issued
To facilitate resolution of grievance cases by June 2018 | Human and financial resources | Grievance facilitation | Speedy resolution of grievances | Facilitation of Grievance cases | 2 resolution of grievance cases facilitated | Number of resolution of grievance cases facilitated | All resolution of grievance cases facilitated | All resolution of grievance cases facilitated | Achieved | All resolution grievance cases facilitated | none | none | Grievance cases Reports
To facilitate resolution of misconduct cases by June 2018 | Human and financial resources | Misconduct facilitation | Improved adherence to policies and rules | Misconduct cases | 100% Resolution of misconduct cases facilitated | Percentage resolution of misconduct cases facilitated | 100% Resolution of misconduct cases facilitated | 100% Resolution of misconduct cases facilitated | Achieved | 100% misconduct cases facilitated | none | none | Misconduct cases Reports
To facilitate resolution of labour disputes by June 2018 | Human and financial resources | Resolution of disputes | Facilitation of resolution of disputes | Dispute resolution | 100 % Resolution of labour disbutes cases facilitated | Percentage resolution of labour disbutes cases facilitated | 100% Resolution of labour disputes facilitated | 100% Resolution of labour disputes facilitated | Achieved | 100% Resolution of labour disputes facilitated (10 Labour Relations disputes facilitated) | none | none | Reports
INFORMATION TECHNOLOGY
To develop intranet portal and telephone infrastructure for depots by June 2018. |  |  |  | Development of Intranet portal and telephone infrastructure | •MS Office applications .• MunAdmin for document and records management •Call Centre for Disaster incident management in place * 3 depots installed telephone infrastructure | •Number of Intranet Portal and telephone infrastructure for depots developed | 1 intranet portal and 11 telephone infrastructure developed. | 1 intranet portal developed | Achieved | * Microsoft SharePoint commissioned * Microsoft SharePoint configured for Intranet portal | None | None | * Reports for Intranet Portal and telephone infrastructure * Proof of Payments | R2, 190m
To procure audio recording solution for Council by June 2018. |  |  |  | Procurement of audio recording solution for Council | 6x Dictaphones recordings in place | Number of audio recording solution for council procured | 1 Wireless digital conference audio recording system for council procured | Procurement of Council's Wireless digital conference audio recording system | Not Achieved | Tender for procurement of Council's Wireless digital conference audio recording system advertised | SCM processes not concluded (in progress) | Experdite evaluation of received bids and the appointment of subitable service provider for provision of Council's Wireless digital conference audio recording system | * Wireless digital audio recording proof of payment * Terms of reference
To establish ICT network infrastructure for Disaster Recovery Site(DRP) and new MM's Offices by June 2018 |  |  |  | Establishment of ICT network infrastructure for Data Centre and new MM's Offices | • Server Room backend infrastructure (servers, CCTV, switches,UPSs and Tape Drive) • Cabling network infrastructre at Bareki Mall | * Number of DRP infrastructure site established * Number of network cabling and switching infrastructure for new MM's offices established | * 1 DRP infrastructure site established * 1 network cabling and switching infrastructure for new MM's offices established | No Activity | N/A | N/A | N/A | N/A | * Disaster Recovery Plan Reports * Cabling handover over report * Proof of Payments | R4.200m
To acquire Cloud data backup services by June 2018 |  |  |  | Acquisition of Cloud data backup services | • Data Backup Tape Drive * File Server * Data Replication between the File Server and workstations | Number of Cloud data backup services acquired | 1 Cloud data backup services acquired | * 1 Cloud Data Backup service acquired | Not Achieved | Tender for procurement of Disaster Recovery and Information Security solutions advertised | SCM processes not concluded (in progress) | Experdite evaluation of received bids and the appointment of subitable service provider for provision of Disaster Recovery and Information Security solutions | * Cloud data backup SLA * Proof of Payments
To manage SLA performance service standards approved software licenses and information security by June 2018 |  |  |  | Management of SLA performance service standard, approved software licenses and information security | * 12 Service Level Agreement meetings held with Telkom, Unics, Open Kigndom Technologies and BCX * 11 approved software licenses renewed | * Number of SLA performance service standards, approved software licenses renewed and Information Security managed | * 8 SLAs performance service standards managed * 9 SDM approved software licenses managed * 2 Information Security managed | * 4 SLAs performance service standards managed * 4 SDM approved software licenses managed * 1 Information Security managed | Not Achieved | * 4 SLAs performance service standards managed * 5 SDM approved software licenses managed * Tender for procurement of Disaster Recovery and Information Security solutions advertised | SCM processes not concluded (in progress) | Experdite evaluation of received bids and the appointment of subitable service provider for provision of Disaster Recovery and Information Security solutions | * SLA Quarterly Reports * Attendance Registers and Minutes * Proof of Payments | R5 170 m
To provide ICT products and services by June 2018 |  |  |  | Provision of ICT products and services | * 30 audited ICT computer consumables needs resolved * 1 Surveillance Camera System (CCTV) in the server room * 500 technical support requests of Business applications (e-Venus, VIP, MunAdmin etc) and resolved | Number of ICT products and services provided | All ICT products and services provided | All ICT products and services provided | Achieved | All ICT products and services provided | None | None | * Consumables Distribution Register * Reports of technical faults * Proof of Payments * TOR for CCTV
AUXILIARY SERVICES
To conduct awareness campaigns for records management by June 2018. | Human and Financial resources | Sound record management | Improved record management system | Conduct campaigns for Records management. | 4 Records management awareness campaigns conducted | Number of records awareness campaigns conducted | 4 records awareness campaigns conducted | 1 records awareness campaigns conducted | Achieved | 1 records awareness campaigns conducted at Fetakgomo Regional Office | None | None | * Record management awareness campaigns Reports * Attendance registers | 0
To update personnel files by June 2018 | Human resources | Updated personnel files | Compliance and Accountability | Update of Personnel files | 668 personnel files updated | Number of personnel files updated | 916 personnel files updated | 250 personnel files updated | Achieved | 614 personnel files updated |  |  | Personnel file update Register. | 0
To facilitate disposal of listed inactive records by June 2018 | Human and Financial Resources | Disposal authority certificate | Improved record management | Facilitation of disposal of listed inactive records | 5000 inactive records listed and awaiting disposal by Provincial Archivist | Number of inactive records listed for disposal | 5000 Inactive records listed for disposal | 2500 Inactive records listed for disposal | Not Achieved | 220 Inactive records listed for disposal |  |  | * Register for listed inactive records, * Letter to Provincial Archive | 0
To ensure processing of received mail by June 2018 | Human and Financial Resources | Proper management of records | Improved external and internal communication | Processing of received mail | All received mail processed | Number of received mail processed. | All received mail processed | All received mail processed | Achieved | 30390 received mail processed |  |  | * Mail registers | 650000
To ensure provision of office furniture by June 2018 | Human and financial resources | Healthy and safe working enviroment | Improved healthy enviroment. | Provision of Office furniture | Furniture for MM. Coach for Speaker and High back chairs for staff provided | Number of office furniture provided | 5 sets of furniture provided | * ICT services station funiture * Coaches for fire stations | Not Achieved | *Lekgotla boardroom provided. *ICT services station funiture memo to SCM * Coaches for fire stations memo to SCM | Delay in SCM processes | Constant follow up to be made. | List of furniture Proof of payment | R1m
To facilitate management of facilitiesby June 2018 | Human and Financial resources | Proper management of facilities | Improved healthy enviroment. | management of facilities | 4 offices rented | Number of facilities managed | 36 facilities managed | 36 facilities managed | Achieved | 36 facilities managed | None | None | * Cleaning reports * List of Equipment, * Facility Management policy. | 6132076
To faciliate fleet management services by June 2018 | Human and Financial resources | Proper management of fleet | Improved service delivery | Facilitation of Fleet Management | * 22 SDM-owned vehicles repaired * 117 fleet rentals paid | Number of fleet managed | 150 of fleet managed | 150 of fleet managed | Achieved | 150 of fleet managed | None | None | * Fleet Management Policy * Maintanance reports * Licensing reports * Proof of payment | 41000000
ORGANISATIONAL DEVELOPMENT
To conduct organisational development interventions/ assessment by June 2018 | Human and financial resources | Assessments reports | Impropved productivity | Conduct Organizational development assessment | *2 Work-study reports in place *1 organizational development assessment in place | Number of Organizational development assessment/ interventions conducted | All Organizational development assessment/ interventions conducted | All Organizational development assessment/ interventions conducted | Achieved | Organisationa development assessment/interventions conducted (Employees satisfaction survey conducted (Bareki offices; Tubatse Region, Fetakgomo Region, Ephraim Mogale Region and Makhuduthamaga Region) | none | none | Organisational Assessment Report | 150000
To facilitate job evaluation for newly created jobs by June 2018 | Human and resources | Job evaluation report | Rationalised salary grades | Facilitation of Job evaluation | *199 job descriptions reviewed * 155 job descriptions signed *job evaluation committee in place *job evaluation policy in place | Number of newly created jobs evaluated. | All newly created jobs evaluated | All newly created jobs evaluated | Not achieved | Evaluated 198 amalgamated municipalities (Fetakgomo Tubatse Local Municipality) | A morotorium was issued to prioritize amalgamated municipalities | Request SALGA to set aside the morotorium after completion of job evaluation for amalgamated municipalities | Report on Graded Jobs | 0
To facilitate development and implementation of organizational structure by June 2018 | Human resources | Organisational structure & assessment reports | Improved productivity | Facilitation and Implementation of Organizational structure | 2015/16 approved organizational structure | Number of assessments of the organizational structure facilitated and implemented | All assessments of the organizational structure facilitated and implemented | All assessments of the organizational structure facilitated and implemented | Achieved | organisational structure assessment facilitated and implemented for CPS and IWS & MM's Office | none | none | Approved organisational Structure | 0
To facilitate review of procedure manuals & process maps by June 2018 | Human resources | Procedure manuals and process maps | improved business operations | Facilitation of review of procedure manuals and process maps | 39 Reviewed departmental procedure manuals in place | Number of review of departmental procedure manuals & process maps facilitated | 46 review of departmental procedure manuals & process maps facilitated | 24 review of departmental procedure manuals & process maps facilitated | Achieved | 24 Procedure manuals and process maps for IWS, CPS, CMS, PED, MM reviewed | none | none | Reviewed procedure manuals and process maps | 0
EMPLOYEE WELNESS
Tofacilitate substance abuse programmes by June 2018 | Human and Financial Resources | Healthy life style | Improved work performance and productivity | *22 substance abuse cases attended. *8 group therapy for substance abusers conducted. *4 family conferences for substance abusers held. *1 stress and trauma management held. | Number of substance abuses programmes facilitated | 12 substance abuses programmes facilitated | 6 substance abuses programmes facilitated | 3 substance abuse programees facilitated. | Achieved | 3 substance abuse programees facilitated. | None | None | * Substance abuse programmes Reports *Attendance registers | 760000
To facilitate employee sport programme by June 2018. | Human and Financial Resources | Healthy life style | Improved work performance and productivity | 23 employee sports programmes facilitated | Number of employee sports programmes facilitated | 50 employee sports programmes facilitated | 25 employee sports programmes facilitated | 11 sports days conducted. 1 Fun walk activity held. | Achieved | 11 sports days conducted. 1 Fun walk activity held. | None | None | *Employee sport programmes Reports *Attendance registers
To conduct wellness and counselling programmes by June 2018 | Human and Financial Resources | Healthy life style | Improved work performance and productivity | *2 stress and trauma management programmes conducted *8 wellness awareness programmes conducted | Number of wellness and counselling programmes conducted | 15 wellness and counselling programmes conducted | 7 Wellness and counselling programme conducted | 3 Wellness awareness programmes conducted. 1 Stress & Trauma management programme held. | Not Achieved | 3 Wellness awareness programmes conducted | One stress & trauma management programme is delayed due to unavailabiltiy of venue. | Second Stress & Trauma will be conducted in Febraury 2018. | *Wellness and counselling reports *Attendance Registers attendance registers
To conduct occupational health and safety elements by June 2018. | Human and Financial Resources | Healthy and safe enviroment | Improved healthy and safe enviroment. | 27 Occupational Health and Safety elements conducted | Number of Occupational Health and Safety elements conducted. | 60 Occupational Health and Safety elements conducted. | 30 Occupational Health and Safety elements conducted. | 9 workplace and tools inspection conducted. 5 safety awareness campaigns held. | Achieved | 9 workplace and tools inspection conducted. 5 safety awareness campaigns held. | None | None | * Occupational Health and Safety elements Reports, * Attendance registers | R2,m
To conduct medical surveillance programme by June 2018 | Human and Financial Resources | Healthy and safe enviroment | Improved healthy and safe enviroment. | 0 employees were subjected to medical surveillance programmes | Number of medical surveillance programmes conducted | 2 medical surveillance programme conducted | 1 medical surveillance programme conducted. | 1 medical surveillance programme conducted. | Not Achieved | No medical surveillance programme conducted. | Lack of funds | Allocate budget | Not applicable.
HUMAN RESOURCE MANAGEMENT
| Human and Financial resources | Reduced Vacancy rate | Improved Productivity | Filling of funded and vacant posts | 134 vacant and funded posts filled | Number of vacant and funded posts filled | All vacant and funded posts filled | All vacant and funded posts filled | Achieved | All vacant and funded posts filled (17 Employess appointed ) | N/A | N/A | Report on vacant and funded posts | 310000
To ensure compliance submission of Employment Equity(EE) plan by June 2018. | Human resources | Employment Equity report | Compliance and Accountability | Compliance on Employment Equity | EE Plan in place | Number of EE report compiled and submitted | 1 EE report compiled and submitted | Consultation with Organised Labour | Achieved | Organised Labour Consulted | N/A | N/A | Proof of submission of employment equity report | 0
To implement Human Resource(HR) Plan by June 2018. | Human resources | HR Plan | Improved productivity | Implementation of Human Resource Plan | 2016/2017 HR Plan in place | Number of Human resources plan implemented | 1 Human resources plan implemented | Human resources plan implemented | Achieved | Human Resources Plan Implemented ( Approved EE Plan,Reviewd Organisational Structure and functional Local Labour Forum) | None | None | Human Resource Plan Report | 0
HUMAN RESOURCE DEVELOPMENT
To award external bursaries by June 2018 | Human and Financial Resources | Awarded bursaries | Improved human capital development | Award of External Bursaries | 10 external bursaries awarded 24 maintained | Number of external bursaries awarded & maintained | 15 bursaries awarded and 28 maintained | *Adjudication of bursary applications *28 bursaries maintained | Not Achieved | *Bursary advertised. *Applications received | Bursary commettee meeting not convened. | Convene bursary committeee meeting to select bursars before close of registration window in January 2018 | Approval letter and bursary contracts of learners | R4m
To facilitate training and development activities and ensure compliance to skills development legislation by June 2018 | Human and Financial Resources | WSP and ATR | Compliance and Accountability | Facilitation of Training and Development activities | Workplace Skills Plan/Annual Training Report 2015/2016 submitted | Number of training and development activities facilitated | All training and development activities facilitated | All training and development activities facilitated | Achieved | *Project management learnership course implemented for 10 officials. *15 officials approved by LGSETA for computer training at TVET | None | None | Training and development activites reports | 100000