## Sheet1
2018/2019 SERVICE DELIVERY BUDGET AND IMPLEMENTATION PLAN: INFRASTRUCTURE AND WATER SERVICES
MEASURABLE OBJECTIVE | INPUT | OUTPUT | OUTCOME | PROJECT | BASELINE 2017/2018 | INDICATORS | ANNUAL TARGET 2018/2019 | Q1 | Q2 | Q3 | Q4 | ACHIEVED/ NOT ACHIEVED | ACTUAL PROGRESS FOR QUARTER 3 | CHALLENGES | REMEDIAL ACTIONS | Portfolio of Evidence | BUDGET 2018-2019
RBIG
To construct pipeline from Burgersfort to Dresden pump station by June 2019 | Financial and Human Resource | Bulk supply line | Improved water supply | Construction of Mooihoek Bulk Water Supply Phase 4E | Mooihoek bulk water supply phase 4D completed | Number of Kilometers of bulk pipeline constructed and number of booster pump station constructed , number of reservoirs constructed | 3 Kilometers of bulk pipeline constructed,1 booster pump station, 1 concrete reservoir | Site establishment and 0.2km pipeline constructed | 1km of bulk pipeline constructed | 1.5 Kilometers of bulk pipeline constructed,0* booster pump station constructed ,0*concrete reservoir constructed | 1,5 Kilometers of bulk pipeline constructed, ,0* booster pump station constructed ,0*concrete reservoir constructed | Achieved | 1.5 Kilometers of bulk pipeline constructed,0* booster pump station constructed ,0*concrete reservoir constructed | None | None | Progress Report | 108000000
To construct reservoir at Burgersfort by June 2019 | Financial and Human Resource | Bulk supply line | Improved water supply | Mooihoek bulk water supply phase 4BB | 1 X 5 Ml reservoir completed Phase 4A | Number of concrete reservoir constructed inlcuding floor slabs, walls, roof slas and inlet and outlet vlave | 2 X 5 Ml concrete reservoir constructed inlcuding floor slabs, walls, roof slas and inlet and outlet vlave | 15%, 2 X 5 Ml concrete reservoir constructed | 20%, 2 X 5 Ml concrete reservoir constructed | No activity | 2 X 5 Ml concrete reservoir constructed inlcuding floor slabs, walls, roof slas and inlet and outlet vlave | N/A | The physical progress on the 2 concrete reserviors is at 87% | Works suspended for safety reasons due to resignation of contracts manager and safety officer | Contractor was instructed in writing to appoint the key personnel as per contract | Progress Report
To construct bulk pipeline from Praktiseer to Motodi by June 2019 | Financial and Human Resource | Bulk supply line | Improved water supply | Mooihoek bulk water supply phase 4F | Mooihoek bulk water supply phase 2 completed | Number of Kilometers of bulk water pipeline constructed | 4 Kilometers of bulk water pipeline constructed | Site establishment and 0.5km pipeline constructed | 1 km of bulk pipeline constructed | 1,5 kilometer of bulk water pipeline constructed | 1 kilometer of bulk water pipeline constructed | Achieved | 1,5 kilometer of bulk water pipeline constructed | None | None | Progress Report
To construct bulk pipeline from Praktiseer to Alverton by June 2019 | Financial and Human Resource | Bulk supply line | Improved water supply | Mooihoek bulk water supply phase 4G1 & G2 | Mooihoek Bulk water supply Phase 2 completed | Number of Kilometers of bulk pipeline constructed | 4 Kilometers of bulk water pipeline constructed | Site establishment and 0.5km pipeline constructed | 1 km of bulk pipeline constructed | No activity | 2 X 5 Ml concrete reservoir constructed inlcuding floor slabs, walls, roof slas and inlet and outlet vlave | N/A | Contractors appointed for both phase G1 & G2 | Limited funding to commence with the projects | Projects to commenced in July 2019 | Progress Report
To construct 400m long, 750mm diameter pipeline and 900m long, 450mm dimeter steel pipe line by June 2019. | Financial and Human Resource | Bulk supply line | Improved water supply | Mooihoek bulk water supply phase C1.2 | 80% completion of 400m long, 750mm diameter pipe line and 900m long, 450mm dimeter steel pipe | Number of Kilometers of 750mm diameter pipeline and 450mm dimeter steel pipe constructed | 1,3 Kilometers of 750mm diameter pipe line and 450mm dimeter steel pipe constructed | 85% completion of 400m long, 750mm diameter pipe line and 900m long, 450mm dimeter steel pipe | 5% completion of 400m long, 750mm diameter pipe line and 900m long, 450mm dimeter steel pipe | No activity | 2 X 5 Ml concrete reservoir constructed inlcuding floor slabs, walls, roof slas and inlet and outlet vlave | N/A | The physical progress is at 95% | Pipe leakages detected during presusrre testing | Constractor instructed to check the pipe laying and redo the preasure testing | Completion certicicates
To Construct Mooihoek Tubatse 4C2:2700m, 500mm DIA and 2600m,400mm DIA Steel Water Pipeline by June 2018. | Financial and Human Resource | Bulk supply line | Improved water supply | Mooihoek bulk water supply phase 4C2 | 90% Construction of Mooihoek Tubatse 4C2:2700, 500mm DIA and 2600, 400mm DIA Steel Water Pipeline, Installation of chambers fittings | Number of Kilometers of 4C2, 500mm DIA and 400mm DIA Steel Water Pipeline constructed | 5,3 Kilometers of 4C2, 500mm DIA and 400mm DIA Steel Water Pipeline constructed | 95% Construction of Mooihoek Tubatse 4C2:2700, 500mm DIA and 2600, 400mm DIA Steel Water Pipeline, Installation of chambers fittings | 5% Construction of Mooihoek Tubatse 4C2:2700, 500mm DIA and 2600, 400mm DIA Steel Water Pipeline, Installation of chambers fittings | No activity | 2 X 5 Ml concrete reservoir constructed inlcuding floor slabs, walls, roof slas and inlet and outlet vlave | N/A | The physical progress is at 95% | Limited availability of water to complete the pressure testing | Engaging LNW to assist with releasing water for testing | Completion certicicates
To construct bulk water pipeline from T-off of Makgeru to the new 10ML reservoir at Schoonoord by June 2019 | Financial and Human Resource | Bulk supply line | Improved water supply | Nebo BWS (RL19) Makgeru to Schoonoord | 55% Reservoir completed, Pipeline is completed | Number of bulk water pipeline from T-off of Makgeru to the new 10ML reservoir at Schoonoord constructed by June 2019 | 8 KM of bulk water pipeline from T-off of Makgeru to the 1 new 10ML reservoir at Schoonoord constructed by June 2019 | 60% Bulk Pipeline constructed and Reservoir completed | 15% Bulk Pipeline constructed and Reservoir completed | 2 KM of bulk water pipeline from T-off of Makgeru to the 0 new 10ML reservoir at Schoonoord constructed by June 2019 | 4,6 KM of bulk water pipeline from T-off of Makgeru to the 1 new 10ML reservoir at Schoonoord constructed by June 2019 | Not achieved | Pipework is at 76%, Reservoir is at 91% Overall progress of project is 84% Overall Bulk pipeline constructed is 18.07km to date. Reservoir only left with casting of roof slab | Delays in delivery of pipes by the service provider as per their initial procurement plan. Shortage of most of material on site for the contractor to work on support work for reservoir roof. | The pipes will reach Durban port from China on the 25th of March 2019 and service provider still needs to send us the revised delivery dates to Schoonoord Contracts Manager from DWS Construction West to engage his colleagues from other sites to get the outstanding material. | Progress Report | 58000000
To test and commissioned bulk water pipeline and main pump stations by June 2019 | Financial and Human Resource | Bulk supply line | Improved water supply | Nebo BWS Ga Malekana to Jane Furse Phase 1A | 85% Nebo Phase1A pipeline completed . | Number of bulk water pipeline and Main pump station tested and commissioned | 6km of bulk water pipeline and 2 Main pump station tested and commissioned | 90% Nebo Phase1A pipeline completed . | 10% Nebo Phase1A pipeline completed . | 3km of bulk water pipeline and 1 Main pump station tested and commissioned | 3km of bulk water pipeline and 1 Main pump station tested and commissioned | Not achieved | Inspection and verifying of pipelines and installations = 80% Mechanical repairs on pipeline 2 = 30%. Overall progress on the commissioning of the project is 62%. | Project on hold. Late payments and approval of extension of time and variation orders. Contractor under business rescue. | Consultant `s to be paid and submit recommendation based on the contractor`s status. Consultant should further evaluate the submission by Lepelle Northern Water to complete the commissioning | Progress Report
To construct Bulk water Pipeline and test main pump stations by June 2019 | Financial and Human Resource | Bulk supply line | Improved water supply | Moutse BWS Phase 1-6 | Bulk Pipeline and Valve constructed up 54% | Number of Bulk water pipeline constructed and main pump stations tested | 15km of Bulk water pipeline constructed and 2 main pump stations tested | 55% Bulk Pipeline and Valve constructed | 10% Bulk Pipeline and Valve constructed | No activity | 2 X 5 Ml concrete reservoir constructed inlcuding floor slabs, walls, roof slas and inlet and outlet vlave | N/A | Ph 01 - The extension of Groblersdal WTW (Civil Works) is at 99% Ph 02 - Construction and Installation of 6.6km of 500 NB class K9 ductile iron pipe and associated structures is at 100% Ph 03 - Construction of Installation of Pumping Main from Groblersdal Reservoirs is at 100% Ph 04 & 05 - Construction and Installation of Pumping Main from Groblersdal Reservoirs is at 100% Ph 06 - Construction of new Pumstation next to Reservoir no.1 is at 95% | Contractual disputes on professional services. Litigations against SDM. Delays in procuring of material by DWS National. Project on hold. No expenditure for 2 years | The project is currently under evaluation by Engineering specialist and the report will provided to the Municipality to make recommendations | Progress Report | 30000000
To install mechanical and Electrical (M & E) for the extensions to the Groblersdal Water Treatment Works by June 2019 | Financial and Human Resource | Bulk supply line | Improved water supply | Moutse BWS Project 13 & 14 (RL14) | The upgrading of WTW is completed | Number of mechanical and Electrical (M & E) components installed for the extensions to the Groblersdal Water Treatment Works | Two mechanical and Electrical (M & E) components installed for the extensions to the Groblersdal Water Treatment Works | 10% M&E Components Installed | 30% M&E Components Installed | No activity | 2 X 5 Ml concrete reservoir constructed inlcuding floor slabs, walls, roof slas and inlet and outlet vlave | N/A | The istallation of mechanical and electrical components is at 57% | Contractual disputes on professional services. Litigations against SDM. Delays in procuring of material by DWS National. Project on hold. No expenditure for 2 years | The project is currently under evaluation by Engineering specialist and the report will provided to the Municipality to make recommendations | Progress Report
To construct Bulk water Pipeline and test main pump stations by June 2019 | Financial and Human Resource | Bulk supply line | Improved water supply | Moutse BWS Project 7 - 12 | Bulk Pipeline and Valve constructed up 54% | Number of Bulk water pipeline constructed and main pump stations tested | 15km of Bulk water pipeline constructed and 2 main pump stations tested | 55% Bulk Pipeline and Valve constructed | 10% Bulk Pipeline and Valve constructed | No activity | 2 X 5 Ml concrete reservoir constructed inlcuding floor slabs, walls, roof slas and inlet and outlet vlave | N/A | Ph 7 - 12 Construction and Installation of Pumping Main and Gravity Line from Groblersdal Reservoirs is at 95% | Contractual disputes on professional services. Litigations against SDM. Delays in procuring of material by DWS National. Project on hold. No expenditure for 2 years | The project is currently under evaluation by Engineering specialist and the report will provided to the Municipality to make recommendations | Progress Report
WATER QUALITY
To generate Water Quality Reports by June 2019 | WSDP and Water Master Plan | Regulatory Compliance | Improved service delivery | Generation of Water Quality Reports | 10 reports generated | Number of Water Quality Reports generated | 12 Water Quality Reports generated | 3 Water Quality Reports generated | 3 Water Quality Reports generated | 3 Water Quality Reports generated | 3 Water Quality Reports generated | Achieved | 3 Water Quality Reports generated | None | none | Progress Report | 5650000
To conduct Full SANS 241 Analysis by June 2019 | WSDP and Water Master Plan | Regulatory Compliance | Improved service delivery | Full SANS 241 Water Quality Analysis | Signed CSIR SLA in 2015/16 financial year | Number of Full SANS 241 Analysis conducted | 1 Full SANS 241 Analysis conducted | 1 Full SANS 241 Analysis (30 samples) conducted | 1 Full SANS 241 Analysis (30 samples) conducted | No activity | 1 Full SANS 241 Analysis conducted | N/A | The water samples collecting in the last three months will be submitted analysis by the agredited laboratory and be reported in the next quarter | None | none | Progress Report
To purchase Laboratories chemical by June 2019 | WSDP and Water Master Plan | Regulatory Compliance | Improved service delivery | Purchase of LAB Chemicals | WTW & WWTW in place | Number of % of LAB chemical purchased | 100% of LAB chemical purchased | 100% of LAB chemical purchased | 100% of LAB chemical purchased | 100% of LAB chemical purchased | 100% of LAB chemical purchased | Achieved | 100% of LAB chemical purchased | None | None | Progress Report
To participate in Blue and Green Drops Certification Programme by June 2018 | WSDP and Water Master Plan | Regulatory Compliance | Improved service delivery | Plants participation in Blue and Green Drops Certification Programme | 15 Water Treatment Works participating in Blue Drop Certification programme in place | Number of Plants participating in Blue and Greed Drops Certification Programme | 15 WTW participating in Blue Drop and 16 WWTW Participating in Green Drop Certification Programme | 15 WTW participating in Blue Drop and 16 WWTW Participating in Green Drop Certification Programme | 15 WTW participating in Blue Drop and 16 WWTW Participating in Green Drop Certification Programme | 15 WTW participating in Blue Drop and 16 WWTW Participating in Green Drop Certification Programme | 15 WTW participating in Blue Drop and 16 WWTW Participating in Green Drop Certification Programme | Not achieved | Collection of water samples limited to water reticulation network points | Lack of human resources (process controlers) in both WWTW & WTW affect the improvement in terms of blue and green drop status | Prioritise the sourcing of process controllers and taking samples from both WTW`s and WWTW`s. | Progress Report
O & M EXPENDITURE
To resolve registered sanitation incidents within 14 days. | Financial and Human Resource | Reduced sewer spillage and environmental pollution | Improved green drop status | Sanitation incidents | 700 registered sanitation incidents resolved within 14 days | Number of registered sanitation incidents resolved within 14 days | 700 registered sanitation incidents resolved within 14 days | 175 registered sanitation incidents resolved within 14 days | 175 registered sanitation incidents resolved within 14 days | 175 registered sanitation incidents resolved within 14 days | 175 registered sanitation incidents resolved within 14 days | Achieved | 302 registered sanitation incidents resolved within 14 days | None | None | Progress Report | 71807845
To resolve registered water incidents within 14 days. | Financial and Human Resource | Reduced non-revenue water losses | Improved no drop status. | Water incidents | 7000 registered water incidents resolved within 14 days | Number registered water incidents resolved within 14 days | 7000 registered water incidents resolved within 14 days | 1 750 registered water incidents resolved within 14 days | 1 750 registered water incidents resolved within 14 days | 1 750 registered water incidents resolved within 14 days | 1 750 registered water incidents resolved within 14 days | Not Achieved | 1 381 registered water incidents resolved within 14 days | Shortage of material repair and maintain | Prioritise the required material to be purchased | Progress Report
To render tankering services by June 2019 | Financial and Human Resource | Consistent supply of water | Improved water supply | Delivery of portable water | 9.6 Ml delivery of Potable Water in Jane Furse Hospital and Buffelshoek | Number tankering services rendered | 9.6 Ml delivery of Potable Water in Jane Furse Hospital and Buffelshoek | 2.4 Ml delivery of Potable Water in Jane Furse Hospital and Buffelshoek | 2.4 Ml delivery of Potable Water in Jane Furse Hospital and Buffelshoek | 2.4 Ml delivery of Potable Water in Jane Furse Hospital and Buffelshoek | 2.4 Ml delivery of Potable Water in Jane Furse Hospital and Buffelshoek | Achieved | 30.48 Ml delivery of Potable Water in Jane Furse Hospital and Buffelshoek | None | None | Progress Report | 14742000
To provide diesel consistently to diesel driven machines by June 2019 | Financial and Human Resource | Consistant water supply. | Reliable water supply. | Supply of diesel | 40 000ℓ of diesel supplied annually. | Number of Litres of diesel supplied annually | 40 000ℓ of diesel supplied annually. | 10 000ℓ of diesel supplied annually. | 10 000ℓ of diesel supplied annually. | 10 000ℓ of diesel supplied annually. | 10 000ℓ of diesel supplied annually. | Not Achieved | 7445ℓ of diesel supplied. | Shortage of funds to purchase fuel | Viament process was done to ensure that the fuel vote line item has funds | Progress Report | 1193000
To provide petrol consistently to petrol driven machines by June 2019 | Financial and Human Resource | Consistant water supply. | Reliable water supply. | Supply of petrol | 400ℓ of petrol supplied annually. | Number of Litres petrol supplied annually. | 400ℓ of petrol supplied annually. | 100ℓ of petrol supplied annually. | 100ℓ of petrol supplied annually. | 100ℓ of petrol supplied annually. | 100ℓ of petrol supplied annually. | Achieved | 393ℓ of petrol supplied. | None | None | Progress Report
To provide oil consistently to diesel and petrol driven machines by June 2019 | Financial and Human Resource | Consistant water supply. | Reliable water supply. | Supply of oil | 300ℓ of oil supplied annually. | Number of Litres of oil supplied annually. | 300ℓ of oil supplied annually. | 75ℓ of oil supplied annually. | 75ℓ of oil supplied annually. | 75ℓ of oil supplied annually. | 75ℓ of oil supplied annually. | Achieved | 164.5ℓ of oil supplied. | None | None | Progress Report
To resolve registered M & E incidents within 14 days. | Financial and Human Resource | Consistent supply of water | Improved water supply | Mechanical & Electrical Services | 450 of registered M & E incidents within 14 days | Number of registered M & E incidents resolved within 14 days | 450 of registered M & E incidents within 14 days | 112.5 of registered M & E incidents within 14 days | 112.5 of registered M & E incidents within 14 days | 112.5 of registered M & E incidents within 14 days | 112.5 of registered M & E incidents within 14 days | Achieved | 266 of registered M & E incidents within 14 days | None | None | Progress Report | 9500000
To install Bulk Water Meters by June 2019 | Financial and Human Resource | Consistent supply of water | Improved water supply | Installation of Bulk Water Meters | 8 bulk water meters installed | Number of bulk water meters installed by June 2018 | 8 bulk water meters installed | 2 bulk water meters installed | 2 bulk water meters installed | 2 bulk water meters installed | 2 bulk water meters installed | Not Achieved | Terms of reference finalised for istalation of bulk water metres | Delays in finalisation of Specifications to proceed with procurement processes | Bid specisfication committee to finalise the specification in the next quarter | Progress Report | 500000
To purchase Mℓ Bulk water by June 2019 | Financial and Human Resource | Consistent supply of water | Improved water supply | ML Bulk Water Purchases | 10 062Mℓ of water purchased | Number Mℓ of water purchased | 10 062Mℓ of water purchased | 2 515.5Mℓ of water purchased | 2 515.5Mℓ of water purchased | 2 515.5Mℓ of water purchased | 2 515.5Mℓ of water purchased | Achieved | 4 344.829 Mℓ water volume purchased | None | None | Progress Report | 112542000
PLANNING
To develop Water Conservation /Water Demand Management Strategy for SDM by June 2019 | WSDP and Water Master Plan | Document on Water Conservation and Demand Management | Strategy on Water Conservation and Demand Management | Water Conservation and Water Demand Management Plan | Water Services Master Plan and WSDP developed in 2014/15 and 2015/16 FY respectively | Number of WC/WDM Strategy developed | One WC/WDM Strategy developed | Appointment of service provider for WC/WDM Strategy | Collection of information/Assessment of status quo and Inception report of WC/WDM | No activity | One WC/WDM Strategy developed | N/A | Bid advetised to develop the WC/WDM strategy through DBSA | None | None | Draft WC/WDM strategy | 0
To develop and review Water & Sanitation Master Plan by June 2019 | Exisitng Water Master Plan | Effective Water & Sanitation Infrastructure Plans | Reviewed Water and Sanitation Master Plan & Developed WSDP | One Water & Sanitation Master Plan (WSMP) & One WSDP | Professional Service Provider appointed in Nov 2016 scoping report and methodology developed. | Number of Water & Sanitation Master Plan developed | One Water & Sanitation Master Plan reviewed and One WSDP developed | Develop Terms of Reference and Appointment of PSP for Water & Sanitation Master Plan & WSDP | Collection of information/Assessment of status quo and Inception report of WSMP & WSDP | No activity | One Water & Sanitation Master Plan developed | N/A | 6 Professional Services Providers invited to bid for the review of Water & Sanitation Master Plan and development of Water Services Develoment Plan | None | None | Draft WSMP/WSDP | 1300000
To upgrade Groblersdal sewer pump- station by June 2019 | Bulk sewer intervention plan | Upgraded Sewer infrastructure | Enhanced sewer system | Groblersdal sewer network | Assessment report and upgrade portion of the outfall sewer system took place in 2015/16 financial year | Number of km sewer pipe line inspected using the CCTV camera and report analysed. | 5 km of sewer pipe line inspected using the CCTV camera and report analysed. | The PSP to submit inception report together with cost estimate for the CCTV survey. | 2km sewer pipeline inspected | No activity | 5 km of sewer pipe line inspected using the CCTV camera and report analysed. | N/A | Professional Services Providers to be appointed in the next quarter | None | None | Progress Report | 500000
To conduct Condition Assessment and develop O & M Plans by June 2019 | Asset register & O& M plan | Effective Maintenance & Operation of Existing Infratsrucutre | Operation & Manitenance Paln | Conduct Condition Assessment and develop O & M Plans | 40% Development of O&M plan and Condition assesment of IWS infrastructure conducted | Number of conditional assessment and O & M Plan developed | 1 conditional assessment and 1 O & M Plan developed | 45% conduct of Condition Assessment and O & M Plan developed | 5% conduct of Condition Assessment and O & M Plan developed | No activity | 1 conditional assessment and 1 O & M Plan developed | N/A | The dratf Opreation and Mantenance plan completed | None | None | Progress Report | 1300000
To facilitate District Water & Sanitation Summit by June 2019 | Asset register & O& M plan | Effective Maintenance & Operation of Existing Infratsrucutre | Operation & Manitenance Paln | District Water & Sanitation Summit | 2015 Water & Sanitation Resolution | Number of Water & Sanitation Summit facilitated | 1 District Water & Sanitation Summit facilitated | One District Water & Sanitation Summit facilitated | Adoption of Water & Sanitation summit resolution | No activity | No activity | N/A | District Water & Sanitation Summit facilitated in the previous quarter | None | None | Progress Report | 0
To Conduct Feasibility Studies and develop Technical Report by June 2019 | Assignment of PSP to do the Technical Reports | Technical Reports | MIG registered Projectss | Conduct Feasibility Studies and develop Technical Report | WSDP, IDP and BWS Master completed in plan 2014 | Number of Feasibility Studies conducted and technical report developed | 15 Feasibility Studies conducted and technical Reports developed | 5 Feasibility Studies conducted and technical Reports developed | 4 Feasibility Studies conducted and technical Reports developed | 3 Feasibility Studies conducted and technical Reports development | 3 Feasibility Studies conducted and technical Reports development | Achieved | 3 Feasibility Studies conducted and technical Reports development | None | None | Progress Report | 5000000
WSIG PROJECTS
To complete Tukakgomo water reticulation by June 2019 | Financial and human resource | Reticulated water supply | Improved access to safe, reliable drinking water. | Tukakgomo water intervention and refurbishment. | 1 borehole drilled and equipped. Refurbished pumpstations Refurbished Rising main | Number of Kilometers completed for Tukakgomo water reticulation | 4 km of Tukakgomo water reticulation constructed | *Reticulation network at 100% | *Testing and commissioning. | No activity | 4 km of Tukakgomo water reticulation constructed | N/A | No progress reported | Delayed appointment of Contractor and confirmation of the PSP`s fees | Appoint the contractor & confirm the PSP`s fees based on the scope to be executed | Memo for appointments. | 7961618
To construct reticulation and standpipes by June 2019 | Financial and human resource | Reticulated water supply | Improved access to safe, reliable drinking water. | Mahlwakwena to Mapodile pipeline(Tukakgomo Extension) | 1,8km of rising main from the highlift pumpstation to the Elevated Steel tank costructed | Number of Kilometers of reticulation and standpipes constructed | 6.3Km of reticulation network and 29 standpipes completed | *Excavations for internal reticulation(3km). *15 standpipes constructed | *Construction of 3.3km internal reticulation completed. *Installation of 14 standpipes. | No activity | 6.3Km of reticulation network and 29 standpipes completed | N/A | No progress reported | Contractor suspended the works due to non-payment of the work. | PSP to instruct the contractor to resume site Contractor to be paid based on the work executed and verified | Monthly Reports | 3085203
To complete Phiring water reticulation & storage by June 2019 | Financial and human resource | Reticulated water supply | Improved access to safe, reliable drinking water. | Phiring Water Intervention(Leboeng) | Borehole refurbished and connected to the existing steel pipeline. Elevated steel tank constructed. | Number of Kilometer of Phiring water reticulation constructed. Number of storage tanks constructed Number of borehole Refurbished. | 1.5km Kilometer of Phiring water reticulation constructed. One storage tank constructed One borehole Refurbished. | 40% of 3.5km of reticulation & 50% storage constructed,60% Drilling and Equipping of boreholes | 60% of 3.5km of reticulation & 50% storage constructed,40% Drilling and Equipping of boreholes | No activity | 1.5km Kilometer of Phiring water reticulation constructed. One storage tank constructed One borehole Refurbished. | N/A | No progress reported | Delayed appointment of Contractor and confirmation of the PSP`s fees | Appoint the contractor & confirm the PSP`s fees based on the scope to be executed | Request for Appointment of Contractor | 5153179
To complete Internal Bulk -Distribution mains and Pressure Management System by June 2019 | Financial and human resource | WC/WD Management Provisioning | Improved access to safe, reliable drinking water. | Nebo Phase 1A testing and commissioning | 1.8km pipeline from 25ML reservoir to Mashishing Reservoir constructed | Number of close out and social facilitation reports completed for phase 1. | 1 close out and social facilitation reports completed for phase 1. | 25% completion of Internal Bulk -Distribution mains and Pressure Management System | 25% completion of Internal Bulk -Distribution mains and Pressure Management System | No activity | 1 close out and social facilitation reports completed for phase 1. | N/A | No progress reported | Functionality affected by the commissioning of GaMalekana to Jane Furse Pipeline. | Project to be kept on hold until Ga Malekana to Jane Furse pipeline commissioning is completed. | Progress Report | 1000000
To construct water storage and equip the 2 existing boreholes by June 2019 | Financial and human resource | Reticulated water supply | Improved access to safe, reliable drinking water. | Uitspanning Water Supply Intervention | 60% Construction of water storage and equipping of the existing boreholes | Number of km of Uitspanning water supply | 1 Construction of water storage and 2 equipping of the existing boreholes, securing of boreholes with pumphouses. | 85% Construction of pipeline , relocation of elevated tanks and communal stand pipes. | 5% Construction of pipeline , relocation of elevated tanks and communal stand pipes. | No activity | No activity | N/A | Testing of 2 boreholes completed | *Delayed appointment of Contractor and confirmation of the PSP`s fees | Appoint the contractor & confirm the PSP`s fees based on the scope to be executed | Memo for appointments. | 4000000
To complete reticulation and installations of water meters by June 2019 | Financial and human resource | WC/WD Management Provisioning | Improved access to safe, reliable drinking water. | Flag Boshielo WC/WD Management( Letebejane pilot project) | 80% completion of Letebejane Water Project reticulation and installations of water meters. | 10% completion of Letebejane Water Project reticulation and installations of water meters. | 8 km of reticulation. 400 Water meters installed. | 80% completion of Letebejane Water Project reticulation and installations of water meters. | 10% completion of Letebejane Water Project reticulation and installations of water meters. | No activity | 8 km of reticulation. 400 Water meters installed. | N/A | Trench excavation 100%, pipe laying 100%, Installation of meters 100%, Refurbishment of the 5 elevated Jojo tanks 95% and 98% overall progress. Completion of the outstanding works, commissioning and testing is at 0% | *The contractor has stopped working. None payment of the contractor caused delay to resume with the Works on site. | PSP to instruct the contractor to resume site Contractor to be paid based on the work executed and verified | Progress Report | 7400000
To complete Package Plant in Jane Furse RDP by June 2019. | Financial and human resource | Packaged plant | Improved access to safe, reliable drinking water. | Jane Furse RDP Package plant | 70% completion of Package Plant , risnig main and storage in Jane Furse RDP | 10% completion of Package Plant , risnig main and storage in Jane Furse RDP | 1 Package Plant installed | 70% completion of Package Plant , risnig main and storage in Jane Furse RDP | 10% completion of Package Plant , risnig main and storage in Jane Furse RDP | No activity | 1 Package Plant installed | N/A | No progress reported | Delays to appoint the contractor for package plant due funds not being transferred | Appoint the contractor & confirm the PSP`s fees based on the scope to be executed | Memo for appointments. | 7500000
To construct a rising main at Maebe by June 2019 | Financial and human resource | Developed source | Improved access to safe, reliable drinking water. | Maebe/Mohlaletsi interventions | 40% development of water source and installations of rising main at Maebe. | 30% development of water source and installations of rising main at Maebe. | 3,5 kilometers of rising main installed. | 40% development of water source and installations of rising main at Maebe. | 30% development of water source and installations of rising main at Maebe. | 1 km of rising main installed. | 2,5 km of rising main installed. | Not Achieved | No progress reported | Delays to appoint the contractor for package plant due funds not being transferred | Appoint the contractor & confirm the PSP`s fees based on the scope to be executed | Memo for appointments. | 7000000
To construct VIDP Sanitation units by June 2019. | Financial and human resource | Onsite sanitation, health hygiene & user education | Improved access to safe, reliable sanitation service | Construction of Moretsele VDIP | No activity | 70 VDIP Sanitation units constructed | 370 VIDP Sanitation units constructed | No activity | 70 VDIP Sanitation units constructed | 70 VIDP Sanitation units constructed | 300 VIDP Sanitation units constructed | Not Achieved | Site establishment and settings of works completed | Delays was due to funds bot being transferred timeously | Contractor to fast track the construction | Monthly Reports | 6600000
To package plant in Tjibeng by June 2019. | Financial and human resource | Packaged plant | Improved access to safe, reliable drinking water. | WSIG-REFURBISHMENT OF TJIBENG PACKAGE PLANT | The package plant is dilapitated. | Number of package plant installed. | 1 package plant installed. | 0 package plant installed. | 0 package plant installed. | No activity | 1 package plant installed. | N/A | No progress reported | *Delays in appointment of the contractor. | Appoint the contractor based on the scope to executed. | Monthly Reports | 3000000
To construct water supply pipeline by June 2019 | Financial and human resource | Reticulated water supply | Improved access to safe, reliable drinking water. | WSIG-LOBETHAL WATER SUPPLY | New Infrastructure | Number of Kilometers completed for Lobethal water supply | 3 km of reticulation completed. | Number of Kilometers completed for Lobethal water supply | Number of Kilometers completed for Lobethal water supply | 1 km of reticulation completed. | 3 km of reticulation completed. | Not Achieved | Overall progress 99%. Busy with final site inspection, preparing for practical completion | Delays was due to funds bot being transferred timeously | Fast track the completion of wotks | Progress Report | 3000000
To construct water source development and bulk infrastructure development by June 2019 | Financial and human resource | Developed source | Improved access to safe, reliable drinking water. | Laesdrift Water Source Development and Bulk Infrastructure Development | New Infrastructure | Number of water source development and bulk infrastructure development completed | 1 of water source development and bulk infrastructure development completed | No Activity | No Activity | No activity |  | N/A | No progress reported | None | None | Item for council | 1000000
To construct water source development and bulk services by June 2019 | Financial and human resource | Developed source | Improved access to safe, reliable drinking water. | Riba Cross Water Source Development with Bulk Services | New Infrastructure | Number of drilled boreholes, construction of rising main and elevated steel tank with communal stand pipes. | 1 of drilled boreholes, construction of rising main and elevated steel tank with communal stand pipes. | No Activity | No Activity | No activity |  | N/A | No progress reported | None | None | Item for council | 1500000
To construct water source development and bulk services by June 2019 | Financial and human resource | Developed source | Improved access to safe, reliable drinking water. | Mpita Water Source Development with bulk services infrastructure | New Infrastructure | Number of drilled boreholes, construction of rising main and elevated steel tank with communal stand pipes. | 2 of drilled boreholes, 2km of rising main constructed and 1 elevated steel tank with communal stand pipes completed. | No Activity | No Activity | No activity |  | N/A | No progress reported | None | None | Item for council | 1000000
To construct water source development and bulk services by June 2019 | Financial and human resource | Developed source | Improved access to safe, reliable drinking water. | Shakung Water Supply and source development with package plant | New Infrastructure | Number of drilled boreholes, construction of rising main and elevated steel tank, package plant. | 1 of drilled boreholes, 2km of rising main constructed and 1 elevated steel tank, package plant. | No Activity | No Activity | No activity |  | N/A | No progress reported | None | None | Item for council | 1500000
To Investigate and remove of illigal water connections, install water meters and replace old water pipelines to reduce water losses by 2019 | Financial and human resource | Developed source | Improved access to safe, reliable drinking water. | Mapodile WC/WDM | New Infrastructure | Percentage of investigation and removal of illigal water connections, install 50 water meters and replace old water pipelines to reduce water losses | Investigation and removal of illigal water connections, install 50 water meters and replace old water pipelines to reduce water losses | No Activity | No Activity | No activity |  | N/A | No progress reported | None | None | Item for council | 500000
To do source development, refurbishment of package plant and water reticulation by 2019. | Financial and human resource | Packaged plant | Improved access to safe, reliable drinking water. | Nkosini Water Supply with package plant | New Infrastructure | Number of source development, refurbishment of package plant and water reticulation completed. | 1 of source development, refurbishment of 1 package plant and 1km water reticulation completed. | No Activity | No Activity | No activity |  | N/A | No progress reported | None | None | Item for council | 1200000
To drill boreholes and construct rising main and storage steel tank. | Financial and human resource | Developed source | Improved access to safe, reliable drinking water. | Magoroane Water Supply | New Infrastructure | Number of boreholes drilled and construct rising main and storage steel tank. | 1 boreholes drilled and 2.5km rising main and 1 storage steel tank. | 10% of water source developed. | 30% of water source developed. | No activity | 20% of water source developed. | N/A | No progress reported | None | None | Item for council | 1600000
To install Package plant and construct rising main by 2019 | Financial and human resource | Packaged plant | Improved access to safe, reliable drinking water. | Strydkraal Water Intervention | New Infrastructure | Number of Package plant and construction of 3km rising main | 1 Package plant and construction of 3km rising main | 15% completion of water supply pipeline, package plant and steel storage tank | 45% completion of water supply pipeline, package plant and steel storage tank | No activity | 20% completion of water supply pipeline, package plant and steel storage tank | N/A | No progress reported | None | None | Item for council | 1000000
To construct storage tank and standpipes by June 2019 | Bulk Provisioning | Improved access to safe, reliable drinking water. | Improved access to safe, reliable drinking water. | Zaaiplaas(Mzimdala) Borehole Equipping (RO) | Borehole drilled and secured with concrete pump house. Ring main installed. Gravity main installed. | Number of storage tanks installed. Number of communal standpipes installed. | 1 storage tank installed. 10 communal standpipes installed. | 0 storage tank installed. 0 communal standpipes installed. | 0 storage tank installed. 0 communal standpipes installed. | No activity | 1 storage tank installed. 5 communal standpipes installed. | N/A | 0 storage tank installed. 3 communal standpipes installed. | None | None | Monthly Reports | 2400000
To construct reticulation network by June 2019 | Financial and human resource | Reticulated water supply | Improved access to safe, reliable drinking water. | Rutseng Water Intervention (RO) | Water reticulation installed with communal standpipes. | Number of kilometers of reticulation constructed. Number of fountains refurbished | 1,5 km of reticulation constructed. 1 fountain refurbished | 0 km of reticulation constructed. 0 fountain refurbished | 0 km of reticulation constructed. 0 fountain refurbished | No activity | 1,5 km of reticulation constructed. 1 fountain refurbished | N/A | Geo-hydrological investigation 100%, communal stand pipes 100%, repair of rising main 100% and 100% reticulation complete, 90% Refurbishment of 340kl concrete reservoir,95% physical progress on site. | The contractor is denied access to the source as the other community is currently not benefiting from the project. The community of Ga-Molepo want their own source not the one from Ga-Nkoana and there is limited budget to use alternative source. | To explore the ground water (Drilling and Equipping of Boreholes) at Ga-Molepo village for interim water supply. | Monthly Reports | 1505665.91
To complete Mamatjekele Package Plant by June 2019 | Financial and human resource | Packaged plant | Improved access to safe, reliable drinking water. | Completion of Mamatjekele Package plant (RO) | Package plant installed and secured with palisade fencing. | Number of Eskom transformers installed. | 1 Eskom transformers installed. | 0 Eskom transformer installed. | 0 Eskom transformer installed. | No activity | 1 Eskom transformer installed. | N/A | 1 Eskom transformer installed. | Awaiting for Eskom to switch on the Transformer. | Eskom to switch on the transformer by the 12th of April 2019. | Monthly Reports | 520000
To complete Jane Furse RDP Package Plant by June 2019. | Financial and human resource | Packaged plant | Improved access to safe, reliable drinking water. | Jane Furse RDP Package plant (RO) | 1 Borehole drilled & tested, equipped & secured with concrete pump house, 580m of Rising main complete. | Number of isolation valves and fitings installed. | 7 isolation valves and fitings installed. | 70% completion of Package Plant , risnig main and storage in Jane Furse RDP | 10% completion of Package Plant , risnig main and storage in Jane Furse RDP | No activity | 7 isolation valves and fitings installed. | N/A | Borehole drilling, testing 100%, equipping of the borehole 100% & securing it with concrete pump house 100%, Rising main 100% complete, installation of 4x10kl jojo tanks 100% , connection to RDP 99%,and Physical progress at 99%. Installation of valves and fittings is at 0% | Awaiting for Eskom to switch on the Transformer and delays in istallation of valves and fittings | Eskom to switch on the transformer in April and contractor fast truck the installations of valves & fittings | Monthly Reports | 677225.77
To complete 1.8km pipeline from 25ML reservoir to Mashishing Reservoir constructed by June 2019. | Financial and human resource | WC/WD Management Provisioning | Improved access to safe, reliable drinking water. | Nebo Phase 1A testing and comissioning(Water Demand Management Provisioning). (RO) | 1.8km pipeline from 25ML reservoir to Mashishing Reservoir constructed | Number of close out and social facilitation reports completed for phase 1. | 1 close out and social facilitation reports completed for phase 1. | One close out and social facilitation reports completed for phase 1. | One close out and social facilitation reports completed for phase 1. | No activity | 1 close out and social facilitation reports completed for phase 1. | N/A | Water tightness at Mashishing 100%, Pressure testing at 100%, disinfection of the existing outlet 0%, Installations of fittings 100%, construction of pipeline at 100% and physical progress 99% | Non availability of water for testing & commissioning | To fast track the commissioning of the 25ML reservoir. | Monthly Reports | 1967108.32
To complete electrical connections for Keerom by June 2019. | Financial and human resource | Developed source | Improved access to safe, reliable drinking water. | Keerom Water Supply (RO) | Borehole developed. Electrical pumps installed Rising main installed | Number of Eskom transformers installed. Number of electrical panels installed. | 3 Eskom transformers installed. 1 electrical panel installed. | 0 Eskom transformers installed. 0 electrical panel installed. | 0 Eskom transformers installed. 0 electrical panel installed. | No activity | 3 Eskom transformers installed. 1 electrical panel installed. | N/A | 3 Eskom transformers installed. 3 electrical panel installed. | Project was delayed by land disputes. | Testing and Commissioning to done by the 11th of April 2019. | Monthly Reports | 700000
To install electrical fittings and security fence for Rathoke Water Supply Supply by June 2019. | Financial and human resource | Developed source | Improved access to safe, reliable drinking water. | Rathoke Water Supply Ext (RO) | Booster pumpstation, 1ML elevated steel tank and connection to the existing rising main. | Number of Electrical fittings installed. Number of security fences and gates. | 3 Electrical fittings installed. 1 security fence 1 security gates.. | 0 Electrical fittings installed. 0 security fence 0 security gates.. | 0 Electrical fittings installed. 0 security fence 0 security gates.. | No activity | 3 Electrical fittings installed. 1 security fence 1 security gates.. | N/A | 0 Electrical fittings installed. 0 security fence 1 security gates. | Delays from the supplier to install the panels. Variation order for the electrical works from the transformer to the PS and electrical fence to be finalized. | To fast track the approval of the VO. Supplier will install the panels on the 8th of April 2019. | Monthly Reports | 260000
Ti finalize testing and commissioning of 3 boreholes at Maebe by June 2019 | Financial and human resource | Developed source | Improved access to safe, reliable drinking water. | Maebe drilling and equipping of borehole (RO) | Three (3) Boreholes drilled, tested and equipped. Securing of boreholes with concrete structures. | Number of boreholes to be tested and commissioned. | 3 boreholes tested and commissioned. | 40% development of water source and installations of rising main at Maebe. | 30% development of water source and installations of rising main at Maebe. | 3 boreholes tested and commissioned. | No Activity | Achieved | 3 boreholes tested and 3 commissioned. | None. | None. | Practical Completion Certificate | 70000
MUNICIPAL INFRASTRUCTURE GRANT (MIG)
To construct VIP Sanitation units by June 2019 within Ephraim Mogale Municipality | Financial and Human Resource | 1 020 VIP Sanitation toilets completed | Improved health and hygiene | VIP Sanitation Programme Phase 2.2 | 15 180 VIP Units constructed | Number of VIP sanitation units constructed | 1020 of VIP sanitation units constructed | No activity | 200 VIP Sanitation toilets constructed | No activity | 1020 VIP Sanitation toilets constructed | N/A | Contractors appointed and project introduction completed | Contractors were appointed late in the third quarter | Contractor to fast track the construction works and complete by June 2019 | Progress Report | 19424125
To construct VIP Sanitation units by June 2019 within Elias Motsoaledi Municipality | Financial and Human Resource | 1 630 VIP Sanitation toilets completed | Improved health and hygiene | VIP Sanitation Programme Phase 2.2 | 15 180 VIP Units constructed | Number of VIP sanitation units constructed | 1630 of VIP sanitation units constructed | No activity | 400 VIP Sanitation toilets constructed | No activity | 1630 VIP Sanitation toilets constructed | N/A | Contractors appointed and project introduction completed | Contractors were appointed late in the third quarter | Contractor to fast track the construction works and complete by June 2019 | Progress Report | 20476512
To complete Zaaiplaas bulk pipeline, command reservior and pump station by June 2019 | Financial and Human Resource | Completed BWS | Improved water supply to Zaaiplaas | Zaaiplaas Village Reticulation Phase 2 | 80% construction of Dindela Reservoir. Commissioning of bulk pipeline and pump station completed | Number of Zaaiplaas bulk pipeline commissioned, command reservior constructed and pump station installed | 12,6 KM of Zaaiplaas bulk pipeline commissioned, 1 command reservior constructed and 1 pump station installed | 85% of Zaaiplaas bulk pipeline, command reservior and pump station constructed | 10% of Zaaiplaas bulk pipeline, command reservior and pump station constructed | No activity | 12,6 KM of Zaaiplaas bulk pipeline commissioned, 0 command reservior constructed and 1 pump station installed | N/A | The construction of reinforced concrete inlcuding floor slab, and first wall completed. Internal & external shuttering for second wall is at 40% | Consultant had abandoned site due to non-payment by the municipality. The contractor could not proceed with the works without the consultants supervision | The payment was done end of March 2019 and the works on site will resume in April 2019 | Progress Report | 6816418
To upgrade and extend Roosenekal Waste Water Treatment Works (WWTW) by June 2019 | Improved water supply | WWTW upgrade | Improved Living standards. | Roosenekal WWTW | 70% of Roosenekal WWTW done | Number of WWTW upgraded and extended | 1 WWTW upgraded and extended | 75% Upgrading and Extension of Roosenekal WWTW constructed | 15% Upgrading and Extension of Roosenekal WWTW constructed | No activity | 1 WWTW upgraded and extended | N/A | Clarifier base was casted. Current activites on site is fixing of steel for the wallls | Project is on penalties. Financial difficulties are being experienced on the project which slows down the progress | Contractor encouraged to expedite the works to reach practical completion which will stop the penalties. | Progress Report | 3000000
To construct VIP Sanitation units by June 2019 within Makhuduthamaga Municipality | Financial and Human Resource | 1 835 VIP Sanitation toilets completed | Improved health and hygiene | VIP Sanitation programme phase 2.2 | 15 180 VIP Units constructed | Number of VIP sanitation units constructed | 1835 VIP Sanitation units constructed | No activity | 600 VIP Sanitation toilets constructed | No activity | 1835 VIP Sanitation toilets constructed | N/A | Contractors appointed and project introduction completed | Contractors were appointed late in the third quarter | Contractor to fast track the construction works and complete by June 2019 | Progress Report | 33807437.25
To construct reticulation network in Ga- Mashabela by June 2019 | Completed Ga-Mashabela water reticulation network | Improved water supply to Ga-Mashabela | Ga-Mashabela water reticulation supply | Ga- Mashabela water reticulation supply | 60% of water reticulation constructed | Number of Km of pipeline constructed , number of Reservoir completed, number of boreholes completed | 30km of pipeline constructed , 4 Reservoir completed, 7 boreholes completed | 85% construction of water reticulation constructed | 10% construction of water reticulation constructed | 7km of pipeline constructed , 1 Reservoir completed, 5*boreholes completed | 3km of pipeline constructed , 1* Reservoir completed, 2*boreholes completed | Not Achieved | The overall construction progress is at 85% | Two boreholes in Mohwelere not energised, currently supplying from one borehole | Engagement with Eskom to fast track the energising of the borehole | Progress Report | 21565517.12
To construct reticulation network in Ga- Marishane by June 2019 | Financial and Human Resource | Completed Ga-Marishane water reticulation network | Improved water supply to Ga-Marishane | Ga- Marishane water reticulation supply | 30% water reticulation constructed | Number of bulk pipeline constructed , Reservoir completed and WTW completed | 3.4km of bulk pipeline constructed , 1 reservoir completed and 1 WTW completed | 45% construction of water reticulation constructed | 25% construction of water reticulation constructed | No activity | 0km of bulk pipeline constructed , 1 reservoir completed and 1 WTW completed | N/A | The overall construction progress is at 45% | Contractor terminated due to poor performance. The contractor has been engaging the municipality pleading to be given a third attempt on the project | Turnkey appointment to complete the project be finalised | Progress Report | 9590358.5
To construct reticulation network in Lobethal by June 2019 | Financial and Human Resource | Completed Lobethal water supply | Improved water supply to Lobethal | Lobethal water supply | 40% construction constructed | Number of Km of pipeline constructed , number of Reservoir completed, number of boreholes completed | 3km of pipeline constructed,1* Reservoir completed, 4*boreholes completed | 60% construction of water supply constructed | 20% construction of water supply constructed | No activity | No activity | N/A | Busy with final site inspection, preparing for practical completion | Waiting for letter from CoGHSTA confirming the additional funds of the project | Constant engagement with CoGHSTA. Handover of the project date will be arranged. | Progress Report | 13500000
To construct reticulation network in Ga- Phaahla by June 2019 | Financial and Human Resource | Completed Ga-Phaahla water supply | Improved water supply to Ga-Phaahla water supply | Ga- Phaahla water supply | 40% construction constructed | Number Km of pipeline constructed,WTW completed,booster pump station complted and elevated steel tank completed | 24km pipeline, 1 booster pump station 1 WTW, 1 elevated steel tank | 60% construction of water supply constructed | 20% construction of water supply constructed | 24km pipeline constructed,1* booster pump station, 1 * WTW completed, 1*elevated steeel tank completed | No activity | Not achieved | The overall construction progress is at 87% | Waiting for ESKOM to energise the project | Constant engagement with ESKOM to mobilise to site and energise the project | Progress Report | 6721314.72
To construct Fetakgomo Tubatse LM VIP Sanitation units by June 2019 | Financial and Human Resource | 715 VIP Sanitation toilets completed | Improved health and hygiene | VIP Sanitation programme phase 2.2 | 15 180 VIP Units constructed | Number of VIP sanitation units constructed | 715 VIP Sanitation units constructed | No activity | 300 VIP Sanitation toilets constructed | No activity | 715 VIP Sanitation toilets constructed | N/A | Contractors appointed and project introduction completed | Contractors were appointed late in the third quarter | Contractor to fast track the construction works and complete by June 2019 | Progress Report | 11894616.96
To construct completion of bulk water reticulation in Mooiplaas and Strydkraal Supplement by June 2019 | Financial and Human Resources | Refurbished and new developed Water Boreholes | Improved Water Supply | Contract 21,22& 24 : (Bulk, Res, PS & WDM Chamber in various villages | 85% Water supply below RDP level | Number of boreholes completed and the kilometers of pipeline completed | 4 boreholes developed and 3km of pipeline | 90% completion of bulk water reticulation in Mooiplaas and Strydkraal Supplement constructed | 10% completion of bulk water reticulation in Mooiplaas and Strydkraal Supplement constructed | No activity | 0 boreholes developed and 0 km of pipeline | N/A | The overall construction progress is at 95% for both contract 21 & 22 and 65% for contract 24 | Practical completion not achieved due Eskom delay on electrifying boreholes for both contract 21 & 22 Disputes between to tribal authorities stalled contract 24 | Engage with ESKOM to fast track the connection to ensure testing commissioning of the projects under contract 21 & 22 Porject under contract 24 to be closed at 65% physical progress | Progress report | 9000000
To complete Concrete reservoirs; Bulk Water Supply;and Reticulation at Nkadimeng: Phase 9 to 11 by June 2019 | Financial and Human Resources | Nkadimeng: Phase 9 to 11 (Makhuduthamaga) - | Improved Living standards. | Nkadimeng RWS Extension 2( Phase 9 to 11) (Fetakgom o) Ga- Mmela to Mashilavele , Ga- Pahla, Molapong, Ga- Magolego, Mankontu and Masehleng | 40% Nkadimeng WTW, Command Reservoir, reticulation and bulk line below RDP level constructed | Number Km of pipeline constructed and Reservoir completed | 67km of pipeline constructed, 2 reservoir completed | 60% Completion of Concrete reservoirs; Bulk Water Supply; Reticulation at Nkadimeng: Phase 9 to 11 | 20% Completion of Concrete reservoirs; Bulk Water Supply; Reticulation at Nkadimeng: Phase 9 to 11 | 2km of bulk pipeline and reticulation constructed, 0 reservoir completed | 2km of bulk pipeline and constructed, 1 reservoir completed | Not achieved | Contract 11A is at 78% verall progress which the construction of the reservoir at Letlhabile and chambers underway together with testing of the pipeline | Constant stoppages of project by local subcontractors and labours due to non payments | Ensure that the payment certificate are submitted on time to avoid delays | Progress Report | 15937980.32
To construct VIP Sanitation units by June 2019 (Fetakgomo Greater Tubatse LM) | Financial and Human Resource | 1630 VIP Sanitation toilets completed | Improved health and hygiene | VIP Sanitation programme phase 2.2 | 15 180 VIP Units constructed | Number of VIP sanitation units constructed | 1 630 VIP Sanitation units constructed | No Activity | 400 VIP Sanitation toilets constructed | No Activity | 1630 VIP Sanitation toilets constructed | N/A | Contractors appointed and project introduction completed | Contractors were appointed late in the third quarter | Contractor to fast track the construction works and complete by June 2019 | Progress Report | 29524641.1
To construct command reservoir, pump station and pipelines at GaMaphopha by June 2019 | Improved water supply | Ga - Maphopha Command Reservoir | Improved Living standards. | Ga - Maphopha Command Reservoir | 20% completion of Maphopha Command Reservoir constructed | Number of bulk pipeline constructed , Reservoir completed and pump station | 3km of bulk pipeline constructed, 1 reservoir completed and 1 pump station | 40% completion of command reservoir, pump station and pipelines at Ga-Maphopha constructed | 30% completion of command reservoir, pump station and pipelines at Ga-Maphopha constructed | No Activity | 0km of bulk pipeline constructed, 1 reservoir completed and 1 pump station | N/A | Pump station is at 95%.Second lift of reservoir walls casted, preparing for the third lift. Pipeline = 85% | Non compliance of OHS by the contractor. The site was stopped for a week by OHS consultant | Contractor instructed to attend to all safety issues raised by Monday 08/03/2019 | Progress Report | 18574560.96
To construct connector pipe network in Lebalelo South by June 2019 | Improved water supply | Lebalelo South connector pipes completed | Improved Living standards. | Lebalelo South connector pipes | 30% connector pipes constructed / Project advertised and waiting procurement of Contractors | Number of KM of connector pipe network in Lebalelo South constructed | 190KM of connector pipe network in Lebalelo South constructed | 20KM of connector pipe network in Lebalelo South constructed | 30KM of connector pipe network in Lebalelo South constructed | 70KM of connector pipe network in Lebalelo South constructed | 70KM of connector pipe network in Lebalelo South constructed | Not achieved | Appointment of reservoir service providers done and pre handover done, awaiting to introduce the contractors to the community. | Delays in ecxecution of works by the contractors | Site instruction to be issued to the contractors to fast the construction activities on site | Progress Report | 198119026.18
To complete designs for reticulation network and reservoirs in Lebalelo South phase 2 by June 2020 | Improved water supply | Lebalelo South connector pipes completed | Improved Living standards. | Connector pipes and reticulation to Lebalelo South Village (Ga-Maroga and Motlolo Bulk and Reticulation) | None | Number designs completed for reticulation network and reservoirs in Lebalelo South phase 2 | 1 designs completed for reticulation network and reservoirs in Lebalelo South phase 2 | 0 designs completed for reticulation network and reservoirs in Lebalelo South phase 2 | 0 designs completed for reticulation network and reservoirs in Lebalelo South phase 2 | 1 designs completed for reticulation network and reservoirs in Lebalelo South phase 2 | 0 designs completed for reticulation network and reservoirs in Lebalelo South phase 2 | Achieved | 1 designs completed for reticulation network and reservoirs in Lebalelo South phase 2 | None | None | Final design report | 7000000
To develop and approve finall design for water reticulation network and reservoirs in Lebalelo South phase 2 by June 2020 | Improved water supply | Lebalelo South connector pipes completed | Improved Living standards. | Ga-Malekana Water Supply Scheme Phase II | None | Number of final design report developed and appoved for water reticulation network and reservoirs in Ga-Malekana Water Supply Scheme Phase II | 1 final design report developed and appoved for water reticulation network and reservoirs in Ga-Malekana Water Supply Scheme Phase II | No Activity | No Activity | 1 final design report appoved for water reticulation network and reservoirs in Ga-Malekana Water Supply Scheme Phase II | No Activity | Achieved | 1 designs completed for reticulation network and reservoirs in Ga-Malekana Water Supply Scheme Phase II | None | None | Final design report | 15000000
To develop and approve finall design for water supply network in Ga-Mogashoa by June 2020 | Improved water supply | Ga Mogashoa concrete reservior completed | Improved Living standards. | Ga-Mogashoa(Senkgapudi) water supply network and concrete reservoirs | None | Number of final design report developed and appoved for water supply network in Ga-Mogashoa (Senkgapudi) | 1 final design report developed and appoved for water supply network in Ga-Mogashoa (Senkgapudi) | No Activity | No Activity | 1 final design report developed and appoved for water supply network in Ga-Mogashoa (Senkgapudi) | No Activity | Achieved | 1 designs completed for reticulation network and reservoirs in Ga-Mogashoa (Senkgapudi) | None | None | Final design report | 4000000
To develop and approve finall design for water supply network in Ga-Mogashoa by June 2020 | Improved water supply | Ga Mogashoa water reticulation completed | Improved Living standards. | Ga-Mogashoa(Manamane) water supply network and concrete reservior | None | Number of final design report developed and appoved for water supply network in Ga-Mogashoa (Manamane) | 1 of final design report developed and appoved for water supply network in Ga-Mogashoa (Manamane) | No Activity | No Activity | 1 of final design report developed and appoved for water supply network in Ga-Mogashoa (Manamane) | No Activity | Achieved | 1 designs completed for reticulation network and reservoirs in Ga-Mogashoa (Manamane) | None | None | Final design report | 5000000
ACTING DIRECTOR: INFRASTRUCTURE AND WATER SERVICES | [11 empty] | DATE