## Final
NO | MEASURABLE OBJECTIVE | PROJECT | BASELINE 2017/2018 | INDICATORS | ANNUAL TARGET 2018/2019 | Q3 TARGET | PROGRESS (Achieved/ not chieved) | ACTUAL PROGRESS | CHALLENGE | REMEDIAL ACTIONS | EVIDENCE | BUDGET 2018-2019 | TOTAL BUDGET 2018-2019
1 | Act as an engine for economic growth by diversifying& expanding local economic base. To secure a stable and sustainable financial base for the future of the agency. Develop/facilitate business that creates sustainable jobs. Source funds for economic concepts/projects | Partnership for Supply of Dry sanitation VIP Toilets | MOU | #of VIP units supplied | 3000 units supplied to emegring contractors | Obtain a List of appointed emerging contractors | Achieved | List of appointed emerging contractors obtained and process of cessions started | None | None | Signed MOU, Copy of PC Plan *List of contractors *Signed paytment agreement | 0 | 0
2 |  | Fresh Produce Market | TOR’s | #Business plans/ Feasibility study developed | 1 business plan/ Feasibility study developed | Support to strategic partner | Achieved | Support given to strategic partners *Support letters sent DRDLR Engagement held with private investor, DTI and FTLM | None | None | Approved copy of business plan/ feasilibity study. Approved TOR's | 0 | 0
3 |  | Investment promotion for Flag-Boshielo Dam/Recreational | Business plan | #investors attracted | 1 investor | *Signing of MOA/SLA*Engagement with DWS | Achieved | SLA signed with 3 Service Providers' | None | None | *Copy of signed SLA *Minutes of meeting | 0 | 0
4 |  | Agri-park | Approved plan | #Investors secured | 1 investor (DRDMR) | *1 Enaggement held with DRLDR*Identify local farmers&commodities | Achieved | 1 Engagement held with DRDLR *Local farmers and commodities identified | None | None | Minutes/attedence register. *List of farmers | 0 | 0
5 |  | BEE Keeping | Two Existing informal bee keeping projects | 2x Bee Keeping project supported | N/A | *Formalise registration of the cooperative *Sign MOU with SEDA for project support | Achieved | Cooperative registered an the registration certificate obtained * MOU signed with SEDA | None | None | Minutes/attedence register * Application forms *Registration certificate | 0 | #REF!
6 |  | Tourism Route Development | SDM Tourism Strategy | 4x Tourism project packaging and marketing | Tourism route | Identify tourism attraction that are ready and that are not ready | Achieved | Four tourism attraction side identified, visited and inspected ( Tsate heritage side, Mapoch's cave, Potlake Nature reserve and Mantrombi Nature reserve). | None | None | *Report *Tourism guide map | 0 | 30000
7 |  | Accreditation with SETA | Application | #Finalisation of Agri SETA and LGSETA accreditation and MOU | 2 SETA accreditation LGSETA and Agri SETA | *Submission of quality assurance materials/manuals | Achieved | *Submission of quality assurance materials/manuals sent to Agri SETA | None | None | Minutes/emails * certificate | 0 | 30000
8 |  | MINTEK | MOU | Implementation of the MOU | Research Report / Feasibility Study | *Meeting to finalise project action plan *Go ahead letter | Achieved | Meeting to finalise project action plan held. Letter of intent from MINTEK obtained | None | None | *Minutes & attedence register *Commitment letter *Draft report | 0 | 0
9 |  | Mining Input Supplier Park | Glencow MISP | # engagements held with local participation | Full operation of the Mining Input Supply Park | *Letter of intend to Glenco *Meeting with Glenco | Achieved | Letter of intend sent * Meeting held with Glenco and board members | None | None | Minutes/attedence register | 0 | 0
10 |  | Erf 488 portion 1 of 5 land development | Evaluation report | #private investor appointed | 1 investor appointed | *Prepare TOR's *Obtain Tittle deed | Not Achieved | The registration process has not been finalised | Awaiting for the Deeds office to issue the tittle deed | Requested the service provider to fastrack the process of obtaining the tittle deed. | *Memo for appointment of lawyers *Copy of TOR *Tittle deed *Copy of advert | 0 | 0
11 |  | Stakeholder management | *By-law , *shareholder compact | # of engagements held with the public | 1 engagement (AGM) | Not applicable for Q3. | Not applicable for Q3. | AGM is held once a year in June / 4th Quarter | None | None | *Copy of publications and AGM Minutes/attedence register | 0 | 0
12 |  | Website Development and Management | SDA Communication strategy | #Website devloped | Website and corporate Identity manual | Develop ToR's for new website * SCM process | Achieved | ToR's for new website developed * SCM process In place | None | None | *Draft specifications *Funtional website | 0 | 0
13 |  | 4th Industrial Revolution | Engagement with Limpopo Conexession | #Partnerships established | 1 broadband project | *Engagements with 1 state owned ICT agency *Engagements with 1 private ICT entity | Not Achieved | Engagements held with 1 state owned ICT entity (Limpopo Connexion) and Private ICT entity | Difficulty in securing the meeting with the state owened ICT company to finalise the MOU process. | Meeting arranged for April/May 2019 | *Copy of signed MOU | 0 | 0
14 |  | Wild Life Farming | Wildlife Farming Ranchers Assosiation of South Africa (WRSA) | #Partnerships established | 1 Wild Life partnership with Ekim& Tompi-Seleka | *Concept document with startegic partner *Singining of MOU | Achieved | Cconcept document with strategic partner developed * MOU Signed | None | None | *Copy of signed MOU *Copy of Action plan | 0 | 0
15 |  | Recycling project (Green Econopmy) | SDA Tyre Recycling study | 1x recycling project facilitated | 1 Recycling project supported | *Identify 1 reclying project *Draft business plan | Not Achieved | Still engaging local municipalities and other role players to identify credible community recycling projects. | Slow response time from various stakeholders. | Project to be identified and supported in the 4th Q 2018/2019 | Approved copy of business plan/ feasilibity study. Approved TOR's | 0 | 60000
16 |  | Small Business Support | Meeting/Consultation held with SEDA | 1 MOU | 1 partnership established through MOU | *Draft MOU*Signed MOU | Not Achieved | Draft MOU In place | Awaiting SEDA to amend changes | Fastrack enaggements with SEDA | Copy of signed MOU *Minutes& attedence register *Application forms | 0 | 0
17 |  | Conversion from Pty to SOC | SARS exemption and Donor requirement | Conversion from PTY to SOC | State owned Company (SOC) registration | Obtain final board resolution | Achieved | Board resolution obtained. Council resolution obtained. | None | None | *Benchmarking report *Board resolution *Registration certificate | 0 | 0

## Main
MEASURABLE OBJECTIVE | STRATEGY | INPUT | OUTPUT | OUTCOME | PROJECT | BASELINE 2017/2018 | INDICATORS | ANNUAL TARGET 2018/2019 | Q1 | Q2 | Q3 TARGET | PROGRESS (Achieved/ not chieved) | ACTUAL PROGRESS | CHALLENGE | REMEDIAL ACTIONS | EVIDENCE | BUDGET 2018-2019 | TOTAL BUDGET 2018-2019
Act as an engine for economic growth by diversifying& expanding local economic base. To secure a stable and sustainable financial base for the future of the agency. Develop/facilitate business that creates sustainable jobs. Source funds for economic concepts/projects | Facilitate private investor | Human resources | Investor/operationla factory | job creation * revenue generation | Partnership for Supply of Dry sanitation VIP Toilets | MOU | #of VIP units supplied | 3000 units supplied to emegring contractors | Signed MOU | Project costing plan | Obtain a List of appointed emerging contractors of appointed emerging contractor | Achieved | List of appointed emerging contractors obtained | None | None | Signed MOU, Copy of PC Plan *List of contractors *Signed paytment agreement | 0 | #REF!
| Facilitate appointment of consultants | Human resources | TOR's | feasibility study | Fresh Produce Market | TOR’s | #Business plans/ Feasibility study developed | 1 business plan/ Feasibility study developed | Identify startegic partner | Sign MOU with strategic partner | Support to strategic partner | Not Achieved | MOU signed with private investor | Lack Funding | Engagement held with private investor, DTI and FTLM | Approved copy of business plan/ feasilibity study. Approved TOR's | 0 | 0
| Facilitate private investor | Human resources | Appointed panel of consultants | Revenue generation | Investment promotion for Flag-Boshielo Dam/Recreational | Business plan | #investors attracted | 1 investor | SMC Process. Evaluation and appointment | 1 Engagement with appointed SP's | *Signing of MOA/SLA*Engagement with DWS | Not Achieved | 3 Service providers appointed and were handed business plans to review. | Difficulty in securing a meeting with DWS | Follow up calls and email | *Copy of signed SLA *Minutes of meeting | 0 | 0
| Facilitate operationalisation | Human resources | Enagemnets meetings | Job creation . Imporved | Agri-park | Approved plan | #Investors secured | 1 investor (DRDMR) | *1 enagement held with DRDLR | *1 enagements held with DRDLR | *1 Enaggement held with DRLDR*Identify local farmers&commodities | Achieved | Local farmers and commodities identified | None | None | Minutes/attedence register. *List of farmers | 0 | 0
[5 empty] | BEE Keeping | Two Existing informal bee keeping projects | 2x Bee Keeping project supported | N/A | N/A | *Engage Stake holders*Identify partners | *Formalise registration of the cooperative *Sign MOU with SEDA for project support | Achieved | 1x Cooperative registered an the registration certificate obtained * MOU signed with SEDA | None | None | Minutes/attedence register * Application forms *Registration certificate | 0 | #REF!
[5 empty] | Tourism Route Development | SDM Tourism Strategy | 4x Tourism project packaging and marketing | Tourism route | N/A | N/A | Identify tourism attraction that are ready and that are not ready | Achieved | Four tourism attraction side identified, visited and inspected ( Tsate heritage side, Mapoch's cave, Potlake Nature reserve and Mantrombi Nature reserve). | All identified tourism attraction are not tourism ready | Provision of funding for renovation and upgrade | *Report *Tourism guide map | 0 | 30000
| Appoint consultant for accreditation | Financial resources | Accrediation certificate | skills development | Accreditation with SETA | Application | #Finalisation of Agri SETA and LGSETA accreditation and MOU | 2 SETA accreditation LGSETA and Agri SETA | *Assesment of trainining facility | *Assesment for Agri SETA | *Submission of quality assurance materials/manuals | Not Achieved | All relevent information that was requested by SETA was sent to them. | Delays in SETA processes to grant approval of assessor and moderators to enable the submission of quality assurance manuals | Several emails sent to SETA and committed to respond by the 8th April 2019 | Minutes/emails * certificate | 0 | 30000
| Facilitate registration process | Human & resources | registration certificates | trading rights | SDA Mining and Construction company | Board resolution | # Registration and Profiling of the companies | 2 registered and profiled companies | *Finalise regstration with statutory bodies | profile the companies | identify and forge partnerships | Removed from the SDBIP during Adjustment processes |  |  |  | certificates and profiles | 0 | #REF!
| Monitoring and Evaluation of SLP and SPP | Human resources | Minutes/reports | compliance to mining charter | SLP and SPP | Board resolution | Improved implementation of SLP and SPP | 4 implementation of SLP and SPP | 1 enagement held with DMR&Mining houses | 1 engagement with DMR&Mining houses | 1 enagement with DMR & Mining houses | Removed from the SDBIP during Adjustment processes |  |  |  | Minutes/attedence register | 0 | #REF!
| Implementation of MOU with MINTEK | Human&financial resources | Report | Enhanced knowledge/information | MINTEK | MOU | Implementation of the MOU | Research Report / Feasibility Study | Concept document | x 1 engagament | *Meeting to finalise project action plan *Go ahead letter | Achieved | Meeting held. Go ahead letter obtained | None | None | *Minutes & attedence register *Commitment letter *Draft report | 0 | #REF!
| Facilitate local participation | Human reources | Investors | job creation/enahnces local manufacturing | Mining Input Supplier Park | Glencow MISP | # engagements held with local participation | Full operation of the Mining Input Supply Park | N/A | Prsentation by LEDA/SEZ Draft document | *Letter of intent to Glenco *Meeting with Glenco |  |  |  |  | Minutes/attedence register | 0 | #REF!
| Facilitate appointment of private investor | Human reources | developer | Revenue generation | Erf 488 portion 1 of 5 land development | Evaluation report | #private investor appointed | 1 investor appointed | Land trasfrer process | Land transfer process | *Prepare TOR's *Obtain Tittle deed | Not Achieved | The registration process has been finalised | Awaiting for the Deeds office to issue the tittle deed | Requested the service provider to fastrack the process of obtaining the tittle deed. | *Memo for appointment of lawyers *Copy of TOR *Tittle deed *Copy of advert | 0 | #REF!
| Facilitate stakeholder engagements | Human& financial resources | Implementation of commuications strategy | improved stakeholder engagement | Stakeholder management | *By-law , *shareholder compact | # of engagements held with the public | 1 engagement (AGM) | N/A | *Community/stakoeldher meetings *newsletter | *newsletters/publications |  |  |  |  | *copy of publications and AGM Minutes/attedence register | 0 | #REF!
[5 empty] | Website Development and Management | SDA Communication strategy | #Website devloped | Website and corporate Identity manual | N/A | N/A | Develop ToR's for new website * SCM process | Achieved | Advert to source a service provider for the development of the website was published on the 17th March 2019 ; the public Briefing meeting was held on the 25th March 2019 and it closed on the 2nd April 2019. | None | None | *Draft specifications *Funtional website | 0 | #REF!
[5 empty] | 4th Indutrial Revolution | Engagement with Limpopo Conexession | #Partnerships established | 1 broadband project | N/A | N/A | *Engagements with 1 state owned ICT agency *Engagements with 1 private ICT entity | Not Achieved | Liased with 1 state owned ICT entity (Limpopo Connexion) | Difficulty in securing a meeting with Limpopo Connexion with the CEO | Meeting secured for the 15th April | *Copy of signed MOU | 0 | #REF!
[5 empty] | Wild Life Farming | Wildlife Farming Ranchers Assosiation of South Africa (WRSA) | #Partnerships established | 1 Wild Life partnership with Ekim& Tompi-Seleka | N/A | N/A | *Concept document with startegic partner *Singining of MOU | Achieved | MOU Signed and the concept document | None | None | *Copy of signed MOU *Copy of Action plan | 0 | 0
[5 empty] | Recycling project (Green Econopmy) | SDA Tyre Recycling study | 1x recycling project facilitated | 1 Recycling project supported | N/A | N/A | *Identify 1 reclying project *Draft business plan | Achieved | Draft business plan in place | None | None | Application documents for recycling project | 0 | 60000 | Strategic Sector Project Name Baseline Indicator Sub -Projects Strategic Partner Budget 2018/2019 2019/2020 Q1 Q2 Q3 Q4 Q1 Q2 Q3 Q4 Strategic Pillar 1. Agriculture 1. Agri-Park Agri-Park Business Plan and Agri-Park structures 3X Agri Park sub-projects facilitated 1.Milling market access 2.Abattoir market access 3.Strategic partnership with established famers( MOU) Department of Rural Development & Land Affairs R 150,000 N/A N/A *Identify local farmers and commodities Asses capacity and requirements Sign Agreement with Milling company Facilitate access to market Facilitate access to market Facilitate access to market 2. Aquaculture (De Hoop and Flag Boshielo Dams) Tow Feasibility studies and business plans 3 X XAquaculture sub-projects facilitated 1.Identify operating partner 2.Develop community business models 3. Source funding Department of Water& Sanitation R 500,000 N/A N/A Handover of 2 feasibility reports from SDM to SDA Engage stakeholders Advertise for operators/Strategic Partners Appointment operator/Partners Implements phase 1 of the project Implement phase 1 of the project 3. Bee Keeping Two existing Informal bee keeping projects 2 X BEE Keeping projects supported 1.Establish and support Ga-Masemola Bee keeping project 2. establish and support Tsimanyana Bee keeping project *SEDA *Berg Bee Academy R 200, 000 N/A Engage stakeholders Identify partners Visits existing projects Formally register 2 cooperatives/SMME’s Sign agreement with SEDA for support Capacity building of cooperative members Purchasing of equipment d project roll-out project roll out 4. Fresh Produce Market MOU signed with Fresh Harvest 1x Private Investor supported Support Fresh Harvest (local /BEE Company) to secure funding for feasibility study *Fresh Harvest *Limpopo Department of Agriculture *Department of Trade& Industry R 100, 000 1X engagements with the Investor and other partners 1x Engagements with investor and other partyners 1 x Engagements with investors and other partners 1x Engagements with investors and other partners 1x Engagements with investors and other partners 1x Engagements with investors and other partners X Engagements with investors and other partners 1x Engagements with investors and other partners Strategic Pillar 2-Mining & Manufacturing 1. Mining Development Research MOU signed with MINTEK 1 strategic Partner supported 1.Staheolder mobilisation for mining research project MINTEK R 00,000 N/A N/A 1x Engagement with MINTEK Establishment of project steering committee Projects Implementation Plan Conducting of research Draft report Final report 2.Supply of VIP dry sanitation MOU signed with Amalooloo 5 x engagements held 1. Supply of VIP Toilets top structures to emerging contractors2.Feasibility study for establishment of sanitation factory. *Sekhukhune District Municipality *Betrum (Amalooloo R 00,000 1X engagements with the Investor 1X engagement with the Investor 1 x engagements with the Investor 1x engagement with the Investor 1x engagement with the investor N/A N/A N/A 3.LED Lights manufacturing Benchmarking with Gauteng and Richards-bay manufacturing project 2x LED Manufacturing initiated facilitated 1.Develop business proposal for LED Lights manufacturing 2.Establish and support Local LED Lights manufacturing 3.Setup local business model 4.Sign MOU with SEDA for financial and non-financial support for LED Lights project Limpopo Government R 100,000 N/A Visits to JHB&KZN for benchmarking Development of a Draft proposal Development of a final Proposal Feasibility study Submission for funding &sourcing of strategic partners Submission for funding & sourcing of strategic partner Submission for funding and sourcing of strategist partner Strategic Pillar 4-Tourism 1. SDM Tourism Route Development SDM tourism strategy 4x Tourism promotion facilitated 1.Tourism project packaging And marketing LEDET/LTA R 350,000 N/A N/A Identify tourism attractions that are ready and not ready Packaging of tourism Guide map Engage LEDET and Other stakeholders for signage provision Marketing of tourism attractions Marketing of tourism attractions Marketing of tourist attractions Strategic Pillar 5-Investment and Funding 1. One-stop Investment Centre Provincial& National 1 stop Investment centres 1x Sekhukhune investment centre established 1.Develop a process flow chart for the processing of development application 2.Sign a protocol agreement with District and 4 locals 3.Develop applications repository and tracking system 4.Sign MOU with LEDET for operationalization of One stop investment center Limpopo Department of Economic, Environment &Tourism R 200,000 N/A N/A Meeting with stakeholders (LEDET/SDM/Locals/LEDA) Development of applications flow chart Sing protocol agreement with SDM & 4 locals *Develop applications repository system *Sign MOU with LEDET Project Implementation and Monitoring Project Implementation and monitoring 2. Contact Management of three private financial mobilisation SPs 3 Appointed SP’s 4X contract management sessions facilitated 1.Sign SLA with 3 SP’s 2.Project/sector allocation per company 3.submission of financial mobilization strategy per company 4. Quarterly M&E meetings. *Private sector R00 Appointment of companies Submission of base documents to companies 1st Introductory meeting /Presentations Signing of SLA 1x quarterly engagement 1x quarterly engagement 1 x quarterly engagement 1x quarterly engagements Strategic pillar 6-Skills Development 1. Agri-SETA accreditation Application process lodged 1x accreditation certificate facilitated Obtain accreditation certificate Dep of Higher Education& Training R 50,000 N/A Visits by Agri-Sita 1x engagement with Agri-Seta and consultant Submission of modules by consultant Accreditation certificate Application of discretionary funds Application of funds Recruitment and training 2. Mining Skills Development MOU signed between Glenco&SEK-TVET 3 x mining skills initiates facilitated 1.Application to MERSETA and GLENCOR for funding 2.Support 1 Local SMME to register with MERSETA and other SETA’s 3.Support and partner 1 SMME to develop proposal for trade testing centre DMR & DHET R 100,000 N/A N/A Obtain and analyse MOU between SEK TVET& Glenco 1x engagement held with SEK TVET and Glenco Identify 1 Local SMME and sign MOU Develop proposal in partnership with 1 local SMME Submit funding application to MERSETA Project implementation phase 3. Digital Economy / 4th industrial revolution Limpopo Connection 2 x Digital economy projects facilitated 1.Sign MOU with Limpopo connextion 2.Develop a proposal for funding of a broadband network 3.Identify private partner for rolling out broadband and training Limpopo Provincial Government R100,000 N/A 1X engagement with Limpopo Connect Sign MOU with Limpopo connect and 1 private strategic partner Develop proposal for funding Funding application Funding application 1st Roll-out of Broad band/Digital project Monitoring of the project Strategic Pillar 7-Green Economy 1.Recycling project 2.Solar Panel for SDM projects SDA Tyre Recycling Study 1x recycling project facilitated 1.Identify and support 1 recycling project 2.Develop proposal to source funding for installation of solar panel for SDM infrastructure 3.Develop proposal for energy power bank Dep of Environmental Affairs/LEDET R 250,000 N/A N/A *Obtain a list of reclog projects within SDM *Issue tender notice for applications *Appoint 1 successful project *Meeting with project operators *Training and capacity building Monitoring of the project Monitoring of the project Monitoring of the project Strategic Pillar 8- Brand Sekhukhune 1.SDA Corporate Identity Manual 2.Website& Digital media strategy SDA communication strategy 2 X brand Sekhukhune projects facilitated 1.Develop SDA CI manual 2.Develop and launch SDA website and Digital media strategy Brand SA R 300,000 N/A N/A *develop TOR’s for new website *Appointment of website developer *Launch the website *develop draft CI manua *Final CI manual approval *Website management *Website management Website management Website management 3.SDA Investment brochure SDA Investment Passport 1 x Investment brochure developed 1.Package, print and distribute investment profile LEDA R 200,000 N/A N/A N/A N/A Benchmark with other agencies by getting copies of their brochures *Develop brochure specification Appointment service provider to design and print the brochure Distribution and marketing Distribution and marketing 4. SDA Investment roadshows *SDA investment passport *SDM LED profile 2X Investment road shows facilitated 1.Conduct 2 investment roadshows 2.Attend external business roadshows and expos LEDA/DTI R 250,000 N/A N/A N/A *Attend Durban Indaba for benchmarking *Package material for Sekhukhune Invest Expo Source strategic partner Host Sekhukhune Invest Expo (Big Business) Follow up engagements with investors who committed Host Sekhukhune Small Business expo Strategic Sector Project Name Baseline Indicator Sub -Projects Strategic Partner Budget 2018/2019 2019/2020 Q1 Q2 Q3 Q4 Q1 Q2 Q3 Q4 Strategic Pillar 1. Agriculture 1. Agri-Park Agri-Park Business Plan and Agri-Park structures 3X Agri Park sub-projects facilitated 1.Milling market access 2.Abattoir market access 3.Strategic partnership with established famers( MOU) Department of Rural Development & Land Affairs R 150,000 N/A N/A *Identify local farmers and commodities Asses capacity and requirements Sign Agreement with Milling company Facilitate access to market Facilitate access to market Facilitate access to market 2. Aquaculture (De Hoop and Flag Boshielo Dams) Tow Feasibility studies and business plans 3 X XAquaculture sub-projects facilitated 1.Identify operating partner 2.Develop community business models 3. Source funding Department of Water& Sanitation R 500,000 N/A N/A Handover of 2 feasibility reports from SDM to SDA Engage stakeholders Advertise for operators/Strategic Partners Appointment operator/Partners Implements phase 1 of the project Implement phase 1 of the project 3. Bee Keeping Two existing Informal bee keeping projects 2 X BEE Keeping projects supported 1.Establish and support Ga-Masemola Bee keeping project 2. establish and support Tsimanyana Bee keeping project *SEDA *Berg Bee Academy R 200, 000 N/A Engage stakeholders Identify partners Visits existing projects Formally register 2 cooperatives/SMME’s Sign agreement with SEDA for support Capacity building of cooperative members Purchasing of equipment d project roll-out project roll out 4. Fresh Produce Market MOU signed with Fresh Harvest 1x Private Investor supported Support Fresh Harvest (local /BEE Company) to secure funding for feasibility study *Fresh Harvest *Limpopo Department of Agriculture *Department of Trade& Industry R 100, 000 1X engagements with the Investor and other partners 1x Engagements with investor and other partyners 1 x Engagements with investors and other partners 1x Engagements with investors and other partners 1x Engagements with investors and other partners 1x Engagements with investors and other partners X Engagements with investors and other partners 1x Engagements with investors and other partners Strategic Pillar 2-Mining & Manufacturing 1. Mining Development Research MOU signed with MINTEK 1 strategic Partner supported 1.Staheolder mobilisation for mining research project MINTEK R 00,000 N/A N/A 1x Engagement with MINTEK Establishment of project steering committee Projects Implementation Plan Conducting of research Draft report Final report 2.Supply of VIP dry sanitation MOU signed with Amalooloo 5 x engagements held 1. Supply of VIP Toilets top structures to emerging contractors2.Feasibility study for establishment of sanitation factory. *Sekhukhune District Municipality *Betrum (Amalooloo R 00,000 1X engagements with the Investor 1X engagement with the Investor 1 x engagements with the Investor 1x engagement with the Investor 1x engagement with the investor N/A N/A N/A 3.LED Lights manufacturing Benchmarking with Gauteng and Richards-bay manufacturing project 2x LED Manufacturing initiated facilitated 1.Develop business proposal for LED Lights manufacturing 2.Establish and support Local LED Lights manufacturing 3.Setup local business model 4.Sign MOU with SEDA for financial and non-financial support for LED Lights project Limpopo Government R 100,000 N/A Visits to JHB&KZN for benchmarking Development of a Draft proposal Development of a final Proposal Feasibility study Submission for funding &sourcing of strategic partners Submission for funding & sourcing of strategic partner Submission for funding and sourcing of strategist partner Strategic Pillar 4-Tourism 1. SDM Tourism Route Development SDM tourism strategy 4x Tourism promotion facilitated 1.Tourism project packaging And marketing LEDET/LTA R 350,000 N/A N/A Identify tourism attractions that are ready and not ready Packaging of tourism Guide map Engage LEDET and Other stakeholders for signage provision Marketing of tourism attractions Marketing of tourism attractions Marketing of tourist attractions Strategic Pillar 5-Investment and Funding 1. One-stop Investment Centre Provincial& National 1 stop Investment centres 1x Sekhukhune investment centre established 1.Develop a process flow chart for the processing of development application 2.Sign a protocol agreement with District and 4 locals 3.Develop applications repository and tracking system 4.Sign MOU with LEDET for operationalization of One stop investment center Limpopo Department of Economic, Environment &Tourism R 200,000 N/A N/A Meeting with stakeholders (LEDET/SDM/Locals/LEDA) Development of applications flow chart Sing protocol agreement with SDM & 4 locals *Develop applications repository system *Sign MOU with LEDET Project Implementation and Monitoring Project Implementation and monitoring 2. Contact Management of three private financial mobilisation SPs 3 Appointed SP’s 4X contract management sessions facilitated 1.Sign SLA with 3 SP’s 2.Project/sector allocation per company 3.submission of financial mobilization strategy per company 4. Quarterly M&E meetings. *Private sector R00 Appointment of companies Submission of base documents to companies 1st Introductory meeting /Presentations Signing of SLA 1x quarterly engagement 1x quarterly engagement 1 x quarterly engagement 1x quarterly engagements Strategic pillar 6-Skills Development 1. Agri-SETA accreditation Application process lodged 1x accreditation certificate facilitated Obtain accreditation certificate Dep of Higher Education& Training R 50,000 N/A Visits by Agri-Sita 1x engagement with Agri-Seta and consultant Submission of modules by consultant Accreditation certificate Application of discretionary funds Application of funds Recruitment and training 2. Mining Skills Development MOU signed between Glenco&SEK-TVET 3 x mining skills initiates facilitated 1.Application to MERSETA and GLENCOR for funding 2.Support 1 Local SMME to register with MERSETA and other SETA’s 3.Support and partner 1 SMME to develop proposal for trade testing centre DMR & DHET R 100,000 N/A N/A Obtain and analyse MOU between SEK TVET& Glenco 1x engagement held with SEK TVET and Glenco Identify 1 Local SMME and sign MOU Develop proposal in partnership with 1 local SMME Submit funding application to MERSETA Project implementation phase 3. Digital Economy / 4th industrial revolution Limpopo Connection 2 x Digital economy projects facilitated 1.Sign MOU with Limpopo connextion 2.Develop a proposal for funding of a broadband network 3.Identify private partner for rolling out broadband and training Limpopo Provincial Government R100,000 N/A 1X engagement with Limpopo Connect Sign MOU with Limpopo connect and 1 private strategic partner Develop proposal for funding Funding application Funding application 1st Roll-out of Broad band/Digital project Monitoring of the project Strategic Pillar 7-Green Economy 1.Recycling project 2.Solar Panel for SDM projects SDA Tyre Recycling Study 1x recycling project facilitated 1.Identify and support 1 recycling project 2.Develop proposal to source funding for installation of solar panel for SDM infrastructure 3.Develop proposal for energy power bank Dep of Environmental Affairs/LEDET R 250,000 N/A N/A *Obtain a list of reclog projects within SDM *Issue tender notice for applications *Appoint 1 successful project *Meeting with project operators *Training and capacity building Monitoring of the project Monitoring of the project Monitoring of the project Strategic Pillar 8- Brand Sekhukhune 1.SDA Corporate Identity Manual 2.Website& Digital media strategy SDA communication strategy 2 X brand Sekhukhune projects facilitated 1.Develop SDA CI manual 2.Develop and launch SDA website and Digital media strategy Brand SA R 300,000 N/A N/A *develop TOR’s for new website *Appointment of website developer *Launch the website *develop draft CI manua *Final CI manual approval *Website management *Website management Website management Website management 3.SDA Investment brochure SDA Investment Passport 1 x Investment brochure developed 1.Package, print and distribute investment profile LEDA R 200,000 N/A N/A N/A N/A Benchmark with other agencies by getting copies of their brochures *Develop brochure specification Appointment service provider to design and print the brochure Distribution and marketing Distribution and marketing 4. SDA Investment roadshows *SDA investment passport *SDM LED profile 2X Investment road shows facilitated 1.Conduct 2 investment roadshows 2.Attend external business roadshows and expos LEDA/DTI R 250,000 N/A N/A N/A *Attend Durban Indaba for benchmarking *Package material for Sekhukhune Invest Expo Source strategic partner Host Sekhukhune Invest Expo (Big Business) Follow up engagements with investors who committed Host Sekhukhune Small Business expo
[5 empty] | Small Business Support | Meeting/Consultation held with SEDA | 1 MOU | 1 partnership established through MOU | N/A | N/A | *Draft MOU*Signed MOU | Achieved | MOU signed | None | None | Copy of signed MOU *Minutes& attedence register *Application forms | 0 | #REF!
[5 empty] | Conversion from Pty to SOC | SARS exemption and Donor requirement | Conversion from PTY to SOC | State owned Company (SOC) registration | N/A | Benchmarking with similar agencies | Obtain final board resolution | Achieved | Board resolution obtained. Council resolution obtained. | None | None | *Benchmarking report *Board resolution *Registration certificate | 0 | #REF!
| Facilitate the study/ research of Regional economic Plan | Human resources | Rsearch report | improved knowledge | Regional Economic Development Master Plan | None | Facilitation of the Master plan | 1 Development Master Plan | TOR's and project plan | Stakeholder enagements | Draft report | Removed from the SDBIP during Adjustment processes |  |  |  |  | 0 | #REF!
[5 empty] | TOTAL | [11 empty] | 0 | #REF!