## Sheet1
2018/2019 SERVICE DELIVERY BUDGET AND IMPLEMENTATION PLAN: OFFICE OF THE EXECUTIVE MAYOR
STRATEGIC OBJECTIVE | INPUT | OUTPUT | OUTCOME | PROJECT | BASELINE 2017/2018 | INDICATORS | ANNUAL TARGET 2018/2019 | Q3 TARGETS | PROGRESS (Achieved/ Not achieved) | ACTUAL PROGRSS | CHALLENGE | REMEDIAL ACTIONS | EVIDENCE | BUDGET 2018-2019
COMMUNICATIONS; ADVOCACY, SOCIAL FACILITATION; SPECIAL PROGRAMMES AND ARTS AND CULTURE
To facilitate stakeholder engagement /Mayoral outreaches by June 2019 | Finanicial&Human resources | Community and stakholder meetings | Improved citizenry engagemens | Mayoral Outreaches and Stakeholder Engagements | 12 Mayoral Outreaches Programmes/Mayoral outreaches facilitated | Number of stakeholder engagement/mayoral outreaches facilitated | 8 stakeholder engagement/mayoral outreaches facilitated | 2 engagement/mayoral outreaches facilitated | Achieved | 4 Outreaches /stakeholder engagement - Outreach 22/01/2019 Phahla-Manoge, 18/02/2019 Uitspaning and 06/03/2019 Ga-Mashsbela, SODA held 15/03/2019 at Dichoeung Village. | None | N/A | Exit reports&Attedence registers | 2263200
To provide support to Mayoral Committee meetings by June 2019 | Human and Financial resources | Integrated Executive Support (Mayoral Committee and Lekgotla) | Promote Stakeholder Engagement In Public Service | Executive Support to Mayoral Committee | 12 Mayoral Committee meetings held | Number of logistical supports provided to Mayoral Committee meetings. | 12 logistical supports provided to Mayoral Committee meetings. | 3 logistical supports provided to Mayoral Committee meetings. | Achieved | 5 Logistical Supports provided to Mayoral Committee meetings held on the. 23/01/2019, 20/02/2019, 26/02/2019, 19/03/2019 and 27/03/2019 respectively. | None | N/A | Minutes and attendance registers
To promote art and culture activities by June 2019 | Finanicial&Human resources | Successul tra | Governance stability/Enhanced oversight | Cultural Heritage Celebrations and Language Promotions | 3 art & culture programmes promoted | Number of art and culture activities promoted | 3 art and culture activities promoted | No Target | No Activity | No Activity | None | N/A | Exit reports/attedence registers | 0
To produce news letters by June 2019 | Finanicial&Human resources | Newsletter publications and pormotional materials | Informed citizenry | Newsletter | 4 internal, 2 Special and 1200 diaries produced | Number of newsletters produced | 15 news letters produced. | 2 internal, 1 special and 1 external, 1 diaries and calenders | Not Achieved | 0 internal, 0 special and 0 external, diaries and calenders delivered | Contract for pannel of SP expired in Jan 2019. SCM Processes followed and waiting appointment. | Engage MM/CFO to finalise appointment | copies of newsletters, diaries and calenders | 500000
To market the district by June 2019 | Finanicial&Human resources | pictures | enhanced branding and visibilsity | Media Relations and Marketing | 10 Events Branded | Number of Events Branded & procurment of material done | 12 Events Branded & procurment of material done | 3 events branded | Achieved | 3 Events Branded. Back to school, Annual Report, SODA | None | N/A | pictures & exit reports | 225000
To update the website by June 2019 | Finanicial&Human resources | Functional website | informed citezinry and marketing | Website Management | 20 Updates | Number of Website Updates undertaken | 20 Updates undertaken | 5 websites updates under taken | Not Achieved | Annual Report uploaded, SDM Public noteses, posters LED event,SODA | Late upload by Service Provider | IDP tobe uploaded in April 2019 | Exit reports&screen shots | R81 000.00
To manage business of the executive arm and systematic support to Traditional Leaders by June 2019 | Finanicial&Human resources | Events | Improved relationship with traidtional leaders | Executive Support and Traditional Leadership Affairs | 2 SPLUMA meeting supported | Number of Traditional Leaders meetings coordinated | 4 meetings coordinated | 1 meeting coordinated | Not Achieved | Meeting not held. | Conflicting Programmes | Meeting rescheduled for the 4th Quarter | Exit reports | 550000
To coordinate special Mayoral events by June 2019 | Finanicial&Human resources | Events | Improved corporate branding | Special Mayoral strategic Events | 5 strategic events Facilitated | Number of Strategic Events facilitated | 7 Strategic Events facilitated | 2 Strategic events held: Kgoshi Mampuru & SODA | Achieved | 2 Strategic Events held: Kgoshi Mampuru Day Commemoration held in January 2019 & SODA held 15/03/2019 at Dichoeung 2019. Bapadi Kings Commemoration held 31/03/2019 at Mohlaletse Tjate 3. | None | N/A | Exit reports | 1135000
To facilitate Moral Regeneration Movement (MRM) programmes by June 2019 | Human and Financial resources | Integrated Society MRM | Promote Stakeholder Engagement In Public Service | Strengthening of Moral Regeneration Movement Committee | MRM committee established | Number of programmes for MRM committee facilitated | 2 MRM committee programme facilitated | 1 MRM committee programme facilitated | Not Achieved | No Activity | Local MRM Committees not functional | Committees to be revived in the 4th Quarter | Exit report
To facilitate HIV/AIDS programmes by June 2019 | Finanicial&Human resources | Coordinated health events | Improved health programmes | AIDS Council Activities | District Aids and Health Council activities | Number of HIV/AIDS Programmes facilitated | 4 HIV/AIDS programmes facilitated | 1 STI/Condoms wee, 1 TB Awareness day facilitated | Achieved | Coordinate STIs Condom Week Campaign * Coordinate TB Month Commemoration.27& 28 /03/2019 Tafelkop Ga- Matsepe | None | N/A | Exit reports/attedence registers | 100000
To conduct youth programmes by June 2019 | Finanicial&Human resources | succssful hosting of Youth Expo | Improved youth development | Youth Opportunities Expo | 3 Programmes | Number of Youth Programmes conducted. Support to youth council provided | 3 Youth Programmes conducted. 3 Support to youth council provided | *1 career expo conducted. * 1 Support to youth council | Not Achieved | 1 support meeting towards establishment of youth council held | Conflicting Programmes in the Office of the Executive Mayor | Career Expo held on the 05/04/2019 at Peter Nchabeleng school, Makhuduthamaga municipality. | Exit reports | 218000
To facilitate sport activities by June 2019 | Finanicial&Human resources | successful sports events | Improved healthy living | Facilitation of Mayoral Sports activities | 3 Programmes facilitated | Number of Sport activities facilitated | 2 Sport activities facilitated (1 Indigenous games, 1 Mayors cup) | No activity | Not Achieved | Meetings held in preparations for the 2019 Executive Mayor's Cup. | 3 of the 4 Municipalities are yet to play their Local Mayor's Cups | Support the Locals to play their Local Mayor's Cups. | Exit reports | R150 000.00
To inculcate the culture of people first and friendly customer frontline services by June 2019 | Finanicial&Human resources | effective query management system | enhanced accountability | Customer Care Services | 24 reports generated | Number of reports generated | 24 queries/ complains reports on customer care generated | 6x reports generated (3 sdm, 3 premier & presidential) | Achieved | 8 x Reports Generated 3 SDM & 2 Premier 3 Presidential generated | None | N/A | Reports | 200000
|  |  |  | Batho pele | 6 Programmes conducted | Number of Batho Pele Programmes conducted | 5 Batho Pele Programmes conducted | 1 Batho Pele Programmes conducted | Achieved | 1 Batho Pele Programmes conducted | None | N/A | Reports | 50000
To facilitate awareness programmes for people with disability by June 2019 | Finanicial&Human resources | Events/meetings | awareness | People with disability | 3 awareness programmes | Number of awareness programmes facilitated | 3 awareness programmes facilitated | 1 Human rights day for people with disabilities facilitated | Achieved | 1 Human rights day for people with disabilities held at Mohlaletse Disability Centre - 27/03/2019 | None | N/A | Exit reports&Attedence registers | R51 000.00
To facilitate women deveelopment programmes by June 2019 | Finanicial&Human resources | Women programmes | awareness | Woman Development Initiative | 4 women activities coordinated | Number of women development programmes facilitated | 4 women development programmes facilitated | *1 orange day *1 international womens day programme facilitated | Achieved | 1. Observe Orange day. 2.International womens day held - 29/03/2019 at Lekgotla Boardroom. | None | N/A | Exit repors/attedence registers | 130000
To facilitate children activities by June 2019 | Finanicial&Human resources | childrens programmes | awareness | Children’s Care | 2 childrens acvities facilitated | Number of children's activities facilitated | 2 children activities facilitated | No activity | No Activity | No Activity | None | N/A | Exit reports/attedence registers | 40800
To coordinate aged care programmes by June 2019 | Finanicial&Human resources | Aged programmes | awareness | Aged care | 2 aged care programmes coordinated | number of aged care programmes coordinated | 2 aged care programmes coordinated | No Target | No Activity | No Activity | None | N/A | Exit reports/attedence registers | 200000
To coordinate State of the District Address (SODA) by June 2019 |  |  |  | SODA | 2017/2018 SODA held | Number of SODA organised | 1 SODA coordinated | 1 SODA coordinated | Achieved | 1 SODA held 15/03/2019 at Dichoeung | None | N/A | Exit Report | 10200
DEPUTY DIRECTOR: Mr. K PHASHA | [7 empty] | DATE