## Sheet1
MEASURABLE OBJECTIVE | STRATEGY | INPUT | OUTPUT | OUTCOME | PROJECT | BASELINE 2017/2018 | INDICATORS | ANNUAL TARGET 2018/2019 | Q1 | Q2 | Q3 | Q4 | EVIDENCE | BUDGET 2018-2019 | BUDGET ADJUSTMENT 2018-2019 | TOTAL BUDGET 2018-2019
Act as an engine for economic growth by diversifying& expanding local economic base. To secure a stable and sustainable financial base for the future of the agency. Develop/facilitate business that creates sustainable jobs. Source funds for economic concepts/projects | Facilitate private investor | Human resources | Investor/operationla factory | job creation * revenue generation | Factory for dry sanitation technologies | MOU | #of factories facilitated | 1 factory constructed | Signed MOU | Facilitate the Construction of the factory | Monitoring of implementation of the MOU | Monitoring of implementation of the MOU | Signed MOU and Report | 0 | 0 | 0
| Facilitate appointment of consultants | Human resources | TOR's | feasibility study | Fresh Produce Market | TOR’s | #Business plans/ Feasibility study developed | 1 business plan/ Feasibility study developed | Issue an advert | appoint consultants | conducting feasibility study/ business plan | conducting feaisbility study/ business Plan | Approved copy of business plan/ feasilibity study. Approved TOR's | 100000 | 0 | 100000
| Facilitate private investor | Human resources | Appointed panel of consultants | Revenue generation | Investment promotion for Flag-Boshielo Dam/Recreational | Business plan | #investors attracted | 1 investor | SMC Process. Evaluation and appointment | Signing of MOA | Monitoring of implementation MOA | Monitoring of implementation MOA | Appoitnment letter nd MOA | 0 | 120000 | 120000
| Facilitate operationalisation | Human resources | Enagemnets meetings | Job creation . Imporved | Agri-park | Approved plan | #Investors secured | 1 investor (DRDMR) | 1 enagement held with DRDLR | 1 enagements held with DRLDR | 1 Enaggement held with DRLDR | 1 enagagement with DRDLR | Minutes/attedence register | 0 | 100000 | 100000
[5 empty] | Bee Keeping | Two Existing informal bee keeping projects | 2x Bee Keeping project supported | N/A | N/A | Engage Stake holders | Identify Partners | Visit Existing projects | Minutes/attedence register | 0 | 100000 | 100000
[5 empty] | Tourism Route Development | SDM Tourism Strategy | 4x Tourism project packaging and marketing | Tourism route | N/A | N/A | Identify tourism attraction that are ready and that are not ready | Packaging of tourism Guide Map | Tourism guide map | 0 | 150000 | 150000
| Appoint consultant for accreditation | Financial resources | Accrediation certificate | skills development | Accreditation with SETA | Application | #Finalisation of Agri SETA and LGSETA accreditation and MOU | 2 SETA accreditation LGSETA and Agri SETA | *Assesment of training facilities Agri-Seta *application for LG SITA | *Assesment for LG SETA | *Signing of MOU for Agr-Seta and LG SETA | Training facilitation | certificates and MOU | 0 | 30000 | 30000
| Facilitate registration process | Human & resources | registration certificates | trading rights | SDA Mining and Construction company | Board resolution | # Registration and Profiling of the companies | 2 registered and profiled companies | *Finalise regstration with statutory bodies | profile the companies | identify and forge partnerships | identify & forger partnerships | certificates and profiles | 0 | 0 | 0
| Monitoring and Evaluation of SLP and SPP | Human resources | Minutes/reports | compliance to mining charter | SLP and SPP | Board resolution | Improved implementation of SLP and SPP | 4 implementation of SLP and SPP | 1 enagement held with DMR&Mining houses | 1 engagement with DMR&Mining houses | 1 enagement with DMR & Mining houses | 1 enagenment with DMR &Mining houses | Minutes/attedence register | 0 | 0 | 0
| Implementation of MOU with MINTEK | Human&financial resources | Report | Enhanced knowledge/information | MINTEK | MOU | Implementation of the MOU | Research Report / Feasibility Study | TOR's and project plan | Draft report | Final draft | submission of report to SDA board and shareholder | Research report and Minutes | 0 | 0 | 0
| Facilitate local participation | Human reources | Investors | job creation/enahnces local manufacturing | Mining Input Supplier Park | Glencow MISP | # engagements held with local participation | 4 operation of the Mining Input Supply Park | 1 enagement with LEDA/DTI and Glencore | 1 enagement with LEDA/DTI&Glencore | 1 enagagement with LEDA/DTI/Glencore | 1 engagement with LEDA/DTI/Glencore | Minutes/attedence register | 0 | 0 | 0
| Facilitate appointment of private investor | Human reources | developer | Revenue generation | Erf 488 portion 1 of 5 land development | Evaluation report | #private investor appointed | 1 investor appointed | Land transfer | Appoitnment of developer/investor | Iimplementation | Implementation | Title Deed and reports | 100000 | 0 | 100000
| Facilitate stakeholder engagements | Human& financial resources | Implementation of commuications strategy | improved stakeholder engagement | Stakeholder management | *By-law , *shareholder compact | # of engagements held with the public | 1 engagement (AGM) | *website revamping *newsletter | *community/stakoeldher meetings *newsletter | *newsletter | *Annual General meeting | Reports and website | 100000 | -30000 | 70000
[5 empty] | Website Development and Management | SDA Communication strategy | Corporate Identity | #Website and corporate Identity manual | N/A | N/A | Develop ToR's for new website * appointment of website developer | Launch the Website development draft Corporate Idedtity Manual | Website and corporate Identity manual | 0 | 120000 | 120000
[5 empty] | Recycling project (Green Econopmy) | SDA Tyre Recycling study | 1x recycling project facilitated | N/A | N/A | N/A | Obtaining a list of recycling projects within SDM | Issue tender notice for applications | Application documents for recycling project | 0 | 125000 | 125000
[5 empty] | Conversion from Pty to SOC | SARS exemption and Donor requirement | Conversion from PTY to SOC | State owned Company (SOC) registration | N/A | Benchmarking with similar agencies | Conversion and legal processes | Registration | Registration certificate | 0 | 50000 | 50000
| Facilitate the study/ research of Regional economic Plan | Human resources | Rsearch report | improved knowledge | Regional Economic Development Master Plan | None | Facilitation of the Master plan | 1 Development Master Plan | TOR's and project plan | Stakeholder enagements | Draft report | Final report | Regional Economic Development master Plan | 0 | 0 | 0
[5 empty] | TOTAL | [8 empty] | 300000 | 765000 | 1065000
Reasons for Adjustments
1. SDA mining and construction company to be adjusted pending clarity on the conversion from a PTY to SOE and the benchmark with other development agencies in the same industry
2. Special presidential package and Social Labour Plan to be coordinated by the District
3. Regional Economic Development Master Plan to be coordinated by the District
Green Column are the New projects