## Sheet1
MEASURABLE OBJECTIVE | STRATEGY | INPUT | OUTPUT | OUTCOME | PROJECT | BASELINE 2017/2018 | INDICATORS | ANNUAL TARGET 2018/2019 | Q2 | ACHIEVED/ NOT ACHIEVED | ACTUAL PROGRESS | CHALLENGE | REMEDIAL ACTIONS | BUDGET 2018-2019 | EVIDENCE
To secure a stable and sustainable financial base for the future of the agency. Develop/facilitate business that creates sustainable jobs. Source funds for economic concepts/projects by June 2019. | Facilitate private investor | Human resources | Investor/operationla factory | job creation * revenue generation | Factory for dry sanitation technologies | MOU | Number of factories facilitated | 1 factory constructed | Construction | Not achieved | Mou signed.*Project steering committee established | The non implementation of the factory concept due to investor raising issues of value for money as the factory only linked to emerging contractor budget | Meeting held and agreed that a comprehensive feability study be conducted so that the factory does not depent only on SDM sanitation budget but explore other items that can be manufactured. | 0 | Signed MOU
| Facilitate appointment of consultants | Human resources | TOR's | feasibility study | Fresh Produce Market | TOR’s | Number of Business plans developed | 1 business plan developed | appoint consultants | Not Achieved | MOU signed with a private investor as we opted for an option of a private investor doing the work than the SDA | Lack of funds | Engagements held with private investor, DTI and FTLM | 0 | Approved copy of feasilibity study. Approved TOR's
| Facilitate private investor | Human resources | Appointed panel of consultants | Revenue generation | Investment promotion for Flag-Boshielo Dam/Recreational | Business plan | Number of investors attracted | 1 investor | Signing of MOA | Not achieved | 3x Service providers appointed and handed business plans to review. | None | None | 0 | Appoitnment letter
| Facilitate operationalisation | Human resources | Enagemnets meetings | Job creation . Imporved | Agri-park | Approved plan | Number of Investors secured | 1 investor (DRDMR) | 1 enagements held with DRLDR | Achieved | Mintech meeting held with Department of DRDLR on the 02/11/18* construction of storage facility and warehouse is in progress for FPSU in vleisboom* 7 projects linked to vleisboom FPSU supported with production inputs | Agrihub fence construction put on hold due to land dispute | engagements held between splum and DRDLR | 0 | Minutes/attedence register
| Appoint consultant for accreditation | Financial resources | Accrediation certificate | skills development | Accreditation with SETA | Application | Number of MOU Finalised of Agri SETA and LGSETA accreditation | 2 MOU of Agri SETA and LGSETA accreditation finalised | *Assesment for LG SITA | Achieved | Agri-SETA assesed the training facilityon the 29/11/18 | None | None | 0 | certificates/appliction forms
| Facilitate registration process | Human & resources | registration certificates | trading rights | SDA Mining and Construction company | Board resolution | Number of companies registered with Registration of the company | 2 companies registered with Registration of the company | profile the companies | Not achieved | Application for reservation of name done with CIPC awaiting a feedback | The company names have been reserved with CIPC and a benchmarking exercise is being embarked on with other similar entities | The board has commissioned a benchmarking exercise to be conducted with other entities such as Limpopo mining corridor | 0 | certificates
| Monitoring and Evaluation of SLP and SPP | Human resources | Minutes/reports | compliance to mining charter | SLP and SPP | Board resolution | Improved implementation of SLP and SPP | 100% implementation of SLP and SPP | 1 engagement with DMR&Mining houses | Achieved | Meeting took place in Pretoria on the 27/11/18 | None | None | 0 | Minutes/attedence register
| Implementation of MOU with MINTEK | Human&financial resources | Report | Enhanced knowledge/information | MINTEK | MOU | Implementation of the MOU | Research Report / Feasibility Study | Draft report | Achieved | Mintek agreed to finance with the full study from Jan 2019 | None | None | 0 | Research report
| Facilitate local participation | Human reources | Investors | job creation/enahnces local manufacturing | Mining Input Supplier Park | Glencow MISP | Percentage facilitation of local participation | 100% operation of the Mining Input Supply Park | 1 enagement with LEDA/DTI&Glencore | Not achieved | LEDA has been tasked with the resposibility to take over the mining input supplier park at the provincial level and to source funding | LEDA still engaged in the process to secure funding to buy MISP from GLENCOR | discussions are at early stage with LEDA for SDA to have a role in the project | 0
| Facilitate appointment of private investor | Human reources | developer | Revenue generation | Erf 488 portion 1 of 5 land development | Evaluation report | Number of private investor appointed | 1 investor appointed | Appoitnment of developer/investor | Not achieved | the registration for the property at Groblersdal portion 1 of 5 erf 488 has been finalised. | Awaiting for the Pretoria Deeds office to issue out the deed of transfer and title deed for Sekhukhune Development Agency. | Service provider requested to fasttrack the process | 0
| Facilitate stakeholder engagements | Human& financial resources | Implementation of commuications strategy | improved stakeholder engagement | Stakeholder management | *By-law , *shareholder compact | Number of engagements held with the public | 1 engagement (AGM) | *community/stakoeldher meetings *newsletter | Not achieved | Memo was sent to SCM to appoint a service provider for website revamping | Service provider appointed by SCM could not continue to work on website due to company documents not in order | Develop new ToR's for investor friendly website | 100000
| Facilitate the study/ research of Regional economic Plan | Human resources | Rsearch report | improved knowledge | Regional Economic Development Master Plan | None | Number of master plan developed | 1 Master Plan developed | Stakeholder enagements | Not achieved | Request sent to DMR to develop ToR's* Request sent to LEDA to co-fund the project | Lack of financial and technical capacity to undertake the project | Board Chairperson and the shareholder to ascalate the matter with identified partners | 0