## Sheet1
MEASURABLE OBJECTIVE | STRATEGY | INPUT | OUTPUT | OUTCOME | PROJECT | BASELINE 2017/2018 | INDICATORS | ANNUAL TARGET 2018/2019 | Q1 | Q2 | Q3 | Q4 | EVIDENCE | BUDGET 2018-2019 | BUDGET ADJUSTMENT 2018-2019 | TOTAL BUDGET 2018-2019
Act as an engine for economic growth by diversifying& expanding local economic base. To secure a stable and sustainable financial base for the future of the agency. Develop/facilitate business that creates sustainable jobs. Source funds for economic concepts/projects | Facilitate private investor | Human resources | Investor/operationla factory | job creation * revenue generation | Factory for dry sanitation technologies | MOU | #of factories facilitated | 1 factory constructed | Signed MOU | Facilitate the Construction of the factory | Monitoring of implementation of the MOU | Monitoring of implementation of the MOU | Signed MOU and Report | 0 | 0 | 0
| Facilitate appointment of consultants | Human resources | TOR's | feasibility study | Fresh Produce Market | TOR’s | #Business plans/ Feasibility study developed | 1 business plan/ Feasibility study developed | Issue an advert | appoint consultants | conducting feasibility study/ business plan | conducting feaisbility study/ business Plan | Approved copy of business plan/ feasilibity study. Approved TOR's | 100000 | 0 | 100000
| Facilitate private investor | Human resources | Appointed panel of consultants | Revenue generation | Investment promotion for Flag-Boshielo Dam/Recreational | Business plan | #investors attracted | 1 investor | SMC Process. Evaluation and appointment | Signing of MOA | Monitoring of implementation MOA | Monitoring of implementation MOA | Appoitnment letter nd MOA | 0 | 120000 | 120000
| Facilitate operationalisation | Human resources | Enagemnets meetings | Job creation . Imporved | Agri-park | Approved plan | #Investors secured | 1 investor (DRDMR) | 1 enagement held with DRDLR | 1 enagements held with DRLDR | 1 Enaggement held with DRLDR | 1 enagagement with DRDLR | Minutes/attedence register | 0 | 100000 | 100000
[5 empty] | Bee Keeping | Two Existing informal bee keeping projects | 2x Bee Keeping project supported |  |  | Engage Stake holders | Identify Partners | Visit Existing projects |  | 0 | 30000 | 30000
[5 empty] | Tourism Route Development | SDM Tourism Strategy | 4x Tourism project packaging and marketing |  |  |  | Identify tourism attraction that are ready and that are not ready | Packaging of tourism Guide Map |  | 0 | 100000 | 100000
| Appoint consultant for accreditation | Financial resources | Accrediation certificate | skills development | Accreditation with SETA | Application | #Finalisation of Agri SETA and LGSETA accreditation and MOU | 2 SETA accreditation LGSETA and Agri SETA | *Assesment of training facilities Agri-Seta *application for LG SITA | *Assesment for LG SETA | *Signing of MOU for Agr-Seta and LG SETA | Training facilitation | certificates and MOU | 0 | 150000 | 150000
| Facilitate registration process | Human & resources | registration certificates | trading rights | SDA Mining and Construction company | Board resolution | # Registration and Profiling of the companies | 2 registered and profiled companies | *Finalise regstration with statutory bodies | profile the companies | identify and forge partnerships | identify & forger partnerships | certificates and profiles | 0 | 0 | 0
| Monitoring and Evaluation of SLP and SPP | Human resources | Minutes/reports | compliance to mining charter | SLP and SPP | Board resolution | Improved implementation of SLP and SPP | 4 implementation of SLP and SPP | 1 enagement held with DMR&Mining houses | 1 engagement with DMR&Mining houses | 1 enagement with DMR & Mining houses | 1 enagenment with DMR &Mining houses | Minutes/attedence register | 0 | 0 | 0
| Implementation of MOU with MINTEK | Human&financial resources | Report | Enhanced knowledge/information | MINTEK | MOU | Implementation of the MOU | Research Report / Feasibility Study | TOR's and project plan | Draft report | Final draft | submission of report to SDA board and shareholder | Research report and Minutes | 0 | 0 | 0
| Facilitate local participation | Human reources | Investors | job creation/enahnces local manufacturing | Mining Input Supplier Park | Glencow MISP | # engagements held with local participation | 4 operation of the Mining Input Supply Park | 1 enagement with LEDA/DTI and Glencore | 1 enagement with LEDA/DTI&Glencore | 1 enagagement with LEDA/DTI/Glencore | 1 engagement with LEDA/DTI/Glencore | Minutes/attedence register | 0 | 0 | 0
| Facilitate appointment of private investor | Human reources | developer | Revenue generation | Erf 488 portion 1 of 5 land development | Evaluation report | #private investor appointed | 1 investor appointed | Land transfer | Appoitnment of developer/investor | Iimplementation | Implementation | Deed and reports | 100000 | 0 | 100000
| Facilitate stakeholder engagements | Human& financial resources | Implementation of commuications strategy | improved stakeholder engagement | Stakeholder management | *By-law , *shareholder compact | # of engagements held with the public | 1 engagement (AGM) | *website revamping *newsletter | *community/stakoeldher meetings *newsletter | *newsletter | *Annual General meeting | Reports and website | 100000 | 30000 | 130000
[5 empty] | Website Development and Management | SDA Communication strategy |  |  |  |  | Develop ToR's for new website * appointment of website developer | Launch the Website development draft Corporate Idedtity Manual |  | 0 | 120000 | 120000
[5 empty] | Recycling project (Green Econopmy) | SDA Tyre Recycling study | 1x recycling project facilitated |  |  |  | Obtaining a list of recycling projects within SDM | Issue tender notice for applications |  | 0 | 125000 | 125000
[5 empty] | Conversion from Pty to SOE | [8 empty] | 0 | 50000 | 50000
| Facilitate the study/ research of Regional economic Plan | Human resources | Rsearch report | improved knowledge | Regional Economic Development Master Plan | None | Facilitation of the Master plan | 1 Development Master Plan | TOR's and project plan | Stakeholder enagements | Draft report | Final report | Regional Economic Development master Plan | 0 | 0 | 0
The red colum are the project falling off from the SDBIP and the green are the new project