## Annual procurement plan 2025-26
ANNUAL PROCUREMENT PLAN 2026/27 FINANCIAL YEAR
| Name of municipality | Sekhukhune District Municipality
| Name of Accounting Officer / Delegated Officer | Mr. Kgwale MM
Signature of Accounting Officer/Delegated
| Telephone Number and e-mail addresss | kgwalem@sekhukhune.gov.za
Ref No. | Description | Specification | Estimated Cost Rv /Budgeted Amount | Budgeted Amount |  | Procurement Method | Date of Advert | BEC | BAC | Appointment Letter/Contract Sign Date | Contract Completion Date | Comments | Remarks
INFRASTRUCTURE AND WATER SERVICES DEPARTMENT
1 | Groblersdal to Luckau BWS Phase 3 | Groblersdal to Luckau BWS Phase 3 | 127531333.18 | 127531333.18 | Open Tender | MIG | 27/02/2026 | 24/4/2026 | 11/05/2026 | 10/06/2026 |  | Consultant currently busy finalising the detailed design |  |  | Open Tender
2 | Refurbishment of Groblersdal WWTW Phase 1 | Refurbishment of Groblersdal WWTW Phase 1 | 37084989 | 18500000 | Panel (RFQ) | MIG | N/A | N/A | N/A | N/A |  | TR awaiting DWS approval
3 | Roosenekal Wastewater Treatment Plant | Roosenekal Wastewater Treatment Plant | 13160085 | 11000000 | Panel (RFQ) | MIG | N/A | N/A | N/A | N/A |  | TR being revised by PSP before DWS can approve
4 | Elanskraal WWTW | Elanskraal WWTW | 13315433.7 | 11000000 | Panel (RFQ) | MIG | N/A | N/A | N/A | N/A |  | TR awaiting DWS approval
5 | Marble hall WWTW | Marble hall WWTW | 17362294.05 | 12000000 | Panel (RFQ) | MIG | N/A | N/A | N/A | N/A |  | TR awaiting DWS approval
6 | Motetema Wastewater Treatment Plant | Motetema Wastewater Treatment Plant | 21430288 | 15000000 | Panel (RFQ) | MIG | N/A | N/A | N/A | N/A |  | TR being revised by PSP before DWS can approve
7 | Monsterlus Wastewater Treatment Plant | Monsterlus Wastewater Treatment Plant | 12864952 | 7000000 | Panel (RFQ) | MIG | N/A | N/A | N/A | N/A |  | TR being revised by PSP before DWS can approve
8 | Praktiseer Wastewater Treatment Plant | Praktiseer Wastewater Treatment Plant | 38198571 | 15000000 | Panel (RFQ) | MIG | N/A | N/A | N/A | N/A |  | TR awaiting DWS approval
9 | Penge Wastewater Treatment Plant | Penge Wastewater Treatment Plant | 20562776 | 10798000 | Panel (RFQ) | MIG | N/A | N/A | N/A | N/A |  | TR awaiting DWS approval
10 | Burgersfort Sewer Reticulation Network (Rehabilitation and/or refurbishment of Burgersfort Pump Stations and Manholes) | Burgersfort Sewer Reticulation Network (Rehabilitation and/or refurbishment of Burgersfort Pump Stations and Manholes) | 10888380 | 16500000 | Panel (RFQ) | MIG | N/A | N/A | N/A | N/A |  | TR awaiting DWS approval
11 | Mapodile sewer Oxidation Ponds | Mapodile sewer Oxidation Ponds | 27358657 | 18000000 | Panel (RFQ) | MIG | N/A | N/A | N/A | N/A |  | TR awaiting DWS approval
12 | Jane Furse Oxidation Ponds | Jane Furse Oxidation Ponds | 82000000 | 8000000 | Panel (RFQ) | MIG | N/A | N/A | N/A | N/A |  | TR awaiting DWS approval
13 | Kgotlopong Water Supply (Work Package 2) | Kgotlopong Water Supply (Work Package 2) | 44808875.83 |  | Open tender | WSIG | 26/02/2026 | 24/03/2026 | 02/04/2026 | 2026-10-04 |  | Consultant to submit preliminary designs to the client.
14 | Eenzaam Water Supply (Work Package 2) | Eenzaam Water Supply (Work Package 2) | 43416637.5 |  | Open tender | WSIG | 26/02/2026 | 24/03/2026 | 02/04/2026 | 2026-10-04 |  | Consultant to submit preliminary designs to the client.
15 | Tsopaneng Water Reticulation | Tsopaneng Water Reticulation | 65695010.4 | 5000000 | Open tender | WSIG | 30/10/2026 | 01/12/2026 | 2027-12-02 | 15/03/2027 |  | TR and BP awaiting DWS approval
OFFICE OF THE EXECUTIVE MAYOR | OFFICE OF THE SPEAKER
1 | Call Centre Revamp | Revamping of the call center | 1200000 | 1200000 | Open tender | Equitable Share | N/A | N/A | N/A | N/A | N/A | Still to be advertised
OFFICE OF THE SPEAKER
| N/A | NONE
CORPORATE SERVICES
INFORMATION AND COMMUNICATION TECHNOLOGY
1 | Electronic Record Management System | Electronic Record Management System | R2,500,000.00 | R2,500,000.00 | Open tender | Equitable share | 2026-03-01 | 2026-06-01 | 2026-07-01
2 | Disaster Recovery Site | Disaster Recovery Site | R7,000,000.00 | R7,000,000.00 | Open tender | Equitable share | 2026-03-01 | 2026-04-01 | 2026-06-01
LABOUR RELATIONS
N/A
EMPLOYEE ASSISTANCE PROGRAMME
1 | Servicing of fire horse Reels | Servicing of fire horse Reels | 350 000.00 | 350 000.00 | Open tender | Equitable share | 15/02/2026 | 20/03/2026 | 30/03/2026 | N/A |  | Still to be advertised
HUMAN RESOURCE MANAGEMENT
N/A
AUXILLARY SERVICES
1 | Purchase of Vehicles and machinery |  | 5000000 | 5000000 | Transversal Contract | Equitable Share | N/A | N/A | N/A | N/A |  | Appointed National Treasury
2 | Purchase of Mobile offices |  | 2000000 | 2000000 | Open tender | Equitable Share | 30/07/2026 | 30/09/2026 | 15/10/2026 | 30/10/2026 |  | Contract in place
BUDGET AND TREASURY
ASSET MANAGEMENT
REVENUE MANAGEMENT
NONE
ECONOMIC DEVELOPMENT AND PLANNING
LOCAL ECONOMIC DEVELOPMENT
SPATIAL PLANNNING AND GIS
2 | Appointment of Service Provider -SMMEs and Cooperatives support | Tender | 3000000 | 3000000 | Tender | Equitable shares | 2026-07-21 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-10-01 |  | 2026-10-01 | 2027-03-31
COMMUNITY SERVICES
EMERGENCY SERVICES
1 | B& A Air Pollution : Air Quality Modelling & Met Station |  | 800 000.00 | 900 000.00 | Tender | Equitable Share | 26/07/2026 | 26/09/2026 | 26/10/2026 | N/A | 26/10/2026 | Still to be advertised
2 | I & P Argricultural , Bating Materials |  | 300 000.00 | 350000 | Tender | Equitable Share | 26/07/2026 | 26/09/2026 | 26/10/2026 | N/A | 26/10/2026 | Still to be advertised
3 | Maintenance of Equipement |  | 500 000.00 | 550 000.00 | Tender | Equitable Share | 26/07/2026 | 26/09/2026 | 26/10/2026 | N/A | 26/10/2026 | Still to be advertised
4 | MHS Uniform |  | 700 000.00 | 800 000.00 | Tender | Equitable Share | 26/07/2026 | 26/09/2026 | 26/10/2026 | N/A | 26/10/2026 | Still to be advertised
5 | EMS Machinery & Equipment |  | 5500 000.00 | 6000 000.00 | Tender | Equitable Share | 26/07/2026 | 26/09/2026 | 26/10/2026 | N/A | 26/10/2026 | Still to be advertised
6 | MHS Equipments |  | 1 800 000.00 | 2000 000.00 | Tender | Equitable Share | 26/07/2026 | 26/09/2026 | 26/10/2026 | N/A | 26/10/2026 | Still to be advertised
MUNICIPAL HEALTH SERVICES
1 | Lab Services | Lab Services | 3000000 | 3000000 | Tender | Equitable Share | 26/07/2026 | 26/09/2026 | 26/10/2026 | N/A | 26/10/2026 | Still to be advertised