## Sheet1 (2)
2017/18 IDP
2017-18 SDBIP - I&WS - Q2 2017 MONTHLY REPORT
MEASURABLE OBJECTIVE | INPUT | OUTPUT | OUTCOME | PROJECT | BASELINE 2016/2017 | KEY PERFORMANCE INDICATORS | ANNUAL TARGET 2017/2018 | Planned Monthly Activities for Q2 2017 | PROGRESS (Achieved/not achieved) | ACTUAL PROGRESS | CHALLENGES | REMEDIAL ACTION | BUDGET 2017-2018 "R" | PoE
PLANNING, REGULATION AND GOVERNANCE
To develop WC/WDM Strategy for SDM by June 2018 | WSDP and Water Master Plan | Document on Water Conservation and Demand Management | Strategy on Water Conservation and Demand Management | Development of Water Conservation and Water Demand Management Plan | Water Services Master Plan and WSDP developed in 2014/15 and the 2015/16 FY respectively | Number of WC/WDM Strategy developed | One WC/WDM Strategy developed | PSp to produce Status Quo Report. Make final inputs and comments before the draft WC/WDM strategy is taken to Council | Not Achieved | Busy preparing RFP(Request for proposal) to be completed by end of January | Delay in preperation of RFP | Invite WC/WDM specialist to do presentations | 800000 | Draft WC/WDM Strategy
To upgrade Groblersdal sewer pump station by June 2018 | Bulk sewer intervention plan Jan 2015 | Sewer upgrade plan | Enhansed sewer system | Upgrading of Groblersdal sewer pump station. | 15% upgrade of the outfall sewer system took place in 2015/16 FY | Percentage of sewer pumpstation upgrade completed | 50% Upgrade of Sewer pump station( 2 pumps refurbished, screens upgrading & alarm system); | After sewer assessment and flow meter installation the PSP will then Compile the following: Details Report. Hydraulic Modeling of sewer line Details . Recommendations. Develop a report on compliance matters relating to the upgrading of the sewer pump station | Not Achieved | Revised targets has been submitted | Service provider is waiting for payments to be able to go ahead | Payment to be made to PSP | 500000 | Progress report and Status quo report
To develop feasibility study for the upgrade of Marble Hall sewer bulk line and pumpstation by June 2018 | None | Flows and levels | Enhansed sewer system | Development of Feasibilty study in Marble Hall Town for bulk sewer and pump station | Service provider appointed during 2015/16 FY | Number of feasibility studies conducted | One feasibility study completed for Marble Hall sewer line and pumpstation | The PSP to condut assessment of outfall sewer pipe using the CCTV Survey technology Assess whether the Terms Of Reference for Marble Hall Town bulk sewer and pump station comply with relevant requirements | Not Achieved | Scoping report received | Funding not adequate to complete scope of works | Combine the funding of Groblersdal Sewer and Marble Hall Sewer and complete Groblersdal Sewer and allocate additional budget | 300000 | Feasibility study report
To conduct condition assessment and develop O & M plan by June 2018 | Asset register | Document | Preventative and reactive O&M plan | Conduct Condition Assessment and develop Operation and maintenance plans | Terms of reference developed and incorporated into the asset management plan contract and tender advertised for the PSP appointment | Percentage conduct of Condition assessment and 0 & M plan developed | 60% conduct of Condition assessment and 0 & M plan developed | Phase 1: Status Quo/ Condition Assessment. Determine current O&M workflow processes. Determine completeness of asset register with O&M staff. Determine procurement and costs associated with current O&M practices. Compilation of a status quo/ gap analysis report. Assess whether the Terms Of Reference for the development of O & M comply with relevant requirements | Achieved | The O&M plan for the valve components have been done and submitted | There is no preventative maintenance schedule for valves | A schedule has to drawn up and adhered to | 800000 | Progress report
To conduct feasibility study and develop Technical reports for submission to DWS by 30 June 2018 | Assignment of PSP to do the Technical Reports | Technical Reports | MIG registered Projectss | Conduct Feasibility studies and develop technical reports | WSDP, IDP & Bulk Water Service Master completed in Plan 2014 | Number of of feasibility studies conducted and technical reports developed for Leballo South Villages Phase Two | 7 feasibility studies conducted and technical reports developed for Leballo South Villages Phase Two | Source Development if no surface water available: Sighting ,Drilling of boreholes, testing and equiping of the boreholes Develop a report on compliance of the draft feasibility studies and technical reports with relevant requirements | Not Achieved | - PSP are busy conducting studies. - 4x Technical Report have been submitted to SDM | Delay of appointment of PSP | Fast track the implementation plan by PSP | 5000000 | Letters, Minutes of Meeting and Technical Reports
PROJECT MANAGEMENT UNIT
REGIONAL BULK INFRASTRUCTURE GRANT (RBIG)
To construct pipeline from Burgersfort to Dresden pump station by June 2018 | Financial and Human Resource | Bulk supply line | Improved water supply | Construction of Mooihoek bulk water supply phase 4E | Mooihoek bulk water supply phase 4D completed | Number of Kilometers of bulk pipeline constructed | 3 Kilometers of bulk pipeline constructed | Site establishment and 0.2km pipeline constructed | Not Achieved | Tender Evaluated to serve on the BEC | None | To speed up supply chain process and appointment of contractor. | 30000000 | Progress reports on Mooihoek phase 4E
To construct reservoir at Burgersfort by June 2018 | Financial and Human Resource | 2 X 5 Ml concrete reservoirs | Improved water supply | Mooihoek bulk water supply phase 4B | 1 x 5ML resevoir completed Mooihoek Phase 4A | Percentage reservoir constructed | 70% , 1 X 5 Ml concrete reservoir constructed | 20% Construction of Reservoirs | Not Achieved | Contractor been appointed busy with complaints in terms of construction regulation | Contractor not complying with construction regulations. | Contractor tocome with construction acceleration plan. | 18000000 | Progress reports on Burgersfort reservoirs
To construct bulk pipeline from Praktiseer to Motodi by June 2018 | Financial and Human Resource | Bulk supply line | Improved water supply | Mooihoek bulk water supply phase 4F | Mooihoek bulk water supply phase 2 completed | Number of Kilometers of bulk pipeline constructed | 4 Kilometers of bulk water pipeline constructed | Site establishment and 0.1km pipeline constructed | Not Achieved | Tender Evaluated to serve on the BEC | None | Enquire the with DWS National on confirmation of budget | 29000000 | Progress reports on Praktiseer to Motodi bulk pipeline
To construct bulk pipeline from Praktiseer to Alverton by June 2018 | Financial and Human Resource | Bulk supply line | Improved water supply | Mooihoek bulk water supply phase 4G | Mooihoek bulk water supply phase 2 completed | Number of Kilometers of bulk pipeline constructed | 4 Kilometers of bulk water pipeline constructed | Site establishment and 0.1km pipeline constructed | Not Achieved | Tender served on the BSC | Verify funding agreements with DWS before advert | Enquire the with DWS National on confirmation of budget | 28000000 | Progress reports on Praktiseer to Alverton bulk pipeline
To construct pumping pipeline from T-off of Makgeru to the new 10ML reservoir at Schoonoord, construction of gravity pipeline. | Financial and Human Resource | Bulk supply line | Improved water supply | Nebo BWS Makgeru to Schoonoord BWS | Reservoir is 55% completed. *Pipeline is 45% completed | Percentage bulk pipeline constructed and reservoir completed. | 100% bulk pipeline constructed and reservoir completed. | *70% of bulk pipeline constructed *75% of Reservoir completed. | Achieved | The overall progress is at 69%. 56% on the pipeline and 72% on the resevoir. | Delay of procurement of material by DWS constructions | Acceleration Plan | 55000000 | Progress report and practical completion certificate A14
To connect mechanical and Electrical (M & E) for the extensions to the Groblersdal Water Treatment Works by June 2018. | Financial and Human Resource | Mechanical & Electrical Installations | Improved water supply | Moutse BWS Project ( 13 &14) | The upgrading of WTW is completed | Percentage M&E components installed | 100% M&E components Installed | 90% Installation of pumps and electrical fittings. | Not Achieved | Raw water pump station : 100% Mechanical scope: 100% Electrical scope: 100% Clear water pump station : 96% Mechanical scope: 100% Electrical scope: 95% Booster pump station : 96% Mechanical scope: 100% Electrical scope: 86% | Outstanding Scope of Works Equipment for new filters, Backwash pumps, Air blowers, Clarifier sludge draw-off valves, Chlorine dosing equipment, Flow measuring equipment, Lime dosing equipment, Coagulant dosing equipment and Electrical installation | Extension of time approved. Enquire the with DWS National on progress in awarding orders to sub contracts | 60000000 | Progress reports on electrical & mechanical components
To construct bulk pipeline and valve chambers by June 2018 | Financial and Human Resource | Bulk supply line | Improved water supply | Moutse BWS Project ( 7 to 12) | Bulk pipelines and valve constructed up 54%. | Percentage bulk pipeline constructed. | 100% bulk pipeline constructed. | *70% of bulk pipeline constructed. | Not Achieved | Project 5 : 89% Project 7 : 95% Project 8 : 97% Project 9 : 91% Project 10: 63% Project 11 : 66% Project 12 : 75% Overall pipe laying progress : 100% Overall chamber progress : 92 | Delay of delivery for project 5 fittings. Access to site required from commercial farmers to Project 10. | Extension of time approved. Enquire the with DWS National on progress in awarding orders to sub contracts |  | Progress reports
WATER QUALITY
To generate water quality reports by June 2018 | WSDP and Water Master Plan | Regulatory Compliance | Improved service delivery | Generation of Water Quality Reports | 10 reports generated | Number of water quality reports generated | 12 water quality reports generated | 3 X water quality report | Achieved | 3 X water quality report | None | None | 12000000 | Water quality reports
To conduct Full SANS 241 analysis by June 2018 | WSDP and Water Master Plan | Regulatory Compliance | Improved service delivery | Conduct Full SANS 241 Water Quality Analysis | Signed CSIR SLA in 2015/16 FY | Number of Full SANS 241 analysis conducted | 1 Full SANS 241 analysis conducted | Conduct & generate the water quality analysis report | Achieved | Conduct & generate the water quality analysis report | Planned for the forth quorter | None |  | Full SANS 241 report
To purchaseLaboratories Chemical by June 2018 | WSDP and Water Master Plan | Regulatory Compliance | Improved service delivery | Purchase of Lab chemicals | Term contractors appointed | Percentage of lab chemical purchased | 100% lab chemical purchased | 50% of lab of budget spent on lab chemicals purchased | Not Achieved | 30% of lab of budget spent on lab chemicals purchased | Late submission of specification | Submission of specification on time to fast track the process |  | Delivery notes and tax invoices for delivered lab chemicals
To participate in Blue and Green Drop Certification programme by June 2018 | WSDP and Water Master Plan | Regulatory Compliance | Improved service delivery | Plants participation in Blue and Green Drop Cerification Programme | 12 water treatment works participating in Blue Drop Certicification Programme in place | Number of plants participating in Blue and Green Drop Participation Programme | 60 water treatment works participating in Blue Drop and 40 wastewater treatment works participating in Green Drop Certification Programme | 5 water treatment works participating in Blue Drop and 3 wastewater treatment works participating in Green Drop Certification Programme | Achieved | 5 water treatment works participating in Blue Drop and 3 wastewater treatment works participating in Green Drop Certification Programme | More funds is needed to ensure compliance coverage of WTW and WWTW | Avail funds during budget adjustment |  | Blue and Green Drop Annual Report
OPERATION AND MAINTENANCE
To resolve registered sanitation incidents within 14 days. | Financial and Human Resource | Reduced sewer spillage and environmental pollution | Improved green drop status | Sanitation incidents | 90% registered sanitation incidents | Percentage registered sanitation incidents resolved within 14 days | 90% registered sanitation incidents resolved within 14 days | Recording the sewer incidents reported and resolved 90% of them within 14 days. | Achieved | Recording the sewer incidents reported and resolved 100% of them within 14 days. | Shortage of material | Bulk purchase of material at stores | 30000000 | Monthly reports
To resolve registered water incidents within 14 days. | Financial and Human Resource | Reduced non-revenue water losses | Improved no drop status. | Water incidents | 90% registered water incidents | Percentage registered water incidents resolved within 14 days | 90% registered water incidents resolved within 14 days | Recording the water incidents reported and resolved 90% of them within 14 days. | Achieved | Recording the water incidents reported and resolved 92% of them within 14 days. | Shortage of material | Bulk purchase of material at stores |  | Monthly reports
To render Tankering services by June 2018 | Financial and Human Resource | Consistent supply of water | Improved water supply | Delivery of Potable Water | 90% of tankering services rendered | Pecentage tankering services rendered | 90% of tankering services rendered in areas with no water source or infrastructure | Delivering water through tankers to 90% of the areas without water source or infrastructure. | Not Achieved | Delivering water through tankers to 80% of the areas without water source or infrastructure. | Shortage of water tankers | Procure additional water tankers | 32000000 | Monthly Water delivery records and reports
To provide diesel consistently to diesel driven machines by June 2018 | Financial and Human Resource | Consistant water supply. | Reliable water supply. | Supply of Diesel | 80 000 ℓ of diesel supplied | Number of Litres of diesel supplied annually | 80 000ℓ of diesel supplied annually. | Supplying 20 000ℓ of diesel to the areas where their boreholes are diesel driven pumps. | Not Achieved | Supplying 9 604ℓ of diesel to the areas where their boreholes are diesel driven pumps. | More pumps and motors are converted to electricity | None | 1750000 | Monthly reports
To provide Petrol consistently to petrol driven machines by June 2017 | Financial and Human Resource | Consistant water supply. | Reliable water supply. | Supply of Petrol | 5000 ℓ petrol supplied | Number of Litres petrol supplied annually. | 1200 ℓ of petrol supplied annually. | Supplying 300 ℓ of petrol to the areas where their boreholes are petrol driven pump. | Not Achieved | Supplying 18ℓ of petrol to the areas where their boreholes are petrol driven pump. | More pumps and motors are converted to electricity | None |  | monthly reports
To provide Oil consistently to diesel and petrol driven machines by June 2017 | Financial and Human Resource | Consistant water supply. | Reliable water supply. | Supply of Oil | 1500 ℓ of oil supplied | Number of Litres of oil supplied annually. | 720 ℓ of oil supplied annually. | Supplying 180 ℓ of oil to the areas where their boreholes are both diesel and petrol driven pump. | Not Achieved | Supplying 155.35ℓ of oil to the areas where their boreholes are both diesel and petrol driven pump. | More pumps and motors are converted to electricity | None |  | monthly reports
To resolve registered M & E incidents within 14 days | Financial and Human Resource | Consistent supply of water | Improved water supply | Mechanical and electrical services | 50% resolved registered M & E incidents within 14 days | Percentage of registered M & E incidents resolved within 14 days | 80% of registered M & E incidents resolved within 14 days | Recording the M & E incidents reported and resolved 80% of them within 14 days. | Achieved | Recording the M & E incidents reported and resolved 86.7% of them within 14 days. | Shortage of material | Bulk purchase of M & E material at stores | 3500000 | Monthly reports
To install bulk water meters by June 2018 | Financial and Human Resource | Consistent supply of water | Improved water supply | Installation of Bulk water meters . | Reservoirs in place | Number of bulk water meters installed by June 2018 | 8 bulk water meters installed | Preparation of terms of reference for the installation of bulk meters to appoint PSP. | Achieved | Preparation of terms of reference for the installation of bulk meters to appoint PSP. | None | None | 2000000 | Progress reports
To purchase Mℓ bulk water by June 2018 | Financial and Human Resource | Consistent supply of water | Improved water supply | Mℓ Bulk Water Purchases | 10 062 Mℓ of bulk water supplied. | Number Mℓ of water purchased | 10 062Mℓ of water purchased | Purchasing 2 515.5 Mℓ of water from water services providers. | Not Achieved | Purchasing 2 214 479 Mℓ of water from water services providers. | Some readings were submitted late | Improve on the submission time | 64000000 | Delivery registers and Tax invoices
WATER SERVICE INFRASTRUCTURE GRANT (WSIG) PROJECTS
To complete Tukakgomo water reticulation by June 2018 | Human Resource | 3000m of 65mm diameter pipeline and one steel tank constructed. | Improved service delivery | Tukakgomo water intervention and refurbishment. | 1 borehole drilled and equipped. | Percentage completion of Tukakgomo water reticulation. | 100% completion of Tukakgomo water reticulation. | 90% pipeline constructed | Not Achieved | Draft tender document for comments was Re-submitted on the 19th of December 2017. Awaiting for comments. | Delayed appointment of Professional Service Providers | Expedite the approval of the draft tender document and the appointment of the contractor. | 4500000 | Progress report and practical completion certificate
To construct bulk pipeline by June 2018 | Human Resource | 5.5Km of bulk pipeline constructed | Improved service delivery | Mahlwakwena to Mapodile pipeline | The command reservoir at Mahlwakwena is completed. | Number of Kilometers of bulk pipeline constructed | 5.5Km of bulk pipeline constructed | Testing & Commisssioning | Not Achieved | The Scoping Report was Re-submitted on the 5th of December 2017 and it was approved. The consultant to submit the draft tender document. | Late appointment of Professional Service Providers. | Expedite the submission of the draft tender document and the appointment of the Contractor. | 3000000 | Progress report and practical completion certificate
To construct abstraction point at Mampuru village by June 2018. | Human Resource | 100% of Abstruction point completed. | Improved service delivery | Mampuru Water abstraction and reticulation network | 1,5ML WTW in place and abstraction point washed away. | Percentage Abstraction point constructed. | 100% Abstraction point constructed. | 30% Construction of Abstraction point | Not Achieved | Draft tender document for comments was Re-submitted on the 19th of December 2017. Awaiting for comments. | Delayed appointment of Professional Service Providers | Expedite the approval of the draft tender document and the appointment of the contractor. | 3500000 | Progress report and practical completion certificate
To construct pipeline by June 2018 | Human Resource | 7Km kilometers of pipeline constructed | Improved service delivery | Rutseng Water Intervention | Skeletal water infrastructure in place | Number of Kilometers of pipeline constructed | 7km of pipeline constructed | 7km pipeline constructed | Not Achieved | Preliminary design report was referred back with comments and it was re-submitted on the 18th November 2017, then it was approved and a draft tender document was submitted, waiting for approval. | Late appointment of Professional Service Providers | Expedite the approval of draft tender document and appointment of the Contractor. | 3500000 | Progress report and practical completion certificate
To construct bulk pipeline by June 2018 | Human Resource | 3.5km of bulk pipeline constructed | Improved service delivery | Phiring Water Intervetion | The existing booster pump station is vadalised. | Number of Kilometers of bulk pipeline constructed | 3.5km of bulk pipeline constructed | Testing & Commisssioning | Not Achieved | Consultants submitted the scoping report for approval and Geohydrologist was sent to site for Geohydrlogical studies. | Late appointment of Professional Service Providers | Expedite the approval of the scoping report and the appointment of the contractor. | 3500000 | Progress report and practical completion certificate
To complete Mamatjekele Package Plant by June 2018 | Human Resource | Developed source | Improved service delivery | Completion of Mamatjekele Package plant | The borehole is equipped but producing polluted water. | Percentage completion of Mamatjekele Package Plant | 100% completion of Mamatjekele Package Plant | 30% Installation of Package Plant | Not Achieved | Consultant to submit the Geohydrological results by 06th of December 2017. Consultant to submit the draft documents and preliminary designs report. Contractor appointed to proceed with the WTW Package Plant. | Late appointment of Professional Service Providers | Expedite the approval draft tender document and the appointment of the Contractor. | 3000000 | Progress report and practical completion certificate
To complete Jane Furse RDP Package Plant by June 2018 | Human Resource | Package plant | Improved service delivery | Jane Furse RDP Package plant | The high yield borehole is equipped but producing poluted water. | Percentage completion of Mamatjekele Package Plant | 100% completion of Jane Furse RDP Package Plant | 30% Installation of Package Plant | Not Achieved | Geohydrological study was completed and draft tender documents submitted and it was approved with comments. | Late appointment of Professional Service Providers | Expedite the appointment of the Contractor. | 2700000 | Progress report and practical completion certificate
To construct pipeline at Apel Cross RDP by June 2018 | Human Resource | Reticulation network | Improved service delivery | Apel Cross RDP Reticulation network | The high yield borehole is equipped but not connected to any infrastruture. | Number of Kilometers of pipeline constructed | 7 kilometers of pipeline constructed | 7km pipeline constructed | Not Achieved | The scoping report was approved and awaiting for water quality and yield tests results from the Geohydrologist. Consultant submitted the draft tender document and preliminary design report by the 07th December 2017. | Late appointment of Professional Service Providers. | Expedite the approval of draft tender documents and appointment of the Contractor. | 2000000 | Progress report and practical completion certificate
To complete Moretsele water reticulation by June 2018 | Human Resource | Reticulation network | Improved service delivery | Moretsele water rising main | No formal water infrastrucutre in place. | Number of Kilometers of pipeline constructed | 2 kilometers of pipeline constructed | Source development | Not Achieved | Consultants re-submitted the scoping report for approval. Geohydrological studies have been done and Consultants is waiting for Geohydrolocal Report and Results. | Late appointment of Professional Service Providers | Expedite the appointment of the Contractor. | 2000000 | Progress reports
To test and commission bulk pipeline from Malekane WTW to Jane Furse 25Ml command reservoir by June 2018. | Human Resource | Bulk supply line | Improved service delivery | Nebo Phase 1A testing and comissioning | Nebo Phase1A completed but not commisioned. | Number of Kilometers of pipeline commissioned | 33km bulk pipeline tested and commissioned. | RBIG FUNDED | Not Achieved | *Scope was revisited and presented on the 1st November 2017. Consultant awaiting for comments. | Late appointment of PSP. | To fast track the appointment of the Contractor. | 13000000 | Monthly progress reports and practical completion certficate
To develop water source and prepare Technical report at villages around Uitspanning area by June 2018. | Human Resource | Developed source | Improved service delivery | Uitspanning Water Source developmement | Groblersdal WTW and Moutse bulk pipeline in progress. | Number of water source developed and no of technical reports prepared. | 2 water sources developed and technical reports prepared . | Testing & Commisssioning | Not Achieved | Consultant's briefing on the 20th September 2017. A scoping report was approved with option A on the 19th of October 2017. Geohydrological studies have been done and the Consultants is waiting for tests results. | Late appointment of Professional Service Providers | Expedite the appointment of the Contractor. | 2000000 | Monthly reports and Technical report
To develop water source and prepare technical report at villages around Madibong village by June 2018. | Human Resource | Developed source | Improved service delivery | Madibong Water Supply | Jane furse 25Ml completed. | Number of water source developed and no of technical reports prepared. | 4 water source developed and no of technical reports prepared. | Testing & Commisssioning | Not Achieved | Consultants submitted the scoping report for approval and it was referred back with comments. Survey was completed on the 27th November 2017. Geohydrologist to be sent to site for geohydrolocal studies. | Late appointment of Professional Service Providers. | Expedite the appointment of the Contractor. | 1500000 | Monthly reports and Technical report
To construct pipeline by June 2018. | Human Resource | Reticulation network | Improved service delivery | Uitvlught Water Supply | Groblersdal WTW and Moutse bulk pipeline in progress. | Number of Kilometers of pipeline constructed | 1.7 kilometers of pipeline constructed | Source development | Not Achieved | Geohydrological studies have been completed and Consultant to submit the preliminary designs repport and draft tender document. | Late appointment of Professional Service Providers | Expedite the appointment of the Contractor. | 3000000 | Monthly reports
To construct pipeline by June 2018. | Human Resource | Reticulation network | Improved service delivery | Keerom Water Supply | Groblersdal WTW and Moutse bulk pipeline in progress. | Number of Kilometers of pipeline constructed | 2.8 kilometers of pipeline constructed | Source development | Not Achieved | Geohydrological studies have been completed and Consultant to submit the preliminary designs repport and draft tender document. | Late appointment of Professional Service Providers | To fast track the appointment of the Contractor. | 3000000 | Monthly reports
To construct pipeline by June 2018. | Human Resource | Reticulation network | Improved service delivery | Diphaganeng Water Supply | The borehole is equiped and connected to JoJo tank. | Number Kilometers of pipeline constructed | 2.3 kilometers of pipeline constructed | Source development | Not Achieved | Geohydrological studies have been completed and Consultants submitted draft tender document for approval on the 19th December 2017. | Late appointment of Professional Service Providers. | Expedite the approval of draft tender document and appointment of the Contractor. | 2300000 | Monthly reports
To construct pipeline by June 2018. | Human Resource | Reticulation network | Improved service delivery | Rathoke Bulk Water Supply | Groblersdal WTW and Moutse bulk pipeline in progress. | Number Kilometers of pipeline constructed | 3.2 kilometers of pipeline constructed | Approval of Scoping report | Not Achieved | Consultants re-presented the scoping report on the 21st of November 2017 and comments were made on the report for correction. | Late appointment of Professional Service Providers | Expedite the appointment of the Contractor. | 3000000 | Monthly reports
To Install household meters at Letebejane by June 2018. | Human Resource | Meters Installed | Improved service delivery | Letebejane Water meters installation | The village is fully reticulated & supplied water for 24hrs without payment. | Number of households meters installed | 450 household meters Installed. | Installation of 450 household meters | Not Achieved | Consultant's briefing on the 20th September 2017. Consultants presented scoping report on the 19th of October 2017 and it was referred back with comments. | Late appointment of Professional Service Providers | Expedite the appointment of the Contractor. | 3000000 | Monthly reports
To refurbish package plant in Tjibeng by June 2018.. | Human Resource | Package plant | Improved service delivery | Refurbishment of Tjibeng package plant | The package plant is dilapitated. | Number of package plant refurbished. | One package plant refurbished in Tjibeng . | 30% Installation of Package Plant | Not Achieved | Term contractors were Re-invited for bidding on the 14th of November 2017 and briefing cession was held on the 16th of November 2017. The bid is closing on the 5th of December 2017. Tender is awaiting for evaluation. | Delays in the implementation of the project. | Expedite the evaluation process and the appointment of the Contractor. | 3500000 | Monthly reports
To develop water souce and connect to existing reticulation by June 2018 | Human Resource | Developed source | Improved service delivery | Maebe drilling and equipping of borehole | No formal water infrastrucutre in place. | Number of water source developed | One of water source developed | Testing & Commissioning | Not Achieved | Consultants to re-submit the scoping report by the 11th December 2017 and Consultants to assign the Geohydrologist to site. | Late appointment of Professional Service Providers. | To fast track the approval for scoping report and appointment of the Contractor. | 3000000 | Monthly reports
To construct VIDP Sanitation units by June 2018 | Human Resource | VIDPs installed | Improved service delivery | Construction of Moretsele VDIP | New Infrastructure | Number of VIDP sanitation units constructed | 334 VIDP Sanitation units constructed | 20 VIDP's installed, 60 pit linnings constructed | Not Achieved | *The site was handed over on the 14th November 2017 and 30 000 bricks delivered on site. | Handover was delayed by a month due to processes of drafting and signing of the SLA with Bertrams. | Finalize appointment of Contractor. | 4500000 | Monthly reocrts
To construct pipeline by June 2018 | Human Resource | Bulk supply line | Improved service delivery | Lobethal bulk water supply | 18450m of pipeline constructed | Number of Meters of pipeline constructed | 550m of pipeline constructed | N/A | Not Achieved | *Consultant appointed under RBIG. * Project has been halted. | *Delays in finalizing the scope verifition by Consultant and confirmation by DWS. | Expedite appointments of both PSPs and Contractors | 8000000 | Monthly reocrts
To refurbish Thabampshe pump station by June 2018.. | Human Resource | Pump station refurbished and rising main pipeline tested | Improved service delivery | Thabampshe refurbishment of a pumpstation | Pump station and reservoir structure in place | Percentage refurbishment of Thabampshe water pump station ( 2 pumps, motors and electrical panel and replacement of valves and testing of rising main | 100% refurbishment of Thabampshe water pump station ( 2 pumps, motors and electrical panel completed and replacement of valves and testing of rising main | 90% Fencing completed and electrical connections | Not Achieved | *Contractor appointed and 50% physical progress on site. | *Late appointment of the contractor.* Delayed delivery of Pumps. | Expedite progress on site. | 3700000 | Monthly progress reports and practical completion certficate
To refurbish a pumpstation by June 2018 |  |  |  | Leolo Water Intervention | Delapidated pumpstation | number of pumpstation refurbished. | One pumpstation refurbished.1500 pipeline to the two boreholes installed. | Approval of Scoping report | Not Achieved | *Business Plan submitted for approval. *Consultant appointed. * Consultant busy with the scoping report. | Delayed assignment of PSP and Poor perfomance from the Consultant. | Expedite the submission of scoping report and the appointment of the Contractor. The consultant to improve on his/her perfomance. | R1 509 362 | Monthly reports
MUNICIPAL INFRASTRUCTURE GRANT (MIG)
To construct VIP Sanitation units by June 2018 within Ephraim Mogale Municipality | Financial and Human Resource | 1 020 VIP Sanitation toilets completed | Improved health and hygiene | VIP Sanitation programme phase 2.2 | 15 180 VIP Units constructed | Number of VIP sanitation units constructed | 1 020 VIP Sanitation units constructed | Finalize beneficiary list, | Not Achieved | 700 VIP units completed Reconciling all outstanding claims including cessions for suppliers. Draft tender documents submitted for further discussion | Original beneficiary list included vacant land/ unoccupied stands | Re allocate 149 units deserving beneficiaries | 25000000 | Monthly reports, practical completion reports, happy letters
To construct VIP Sanitation units by June 2018 within Elias Motsoaledi Municipality | Financial and Human Resource | 1 630 VIP Sanitation toilets completed | Improved health and hygiene | VIP Sanitation programme phase 2.2 | 15 180 VIP Units constructed | Number of VIP sanitation units constructed | 1 630 VIP Sanitation units constructed | Finalize beneficiary list, | Not Achieved | 240 VIP units completed. Draft tender documents submitted for further discussion before calling of contractors through advert | Contractors experiencing cashflow problems | Contractor will provide us with revise programme of works | 32000000 | Monthly reports, practical completion reports, happy letters
To complete Zaaiplaas village reticulation | Financial and Human Resource | Completed BWS | Improved water supply to Zaaiplaas | Zaaiplaas Village Reticulation Phase 2 | Construction of Dindela Reservoir. Commissioning of bulk pipeline and pump station. | Percentage completion of Zaaiplaas village reticulation including rerservior & bulk pipeline | 100% completion of Zaaiplaas village reticulation including rerservior & bulk pipeline | 0% construction of Dindela Reservoir, 0% construction of bulk pipeline, 0% construction of pump station. | Not Achieved | Reservoir construction is at 35 % | Additional funds needed to complete the project | Finalise motivation for budget maintenance and submit via MIG/MIS for COGHSTA approval. | 5000000 | Monthly reports and practical completion certificate
To finalize construction of Zaaiplass water reticulation by December 2017. | Financial and Human Resource | Completed BWS | Improved water supply to Zaaiplaas | Zaaiplaas Connector pipes from Bulk to villages incl. reservoirs (Khathazweni, Rondebosh,Kosini,Mathula,Khathazweni,Areaganeng,Jeije,Sehlakwane,Elandslaagte and Dindela) | 80% construction of Zaaiplass water reticulation (Construction reservoirs 80%; bulk line 80%). | Percentage Construction of Zaaiplass Connector Pipes. | 100% construction of Zaaiplass water reticulation (Construction reservoirs 100%; bulk line 100%). | 60% construction of Zaaiplass water reticulation (Construction reservoirs 70%; bulk line 70%). | Achieved | Overall progress to date is at 95%. Pipe laying is at 100%, Reservoir connections =100% | Cashflow problems | Programme of works showing how the snag item will be completed | 7606590.67 | Monthly reports and practical completion certificate
To commission Tafelkop Reticulation and Cost Recovery by June 2018 | Financial and Human Resource | Completed Tafelkop water reticulation network | Improved water supply to Tafelkop | Tafelkop Reticulation and Cost Recovery | 60% Construction of Tafelkop reticulation projects | Percentage (%) Commissioning of Tafelkop Reticulation and Cost Recovery | 100% Commissioning of Tafelkop Reticulation and Cost Recovery ( Snag listing 50% and testing 50%) | 60% Commissioning of Tafelkop Reticulation and Cost Recovery ( Snag listing 10% and testing 10%) | Not Achieved | Overall Progress 100 % | Additional funding will be required to deal with hard rock or special piping work at ward 17. Bulk pump main supply requires upgrades | Submit revised technical report to address the additional scope of work | 7972483 | Monthly reports and practical completion certificate
To construct VIP sanitation units by June 2018 within Makhuduthamaga Municipality | Financial and Human Resource | 1 835 VIP Sanitation toilets completed | Improved health and hygiene | VIP Sanitation programme phase 2.2 | 15 180 VIP Units constructed | Number of VIP sanitation Units constructed | To construct 1 835 VIP sanitation units | Finalize beneficiary list, | Not Achieved | 500 VIP units completed Two contractors still on site, they were affected by the late payment received and the last contractor just got paid only waiting 100 top structures to be delivered to site. | Cashflow problems. Late delivery of material caused by late payment. | Revise program of works and cashflow. | 25000000 | Monthly reports, practical completion reports, happy letters
To construct Sekwati Reticulation upgrade Phase 4 by December 2017 | Financial and Human Resource | Completed Sekwati water reticulation network | Improved water supply to Sekwati | Sekwati Reticulation upgrade Phase 4 | 90% Construction of Sekwati Reticulation upgrade Phase 4 | Percentage Construction of Sekwati Reticulation upgrade Phase 4 | 10% Construction of Sekwati Reticulation upgrade Phase 4 | 2% Construction of Sekwati Reticulation upgrade Phase 4 | Achieved | Contract A: 100% complete, 12km pipe laid and tested. Contract B: 99% complete. 13.5km of pipe laid and tested.2km of pipe remaining and also gabion mattresses | None | None | 6958280.06 | Monthly reports and practical completion certificate
To construct Ga Moloi Water Supply water supply by December 2017. | Financial and Human Resource | Completed Ga-Moloi water reticulation network | Improved water supply to Ga-Moloi | Ga Moloi area and surrounding villages water supply (contract B and C) | 90% Construction of reticulation lines at Morgenzon and Stad Van Masleroem; Gravity main, installation of street taps. | Percentage Construction of reticulation lines at Morgenzon and Stad Van Masleroem; Gravity main, installation of street taps. | 10% Construction of reticulation lines at Morgenzon and Stad Van Masleroem; Gravity main, installation of street taps. | 2% Construction of reticulation lines at Morgenzon and Stad Van Masleroem; Gravity main, installation of street taps. | Not Achieved | Contract A is 100% Contract B is at 92% and Contract C is at 99%. | Cashflow problems | Revise program of works and cashflow, request extension of time | 7331650.4718 | Monthly reports and practical completion certificate
To construct reticulation network in Ga-Mashabela by June 2018 | Financial and Human Resource | Completed Ga-Mashabela water reticulation network | Improved water supply to Ga-Mashabela | Ga-Mashabela water reticulation supply | Technical report approval and MIS registration | Percentage of construction completed | 100% construction completed | 0% construction completed, | Not Achieved | Four (4) contractors appointed Site establishment is complete. Material being ordered. Cash flow projection and programme submitted | Delivery of material is January 2018 due to the coming calendar of contractors holidays | None | 34642003.0982 | Monthly reports and Technical report
To construct reticulation network in Ga-Marishane by June 2018 | Financial and Human Resource | Completed Ga-Marishane water reticulation network | Improved water supply to Ga-Marishane | Ga-Marishane water reticulation supply | Technical report approval and MIS registration | Percentage of construction completed | 100% construction completed | 0% construction completed, | Achieved | Constractor appointed and establishing site, based on program of works he will commence in January 2017 | None | None | 22925159.9 | Monthly reports and practical completion certificate
To construct reticulation network in Maloma by June 2018 | Financial and Human Resource | Completed Maloma and surrounding (Lebating and Tsupani) water reticulation network | Improved water supply to Maloma and surrounding (Lebating and Tsupani) | Maloma and surrounding (Lebating and Tsupani) water supply | Technical report approval and MIS registration | Percentage of construction completed | 100% construction completed | 0% construction completed, | Achieved | Excavation on the pipeline complete, pipe laid, pressure testing | None | None | 8045410.12 | Monthly reports and practical completion certificate
To construct reticulation network in Lobethal by June 2018 | Financial and Human Resource | Completed Lobethal water supply | Improved water supply to Lobethal | Lobethal water supply | Technical report approval and MIS registration | Percentage of construction completed | 100% construction completed | 0% construction completed, | Achieved | 3KM of pipeline completed. 50% of the foundation concrete reservoir | None | None | 10855220.6 | Monthly reports and practical completion certificate
To construct reticulation network in Ga-Phaahla by June 2018 | Financial and Human Resource | Completed Ga-Phaahla water supply | Improved water supply to Ga-Phaahla water supply | Ga-Phaahla water supply | Technical report approval and MIS registration | Percentage of construction completed | 100% construction completed | 0% construction completed, | Achieved | Site establishment | None | None | 27448984.9 | Monthly reports and practical completion certificate
To finalize Nkadimeng: Phase 9 to 11 (Makhuduthamakga) - Ditlabaneng, Letlhabile,Tshatane, Sebetsane, Kgoalane & MAtseben`9E | Financial and Human Resource | Concrete reservoirs; Bulk Water Supply;Reticulation. | Improved Living standards. | Nkadimeng: Phase 9 to 11 (Makhuduthamakga) - Ditlabaneng, Rampelane, Matsebeng, Sebetsane, Kgoalane, Mathibeng, Dinotsi, Matolokwane) | 65% Completion of Concrete reservoirs; Bulk Water Supply; Reticulation. | Percentage Completion of Concrete reservoirs; Bulk Water Supply; Reticulation. | 100% Completion of Concrete reservoirs; Bulk Water Supply; Reticulation. | 60% Completion of Concrete reservoirs; Bulk Water Supply; Reticulation. | Not Achieved | 9E-overall progress = 99% Cession to seal reservoirs and fix chamber roofs has been approved | Community distruption to stop projects | To request MMC and ISD to intervene | 1418565.85 | Monthly reports and practical completion certificate
To construct VIP sanitation units by June 2018 within LIM 476 Municipality (Fetakgomo area) | Financial and Human Resource | 715 VIP Sanitation toilets completed | Improved health and hygiene | VIP Sanitation programme phase 2.2 | 15 180 VIP Units constructed | Number VIP Units constructed | 715 VIP sanitation units | Finalising Beneficiery list, | Achieved | 1643 units erected. | one cluster is remaining without practical completion due to debts that the contractor has to settle firstReconciling all outstanding claims including cessions for suppliers. Budget constraints | Revise cashflow and program of works | 15870000 | Monthly reports and practical completion certificate
To implement Borehole Refurbishment Southern Zone by June 2018 | Financial and Human Resources | Refurbished and new developed Water Boreholes | Improved Water Supply | Olifantspoort South Contract 21,22, 24 & 25: Water supply network | Water supply below RDP level | Percentage Completion of boreholes developed and Refurbishment Southern Zone | 70% Completion of boreholes developed and Refurbishment Southern Zone | 2% Implementation of borehole Refurbishment Southern Zone | Not Achieved | Contr 21 Overall progress 65%, Contr 22 Overall progress 58% , Contr 24 Overall progress 65% | No expected expenditure on this contract for Nov.2017 The contractor is struggling to order Pumps. | Contractor to submit a motivation requesting SDM to waive the 30% Cession Limit. This will assist in the progress of ordering the pumps | 18895159.89 | Monthly reports and practical completion certificate
To complete Concrete reservoirs; Bulk Water Supply; Reticulation Nkadimeng: Phase 9 to 11 | Financial and Human Resources | Nkadimeng: Phase 9 to 11 (Makhuduthamaga) - | Improved Living standards. | Nkadimeng RWS Extension 2( Phase 9 to 11) (Fetakgomo) Ga-Mmela to Mashilavele, Ga-Pahla, Molapong, Ga-Magolego, Mankontu and Masehleng | Nkadimeng WTW, Command Reservoir, reticulation and bulk line below RDP level. | Percentage Completion of Concrete reservoirs; Bulk Water Supply; Reticulation. | 80% Completion of Concrete reservoirs; Bulk Water Supply; Reticulation. | 2% Implementation of borehole Refurbishment Southern Zone | Not Achieved | 10A- Overall progress = 91%, 10B- Overall progress is 94%. 10C- Overall progress is 84% | cashflow problems and shortage of water to test | Revise cashflow and program of works | 47038314.95 | Monthly reports and practical completion certificate
To construct VIP sanitation units by June 2018 within LIM 476 Muniipality (Greater Tubatse area) | Financial and Human Resource | 715 VIP Sanitation toilets completed | Improved health and hygiene | VIP Sanitation programme phase 2.2 | 15 180 VIP units contructed | Number of VIP sanitation units | 1630 VIP sanitation units | Finalising Beneficiery list, | Achieved | 952 VIP units completed | Slow progress about 241 units outstanding | Revise cashflow and program of works | 30000000 | Monthly reports and practical completion certificate
To construct Command Reservoir, pump station and pipelines at GaMaphopha by June 2017. | Improved water supply | Ga - Maphopha Command Reservoir | Improved Living standards. | Ga - Maphopha Command Reservior | 60% completion of Maphpha command reservoir, pumpsation and pipelines | Percentage completion of Command Reservoir, pump station and pipelines | 100% completion of Command Reservoir, pump station and pipelines | 20% completion of Command Reservoir, pump station and pipelines | Not Achieved | Overall progress = 74% | contractual disputes on activities and time claimable | Revise cashflow and program of works and additional funding request from funders. | 16000000 | Monthly reports and practical completion certificate
To construct reticulation network in Lebalelo South by June 2018 | Improved water supply | Lebalelo South connector pipes completed | Improved Living standards. | Lebalelo South connector pipes | Technical report approval and MIS registration | Percentage construction completed | 50% construction completed | Procurement of service provider | Achieved | Three contractors have been appointed and they are currently busy with the site establishment. | none | none | 102478995 | Monthly reports
To construct reticulation, reservoir, stand pipes at Ga-Malekane , Masha, GaMaepa by June 2018 | Improved water supply | Ga-Malekane , Masha upgrade and extend reticulation | Improved Living standards. | Ga-Malekane , Masha upgrade and extended reticulation | 65% completion of reticulation, reservoir, stand pipes at Ga-Malekane , Masha, GaMaepa. | Percentage completion of reticulation, reservoir, stand pipes at Ga-Malekane , Masha, GaMaepa. | 35% completion of reticulation, reservoir, stand pipes at Ga-Malekane , Masha, GaMaepa. | 2% completion of reticulation, reservoir, stand pipes at Ga-Malekane , Masha, GaMaepa. | Not Achieved | Overall progress- 97% | delayed delivery of pumps by supplier and outstanding stipent paymnets to PSC | Revise cashflow and program of works | 12000000 | Monthly reports
Name |  | Designation |  | Signature |  | Date
Manager : Governance & Regulations
Manager : Operation & Maintenance
Manager : Project Manager Unit
Manager : RBIG & WSIG
Deputy Director : IWS
Director : IWS

## Final SDBIP 2017-18
2017/18 IDP
,,IDP PROJECTS 2017/2018
MEASURABLE OBJECTIVE | INPUT | OUTPUT | OUTCOME | PROJECT | BASELINE 2016/2017 | KEY PERFORMANCE INDICATORS | ANNUAL TARGET 2017/2018 | Q1 | Q2 | Q3 | Q4 | BUDGET 2017-2018 "R" | PoE
PLANNING, REGULATION AND GOVERNANCE
To develop WC/WDM Strategy for SDM by June 2018 | WSDP and Water Master Plan | Document on Water Conservation and Demand Management | Strategy on Water Conservation and Demand Management | Development of Water Conservation and Water Demand Management Plan | Water Services Master Plan and WSDP developed in 2014/15 and the 2015/16 FY respectively | Number of WC/WDM Strategy developed | One WC/WDM Strategy developed | Development of Terms of Reference and appointment of service provider | Collection of information/Assessment of status quo | Development of strategies | One WC/WDM Strategy Developed | 800000 | Draft WC/WDM Strategy
To upgrade Groblersdal sewer pump station by June 2018 | Bulk sewer intervention plan Jan 2015 | Sewer upgrade plan | Enhansed sewer system | Upgrading of Groblersdal sewer pump station. | 15% upgrade of the outfall sewer system took place in 2015/16 FY | Percentage of sewer pumpstation upgrade completed | 50% Upgrade of Sewer pump station( 2 pumps refurbished, screens upgrading & alarm system); | Complete CCTV line survey | Install and monitor flow meters at the WWTW | Monitor flow meters | Finalise report on status quo sewer pump station system | 500000 | Progress report and Status quo report
To develop feasibility study for the upgrade of Marble Hall sewer bulk line and pumpstation by June 2018 | None | Flows and levels | Enhansed sewer system | Development of Feasibilty study in Marble Hall Town for bulk sewer and pump station | Service provider appointed during 2015/16 FY | Number of feasibility studies conducted | One feasibility study completed for Marble Hall sewer line and pumpstation | Measure flows | Survey of sewer system | 0 | one feasibility study completed for Marble Hall sewer line and pumpstation | 300000 | Feasibility study report
To conduct condition assessment and develop O & M plan by June 2018 | Asset register | Document | Preventative and reactive O&M plan | Conduct Condition Assessment and develop Operation and maintenance plans | Terms of reference developed and incorporated into the asset management plan contract and tender advertised for the PSP appointment | Percentage conduct of Condition assessment and 0 & M plan developed | 60% conduct of Condition assessment and 0 & M plan developed | Appointment of service provider & Methodology approach for, condition assessment and O & M plan | 20% Development of O&M plan and Condition assesment of IWS infrastructure conducted | 40% Development of O&M plan and Condition assesment of IWS infrastructure conducted | 60% Development of O&M plan and Condition assesment of IWS infrastructure conducted | 800000 | Progress report
To conduct feasibility study and develop Technical reports for submission to DWS by 30 June 2018 | Assignment of PSP to do the Technical Reports | Technical Reports | MIG registered Projectss | Conduct Feasibility studies and develop technical reports | WSDP, IDP & Bulk Water Service Master completed in Plan 2014 | Number of of feasibility studies conducted and technical reports developed for Leballo South Villages Phase Two | 7 feasibility studies conducted and technical reports developed for Leballo South Villages Phase Two | Assignment of the PSP to do source development and compile technical reports | 2 feasibility studies conducted and technical reports developed for Leballo South Villages Phase Two and submitted to DWS | 4 feasibility studies conducted and technical reports developed for Leballo South Villages Phase Two and submitted to DWS | 7 feasibility studies conducted and technical reports developed for Leballo South Villages Phase Two and submitted to DWS | 5000000 | Letters, Minutes of Meeting and Technical Reports
PROJECT MANAGEMENT UNIT
RBIG
To construct pipeline from Burgersfort to Dresden pump station by June 2018 | Financial and Human Resource | Bulk supply line | Improved water supply | Construction of Mooihoek bulk water supply phase 4E | Mooihoek bulk water supply phase 4D completed | Number of Kilometers of bulk pipeline constructed | 3 Kilometers of bulk pipeline constructed | Detailed design and procurement of Contractor | Site establishment and 0.2km pipeline constructed | 1km of bulk pipeline constructed | 3 Km of bulk pipeline constructed | 30000000 | Progress reports on Mooihoek phase 4E
To construct reservoir at Burgersfort by June 2018 | Financial and Human Resource | 2 X 5 Ml concrete reservoirs | Improved water supply | Mooihoek bulk water supply phase 4B | 1 x 5ML resevoir completed Mooihoek Phase 4A | Percentage reservoir constructed | 70% , 1 X 5 Ml concrete reservoir constructed | 0% constructed, Detailed design and procurement of Contractor | 20% Construction of Reservoirs | 40% Construction of Reservoirs | 70% Construction of Reservoirs | 18000000 | Progress reports on Burgersfort reservoirs
To construct bulk pipeline from Praktiseer to Motodi by June 2018 | Financial and Human Resource | Bulk supply line | Improved water supply | Mooihoek bulk water supply phase 4F | Mooihoek bulk water supply phase 2 completed | Number of Kilometers of bulk pipeline constructed | 4 Kilometers of bulk water pipeline constructed | Detailed design and procurement of Contractor | Site establishment and 0.1km pipeline constructed | 2Km of bulk pipeline constructed | 4Km of bulk pipeline constructed | 29000000 | Progress reports on Praktiseer to Motodi bulk pipeline
To construct bulk pipeline from Praktiseer to Alverton by June 2018 | Financial and Human Resource | Bulk supply line | Improved water supply | Mooihoek bulk water supply phase 4G | Mooihoek bulk water supply phase 2 completed | Number of Kilometers of bulk pipeline constructed | 4 Kilometers of bulk water pipeline constructed | Detailed design and procurement of Contractor | Site establishment and 0.1km pipeline constructed | 1.5Km of bulk pipeline constructed | 4Km of bulk pipeline constructed | 28000000 | Progress reports on Praktiseer to Alverton bulk pipeline
To construct pumping pipeline from T-off of Makgeru to the new 10ML reservoir at Schoonoord, construction of gravity pipeline. | Financial and Human Resource | Bulk supply line | Improved water supply | Nebo BWS Makgeru to Schoonoord BWS | Reservoir is 55% completed. *Pipeline is 45% completed | Percentage bulk pipeline constructed and reservoir completed. | 100% bulk pipeline constructed and reservoir completed. | *55% of bulk pipeline constructed *65% Reservoir completed. | *70% of bulk pipeline constructed *75% of Reservoir completed. | *80% of bulk pipeline constructed * 85% Reservoir completed. | *100% of bulk pipeline constructed *100% Reservoir completed. | 55000000 | Progress report and practical completion certificate
To connect mechanical and Electrical (M & E) for the extensions to the Groblersdal Water Treatment Works by June 2018. | Financial and Human Resource | Mechanical & Electrical Installations | Improved water supply | Moutse BWS Project ( 13 &14) | The upgrading of WTW is completed | Percentage M&E components installed | 100% M&E components Installed | 80% Installation of pumps and electrical fittings. | 90% Installation of pumps and electrical fittings. | 100% Installation of pumps and electrical fittings. | Testing and Commissioning | 60000000 | Progress reports on electrical & mechanical components
To construct bulk pipeline and valve chambers by June 2018 | Financial and Human Resource | Bulk supply line | Improved water supply | Moutse BWS Project ( 7 to 12) | Bulk pipelines and valve constructed up 54%. | Percentage bulk pipeline constructed. | 100% bulk pipeline constructed. | *60% of bulk pipeline constructed. | *70% of bulk pipeline constructed. | *80% of bulk pipeline constructed. | *100% of bulk pipeline constructed. |  | Progress reports
WATER QUALITY
To generate water quality reports by June 2018 | WSDP and Water Master Plan | Regulatory Compliance | Improved service delivery | Generation of Water Quality Reports | 10 reports generated | Number of water quality reports generated | 12 water quality reports generated | 3 water quality reports generated | 6 water quality reports generated | 9 water quality reports generated | 12 water quality reports generated | 12000000 | Water quality reports
To conduct Full SANS 241 analysis by June 2018 | WSDP and Water Master Plan | Regulatory Compliance | Improved service delivery | Conduct Full SANS 241 Water Quality Analysis | Signed CSIR SLA in 2015/16 FY | Number of Full SANS 241 analysis conducted | 1 Full SANS 241 analysis conducted | n/a | n/a | n/a | 1 x Full SANS 241 analysis conducted |  | Full SANS 241 report
To purchaseLaboratories Chemical by June 2018 | WSDP and Water Master Plan | Regulatory Compliance | Improved service delivery | Purchase of Lab chemicals | Term contractors appointed | Percentage of lab chemical purchased | 100% lab chemical purchased | 25 % lab chemicals purchased | 50% lab chemicals purchased | 75% lab chemicals purchsed | 100 % lab chemicals purchased |  | Delivery notes and tax invoices for delivered lab chemicals
To participate in Blue and Green Drop Certification programme by June 2018 | WSDP and Water Master Plan | Regulatory Compliance | Improved service delivery | Plants participation in Blue and Green Drop Cerification Programme | 12 water treatment works participating in Blue Drop Certicification Programme in place | Number of plants participating in Blue and Green Drop Participation Programme | 60 water treatment works participating in Blue Drop and 40 wastewater treatment works participating in Green Drop Certification Programme | 15 water treatment works participating in Blue Drop and 10 wastewater treatment works participating in Green Drop Certification Programme | 30 water treatment works participating in Blue Drop and 20 wastewater treatment works participating in Green Drop Certification Programme | 45 water treatment works participating in Blue Drop and 30 wastewater treatment works participating in Green Drop Certification Programme | 60 water treatment works participating in Blue Drop and 40 wastewater treatment works participating in Green Drop Certification Programme |  | Blue and Green Drop Annual Report
OPERATION AND MAINTENANCE
To resolve registered sanitation incidents within 14 days. | Financial and Human Resource | Reduced sewer spillage and environmental pollution | Improved green drop status | Sanitation incidents | 90% registered sanitation incidents | Percentage registered sanitation incidents resolved within 14 days | 90% registered sanitation incidents resolved within 14 days | 90% registered sanitation incidents resolved within 14 days | 90% registered sanitation incidents resolved within 14 days | 90% registered sanitation incidents resolved within 14 days | 90% registered sanitation incidents resolved within 14 days | 30000000 | Monthly reports
To resolve registered water incidents within 14 days. | Financial and Human Resource | Reduced non-revenue water losses | Improved no drop status. | Water incidents | 90% registered water incidents | Percentage registered water incidents resolved within 14 days | 90% registered water incidents resolved within 14 days | 90% registered water incidents resolved within 14 days | 90% registered water incidents resolved within 14 days | 90% registered water incidents resolved within 14 days | 90% registered water incidents resolved within 14 days |  | Monthly reports
To render Tankering services by June 2018 | Financial and Human Resource | Consistent supply of water | Improved water supply | Delivery of Potable Water | 90% of tankering services rendered | Pecentage tankering services rendered | 90% of tankering services rendered in areas with no water source or infrastructure | 90% of tankering services rendered in areas with no water source or infrastructure | 90% of tankering services rendered in areas with no water source or infrastructure | 90% of tankering services rendered in areas with no water source or infrastructure | 90% of tankering services rendered in areas with no water source or infrastructure | 32000000 | Monthly Water delivery records and reports
To provide diesel consistently to diesel driven machines by June 2018 | Financial and Human Resource | Consistant water supply. | Reliable water supply. | Supply of Diesel | 80 000? of diesel supplied | Number of Litres of diesel supplied annually | 80 000? of diesel supplied annually. | 20 000? of diesel supplied. | 20 000? of diesel supplied. | 20 000? of diesel supplied. | 20 000? of diesel supplied. | 1750000 | Monthly reports
To provide Petrol consistently to petrol driven machines by June 2017 | Financial and Human Resource | Consistant water supply. | Reliable water supply. | Supply of Petrol | 5000? petrol supplied | Number of Litres petrol supplied annually. | 1200? of petrol supplied annually. | 300? of petrol supplied. | 300? of petrol supplied. | 300? of petrol supplied. | 300? of petrol supplied. |  | monthly reports
To provide Oil consistently to diesel and petrol driven machines by June 2017 | Financial and Human Resource | Consistant water supply. | Reliable water supply. | Supply of Oil | 1500? of oil supplied | Number of Litres of oil supplied annually. | 720? of oil supplied annually. | 180? of oil supplied. | 180? of oil supplied. | 180? of oil supplied. | 180? of oil supplied. |  | monthly reports
To resolve registered M & E incidents within 14 days | Financial and Human Resource | Consistent supply of water | Improved water supply | Mechanical and electrical services | 50% resolved registered M & E incidents within 14 days | Percentage of registered water incidents resolved within 14 days | 80% of registered water incidents resolved within 14 days | 80% of registered water incidents resolved within 14 days | 80% of registered water incidents resolved within 14 days | 80% of registered water incidents resolved within 14 days | 80% of registered water incidents resolved within 14 days | 3500000 | Monthly reports
To install bulk water meters by June 2018 | Financial and Human Resource | Consistent supply of water | Improved water supply | Installation of Bulk water meters . | Reservoirs in place | Number of bulk water meters installed by June 2018 | 8 bulk water meters installed | Specifications developed, and procurement of service provider(s) | Delivery of 8 bulk water meters | Installation of 4 bulk water meters | Installation of 8 bulk water meters | 2000000 | Progress reports
To purchase M? bulk water by June 2018 | Financial and Human Resource | Consistent supply of water | Improved water supply | M? Bulk Water Purchases | 10 062 M? of bulk water supplied. | Number M? of water purchased | 10 062M? of water purchased | 2 515 annual water volume purchased | 5 030 annual water volume purchsed | 7545 annual water volume purchased | 10 062 annual water volume purchased | 64000000 | Delivery registers and Tax invoices
WSIG PROJECTS
To complete Tukakgomo water reticulation by June 2018 | Human Resource | 3000m of 65mm diameter pipeline and one steel tank constructed. | Improved service delivery | Tukakgomo water intervention and refurbishment. | 1 borehole drilled and equipped. | Percentage completion of Tukakgomo water reticulation. | 100% completion of Tukakgomo water reticulation. | Appointment of Consultant, designs and tender document development | Procurement of contractor and 10% construction of water reticulation network and steel tank platform construction | 70% construction of reticulation and installation of steel tank. | 100% construction of reticulation and installation of steel tank. | 4500000 | Progress report and practical completion certificate
To construct bulk pipeline by June 2018 | Human Resource | 5.5Km of bulk pipeline constructed | Improved service delivery | Mahlwakwena to Mapodile pipeline | The command reservoir at Mahlwakwena is completed. | Number of Kilometers of bulk pipeline constructed | 5.5Km of bulk pipeline constructed | Appointment of Consultant, designs and tender document development | Procurement of contractor and 1.5km of bulk pipeline constructed | 4Km of bulk pipeline constructed | 5.5Km of bulk pipeline constructed | 3000000 | Progress report and practical completion certificate
To construct abstraction point at Mampuru village by June 2018. | Human Resource | 100% of Abstruction point completed. | Improved service delivery | Mampuru Water abstraction and reticulation network | 1,5ML WTW in place and abstraction point washed away. | Percentage Abstraction point constructed. | 100% Abstraction point constructed. | Appointment of Consultant, designs and tender document development | Procurement of contractor and 30% of Abstraction point constructed | 70% of Abstraction point constructed. | 100% of Abstraction point completed. | 3500000 | Progress report and practical completion certificate
To construct pipeline by June 2018 | Human Resource | 7Km kilometers of pipeline constructed | Improved service delivery | Rutseng Water Intervention | Skeletal water infrastructure in place | Number of Kilometers of pipeline constructed | 7km of pipeline constructed | Appointment of Consultant, designs and tender document development | Procurement of contractor and 1,5km of pipeline constructed | 3,5km of pipeline constructed | 7km of pipeline constructed | 3500000 | Progress report and practical completion certificate
To construct bulk pipeline by June 2018 | Human Resource | 3.5km of bulk pipeline constructed | Improved service delivery | Phiring Water Intervetion | The existing booster pump station is vadalised. | Number of Kilometers of bulk pipeline constructed | 3.5km of bulk pipeline constructed | Appointment of Consultant, designs and tender document development | Procurement of contractor and 1km bulk pipeline constructed | 2.5km of bulk pipeline constructed | 3.5km of bulk pipeline constructed | 3500000 | Progress report and practical completion certificate
To complete Mamatjekele Package Plant by June 2018 | Human Resource | Developed source | Improved service delivery | Completion of Mamatjekele Package plant | The borehole is equipped but producing polluted water. | Percentage completion of Mamatjekele Package Plant | 100% completion of Mamatjekele Package Plant | Appointment of Consultant, designs and tender document development | 20% Procurement of contractor and material. | 50% Borehole Equipping | 100% Testing and Commissioning | 3000000 | Progress report and practical completion certificate
To complete Jane Furse RDP Package Plant by June 2018 | Human Resource | Package plant | Improved service delivery | Jane Furse RDP Package plant | The high yield borehole is equipped but producing poluted water. | Percentage completion of Mamatjekele Package Plant | 100% completion of Jane Furse RDP Package Plant | Appointment of Consultant, designs and tender document development | 20% Procurement of contractor and materials | 50% Installation of Package Plant | 100% Testing and Commissioning | 2700000 | Progress report and practical completion certificate
To construct pipeline at Apel Cross RDP by June 2018 | Human Resource | Reticulation network | Improved service delivery | Apel Cross RDP Reticulation network | The high yield borehole is equipped but not connected to any infrastruture. | Number of Kilometers of pipeline constructed | 7 kilometers of pipeline constructed | Appointment of Consultant, designs and tender document development | Procurement of contractor and materials | 3 kilometers of pipeline constructed | 7 kilometers of pipeline constructed | 2000000 | Progress report and practical completion certificate
To complete Moretsele water reticulation by June 2018 | Human Resource | Reticulation network | Improved service delivery | Moretsele water rising main | No formal water infrastrucutre in place. | Number of Kilometers of pipeline constructed | 2 kilometers of pipeline constructed | Appointment of Consultant, designs and tender document development | Procurement of contractor and materials | 2km pipeline constructed | n/a | 2000000 | Progress reports
To test and commission bulk pipeline from Malekane WTW to Jane Furse 25Ml command reservoir by June 2018. | Human Resource | Bulk supply line | Improved service delivery | Nebo Phase 1A testing and comissioning | Nebo Phase1A completed but not commisioned. | Number of Kilometers of pipeline commissioned | 33km bulk pipeline tested and commissioned. | 33km bulk pipeline tested and commissioned. | 33km bulk pipeline tested and commissioned. | n/a | n/a | 13000000 | Monthly progress reports and practical completion certficate
To develop water source and prepare Technical report at villages around Uitspanning area by June 2018. | Human Resource | Developed source | Improved service delivery | Uitspanning Water Source developmement | Groblersdal WTW and Moutse bulk pipeline in progress. | Number of water source developed and no of technical reports prepared. | 2 water sources developed and technical reports prepared . | *Appointment of PSP and Approval of Designs. | 2 Drill borehole(s), equip boreholes and water quality testing | Presentation of draft Technical report to SDM internal design committee | Submit to Department of Water & Sanitation (DWS) for approval | 2000000 | Monthly reports and Technical report
To develop water source and prepare technical report at villages around Madibong village by June 2018. | Human Resource | Developed source | Improved service delivery | Madibong Water Supply | Jane furse 25Ml completed. | Number of water source developed and no of technical reports prepared. | 4 water source developed and no of technical reports prepared. | *Appointment of PSP and Approval of Designs. | *Procurement of contractor and materials | *Borehole Drilling Equipping and testing | 4 water sources developed and technical reports completed . | 1500000 | Monthly reports and Technical report
To construct pipeline by June 2018. | Human Resource | Reticulation network | Improved service delivery | Uitvlught Water Supply | Groblersdal WTW and Moutse bulk pipeline in progress. | Number of Kilometers of pipeline constructed | 1.7 kilometers of pipeline constructed | *Appointment of PSP and Approval of Designs. | *Procurement of contractor and materials | * 0.7 km pipeline constructed | 1,7km pipeline constructed | 3000000 | Monthly reports
To construct pipeline by June 2018. | Human Resource | Reticulation network | Improved service delivery | Keerom Water Supply | Groblersdal WTW and Moutse bulk pipeline in progress. | Number of Kilometers of pipeline constructed | 2.8 kilometers of pipeline constructed | *Appointment of PSP and Approval of Designs. | *Procurement of contractor and materials | 0.8 kilometers of pipeline constructed | 2.8 kilometers of pipeline constructed | 3000000 | Monthly reports
To construct pipeline by June 2018. | Human Resource | Reticulation network | Improved service delivery | Diphaganeng Water Supply | The borehole is equiped and connected to JoJo tank. | Number Kilometers of pipeline constructed | 2.3 kilometers of pipeline constructed | *Appointment of PSP and Approval of Designs. | *Procurement of contractor and materials | 1 kilometers of pipeline constructed | 2.3km pipeline constructed | 2300000 | Monthly reports
To construct pipeline by June 2018. | Human Resource | Reticulation network | Improved service delivery | Rathoke Bulk Water Supply | Groblersdal WTW and Moutse bulk pipeline in progress. | Number Kilometers of pipeline constructed | 3.2 kilometers of pipeline constructed | *Appointment of PSP and Approval of Designs. | *Procurement of contractor and materials | 1 kilometers of pipeline constructed | 3.2km pipeline constructed | 3000000 | Monthly reports
To Install household meters at Letebejane by June 2018. | Human Resource | Meters Installed | Improved service delivery | Letebejane Water meters installation | The village is fully reticulated & supplied water for 24hrs without payment. | Number of households meters installed | 450 household meters Installed. | *Appointment of PSP and Approval of Designs. | *Procurement of contractor and materials | 200 household meters Installed. | 450 household meters Installed. | 3000000 | Monthly reports
To refurbish package plant in Tjibeng by June 2018.. | Human Resource | Package plant | Improved service delivery | Refurbishment of Tjibeng package plant | The package plant is dilapitated. | Number of package plant refurbished. | One package plant refurbished in Tjibeng . | *Appointment of PSP and Approval of Designs. | *Procurement of contractor and materials | 1 installation of Package Plant | 1 Testing and Commissioning | 3500000 | Monthly reports
To develop water souce and connect to existing reticulation by June 2018 | Human Resource | Developed source | Improved service delivery | Maebe drilling and equipping of borehole | No formal water infrastrucutre in place. | Number of water source developed | One of water source developed | *Appointment of PSP and Approval of Designs. | *Procurement of contractor and materials | * 1 Borehole Drilling Equipping | * 1 Testing and Commissioning | 3000000 | Monthly reports
To construct VIDP Sanitation units by June 2018 | Human Resource | VIDPs installed | Improved service delivery | Construction of Moretsele VDIP | New Infrastructure | Number of VIDP sanitation units constructed | 334 VIDP Sanitation units constructed | *Procurement of Contractor | *100 hh provided with VIDPs | *220 hh provided with VIDPs | *334 hh provided with VIDPs | 4500000 | Monthly reocrts
To construct pipeline by June 2018 | Human Resource | Bulk supply line | Improved service delivery | Lobethal bulk water supply | 18450m of pipeline constructed | Number of Meters of pipeline constructed | 550m of pipeline constructed | *Procurement of Contractor | *550m pipeline constructed | *Testing and commissioning | *Not Applicable | 8000000 | Monthly reocrts
To refurbish Thabampshe pump station by June 2018.. | Human Resource | Pump station refurbished and rising main pipeline tested | Improved service delivery | Thabampshe refurbishment of a pumpstation | Pump station and reservoir structure in place | Percentage refurbishment of Thabampshe water pump station ( 2 pumps, motors and electrical panel and replacement of valves and testing of rising main | 100% refurbishment of Thabampshe water pump station ( 2 pumps, motors and electrical panel completed and replacement of valves and testing of rising main | *Procurement of Contractor | 25% refurbishment of Thabampshe water pump station ( 2 pumps, motors and electrical panel completed and replacement of valves and testing of rising main | 50% refurbishment of Thabampshe water pump station ( 2 pumps, motors and electrical panel completed and replacement of valves and testing of rising main | 100% completion of Thabampshe water pump station ( 2 pumps, motors and electrical panel completed and replacement of valves and testing of rising main | 2000000 | Monthly progress reports and practical completion certficate
MIG
To construct VIP Sanitation units by June 2018 within Ephraim Mogale Municipality | Financial and Human Resource | 1 020 VIP Sanitation toilets completed | Improved health and hygiene | VIP Sanitation programme phase 2.2 | 15 180 VIP Units constructed | Number of VIP sanitation units constructed | 1 020 VIP Sanitation units constructed | Finalize beneficiary list, establishment of Project Steering Commitees, appointment of CLOs and Appointment of Contractors | 200 VIP Sanitation toilets completed | 550 VIP Sanitation toilets completed | 1020 VIP Sanitation toilets completed | 25000000 | Monthly reports, practical completion reports, happy letters
To construct VIP Sanitation units by June 2018 within Elias Motsoaledi Municipality | Financial and Human Resource | 1 630 VIP Sanitation toilets completed | Improved health and hygiene | VIP Sanitation programme phase 2.2 | 15 180 VIP Units constructed | Number of VIP sanitation units constructed | 1 630 VIP Sanitation units constructed | Finalize beneficiary list, establishment of Project Steering Commitees, appointment of CLOs and Appointment of Contractors | 400 VIP Sanitation toilets completed | 940 VIP Sanitation toilets completed | 1 630 VIP Sanitation toilets completed | 32000000 | Monthly reports, practical completion reports, happy letters
To complete Zaaiplaas village reticulation | Financial and Human Resource | Completed BWS | Improved water supply to Zaaiplaas | Zaaiplaas Village Reticulation Phase 2 | Construction of Dindela Reservoir. Commissioning of bulk pipeline and pump station. | Percentage completion of Zaaiplaas village reticulation including rerservior & bulk pipeline | 100% completion of Zaaiplaas village reticulation including rerservior & bulk pipeline | 20% construction of Dindela Reservoir, 90% construction of bulk pipeline, 80% construction of pump station. | 50% construction of Dindela Reservoir, 95% construction of bulk pipeline, 94% construction of pump station. | 100% construction of Dindela Reservoir, 100% construction of bulk pipeline, 100% construction of pump station. | Testing and commissioning | 5000000 | Monthly reports and practical completion certificate
To finalize construction of Zaaiplass water reticulation by December 2017. | Financial and Human Resource | Completed BWS | Improved water supply to Zaaiplaas | Zaaiplaas Connector pipes from Bulk to villages incl. reservoirs (Khathazweni, Rondebosh,Kosini,Mathula,Khathazweni,Areaganeng,Jeije,Sehlakwane,Elandslaagte and Dindela) | 80% construction of Zaaiplass water reticulation (Construction reservoirs 80%; bulk line 80%). | Percentage Construction of Zaaiplass Connector Pipes. | 100% construction of Zaaiplass water reticulation (Construction reservoirs 100%; bulk line 100%). | 70% construction of Zaaiplass water reticulation (Construction reservoirs 80%; bulk line 80%). | 100% construction of Zaaiplass water reticulation (Construction reservoirs 100%; bulk line 100%). | Testing and Commissioning | n/a | 7606590.67 | Monthly reports and practical completion certificate
To commission Tafelkop Reticulation and Cost Recovery by June 2018 | Financial and Human Resource | Completed Tafelkop water reticulation network | Improved water supply to Tafelkop | Tafelkop Reticulation and Cost Recovery | 60% Construction of Tafelkop reticulation projects | Percentage (%) Commissioning of Tafelkop Reticulation and Cost Recovery | 100% Commissioning of Tafelkop Reticulation and Cost Recovery ( Snag listing 50% and testing 50%) | 80% Commissioning of Tafelkop Reticulation and Cost Recovery ( Snag listing 20% and testing 20%) | 90% Commissioning of Tafelkop Reticulation and Cost Recovery ( Snag listing 50% and testing 50%) | 100% Commissioning of Tafelkop Reticulation and Cost Recovery ( Snag listing 50% and testing 50%) | Testing and Commissioning 10% | 7972483 | Monthly reports and practical completion certificate
To construct VIP sanitation units by June 2018 within Makhuduthamaga Municipality | Financial and Human Resource | 1 835 VIP Sanitation toilets completed | Improved health and hygiene | VIP Sanitation programme phase 2.2 | 15 180 VIP Units constructed | Number of VIP sanitation Units constructed | To construct 1 835 VIP sanitation units | Finalize beneficiary list, establishment of Project Steering Commitees, appointment of CLOs and Appointment of Contractors | 600 VIP Sanitation toilets completed | 1 200 VIP Sanitation toilets completed | 1 835 VIP Sanitation toilets completed | 25000000 | Monthly reports, practical completion reports, happy letters
To construct Sekwati Reticulation upgrade Phase 4 by December 2017 | Financial and Human Resource | Completed Sekwati water reticulation network | Improved water supply to Sekwati | Sekwati Reticulation upgrade Phase 4 | 90% Construction of Sekwati Reticulation upgrade Phase 4 | Percentage Construction of Sekwati Reticulation upgrade Phase 4 | 10% Construction of Sekwati Reticulation upgrade Phase 4 | 5% Construction of Sekwati Reticulation upgrade Phase 4 | 10% Construction of Sekwati Reticulation upgrade Phase 6 | Test and commissioning |  | 6958280.06 | Monthly reports and practical completion certificate
To construct Ga Moloi Water Supply water supply by December 2017. | Financial and Human Resource | Completed Ga-Moloi water reticulation network | Improved water supply to Ga-Moloi | Ga Moloi area and surrounding villages water supply (contract B and C) | 90% Construction of reticulation lines at Morgenzon and Stad Van Masleroem; Gravity main, installation of street taps. | Percentage Construction of reticulation lines at Morgenzon and Stad Van Masleroem; Gravity main, installation of street taps. | 10% Construction of reticulation lines at Morgenzon and Stad Van Masleroem; Gravity main, installation of street taps. | 5% Construction of reticulation lines at Morgenzon and Stad Van Masleroem; Gravity main, installation of street taps. | 10% Construction of reticulation lines at Morgenzon and Stad Van Masleroem; Gravity main, installation of street taps. | Test and commissioning |  | 7331650.4718 | Monthly reports and practical completion certificate
To construct reticulation network in Ga-Mashabela by June 2018 | Financial and Human Resource | Completed Ga-Mashabela water reticulation network | Improved water supply to Ga-Mashabela | Ga-Mashabela water reticulation supply | Technical report approval and MIS registration | Percentage of construction completed | 100% construction completed | 0% construction completed, appointment of contractors and site establishments | 10% construction completed | 50% construction completed | 100% construction completed | 34642003.0982 | Monthly reports and Technical report
To construct reticulation network in Ga-Marishane by June 2018 | Financial and Human Resource | Completed Ga-Marishane water reticulation network | Improved water supply to Ga-Marishane | Ga-Marishane water reticulation supply | Technical report approval and MIS registration | Percentage of construction completed | 100% construction completed | 0% construction completed, appointment of contractors and site establishments | 10% construction completed | 50% construction completed | 100% construction completed | 22925159.9 | Monthly reports and practical completion certificate
To construct reticulation network in Maloma by June 2018 | Financial and Human Resource | Completed Maloma and surrounding (Lebating and Tsupani) water reticulation network | Improved water supply to Maloma and surrounding (Lebating and Tsupani) | Maloma and surrounding (Lebating and Tsupani) water supply | Technical report approval and MIS registration | Percentage of construction completed | 100% construction completed | 0% construction completed, appointment of contractors and site establishments | 10% construction completed | 50% construction completed | 100% construction completed | 8045410.12 | Monthly reports and practical completion certificate
To construct reticulation network in Lobethal by June 2018 | Financial and Human Resource | Completed Lobethal water supply | Improved water supply to Lobethal | Lobethal water supply | Technical report approval and MIS registration | Percentage of construction completed | 100% construction completed | 0% construction completed, appointment of contractors and site establishments | 10% construction completed | 50% construction completed | 100% construction completed | 10855220.6 | Monthly reports and practical completion certificate
To construct reticulation network in Ga-Phaahla by June 2018 | Financial and Human Resource | Completed Ga-Phaahla water supply | Improved water supply to Ga-Phaahla water supply | Ga-Phaahla water supply | Technical report approval and MIS registration | Percentage of construction completed | 100% construction completed | 0% construction completed, appointment of contractors and site establishments | 10% construction completed | 50% construction completed | 100% construction completed | 27448984.9 | Monthly reports and practical completion certificate
To finalize Nkadimeng: Phase 9 to 11 (Makhuduthamakga) - Ditlabaneng, Letlhabile,Tshatane, Sebetsane, Kgoalane & MAtseben`9E | Financial and Human Resource | Concrete reservoirs; Bulk Water Supply;Reticulation. | Improved Living standards. | Nkadimeng: Phase 9 to 11 (Makhuduthamakga) - Ditlabaneng, Rampelane, Matsebeng, Sebetsane, Kgoalane, Mathibeng, Dinotsi, Matolokwane) | 65% Completion of Concrete reservoirs; Bulk Water Supply; Reticulation. | Percentage Completion of Concrete reservoirs; Bulk Water Supply; Reticulation. | 100% Completion of Concrete reservoirs; Bulk Water Supply; Reticulation. | 70% Completion of Concrete reservoirs; Bulk Water Supply; Reticulation. | 80% Completion of Concrete reservoirs; Bulk Water Supply; Reticulation. | 100% Completion of Concrete reservoirs; Bulk Water Supply; Reticulation. | Test and commissioning | 1418565.85 | Monthly reports and practical completion certificate
To construct VIP sanitation units by June 2018 within LIM 476 Municipality (Fetakgomo area) | Financial and Human Resource | 715 VIP Sanitation toilets completed | Improved health and hygiene | VIP Sanitation programme phase 2.2 | 15 180 VIP Units constructed | Number VIP Units constructed | 715 VIP sanitation units | Finalising Beneficiery list, Establishment of Steering commitees, appointment of CLOs and Appointment of Constractors | 300 VIP Sanitation toilets completed | 600 VIP Sanitation toilets completed | 715 VIP Sanitation toilets completed | 15870000 | Monthly reports and practical completion certificate
To implement Borehole Refurbishment Southern Zone by June 2018 | Financial and Human Resources | Refurbished and new developed Water Boreholes | Improved Water Supply | Olifantspoort South Contract 21,22, 24 & 25: Water supply network | Water supply below RDP level | Percentage Completion of boreholes developed and Refurbishment Southern Zone | 70% Completion of boreholes developed and Refurbishment Southern Zone | 10% Implementation of borehole Refurbishment Southern Zone | 30% Implementation of borehole Refurbishment Southern Zone | 45% Implementation of borehole Refurbishment Southern Zone | 70%% Implementation of borehole Refurbishment Southern Zone | 18895159.89 | Monthly reports and practical completion certificate
To complete Concrete reservoirs; Bulk Water Supply; Reticulation Nkadimeng: Phase 9 to 11 | Financial and Human Resources | Nkadimeng: Phase 9 to 11 (Makhuduthamaga) - | Improved Living standards. | Nkadimeng RWS Extension 2( Phase 9 to 11) (Fetakgomo) Ga-Mmela to Mashilavele, Ga-Pahla, Molapong, Ga-Magolego, Mankontu and Masehleng | Nkadimeng WTW, Command Reservoir, reticulation and bulk line below RDP level. | Percentage Completion of Concrete reservoirs; Bulk Water Supply; Reticulation. | 80% Completion of Concrete reservoirs; Bulk Water Supply; Reticulation. | 20% Completion of Concrete reservoirs; Bulk Water Supply; Reticulation. | 60% Completion of Concrete reservoirs; Bulk Water Supply; Reticulation. | 80% Completion of Concrete reservoirs; Bulk Water Supply; Reticulation. | 0% | 47038314.95 | Monthly reports and practical completion certificate
To construct VIP sanitation units by June 2018 within LIM 476 Muniipality (Greater Tubatse area) | Financial and Human Resource | 715 VIP Sanitation toilets completed | Improved health and hygiene | VIP Sanitation programme phase 2.2 | 15 180 VIP units contructed | Number of VIP sanitation units | 1630 VIP sanitation units | Finalising Beneficiery list, Establishment of Steering commitees, appointment of CLOs and Appointment of Constractors | 300 VIP Sanitation toilets completed | 600 VIP Sanitation toilets completed | 1 630 VIP Sanitation toilets completed | 30000000 | Monthly reports and practical completion certificate
To construct Command Reservoir, pump station and pipelines at GaMaphopha by June 2017. | Improved water supply | Ga - Maphopha Command Reservoir | Improved Living standards. | Ga - Maphopha Command Reservior | 60% completion of Maphpha command reservoir, pumpsation and pipelines | Percentage completion of Command Reservoir, pump station and pipelines | 100% completion of Command Reservoir, pump station and pipelines | 80% completion of Command Reservoir, pump station and pipelines | 100% completion of Command Reservoir, pump station and pipelines | Testing and Commissioning of 25M? reservoir . | Testing and Commissioning of 25M? reservoir . | 16000000 | Monthly reports and practical completion certificate
To construct reticulation network in Lebalelo South by June 2018 | Improved water supply | Lebalelo South connector pipes completed | Improved Living standards. | Lebalelo South connector pipes | Technical report approval and MIS registration | Percentage construction completed | 50% construction completed | Procurement of service provider | 10% construction completed | 35% construction completed | 50% construction completed | 102478995 | Monthly reports
To construct reticulation, reservoir, stand pipes at Ga-Malekane , Masha, GaMaepa by June 2018 | Improved water supply | Ga-Malekane , Masha upgrade and extend reticulation | Improved Living standards. | Ga-Malekane , Masha upgrade and extended reticulation | 65% completion of reticulation, reservoir, stand pipes at Ga-Malekane , Masha, GaMaepa. | Percentage completion of reticulation, reservoir, stand pipes at Ga-Malekane , Masha, GaMaepa. | 35% completion of reticulation, reservoir, stand pipes at Ga-Malekane , Masha, GaMaepa. | 5% completion of reticulation, reservoir, stand pipes at Ga-Malekane , Masha, GaMaepa. | 15% completion of reticulation, reservoir, stand pipes at Ga-Malekane , Masha, GaMaepa. | 20% completion of reticulation, reservoir, stand pipes at Ga-Malekane , Masha, GaMaepa. | 35% completion of reticulation, reservoir, stand pipes at Ga-Malekane , Masha, GaMaepa. | 12000000 | Monthly reports
Name |  | Designation |  | Signature |  | Date
Manager : Governance & Regulations
Manager : Operation & Maintenance
Manager : Project Manager Unit
Manager : RBIG & WSIG
Deputy Director : IWS
Director : IWS