## Final 2017-18 Adjusted SDBIP
ADJUSTED 2017/2018 SERVICE DELIVERY BUDGET AND IMPLEMENTATION PLAN:
BASIC SERVICE DELIVERY
MEASURABLE OBJECTIVE | INPUT | OUTPUT | OUTCOME | PROJECT | BASELINE 2016/2017 | KEY PERFORMANCE INDICATORS | ANNUAL TARGET 2017/2018 | Q1 | Q2 | Q3 | Q4 | ACTION (Retained/Remove/ Adjust) | REASON FOR ACTION | ADJUSTED BUDGET 2017-18 | BUDGET 2017-2018 "R" | FINAL ADJUSTED | PoE
PLANNING, REGULATION AND GOVERNANCE
To develop WC/WDM Strategy for SDM by June 2018 | WSDP and Water Master Plan | Document on Water Conservation and Demand Management | Strategy on Water Conservation and Demand Management | Development of Water Conservation and Water Demand Management Strategy | Water Services Master Plan and WSDP developed in 2014/15 and the 2015/16 FY respectively | Number of WC/WDM Strategy developed | One WC/WDM Strategy developed | Development of Terms of Reference and appointment of service provider | Collection of information/Assessment of status quo | Appointment of service provider | Appointment of service provider | Adjust | Target not achievable | -300000 | 800000 | 500000 | Draft WC/WDM Strategy
To complete the line intergrity of sewer network in Groblersdal by June 2018 | Bulk sewer intervention plan Jan 2015 | Sewer upgrade plan | Enhansed sewer system | Upgrading of sewer Network in Groblersdal. | 1360m upgrade of the sewer collector line | Percentage completion of the line intergrity of sewer network in Groblersdal | 100% completion of the line intergrity of sewer network in Groblersdal | Complete CCTV line survey | Install and monitor flow meters at the WWTW | No Activity | No activity | Adjust | Target not achievable | 0 | 500000 | 500000 | Progress report and Status quo report
To conduct condition assessment and develop O & M plan by June 2018 | Asset register | Document | Preventative and reactive O&M plan | Conduct Condition Assessment and develop Operation and maintenance plans | Terms of reference developed and incorporated into the asset management plan contract and tender advertised for the PSP appointment | Percentage conduct of condition assessment and 0 & M plan developed | 60% conduct of conditional assessment and 0 & M plan developed | Appointment of service provider & Methodology approach for, condition assessment and O & M plan | 20% Development of O&M plan and Condition assesment of IWS infrastructure conducted | 20% O&M plan 0% condition assesment draft of IWS infrastructure developed | 30% O&M plan 0% conditional assesment draft of IWS infrastructure developed | Adjust | Target not achievable | 0 | 800000 | 800000 | Progress report
To develop and submit Technical reports to DWS by June 2018 | Assignment of PSP to do the Technical Reports | Technical Reports | MIG registered Projectss | Development of technical reports | WSDP, IDP & Bulk Water Service Master completed in Plan 2014 | Number of technical reports developed and submitted to DWS | 3 technical reports developed and submitted | Assignment of the PSP to do source development and compile technical reports | 2 feasibility studies conducted and technical reports developed for Leballo South Villages Phase Two and submitted to DWS | 2 technical reports developed and submitted to DWS (Leballo South, Masakaneng ) | 1 technical reports developed and submitted to DWS (Sekwati) | Adjust target | Target not achievable | 1000000 | 5000000 | 6000000 | Letters, Minutes of Meeting and Technical Reports
PROJECT MANAGEMENT UNIT
RBIG
To construct pipeline from Burgersfort to Dresden pump station by June 2018 | Financial and Human Resource | Bulk supply line | Improved water supply | Construction of Mooihoek bulk water supply phase 4E | Mooihoek bulk water supply phase 4D completed | Number of Kilometers of bulk pipeline constructed | 3 Kilometers of bulk pipeline constructed | Detailed design and procurement of Contractor | Site establishment and 0.2km pipeline constructed | 1km of bulk pipeline constructed | 3 Km of bulk pipeline constructed | Adjust | Under estimated budget | 6000000 | 30000000 | 36000000 | Progress reports on Mooihoek phase 4E
To construct reservoir at Burgersfort by June 2018 | Financial and Human Resource | 2 X 5 Ml concrete reservoirs | Improved water supply | Mooihoek bulk water supply phase 4BB | 1 x 5ML resevoir completed Mooihoek Phase 4A | Percentage reservoir constructed | 70% , 2 X 5 Ml concrete reservoir constructed(35% of each reservior constructed) | 0% constructed, Detailed design and procurement of Contractor | 20% Construction of Reservoirs | 40% Construction of Reservoirs (20% of each reservoir constructed | 70% Construction of Reservoirs (35% of each reservior constructed) | Adjust | Annual target adjusted | 0 | 18000000 | 18000000 | Progress reports on Burgersfort reservoirs
To construct bulk pipeline from Praktiseer to Motodi by June 2018 | Financial and Human Resource | Bulk supply line | Improved water supply | Mooihoek bulk water supply phase 4F | Mooihoek bulk water supply phase 2 completed | Number of Kilometers of bulk pipeline constructed | 4 Kilometers of bulk water pipeline constructed | Detailed design and procurement of Contractor | Site establishment and 0.1km pipeline constructed | 2Km of bulk pipeline constructed | 4Km of bulk pipeline constructed | Retain | None | 0 | 29000000 | 29000000 | Progress reports on Praktiseer to Motodi bulk pipeline
To construct bulk pipeline from Praktiseer to Alverton by June 2018 | Financial and Human Resource | Bulk supply line | Improved water supply | Mooihoek bulk water supply phase 4G | Mooihoek bulk water supply phase 2 completed | Number of Kilometers of bulk pipeline constructed | 4 Kilometers of bulk water pipeline constructed | Detailed design and procurement of Contractor | Site establishment and 0.1km pipeline constructed | 1.5Km of bulk pipeline constructed | 4Km of bulk pipeline constructed | Adjust | Over estimated budget | -17500000 | 28000000 | 10500000 | Progress reports on Praktiseer to Alverton bulk pipeline
To construct pumping pipeline from T-off of Makgeru to the new 10ML reservoir at Schoonoord, construction of gravity pipeline. | Financial and Human Resource | Bulk supply line | Improved water supply | Nebo BWS Makgeru to Schoonoord BWS | Reservoir is 55% completed. *Pipeline is 45% completed | Percentage bulk pipeline constructed and reservoir completed. | 100% (100%bulk pipeline constructed and 100%reservoir completed). | *55% of bulk pipeline constructed *65% Reservoir completed. | *70% of bulk pipeline constructed *75% of Reservoir completed. | *80% of bulk pipeline constructed * 85% Reservoir completed. | *100% of bulk pipeline constructed *100% Reservoir completed. | Adjust | Annual target adjusted | 0 | 55000000 | 55000000 | Progress report and practical completion certificate
To test and commission bulk pipeline from Ga Malekana – to Jane Furse | Financial and Human Resource | Bulk supply line | Improved water supply | Nebo BWS PHASE1A Commissioning pipeline from Ga Malekana – to Jane Furse | 80% Nebo Phase1A pipeline completed . | Percentage of pipeline tested and commissioned | 100% pipeline tested and commisioned |  |  | 85% of pressure testing of pipeline completed | 100% of pressure testing of pipeline completed | New project | Inadequate funding | 0
To connect mechanical and Electrical (M & E) for the extensions to the Groblersdal Water Treatment Works by June 2018. | Financial and Human Resource | Mechanical & Electrical Installations | Improved water supply | Moutse BWS Project ( 13 &14) | The upgrading of WTW is completed | Percentage M&E components installed | 100% M&E components Installed | 80% Installation of pumps and electrical fittings. | 90% Installation of pumps and electrical fittings. | 30% Installation of pumps mechanical 20% electrical fittings. | 15% Installation of pumps mechanical 20% electrical fittings. | Adjust | Over estimated budget | -27000000 | 60000000 | 33000000 | Progress reports on electrical & mechanical components
To construct bulk pipeline and valve chambers by June 2018 | Financial and Human Resource | Bulk supply line | Improved water supply | Moutse BWS Project ( 7 to 12) | Bulk pipelines and valve constructed up 54%. | Percentage bulk pipeline constructed. | 100% bulk pipeline constructed. | *60% of bulk pipeline constructed. | *70% of bulk pipeline constructed. | *20% of bulk pipeline contruct 30% manholes | *20% Bulk pipes 20% contruction of manhole | [5 empty] | Progress reports
To Construct 100% of 1.1km 650m DIA and 500m of 450 DIA Steel Water Pipeline, 3LPE, Coated and cement Mortar lined | Financial and Human Resource | 1,1km 650mm DIA and500m 0f 450mm DIA Steel Water Pipeline, 3LPE, Coated and cement Mortar lined | Improved water supply | Mooihoek Tubatse BWS Phase 4C1:1,1km 650mm DIA and 500m 0f 450mm DIA Steel Water Pipeline | 80% of (1.1km 650m DIA and 500m of 450 DIA Steel Water Pipeline ) completed | Percentage completion of 1.1km 650m DIA and 500m of 450 DIA Steel Water Pipeline% | 100% of (1.1km 650m DIA and 500m of 450 DIA Steel Water Pipeline, 3LPE, Coated and cement Mortar lined) constructed |  |  | 100% of (1.1km 650m DIA and 500m of 450 DIA Steel Water Pipeline, 3LPE, Coated and cement Mortar lined) constructed | No activity | New project | New Project | 1500000 | 0 | 1500000 | Progress reports
To construct 80% of 400m long, 750mm diameter pipe line and 900m long, 450mm dimeter steel pipe line by June 2018. | Financial and Human Resource | 400m long, 750mm diameter pipe line and 900m long, 450mm dimeter steel pipe line | Improved water supply | Mooihoek Tubatse BWS Phase 4C1.2: 400m 0f 650mm DIA and 900m 0f 450mm DIA Steel Water Pipeline | 80% completion of 400m long, 750mm diameter pipe line and 900m long, 450mm dimeter steel pipe | Percentage completion of 400m long, 750mm diameter pipe line and 900m long, 450mm dimeter steel pipe | 100% of (completion of 400m long, 750mm diameter pipe line and 900m long, 450mm dimeter steel pipe) |  |  | 55% of (completion of 400m long, 750mm diameter pipe line and 900m long, 450mm dimeter steel pipe) | 80% of (completion of 400m long, 750mm diameter pipe line and 900m long, 450mm dimeter steel pipe) | New project | New Project | 26000000 | 0 | 26000000 | Progress reports
To construct 100% Mooihoek Tubatse Phase4C1.3 road crossing using pipe jacking method by June 2018 | Financial and Human Resource | 1 road crossing on R555, Motageng | Improved water supply | Mooihoek Tubatse BWS 4C 1.3: Pipe jacking | 80% Overall Completion of Road crossings. * Jacking at Road R555 at Apies. * Jacking at Road R555 at Fire Station. * Jacking at Road R555 to Penge Junction. *Jacking Railways crossin) | Percentage of road crossings constructed | 100% of (Overall Completion of Road crossings. * Jacking at Road R555 at Apies. * Jacking at Road R555 at Fire Station. * Jacking at Road R555 to Penge Junction. *Jacking Railways crossin) |  |  | 90% of (Overall Completion of Road crossings. * Jacking at Road R555 at Apies. * Jacking at Road R555 at Fire Station. * Jacking at Road R555 to Penge Junction. *Jacking Railways crossin) | 100% of ( Overall Completion of Road crossings. * Jacking at Road R555 at Apies. * Jacking at Road R555 at Fire Station. * Jacking at Road R555 to Penge Junction. *Jacking Railways crossin) | New project | New Project | 1000000 | 0 | 1000000 | Progress reports
To Construct 100% of Mooihoek Tubatse 4C2:2700m, 500mm DIA and 2600m,400mm DIA Steel Water Pipeline by June 2018. | Financial and Human Resource | 2700, 500mm DIA and 2600,400mm DIA Steel Water Pipeline | Improved water supply | Mooihoek Tubatse 4C2 :2700, 500mm DIA and 2600,400mm DIA Steel Water Pipeline, 3LPE, Coated and cement Mortar lined | *The overall progress is 80% completion. *Steel pipe installation & welding joints for 400mm Ø is 91%. *Steel pipe installation & elding joints for 500mm Ø is 83%. *Manhole chambers 58%. *Fittings 20% *Completion *Manhole chambers 44%. *Completion | Percentage Construction of 2700m, 500mm DIA and 2600, 400mm DIA Steel Water Pipeline. | 100% of (Construction of Mooihoek Tubatse 4C2:2700, 500mm DIA and 2600, 400mm DIA Steel Water Pipeline, Installation of chambers fittings) |  |  | 90% of (Construction of Mooihoek Tubatse 4C2:2700, 500mm DIA and 2600, 400mm DIA Steel Water Pipeline, Installation of chambers fittings) | 100% of (Construction of Mooihoek Tubatse 4C2:2700, 500mm DIA and 2600, 400mm DIA Steel Water Pipeline, Installation of chambers fittings) | New project | New Project | 6000000 | 0 | 6000000 | Progress reports
To Construct 100% of Mooihoek Tubatse 2 X 10 Ml Concrete reserviors including fittings, fencing, paving & kerbing. | Financial and Human Resource | Bulk supply line | Improved water supply | Construction of Mooihoek Tubatse 4H 2 X 10 Ml Concrete reserviors including fittings, fencing, paving & kerbing. | 100% of Mooihoek/Tubatse Bulk Water completed ( Phase 4d 3500m 650mm DIA and 1500, 450mm DIA steel water pipeline, installation of chambers and fittings) | Percentage Construction of Mooihoek Tubatse 2 X 10 Ml Concrete reserviors including fittings, fencing, paving & kerbing. | 5% Construction of Mooihoek Tubatse 2 X 10 Ml Concrete reserviors including fittings, fencing, paving & kerbing. (2,5% of each 10Ml reservior constructed) |  |  | 2,5% Construction of Mooihoek Tubatse 2 X 10 Ml Concrete reserviors including fittings, fencing, paving & kerbing.(1.25% of each 10Ml reservior completed) | 5% Construction of Mooihoek Tubatse 2 X 10 Ml Concrete reserviors including fittings, fencing, paving & kerbing.(2,5% of each 10Ml reservior constructed) | New project | New Project | 10000000 | 0 | 10000000 | Progress reports
WATER QUALITY
To generate water quality reports by June 2018 | WSDP and Water Master Plan | Regulatory Compliance | Improved service delivery | Generation of Water Quality Reports | 10 reports generated | Number of water quality reports generated | 12 water quality reports generated | 3 water quality reports generated | 6 water quality reports generated | 9 water quality reports generated | 12 water quality reports generated | Adjust | Reduced budget | -4500000 | 12000000 | 7500000 | Water quality reports
To conduct Full SANS 241 analysis by June 2018 | WSDP and Water Master Plan | Regulatory Compliance | Improved service delivery | Conduct Full SANS 241 Water Quality Analysis | Signed CSIR SLA in 2015/16 FY | Number of Full SANS 241 analysis conducted | 1 Full SANS 241 analysis conducted | n/a | n/a | n/a | 1 x Full SANS 241 analysis conducted | Adjust | Reduced budget |  |  |  | Full SANS 241 report
To purchaseLaboratories Chemical by June 2018 | WSDP and Water Master Plan | Regulatory Compliance | Improved service delivery | Purchase of Lab chemicals | Term contractors appointed | Percentage of lab chemical purchased | 100% lab chemical purchased | 25 % lab chemicals purchased | 50% lab chemicals purchased | 75% lab chemicals purchsed | 100 % lab chemicals purchased | Adjust | Reduced budget |  |  |  | Delivery notes and tax invoices for delivered lab chemicals
To participate in Blue and Green Drop Certification programme by June 2018 | WSDP and Water Master Plan | Regulatory Compliance | Improved service delivery | Plants participation in Blue and Green Drop Cerification Programme | 12 water treatment works participating in Blue Drop Certicification Programme in place | Number of plants participating in Blue and Green Drop Participation Programme | 15 water treatment works participating in Blue Drop and 15 wastewater treatment works participating in Green Drop Certification Programme | 15 water treatment works participating in Blue Drop and 10 wastewater treatment works participating in Green Drop Certification Programme | 30 water treatment works participating in Blue Drop and 20 wastewater treatment works participating in Green Drop Certification Programme | 15 water treatment works participating in Blue Drop and 15 wastewater treatment works participating in Green Drop Certification Programme | 15 water treatment works participating in Blue Drop and 15 wastewater treatment works participating in Green Drop Certification Programme | Adjust | Unrealistic target and reduced target |  |  |  | Action Plan on BDS and GDS monthly report
OPERATION AND MAINTENANCE
To resolve registered sanitation incidents within 14 days. | Financial and Human Resource | Reduced sewer spillage and environmental pollution | Improved green drop status | Sanitation incidents | 90% registered sanitation incidents | Number of registered sanitation incidents resolved within 14 days | 700 registered sanitation incidents resolved within 14 days | 90% registered sanitation incidents resolved within 14 days | 90% registered sanitation incidents resolved within 14 days | 525 registered sanitation incidents resolved within 14 days | 700 registered sanitation incidents resolved within 14 days | Adjust | Under estimated budget | 7800000 | 30000000 | 37800000 | Monthly reports
To resolve registered water incidents within 14 days. | Financial and Human Resource | Reduced non-revenue water losses | Improved no drop status. | Water incidents | 90% registered water incidents | Number of registered water incidents resolved within 14 days | 7000 registered water incidents resolved within 14 days | 90% registered water incidents resolved within 14 days | 90% registered water incidents resolved within 14 days | 5250 registered water incidents resolved within 14 days | 7000 registered water incidents resolved within 14 days | Adjust |  |  |  |  | Monthly reports
To render Tankering services by June 2018 | Financial and Human Resource | Consistent supply of water | Improved water supply | Delivery of Potable Water in Jane Furse Hospital and Buffelshoek | 90% of tankering services rendered | Number of Ml tankering services rendered in Jane Furse Hospital and Bufelshoek | 9.6 Ml delivery of Potable Water in Jane Furse Hospital and Buffelshoek | 90% of tankering services rendered in areas with no water source or infrastructure | 90% of tankering services rendered in areas with no water source or infrastructure | 7.2 Ml delivery of Potable Water in Jane Furse Hospital and Buffelshoek | 9.6 Ml delivery of Potable Water in Jane Furse Hospital and Buffelshoek | Adjust | Unrealistic project | 5500000 | 32000000 | 37500000 | Monthly Water delivery records and reports
To provide diesel consistently to diesel driven machines by June 2018 | Financial and Human Resource | Consistant water supply. | Reliable water supply. | Supply of Diesel | 80 000ℓ of diesel supplied | Number of Litres of diesel supplied annually | 40 000ℓ of diesel supplied annually. | 20 000ℓ of diesel supplied. | 20 000ℓ of diesel supplied. | 10 000ℓ of diesel supplied. | 10 000ℓ of diesel supplied. | Adjust | More pumps and motors converted to electricity | 400000 | 1750000 | 2150000 | Monthly reports
To provide Petrol consistently to petrol driven machines by June 2018 | Financial and Human Resource | Consistant water supply. | Reliable water supply. | Supply of Petrol | 5000ℓ petrol supplied | Number of Litres petrol supplied annually. | 400ℓ of petrol supplied annually. | 300ℓ of petrol supplied. | 300ℓ of petrol supplied. | 100ℓ of petrol supplied. | 100ℓ of petrol supplied. | Adjust | More pumps and motors converted to electricity |  |  |  | monthly reports
To provide Oil consistently to diesel and petrol driven machines by June 2018 | Financial and Human Resource | Consistant water supply. | Reliable water supply. | Supply of Oil | 1500ℓ of oil supplied | Number of Litres of oil supplied annually. | 300ℓ of oil supplied annually. | 180ℓ of oil supplied. | 180ℓ of oil supplied. | 75ℓ of oil supplied. | 750ℓ of oil supplied. | Adjust | Target not achievable |  |  |  | monthly reports
To resolve registered M & E incidents within 14 days | Financial and Human Resource | Consistent supply of water | Improved water supply | Mechanical and electrical services | 50% resolved registered M & E incidents within 14 days | Number of registered M & E incidents resolved within 14 days | 450 of registered M & E incidents within 14 days | 80% of registered water incidents resolved within 14 days | 80% of registered water incidents resolved within 14 days | 337.5 of registered M & E incidents within 14 days | 450 of registered M & E incidents within 14 days | Adjust | Target not talking to objectives | 0 | 3500000 | 3500000 | Monthly reports
To install bulk water meters by June 2018 | Financial and Human Resource | Consistent supply of water | Improved water supply | Installation of Bulk water meters . | Reservoirs in place | Number of bulk water meters installed. | 8 bulk water meters installed | Specifications developed, and procurement of service provider(s) | Delivery of 8 bulk water meters | Installation of 4 bulk water meters | Installation of 4 bulk water meters | Retain | None | -1000000 | 2000000 | 1000000 | Progress reports
To purchase Mℓ bulk water by June 2018 | Financial and Human Resource | Consistent supply of water | Improved water supply | Mℓ Bulk Water Purchases | 10 062 Mℓ of bulk water purchased. | Number Mℓ of water purchased | 10 062Mℓ of water purchased | 2 515 annual water volume purchased | 5 030 annual water volume purchsed | 7546 annual water volume purchased | 10 062 annual water volume purchased | Adjust | Demand increased | 30000000 | 64000000 | 94000000 | Delivery registers and Tax invoices
WSIG PROJECTS
To complete 100% Tukakgomo water intervention and refurbishment by June 2018 | Financial and human resource | Reticulated water supply | Improved access to safe, reliable drinking water. | Tukakgomo water intervention and refurbishment. | 1 borehole drilled and equipped. | Percentage completion of Tukakgomo water reticulation. | 100% completion of Tukakgomo water reticulation(1000m) ; refurbishment of rising main to high lift pumpstation, river abstraction point upgrading ; 2 existing borehole tested and equipped, and refurbishment of the highlift pumpstation and the low lift pumpstation. | Appointment of Consultant, designs and tender document development | Procurement of contractor and 10% construction of water reticulation network and steel tank platform construction | *Refurbishment of pumpstations at 20% *Equpping of borehole at 40% *Repairing of the rising main and gravity main at 20% *Reticulation network at 10% | *Refurbishment of pumpstation at 100% *Equpping of borehole at 100% *Repairing of the rising main and gravity main at 100% *Reticulation network at 100% *Testing and commissioning. | Adjust | Target not achievable Objective corrected | 0 | 4500000 | 4500000 | Monthly Report
To construct 1,8km of bulk pipeline; 6,23km reticulation and 29 standpipes by June 2018 | Financial and human resource | Reticulated water supply | Improved access to safe, reliable drinking water. | Mahlwakwena to Mapodile pipeline(Tukakgomo storage and reticulation) | Command reservoir at Mahlwakwena is completed. | Number of Kilometers of bulk pipeline constructed Number of standpipes constructed | *100% Construction of 639kl elevated steel tank. * Construction of 1.8km rising main. *Construction of 6.23km internal reticulation. *Installation of 29 standpipes. | Appointment of Consultant, designs and tender document development | Procurement of contractor and 1.5km of bulk pipeline constructed | *Appointment of Contractor. Site Establishment. *Clearing, Setting out, material on site. *Location and geotech for the elevated steel tank. *Excavations for rising main(500m). *Excavations for internal reticulation(1km). | *Construction of 639kl elevated steel tank at 100%. * Construction of 1.8km rising main completed. *Construction of 6.3km internal reticulation completed. *Installation of 29 standpipes. | Adjust | Target not achievable | 3000000 | 3000000 | 6000000 | Monthly Report
To complete 100% of Upgrading of Abstraction point by June 2018. | Financial and human resource | Source Identified | Improved access to safe, reliable drinking water. | Mampuru Water abstraction and reticulation network | 1,5ML WTW in place and abstraction point washed away. | Percentage completion of WTW and Abstarction point refurbishment. | 100% of Upgrading of Abstraction point, 1200m installation rising main from borehole to res and Equiping/testing of borehole, Upgrading of WTW, Upgrading of the pumpstation, 1000m of basic reticulation ,refurbish the rising main from WTW to the reservoir, Electrical & Mech for pumstation completed. | Appointment of Consultant, designs and tender document development | Procurement of contractor and 30% of Abstraction point constructed | *Refurbishment of WTW at 70%. *Equipping of borehole at 80% *Refurbishment of the abstraction point 50% *Reticulation network at 40%(400m). | *Refurbishment of Boschkloof WTW at 100%. *Equipping of borehole at 100% *Refurbishment of the abstraction point 100% *Reticulation network at 100%(1000m). *Refurbishment of rising main from WTW to the reservoir 100% *Installation of 1200m rising main from borehole. *Refurbishment of pumpstation 100%. * Electrical & Mech for pumstation completed. *Testing and commissioning. | Adjust | Target not achievable | 0 | 3500000 | 3500000 | Monthly Report
To construct 100% of rising main and reticulation by June 2018 | Financial and human resource | Reticulated water supply | Improved access to safe, reliable drinking water. | Rutseng Water Intervention | Skeletal water infrastructure in place | Percentage completion of source and of Kilometers of pipeline constructed | *100% Refurbishment of 6,2km rising main from the source to reservoir. *100% Refurbishment of the fountain. *100% Refurbishment of 340kl concrete reservoir. *Construction of 5,935km of reticulation. | Appointment of Consultant, designs and tender document development | Procurement of contractor and 1,5km of pipeline constructed | *50% Refurbishment of rising main(3,1km) from the source to reservoir. *100% Refurbishment of the fountain. *60% Refurbishment of 340kl concrete reservoir. | *100% Refurbishment of rising main(6,2km) from the source to reservoir. *100% Refurbishment of the fountain. *100% Refurbishment of 340kl concrete reservoir. *Testing and Commissioning | Adjust | Target not achievable | -1000000 | 3500000 | 2500000 | Monthly Report
To complete 100% of Rutseng water supply intervention by June 2018 | Financial and human resource | Reticulated water supply | Improved access to safe, reliable drinking water. | Phiring Water Intervetion | The existing booster pump station is vandalised. | Percentage Completion of Phiring water intervention | *100% Refurbishment of existing borehole. *100% Erection of 400kl steel tank. *100% Connecting the existing rising main to newly constructed steel tank. | Appointment of Consultant, designs and tender document development | Procurement of contractor and 1km bulk pipeline constructed | *Borehole equipping at 50%. *Footing for storage. | *Refurbishing of existing borehole at 100%. *Erection of 400kl steel tank. *Connecting the existing rising main to newly constructed steel tank. | Adjust | Target not achievable | 2659591.45 | 1000000 | 3659591.45 | Monthly Report
To complete 100% of Mamatjekele Package Plant by June 2018 | Financial and human resource | Packaged plant | Improved access to safe, reliable drinking water. | Completion of Mamatjekele Package plant | The borehole is equipped but producing polluted water. | Percentage completion of Mamatjekele Package Plant | *100% completion of Mamatjekele Package Plant | Appointment of Consultant, designs and tender document development | 20% Procurement of contractor and material. | *40% Installation of package plant *Excavations and preparations for installation of palisade fencing. | *100% Installation of package plant *100% installation of palisade fencing. *100% installation of transformer. *Testing and commissioning. | Adjusted | Scope breakdown added | 400000 | 3000000 | 3400000 | Monthly Report
To complete 100% of technical report for Jane Furse RDP Package Plant , 100% completion of risnig main and storage by June 2018. | Financial and human resource | Packaged plant | Improved access to safe, reliable drinking water. | Jane Furse RDP Package plant | The high yield borehole is equipped but producing polluted water. | Percentage completion of Jane Furse RDP Package Plant , Drilling, testing and equipping of borehole; construction of 600m rising main, connection to the existing RDP network, installation of concrete pumphouse, installation of 4x10kl jojo tanks. | 100% completion of Jane Furse RDP Package Plant , Drilling, testing and equipping of borehole;100% construction of 600m rising main, 100% connection to the existing RDP network,100% installation of concrete pumphouse, 100% installation of 4x10kl jojo tanks. | Appointment of Consultant, designs and tender document development | 20% Procurement of contractor and materials | 100% completion of technical report for Jane Furse RDP Package Plant , Drilling, testing and equipping of borehole;excavations of 600m rising main. | *100%Construction of 600m rising main *100% Connection to the existing RDP network. *100% Installation of concrete pumphouse. *100% installation of 4x10kl jojo tanks. *Eskom connections. *Testing and Commissioning. | Adjusted | Scope breakdown added | 0 | 2700000 | 2700000 | Monthly Report
To construct 100% of basic reticulation at Apel Cross by June 2018 | Financial and human resource | Reticulated water supply | Improved access to safe, reliable drinking water. | Apel Cross RDP Reticulation network | The high yield borehole is equipped but not connected to any infrastruture. | *Percentage completion of 240m of rising main , 594m of basic reticulation completed and 12 communal standpipes | *100% completion of 240m of rising main,. 100% completion of 594m of basic reticulation, 100% Relocation of existing elevated tankat and 12 communal standpipes | Appointment of Consultant, designs and tender document development | Procurement of contractor and materials | *Repositioning of steel tank at 80%. *Excavations for reticulation at 594m.. *Excavations for rising main at 60%. | *Construction of 240m of rising completed. *594m of basic reticulation completed *Relocation of existing elevated tank at 100% * 12 communal standpipes | Adjusted | Scope breakdown added | 0 | 2000000 | 2000000 | Monthly Report
To complete 100% of Moretsele water reticulation by June 2018 | Financial and human resource | Bulk Provisioning | Improved access to safe, reliable drinking water. | Moretsele water rising main | No formal water infrastrucutre in place. | Percentage completion of Moretsele Water Rising Main. | *100% completion of Moretsele Water Rising Main. (Drilling, testing and equipping of 2 boreholes, Installation of 74kl steel tank, Construction of 1000m rising main). | Appointment of Consultant, designs and tender document development | Procurement of contractor and materials | *Appointment of contractor. *Site establishment and clearing, material on site. *1km of excavation done for rising main. | *Borehole equipping at 99%. *1000m rising main installed. *Installation of 74kl steel tank completed. *Testing and commissioning | Adjusted | Scope breakdown added | 0 | 2000000 | 2000000 | Monthly Report
To complete 100% of water tight testing of 0.5ML reservoir in Mashishing, pressure test and disinfection of existing outket for reuse,install required fittings and further extension of the existing reservoir, equitable distribution/resource balance of water by June 2018. | Financial and human resource | WC/WD Management Provisioning | Improved access to safe, reliable drinking water. | Nebo Phase 1A testing and comissioning(Water Demand Management Provisioning). | Bulk line from GaMalekane to Jane Furse, Pumpstations, WTW and 25 ML Reservoir. | Percentage completion of Nebotesting and commissioning . | 100% completion of Nebotesting and commissioning . (100% of water tight testing of 0.5ML reservoir in Mashishing. *100% Pressure test and disinfection of existing outket for reuse. *100% Install required fittings and further extension of the existing reservoir' *100% Equitable distribution/resource balance of water | 33km bulk pipeline tested and commissioned. | 33km bulk pipeline tested and commissioned. | *Site Establishment. *Clearing, Setting out, material on site. | *100% of water tight testing of 0.5ML reservoir in Mashishing. *Pressure test and disinfection of existing outket for reuse. *Install required fittings and further extension of the existing reservoir' *Equitable distribution/resource balance of water . | Adjusted | Target not achievable, Scopen breakdown added | -8024300 | 13000000 | 4975700 | Monthly progress reports
100% development of water source and preparation of Technical Report for reticulation of Uitspanning by June 2018. | Financial and human resource | Developed source | Improved access to safe, reliable drinking water. | Uitspanning Water Source developmement | Groblersdal WTW and Moutse bulk pipeline in progress. | Number of boreholes drilled and tested and technical report compiled | 2 boreholes drilled and tested and 1 technical report compiled. | *Appointment of PSP and Approval of Designs. | 2 Drill borehole(s), equip boreholes and water quality testing | *Approval of Technical report by DWS. | *Equipping and testing of 2 boreholes. *Technical report at 100% | Adjusted | None | 0 | 2000000 | 2000000 | Technical report
100% development water source and preparation of Technical Report at villages around Madibong village by June 2018. | Financial and human resource | Developed source | Improved access to safe, reliable drinking water. | Madibong Water Supply | Jane furse 25Ml completed. | Number of boreholes drilled and tested. | 3 boreholes drilled and tested. | *Appointment of PSP and Approval of Designs. | *Procurement of contractor and materials | *Drilling, testing of three boreholes. | *No Activity(Awaiting commissioning of PH1A. | Retained | None | -500000 | 1500000 | 1000000 | Geohydrological studies
100% development of 3 boreholes,Electrical pumps, and rising main by June 2018. | Financial and human resource | Developed source | Improved access to safe, reliable drinking water. | Uitvlught Water Supply | Groblersdal WTW and Moutse bulk pipeline in progress. | Percentage completion of boreholes, drilling and testing, rising main, installation of concrete pump houses and Eskom connection. | 100% completion of boreholes, drilling and testing, (5,040km )rising main, installation of concrete pump houses and Eskom connection. | *Appointment of PSP and Approval of Designs. | *Procurement of contractor and materials | *Boreholes drilling and testing at 100 %. *Boreholes Equiping at 0%. *2000m Excavations for rising main. *2000m Pipeline installation . | *Electrical pumps. *Eskom connections *Construction of 5040m uPVC rising main constructed. *Testing & Commissioning. | Retained | None | 0 | 3000000 | 3000000 | Monthly reports
|  |  | Improved access to safe, reliable drinking water. | Keerom Water Supply | Groblersdal WTW and Moutse bulk pipeline in progress. |  |  | *Appointment of PSP and Approval of Designs. | *Procurement of contractor and materials |  |  | Retained | None | 0 | 3000000 | 3000000 | Monthly reports
To complete 100% of Diphaganeng by June 2018. | Financial and human resource | Developed source | Improved access to safe, reliable drinking water. | Diphaganeng Water Supply | The borehole is equiped and connected to JoJo tank. | Percentage completion of rising main, source development , installation of concrete pump houses and eskom connection | 100% completion of rising main, source development , installation of concrete pump houses and eskom connection | *Appointment of PSP and Approval of Designs. | *Procurement of contractor and materials | *Testing and equipping of borehole at 60% *Excavations at 40% for rising main. *1km Rising main installed. | *Rising main installation at 100%(1000m). *Testing and commissioning. | Retained | None | 600000 | 2300000 | 2900000 | Monthly reports
To construct 100% Rathoke Water Supply Supply by June 2018. | Financial and human resource | Developed source | Improved access to safe, reliable drinking water. | Rathoke Bulk Water Supply | Groblersdal WTW and Moutse bulk pipeline in progress. | Percentage completion of boreholes testing and equiping,refurbusment of existing tank, rising main and communal standpipes. | 100% completion of boreholes testing and equiping,refurbusment of existing tank, rising main(1km) and communal standpipes (7). | *Appointment of PSP and Approval of Designs. | *Procurement of contractor and materials | *Refurbishment of existing storage at 60%. *Testing, equiping of borehole at 100% * 600m Installation of rising main. *Excavations for rising main at 80%. *Construction of a rising main at 60% | *Construction of 1000m rising main at 100%. *Installation of 7 comkmunal standpipes. *Eskom connections. *Testing and commissioning. | Retained | None | 0 | 3000000 | 3000000 | Monthly reports
To construct 100% of pipeline ,storage and installation of meters by June 2018. | Financial and human resource | WC/WD Management Provisioning | Improved access to safe, reliable drinking water. | Flag Boshielo WC/WD Management( Letebejane pilot project) | The village is fully reticulated & supplied water for 24hrs without payment. | Percentage Installation of JOJO Tanks, Installation of reticulation,Installation of meters, Provisioning of WC/WD Management Planand Effecting Pressure Management Zones | *100% Installation of 5x 10kl JOJO Tanks, Installation of 9km reticulation,Installation of 481 meters, Provisioning of WC/WD Management Planand Effecting Pressure Management Zones | *Appointment of PSP and Approval of Designs. | *Procurement of contractor and materials | * Praparation for Installation of 5x 10kl JOJO Tanks. *Installation of 4km reticulation. *Installation of 200 meters. | *Installation of 5x 10kl JOJO Tanks. *Installation of 9km reticulation. *Installation of 481 meters. *Provisioning of WC/WD Management Plan. *Effecting Pressure Management Zones | Adjusted | Scope increased to address functionality of existing infrastructure before the meters can be installed. | 1235132 | 3000000 | 4235132 | Monthly reports
To install 100% of package plant in Tjibeng by June 2018. | Financial and human resource | Packaged plant | Improved access to safe, reliable drinking water. | Refurbishment of Tjibeng package plant | The package plant is dilapitated. | Percentage Testing of existing borehole. *One package plant installed at Tjibeng . *Refurbishment of existing fence. | *100% Testing of existing borehole. *One package plant installed at Tjibeng . *Refurbishment of existing fence. | *Appointment of PSP and Approval of Designs. | *Procurement of contractor and materials | *60% installation of package plant. *Testing of existing borehole. | *Refurbishment of existing fencing. *100% intallation of package plant | Retained | None | 0 | 3500000 | 3500000 | Monthly reports
100% development of water source and install rising main at Maebe by June 2018 | Financial and human resource | Developed source | Improved access to safe, reliable drinking water. | Maebe drilling and equipping of borehole | No formal water infrastrucutre in place. | Percentage completion of boreholes drilled, tested and equipped, Installation of rising main. *Business Plan finalized for installation of package plant. | * 100% completion of 3 boreholes drilled, tested and equipped. *100% Installation of 3,5 km rising main. *Business Plan finalized for installation of package plant. | *Appointment of PSP and Approval of Designs. | *Procurement of contractor and materials | *Site Establishment. *Clearing, Setting out, material on site. *Borehole drilling,equipping and testing at 60% | *Equipping of three boreholes. *Construction of 3,5 km rising main. *Business plan finalized for package plant. | Adjusted | Target not achievable | -422865 | 3000000 | 2577135 | Scoping report
To construct 334 VIDP Sanitation units by June 2018 | Financial and human resource | Onsite sanitation, health hygiene & user education | Improved access to safe, reliable sanitation service | Construction of Moretsele VDIP | New Infrastructure | Number of VIDP sanitation units constructed | 334 VIDP Sanitation units constructed | *Procurement of Contractor | *100 hh provided with VIDPs | *334 pits excavated. *204 pit linnings completed. * 245 units installed. | *334 VIDP's installed. * 334 pit linnings. *334 units installed. *Final inspection and closeout. | Retained | None | 447933 | 4500000 | 4947933 | Monthly report
To complete 100% of refurbishment of Thabampshe pump station by June 2018. | Financial and human resource | Developed source | Improved access to safe, reliable drinking water. | Thabampshe refurbishment of a pumpstation | Pump station and reservoir structure in place | Percentage refurbishment of Thabampshe water pump station ( 2 pumps, motors and electrical panel and replacement of valves and testing of rising main ) Installation of fence | *100% refurbishment of Thabampshe water pump station ( 2 pumps, motors and electrical panel completed and replacement of valves and testing of rising main) * Installation of fencing. | *Procurement of Contractor | 25% refurbishment of Thabampshe water pump station ( 2 pumps, motors and electrical panel completed and replacement of valves and testing of rising main | 50% refurbishment of Thabampshe water pump station ( 2 pumps, motors and electrical panel completed and replacement of valves and testing of rising main | 100% Fencing. 100% Alignment of pumps. Testing & Commissioning. | Retained | None | 1300000 | 2000000 | 3300000 | Monthly progress report
100% source development and installation of solar panels on pump station by June 2018 | Financial and human resource | Developed source | Improved access to safe, reliable drinking water. | Leolo Water Intervention | Delapidated infrastructure | Percentage Installation of solar panels on the pump statatopn and Source development. | *100% Installation of solar panels on the pump station. *100% Source development. | One pumpstation refurbished.1500 pipeline to the two boreholes installed. | One pumpstation refurbished.1500 pipeline to the two boreholes installed. | *100% source development. | *Installation of solar panels on the pump station. | Adjusted | Target not achievable | -2400000 | 3000000 | 600000 | Notice letter
To complete 100% of Gakomane supply intervention by June 2018. | Financial and human resource | Reticulated water supply | Improved access to safe, reliable drinking water. | GaKomane Water Supply Intervention | No formal water infrastrucutre in place. | Percentage completion of drilling, Testing and Equipping of borehole, Installation of rising main, Erection of jojo tanks and Communal standpipes. | *100% completion of drilling, Testing and Equipping of borehole. *100% Installation of 4km rising main. *100% Erection of 4x 10 000kl jojo tanks. *2 communal standpipes. |  |  | *Drilling, Testing of borehole. *Installation of 1km rising main. | *Installation of 4km rising main. *Erection of 4x 10 000kl jojo tanks. *2 communal standpipes. | Adjusted | Roll over not approved | 2000000 | 2200000 | 4200000 | Monthly report
To construct 100% of water supply intervention at Phashamagalanoto by June 2018 | Financial and human resource | Reticulated water supply | Improved access to safe, reliable drinking water. | Phashamagalanoto Water Supply Intervention | Water supply below RDP | Percentage competion of Drilling, testing & Equipping of borehole, reticulation network. rising main,elevated steel and Installation standpipes | *100% Drilling, testing & Equipping of 2 borehole. *100% competion 5,7240km of reticulation network. *100% completion of 700m of rising main. *100% Installation of one 252kl elevated steel tank. *100% Installation of 32 standpipes |  |  | * 3,8km of reticulation network and gravity main. *0.6km of 90mm diameter rising main. | *Installation of one 252kl elevated steel tank. *Installation of 32 standpipes. *Eskom connections *Testing & Commissioning. | Adjusted | Roll over not approved | 0 | 4509902 | 4509902 | Monthly reports
To construct 100% of one 200kl elevated steel tank and the 3000m length of 65mm diameter pipeline June 2018 | Financial and human resource | Bulk Provisioning | Improved access to safe, reliable drinking water. | Mohlaletsi Maroteng water supply Ext | Inadequate storage | Percentage construction of elevated steel tank, construction of rising main, Refurbishment of the existing borehole(concrete pumphouse), reticulation and Stand pipes. | 100% construction of 254kl elevated steel tank 100% construction of 1,400 km rising main, 100% , Refurbishment of the existing borehole(concrete pumphouse), 100% Construction of 1,033 Km reticulation, 100% Installation of 8 Stand pipes. |  |  | * 1,2Km length of rising main. * Base for the pumphouse | *0ne 254kl elevated steel tank installed at 100%. * 1,4km rising main. *Concrete pumphouse completed. *1,033km reticulation constructed. *??? Standpipes installed. *Installation of ??? Stanpipes. | Adjusted | Roll over not approved | 0 | 2862686 | 2862686 | Monthly report
To construct 100% of pipelines and storage at GaMoretsele by June 2018 | Financial and human resource | Reticulated water supply | Improved access to safe, reliable drinking water. | Ga-Moretsele (New Section) Water Supply Ext | Inadequate water source | *Percentage completion of Drilling & Equipping of borehole, completion of reticulation network, completion rising main and Installation steel tank | *100% completion of Drilling & Equipping of borehole. *100% completion of 3,5km of 75mm reticulation network . *100% completion of 0,5km rising main. *100% Installation of 74kl steel tank |  |  | *1km of reticulation network . *0.3km of 90mm diameter rising main. *Installation of 73kl steel tank @ 30% | *3,5km of 75mm diameter reticulation network . *0,5km of 90mm diameter rising main. *Testing and Commisioning | Adjusted | Roll over not approved | 0 | 2685773 | 2685773 | Monthly Report.
To construct 100% of pipelines and storage at Thokwane by June 2018 | Financial and human resource | Reticulated water supply | Improved access to safe, reliable drinking water. | Thokwane Borehole equipping | Dilapilated infrastructure | *Percentage competion reticulation network,rising mainand Number of Jojo Tanks erected. | *100% competion 3,5km of 75mm reticulation network. *100% competion of 1,2km of 90mm rising main. *Four Jojo Tanks erected. |  |  | *1,5km of 75mm diameter reticulation network. *0,8km of 90mm diameter rising main. *Two steel tanks Tanks(450 and 200kl). | *3,5km of 75mm diameter reticulation network. *1,2km of 90mm diameter rising main. *Two steel Tanks erected and completed. *Borehole equipped and tested at 100% | Adjusted | Roll over not approved | 0 | 5332903 | 5332903 | Monthly Report
To construct 100% of pipelines and storage at Praktiseer by June 2018 | Financial and human resource | Bulk Provisioning | Improved access to safe, reliable drinking water. | Praktiseer Extension of Water Supply | Dilapilated infrastructure | Percentage construction of rising main, installation of elevated steel tanks, Drilling,testing and equipping of boreholes, Construction of reticulation and Number of standpipes installed. | 100% construction of 2km rising main. 100% installation of elevated steel tanks, 100% Drilling,testing and equipping of two boreholes, 100% Construction of 1km reticulation and installation of 12 standpipes. |  |  | *2km rising main, two elevated steel tanks installed, Construction of 1km reticulation; installation of 12 standpipes . | *Eskom connections. *Testing & Commissioning | Adjusted | Roll over not approved | -3960245.45 | 5000000 | 1039754.55 | Practical completion certificate
100% Refurbishment of two oxidation ponds by June 2018. | Financial and human resource | Onsite sanitation, health hygiene & user education | Improved access to safe, reliable sanitation service | Mapodile Oxidation Ponds | Dilapilated infrastructure | Number of oxidation ponds refurbished. | 2 oxidation ponds refurbished. |  |  | Halted | Halted | Adjusted | Roll over not approved | -2077135 | 2500000 | 422865 | Legal documents
To construct 100% of pipeline and storage by June 2018 | Financial and human resource | Reticulated water supply | Improved access to safe, reliable drinking water. | Magagamatala Borehole Equipping | Inadequate water source | Percentage completion of Drilling, testing & equipping ,rising main and installation of jojo tanks. | 100% completion of Drilling, testing & equipping of 1 borehole. 100% completion of 5km rising main and 100% installation of 4x 10kl jojo tanks |  |  | No Activity | No Activity | Adjusted | Roll over not approved | -3809004.34 | 4000000 | 190995.66 | Completion certificate
To construct 100% of elevated steel tank and booster pump station by June 2018 | Financial and human resource | Bulk Provisioning | Improved access to safe, reliable drinking water. | Rathoke Water Supply Ext | Inadequate infrastructure | Percentage completion of Booster pumpstation, elevated steel tank and connection to the existing rising main constructed. | 100% completion of Booster pumpstation, 100% Installation of 1ML elevated steel tank, 100% connection to the existing rising main constructed. |  |  | Construction of the steel reservoir at 90%. Construction of the booster pump house at 80%. | *Construction of the steel reservoir at 100%. Construction of the booster pump house at 100%. *Connection of the existing rising main. *Eskom connection *Testing & Commissioning | Adjusted | Roll over not approved | 0 | 1199255 | 1199255 | Monthly Report
To refurbish 100% of existing infrastructure and complete water reticulation network by June 2018 | Financial and human resource | Reticulated water supply | Improved access to safe, reliable drinking water. | Leeuwfontein Water Reticulation | Dilapilated infrastructure | Percentage completion of Drilling, testing & Equipping of boreholes, rising main, Concrete pumphouse and palisade | 100% completion of Drilling, testing & Equipping of 3 boreholes, 100% 2,5km rising main, 100% completion of Concrete pumphouse , 100% completion of palisade |  |  | *Construction of 2,5km of rising main. *Construction of 3 borehole pump houses and palisade fencing at 100%. *Eskom connections. | *Energising. Testing & Commissioning. | Adjusted | Roll over not approved | 0 | 854517 | 854517 | Practical completion certificate
To construct 100% of pipeline and reticulation by June 2018 | Financial and human resource | Bulk Provisioning | Improved access to safe, reliable drinking water. | Zaaiplaas(Mzimdala) Borehole Equipping | Inadequate water source | Percentage completion of reticulation network, rising main, steel tank , drilling and equipping of borehole and Number of communal standpipes installed . | 100% completion of 3368m reticulation network, 100% completion of 1,595km rising main, 100% installation of 50kl steel tank , 100% drilling and equipping of 1 borehole and 10 communal standpipes installed . |  |  | *3,368km of pipeline installed. *60 % of steel tank erected. *1,595km rising main installed. *Drilling and equipping of borehole completed | *100% steel tank installed *Eskom connections *10 standpipes completed. *Testing ans commissioning completed. | Adjusted | Roll over not approved | 0 | 2318157 | 2318157 | Monthly Report
To construct 100% of reticulation extension and installation of meters by June 2018 | Financial and human resource | WC/WD Management Provisioning | Improved access to safe, reliable drinking water. | Mooihoek(Tsimanyane) Water Supply Extension | Inadequate infrastructure | Percentage completion of reticulation extension and Number of meters installed | *100% completion of 1,5km of reticulation extension. *120 meters installed |  |  | No Activity | No Activity | Adjusted | Roll over not approved | 0 | 87701 | 87701 | Completion Certificate
MIG
To construct VIP Sanitation units by June 2018 within Ephraim Mogale Municipality | Financial and Human Resource | 1 020 VIP Sanitation toilets completed | Improved health and hygiene | VIP Sanitation programme phase 2.1 | 15 180 VIP Units constructed | Number of VIP sanitation units constructed | 1 295 VIP Sanitation units constructed | Finalize beneficiary list, establishment of Project Steering Commitees, appointment of CLOs and Appointment of Contractors | 200 VIP Sanitation toilets completed | 383 VIP Sanitation toilets completed | Final handover of the 224 VIP Sanitation | Adjust | Target corrected | -5603869.6052 | 25000000 | 19396130.3948 | Monthly reports, practical completion reports, happy letters
To construct VIP Sanitation units by June 2018 within Elias Motsoaledi Municipality | Financial and Human Resource | 1 630 VIP Sanitation toilets completed | Improved health and hygiene | VIP Sanitation programme phase 2.1 | 15 180 VIP Units constructed | Number of VIP sanitation units constructed | 859 VIP Sanitation units constructed | Finalize beneficiary list, establishment of Project Steering Commitees, appointment of CLOs and Appointment of Contractors | 400 VIP Sanitation toilets completed | 23 VIP Sanitation toilets completed | 600 VIP Sanitation toilets completed | Adjust | Target corrected | -11604452.4226 | 32000000 | 20395547.5774 | Monthly reports, practical completion reports, happy letters
To complete Zaaiplaas village reticulation | Financial and Human Resource | Completed BWS | Improved water supply to Zaaiplaas | Zaaiplaas Village Reticulation Phase 2 | Construction of Dindela Reservoir. Commissioning of bulk pipeline and pump station. | Percentage completion of Zaaiplaas village reticulation including rerservior & bulk pipeline | 70% completion of Zaaiplaas village reticulation including rerservior & bulk pipeline | 20% construction of Dindela Reservoir, 90% construction of bulk pipeline, 80% construction of pump station. | 50% construction of Dindela Reservoir, 95% construction of bulk pipeline, 94% construction of pump station. | 60% construction of Dindela Reservoir, 95% construction of bulk pipeline, 94% construction of pump station. | 70% construction of Dindela Reservoir, 95% construction of bulk pipeline, 94% construction of pump station. | Adjust | Additional funds received to complete the project | 12272297 | 5000000 | 17272297 | Monthly reports and practical completion certificate
To finalize construction of Zaaiplass water reticulation by June 2018. | Financial and Human Resource | Completed BWS | Improved water supply to Zaaiplaas | Zaaiplaas Connector pipes from Bulk to villages incl. reservoirs (Khathazweni, Rondebosh,Kosini,Mathula,Khathazweni,Areaganeng,Jeije,Sehlakwane,Elandslaagte and Dindela) | 80% construction of Zaaiplass water reticulation (Construction reservoirs 80%; bulk line 80%). | Percentage Construction of Zaaiplass Connector Pipes. | 100% construction of Zaaiplass water reticulation (Construction reservoirs 100%; bulk line 100%). | 70% construction of Zaaiplass water reticulation (Construction reservoirs 80%; bulk line 80%). | 100% construction of Zaaiplass water reticulation (Construction reservoirs 100%; bulk line 100%). | Testing and Commissioning | Testing and Commissioning | Adjust | Under estimated budget | 1606591 | 6000000 | 7606591 | Monthly reports and practical completion certificate
To commission Tafelkop Reticulation and Cost Recovery by June 2018 | Financial and Human Resource | Completed Tafelkop water reticulation network | Improved water supply to Tafelkop | Tafelkop Reticulation and Cost Recovery | 60% Construction of Tafelkop reticulation projects | Percentage (%) Commissioning of Tafelkop Reticulation and Cost Recovery | 100% Commissioning of Tafelkop Reticulation and Cost Recovery ( Snag listing 50% and testing 50%) | 80% Commissioning of Tafelkop Reticulation and Cost Recovery ( Snag listing 20% and testing 20%) | 90% Commissioning of Tafelkop Reticulation and Cost Recovery ( Snag listing 50% and testing 50%) | 100% Commissioning of Tafelkop Reticulation and Cost Recovery ( Snag listing 50% and testing 50%) | No activity | Adjust | Over estimated budget | -2859822 | 7972483 | 5112661 | Monthly reports and practical completion certificate
To construct VIP sanitation units by June 2018 within Makhuduthamaga Municipality | Financial and Human Resource | 1 835 VIP Sanitation toilets completed | Improved health and hygiene | VIP Sanitation programme phase 2.2 | 15 180 VIP Units constructed | Number of VIP sanitation Units constructed | 960 VIP sanitation units contructed | Finalize beneficiary list, establishment of Project Steering Commitees, appointment of CLOs and Appointment of Contractors | 600 VIP Sanitation toilets completed | 140 VIP Sanitation toilets completed | 220 VIP Sanitation toilets completed | Adjusted | Target corrected | 0 | 25000000 | 25000000 | Monthly reports, practical completion reports, happy letters
To construct Sekwati Reticulation upgrade Phase 4 by June 2018 | Financial and Human Resource | Completed Sekwati water reticulation network | Improved water supply to Sekwati | Sekwati Reticulation upgrade Phase 4 | 90% Construction of Sekwati Reticulation upgrade Phase 4 | Percentage Construction of Sekwati Reticulation upgrade Phase 4 completed | 100% Construction of Sekwati Reticulation upgrade Phase 4 ( pipeline network and stand pipes and upgrading of boreholes) completed | 95% Construction of Sekwati Reticulation upgrade Phase 4 | 100% Construction of Sekwati Reticulation upgrade Phase 6 | 100% Construction of Sekwati Reticulation upgrade Phase 6 | 100% Construction of Sekwati Reticulation upgrade Phase 6 | Adjusted | Multi year project | 0 | 6958280.06 | 6958280.06 | Monthly reports and practical completion certificate
To construct Ga Moloi Water Supply water supply by June 2018. | Financial and Human Resource | Completed Ga-Moloi water reticulation network | Improved water supply to Ga-Moloi | Ga Moloi area and surrounding villages water supply (contract B and C) | 90% Construction of reticulation lines at Morgenzon and Stad Van Masleroem; Gravity main, installation of street taps. | Percentage Construction of reticulation lines at Morgenzon and Stad Van Masleroem; Gravity main, installation of street taps completed | 100% Construction of reticulation lines at Morgenzon and Stad Van Masleroem; Gravity main, installation of street taps completed | 95% Construction of reticulation lines at Morgenzon and Stad Van Masleroem; Gravity main, installation of street taps. | 100% Construction of reticulation lines at Morgenzon and Stad Van Masleroem; Gravity main, installation of street taps. | 100% Construction of reticulation lines at Morgenzon and Stad Van Masleroem; Gravity main, installation of street taps. | 100% Construction of reticulation lines at Morgenzon and Stad Van Masleroem; Gravity main, installation of street taps. | Adjusted | Multi year project | 0 | 7331650.4718 | 7331650.4718 | Monthly reports and practical completion certificate
To construct reticulation network in Ga-Mashabela by June 2018 | Financial and Human Resource | Completed Ga-Mashabela water reticulation network | Improved water supply to Ga-Mashabela | Ga-Mashabela water reticulation supply | Technical report approval and MIS registration | Percentage of construction completed | 50% construction completed ( bulk pipeline, reservior , pump house and chambers ) | 0% construction completed, appointment of contractors and site establishments | 10% construction completed | 25% construction completed | 50% construction completed | Adjust | Multi year projects target adjusted | 0 | 34642003.0982 | 34642003.0982 | Monthly reports and Technical report
To construct reticulation network in Ga-Marishane by June 2018 | Financial and Human Resource | Completed Ga-Marishane water reticulation network | Improved water supply to Ga-Marishane | Ga-Marishane water reticulation supply | Technical report approval and MIS registration | Percentage of construction completed | 50% construction completed ( bulk pipeline, reservior , WTW slow sand filter and chambers ) | 0% construction completed, appointment of contractors and site establishments | 10% construction completed | 25% construction completed | 50% construction completed | Adjust | Multi year projects funds moved to the next financial year | -9590358.5 | 22925159.9 | 13334801.4 | Monthly reports and practical completion certificate
To construct reticulation network in Maloma by June 2018 | Financial and Human Resource | Completed Maloma and surrounding (Lebating and Tsupani) water reticulation network | Improved water supply to Maloma and surrounding (Lebating and Tsupani) | Maloma and surrounding (Lebating and Tsupani) water supply | Technical report approval and MIS registration | Percentage of construction completed | 100% construction completed (pipe work, stand pipes, boreholes , storage Tank , Package Plant and Valve Chamber) | 0% construction completed, appointment of contractors and site establishments | 10% construction completed | 50% construction completed | 100% construction completed | Adjust | None | 0 | 8045410.12 | 8045410.12 | Monthly reports and practical completion certificate
To construct reticulation network in Lobethal by June 2018 | Financial and Human Resource | Completed Lobethal water supply | Improved water supply to Lobethal | Lobethal water supply | Technical report approval and MIS registration | Percentage of construction completed | 70% construction completed (pipe work, concrete chambers and Reservoir construction) | 0% construction completed, appointment of contractors and site establishments | 10% construction completed | 40% construction completed | 70% construction completed | Adjust | None | 0 | 10855220.6 | 10855220.6 | Monthly reports and practical completion certificate
To construct reticulation network in Ga-Phaahla by June 2018 | Financial and Human Resource | Completed Ga-Phaahla water supply | Improved water supply to Ga-Phaahla water supply | Ga-Phaahla water supply | Technical report approval and MIS registration | Percentage of construction completed | 50% construction completed (reticulation pipelines , WTW pump station and air valve chambers) | 0% construction completed, appointment of contractors and site establishments | 10% construction completed | 25% construction completed | 50% construction completed | Adjust | Multi year projects funds moved to the next financial year | -6721314.72 | 27448984.9 | 20727670.18 | Monthly reports and practical completion certificate
To finalize Nkadimeng: Phase 9 to 11 (Makhuduthamakga) - Ditlabaneng, Letlhabile,Tshatane, Sebetsane, Kgoalane & MAtseben`9E | Financial and Human Resource | Concrete reservoirs; Bulk Water Supply;Reticulation. | Improved Living standards. | Nkadimeng: Phase 9 to 11 (Makhuduthamakga) - Ditlabaneng, Rampelane, Matsebeng, Sebetsane, Kgoalane, Mathibeng, Dinotsi, Matolokwane) | 65% Completion of Concrete reservoirs; Bulk Water Supply; Reticulation. | Percentage Completion of Concrete reservoirs; Bulk Water Supply; Reticulation. | 100% Completion of Concrete reservoirs; Bulk Water Supply; standpipes , boreholes and chambers | 70% Completion of Concrete reservoirs; Bulk Water Supply; Reticulation. | 80% Completion of Concrete reservoirs; Bulk Water Supply; Reticulation. | 100% Completion of Concrete reservoirs; Bulk Water Supply; Reticulation. | Test and commissioning | Retain | None | 0 | 1418565.85 | 1418565.85 | Monthly reports and practical completion certificate
To construct VIP sanitation units by June 2018 within LIM 476 Municipality (Fetakgomo area) | Financial and Human Resource | 715 VIP Sanitation toilets completed | Improved health and hygiene | VIP Sanitation programme phase 2.2 | 15 180 VIP Units constructed | Number VIP Units constructed | 1643 VIP sanitation units | Finalising Beneficiery list, Establishment of Steering commitees, appointment of CLOs and Appointment of Constractors | 300 VIP Sanitation toilets completed | 1643 VIP Sanitation toilets completed | No activity | Adjust | Target corrected | -6558239.42 | 15870000 | 9311760.58 | Monthly reports and practical completion certificate
To implement Borehole Refurbishment Southern Zone by June 2018 | Financial and Human Resources | Refurbished and new developed Water Boreholes | Improved Water Supply | Olifantspoort South Contract 21,22, 24 & 25: Water supply network | Water supply below RDP level | Percentage Completion of boreholes developed and Refurbishment Southern Zone | 70% Completion of boreholes developed and Refurbishment Southern Zone (drilling of boreholes, pipe lying and chambers) | 10% Implementation of borehole Refurbishment Southern Zone | 30% Implementation of borehole Refurbishment Southern Zone | 45% Implementation of borehole Refurbishment Southern Zone | 70%% Implementation of borehole Refurbishment Southern Zone | Adjust | None | 0 | 18895159.89 | 18895159.89 | Monthly reports and practical completion certificate
To complete Concrete reservoirs; Bulk Water Supply; Reticulation Nkadimeng: Phase 9 to 11 | Financial and Human Resources | Nkadimeng: Phase 9 to 11 (Makhuduthamaga) - | Improved Living standards. | Nkadimeng RWS Extension 2( Phase 9 to 11) (Fetakgomo) Ga-Mmela to Mashilavele, Ga-Pahla, Molapong, Ga-Magolego, Mankontu and Masehleng | Nkadimeng WTW, Command Reservoir, reticulation and bulk line below RDP level. | Percentage Completion of Concrete reservoirs; Bulk Water Supply; Reticulation. | 100% Completion of Concrete reservoirs; Bulk Water Supply; Reticulation ( testing and completion of snaglist) | 20% Completion of Concrete reservoirs; Bulk Water Supply; Reticulation. | 60% Completion of Concrete reservoirs; Bulk Water Supply; Reticulation. | 80% Completion of Concrete reservoirs; Bulk Water Supply; Reticulation. | 100% Completion of Concrete reservoirs; Bulk Water Supply; Reticulation. | Adjust | Multi year projects funds moved to the next financial year | -15937980.32 | 47038314.95 | 31100334.63 | Monthly reports and practical completion certificate
To construct VIP sanitation units by June 2018 within LIM 476 Muniipality (Greater Tubatse area) | Financial and Human Resource | 715 VIP Sanitation toilets completed | Improved health and hygiene | VIP Sanitation programme phase 2.2 | 15 180 VIP units contructed | Number of VIP sanitation units | 1193 VIP sanitation units | Finalising Beneficiery list, Establishment of Steering commitees, appointment of CLOs and Appointment of Constractors | 300 VIP Sanitation toilets completed | 652 VIP Sanitation toilets constructed | 241 VIP Sanitation toilets constructed | Adjust | Target corrected | -5962163.35 | 30000000 | 24037836.65 | Monthly reports and practical completion certificate
To construct Command Reservoir, pump station and pipelines at GaMaphopha by June 2018. | Improved water supply | Ga - Maphopha Command Reservoir | Improved Living standards. | Ga - Maphopha Command Reservior | 60% completion of Maphpha command reservoir, pumpsation and pipelines | Percentage completion of Command Reservoir, pump station and pipelines | 70% completion of Command Reservoir, pump station and pipelines ( upgrading of pump station , electrical and installation of pumps, 5 ml reservoir and pipeline ) | 80% completion of Command Reservoir, pump station and pipelines | 100% completion of Command Reservoir, pump station and pipelines | 65% completion of Command Reservoir, pump station and pipelines | 70% completion of Command Reservoir, pump station and pipelines | Adjust | Target corrected | 0 | 16000000 | 16000000 | Monthly reports and practical completion certificate
To construct reticulation network in Lebalelo South by June 2018 | Improved water supply | Lebalelo South connector pipes completed | Improved Living standards. | Lebalelo South connector pipes | Technical report approval and MIS registration | Percentage construction completed | 25% construction completed ( Pipe laying and manhole chambers) | Procurement of service provider | 10% construction completed | 20% construction completed | 25% construction completed | Adjust | Multi year projects funds moved to the next financial year | 17951703 | 122006660 | 139958363 | Monthly reports |  |  | **
To provide 4320 Praktiseer households with Water Reticulation by June 2018. |  |  |  | Praktiseer Water Reticulation | Reticulation, Stand Pipes, Distribution lines(Booster Pump Station, High lift Pump station,WTW to be refurbished) | Number of households provided with water | 4320 households provided with water. | litigation | litigation | 2160 households provided with water. | 4320 households provided with water. | Adjust | Litagation process concluded and funds we initialy allocated to VIP Ephraim Mogale | 7000000 | 0 | 7000000 | Monthly reports
To construct reticulation, reservoir, stand pipes at Ga-Malekane , Masha, GaMaepa by June 2018 | Improved water supply | Ga-Malekane , Masha upgrade and extend reticulation | Improved Living standards. | Ga-Malekane , Masha upgrade and extended reticulation | 65% completion of reticulation, reservoir, stand pipes at Ga-Malekane , Masha, GaMaepa. | Percentage completion of reticulation, reservoir, stand pipes at Ga-Malekane , Masha, GaMaepa. | 100% completion of reticulation, reservoir, stand pipes at Ga-Malekane , Masha, GaMaepa (pipeline , standpipes , storage reservoirs , pump house, chambers, boreholes and pumstation transformer) | 5% completion of reticulation, reservoir, stand pipes at Ga-Malekane , Masha, GaMaepa. | 15% completion of reticulation, reservoir, stand pipes at Ga-Malekane , Masha, GaMaepa. | 70% completion of reticulation, reservoir, stand pipes at Ga-Malekane , Masha, GaMaepa. | 100% completion of reticulation, reservoir, stand pipes at Ga-Malekane , Masha, GaMaepa. | Adjust | Under estimated budget | 10000000 | 2000000 | 12000000 | Monthly reports | * | 0 | **********
To upgrade Roosenekal WWTW by June 2018 | Improved water supply | WWTW upgrade | Improved Living standards. | New | 20% Upgrading and Extension of Roosenekal WWTW | Percentage construction completed | 100% Upgrading and Extension of Roosenekal WWTW |  |  | 50% Upgrading and Extension of Roosenekal WWTW | 50% Upgrading and Extension of Roosenekal WWTW | New project | New Project | 8086536 | 0 | 8086536 | Monthly reports