## Sheet1
2018/2019 SERVICE DELIVERY BUDGET AND IMPLEMENTATION PLAN: MUNICIPAL MANAGER'S OFFICE
STRATEGIC OBJECTIVE | INPUT | OUTPUT | OUTCOME | PROJECT | BASELINE 2017/2018 | INDICATORS | ANNUAL TARGET 2018/2019 | Q1 | Q2 | Q3 | PROGRESS(Achieved/ Not achieved) | ACTUAL PROGRESS | CHALLENGE | REMEDIAL ACTIONS | EVIDENCE | BUDGET 2018-2019
INTERNAL AUDIT
To provide internal audit services to SDM and SDA by June 2019 | Risk Assessment report | Three [3] year and Annual Internal Audit Plan | Improved internal controls | Development of 2018-2021 Three Year Internal audit rolling plan | 100% approved 2017-2019 Three Year Rolling plan | Percentage development of the Three(3) Years rolling Plan | 100% development and implementation of the Three(3) Years rolling Plan | 100% development of Three Year rolling Plan | 100% Implementation of Three year rolling plan | 100% Implementation of Three year rolling plan | Achieved | 100% of Three year rolling plan Implemented | None | None | Approved Three Year rolling Plan | 0
To conduct review of internal control systems for SDA and SDM by June 2019 | Approved Three [3] year and Annual Internal Audit Plan | Regularity Audit reports | Improved Internal Controls | Conduct Regularity audits | 38 Regularity audits issued | Number of regularity audit conducted | 38 Regularity audits conducted | 8 Regularity audits conducted | 8 Regularity audits conducted | 16 Regularity audits conducted | Achieved | 16 Regularity audits conducted | None | None | Regularity Audit Reports | 900000
To perform management requests/ investigations by June 2019 | Approved Three [3] year and Annual Internal Audit Plan | Ad Hoc Management Report | Improved Internal Controls | Management / investigation requests | 4 Management / investigation performed | Percentage Management requests/ investigations performed as and when required | 100% Management requests/ investigations performed as and when required | 100% Management requests/ investigations performed as and when required | 100% Management requests/ investigations performed as and when required | 100% Management requests/ investigations performed as and when required | Achieved | 100% Management requests/ investigations performed as and when required | None | None | Management /Investigation reports | 0
To evaluate and assess information and communication technology by June 2019 | Approved Three [3] year and Annual Internal Audit Plan | ICT Audit reports | Reliable ICT Environment | Conduct ICT Audits | 4 ICT Audit reports conducted | Number of ICT audits conducted | 4 ICT Audit reports conducted | 1 ICT Audit report conducted | 1 ICT Audit report conducted | 1 ICT Audit report conducted | Achieved | 3 ICT Audit report conducted | None | None | ICT Audit Reports | 0
To evaluate and assess municipal performance information by conducting Performance Audit by June 2019 | Approved Three [3] year and Annual Internal Audit Plan | Performance Reports | High level of Productivity | Conduct performance audits | 4 Performance Audit conducted | Number of Performance Audit conducted | 4 Performance Audit conducted | 1 Performance Audit conducted | 1 Performance Audit conducted | 1 Performance Audit conducted | Achieved | 2 Performance Audit conducted | None | None | Performance Audit Reports | 0
To monitor implementation of AG Action Plan for 2017/2018 financial year by June 2019 | Issued AG report | External Audit Report | Improved audit opinion | Monitoring implementation of AG Action Plan | 2016/17 Unqualified external audit report issued | Percentage monitoring of implementation of AG action plan for 2017/18 financial year | 100% monitoring of implementation of AG action plan for 2017/18 financial year | 100% monitoring of implementation of AG action plan for 2017/18 financial year | 100% monitoring of implementation of AG action plan for 2017/18 financial year | 100% monitoring of implementation of AG action plan for 2017/18 financial year | Achieved | 100% of implementation of AG action plan for 2017/18 financial year monitored | None | None | Audit Action plan,Agenda/Minutes/Reports | 0
To facilitate external audit fees payments for 2017/18 financial year by December 2018 | Invoices and statement | Proof of Payment | Improved turnaround time for payment processed | Facilitation of External audit fees payments for 2017/18 financial year | 100% 2016/17 financial year external audit fees paid | Percentage external audit fees for 2017/18 financial year facilitated | 100% external audit fees for 2017/2018 financial year facilitated | 100% external audit fees for 2017/2018 financial year facilitated | 100% external audit fees for 2017/2018 financial year facilitated | 100% external audit fees for 2017/2018 financial year facilitated | Achieved | 100% external audit fees for 2017/2018 financial year facilitated | None | None | Claim schedule Register/Proof of payments | 4691150
To coordinate the activities of the audit committee and performance audit committee by June 2019 | Schedule of council activities and Audit Committee charter | Reports | Effective Oversight | Coordination of activities of Audit Committee and Performance audit Committee | 6 Audit and Performance activities coordinated | Number of activities of audit and performance committees coordinated | 4 activities of audit and performance committees coordinated | 1 activity of audit and performance committees coordinated | 1 activity of audit and performance committees coordinated | 1 activity of audit and performance committees coordinated | Achieved | 1 activity of audit and performance committees coordinated | None | None | Minutes/Agenda/AC Reports | 400000
RISK MANAGEMENT
To conduct and review Strategic Risk Assessment by June 2019 | Human Resources | Strategic Risk register | Improved Risk Management | Conduct and review Strategic Risk Assessment | Approved 2017/2018 FY strategic Risk Register | Number of Strategic Risk Assessment and reviews conducted | *1 Strategic Risk Assessment conducted * 4 Strategic Risk Registers reviewed | 1 Strategic Risk register reviewed | 1 Strategic Risk register reviewed | 1 Strategic Risk register reviewed | Achieved | 1 Strategic Risk Register reviewed | None | None | Strategic Risk Register and Reviewed Risk register | 0
To conduct Operational Risk Assessment by June 2019 | Human Resources | Operational risk register | Improved Risk Management | Conduct Operational Risk Assessment | Approved 2017/2018 FY Operational Risk Registers | No of Operational Risk Assessment and reviews conducted | *1 Operational Risk Assessments Conducted *4 Operational Risk Registers reviewed | *1 Operational Risk review conducted | *1 Operational Risk review conducted. | *1 Operational Risk review conducted | Achieved | 1 Operational Risk Register conducted | None | None | Operational Risk Registers Reviewed Risk Registers | 0
To conduct Infrastructure and Water Services Projects Risk Assessment by June 2019 | Human Resources | Project risk assessment report | Improved Risk Management | Conduct Infrastructure and Water Services Projects Risk Assessment | 2017/2018 FY Projects Risk assessment Reports in place. | All IWS Projects risk assessments conducted | All IWS Projects risk assessments conducted | All Projects risk assessments conducted | All Projects risk assessments conducted | All Projects risk assessments conducted | Not Achieved | None | Inadequate capacity (human Resource) | Conduct the assessments in the 4th quarter | Projects Risk Asessment report | 0
To conduct Processes Risk Assessments by June 2019 | Human Resources | Processes risk register | Improved Risk Management | Conduct Processes Risk Assessments | 2011/12 risk assessments | Number of processes risk assessments conducted | 7 x Processes risk assessments conducted | 2 Processes risk assessment conducted | 2 Processes risk assessment conducted | 2 Processes risk assessment conducted | Not Achieved | None | Conflicting work commitments | Reschedule assessments in the 4th Quarter | Processes risk registers | 0
To facilitate placement of insurance coverage for municipal assets by June 2019 | Human Resources and Finanical Resources | Insurance policy contract | Improved Risk management | Facilitation of placement insurance coverage for municipal assets | 2017/2018 FY Assets Insurance Policy contract in place. | Number of insurance coverage for municipal assets facilitated. | All insurance coverage for municipal assets facilitated | All insurance coverage for municipal assets facilitated | All insurance coverage for municipal assets facilitated | All insurance coverage for municipal assets facilitated | Achieved | All insurance coverage for municipal assets facilitated | None | None | Assets Insurance Policy Contract | R2 200 000
To facilitate of Assets Insurance Claims and payments by June 2019 | Human Resources and Finanical Resources | Insurance Claims Report | Loss management | Facilitation Assets Insurance Claims and payments | 2017/2018FY insurance claims report in place. | Number of assets insurance claims processing and payments facilitated. | All assets insurance claims processing and payments facilitated | All assets insurance claims processing and payments facilitated | All assets insurance claims processing and payments facilitated | All assets insurance claims processing and payments facilitated | Achieved | All assets insurance claims processing and payments facilitated | None | None | Quarterly Insurance Claims Report | 350000
To Manage Security operations and SLA by June 2019 | Human Resources and Finanical Resources | Safeguarded assets, employees and visitors | Improved Security | Management of Security operations and SLA | 4 Security Contracts and SLAs in place. | Number of Security operations and contracts managed | 4 Security operations and contracts managed | 4 Security operations and contracts managed | 5 Security operations and contracts managed | 4 Security operations and contracts managed | Achieved | Adhoc meetings held at Operational sites with the different security companies | None | None | Quarterly Physical security report | 35000000
To Ccnduct Security Operational sites Assessments by June 2019 | Human Resources | Identified Security risks | Protected Assets | Conduct Security Operational sites Assessments | 2017/2018 Security Operational sites Assessments reports in place | Number of security operational sites assessments conducted | Forty (40) Security Operational sites assessments conducted | 10 Operational sites assessed | 10 Operational sites assessed | 10 Operational sites assessed | Not Achieved | Eight (8) operational sites assessed | Inadequate capacity (human Resource) | Conduct the assessments in the 4th quarter | Security operational sites report | 0
To have an Improved accountability and transparency by June 2019 | Human Resources and Finanical Resources | Fraud cases reports | Increased awareness | Facilitation of Anti-Fraud & Corruption hotline | 2017/2018FY Fraud cases reported for referral and investigation. | Percentage fraud and corruption allegations cases reported for referral and investigations facilitated | 100% fraud and corruption allegation cases reported for referral and investigations facilitated | 100% fraud and corruption allegation cases reported for referral and investigations facilitated | 100% fraud and corruption allegation cases reported for referral and investigations facilitated | 100% fraud and corruption allegation cases reported for referral and investigations facilitated | Achieved | No cases reported | None | None | Quarterly Disclosure Hotline report | 190000
To improve risk management culture by June 2019 | Human Resources and Finanical Resources | Training module | Capacitated staff & councillors | Undertaking of Risk Management trainings | 2017/2018FY Risk Management training report in place. | Number of Risk Management trainings undertaken | 3 x Risk Management training undertaken. | 1 Risk Management training conducted | No activity | 1 Risk Management training conducted | Not Achieved | Training module developed but training not conducted | Conflicting work commitments | Reschedule training in the 4th Quarter | Training module and Workshop attendance register | 0
To improve governance by June 2019 | Human Resources | Risk Management reports | Effective and efficient oversight | Facilitation of Risk Management Committee activities | 4 Risk management committee meetings facilitated and coordinated. | Number of risk management committee meetings facilitated | 4 x Risk Management Committee meetings facilitated | 1 x Risk Management Committee meeting facilitated | 1 x Risk Management Committee meeting facilitated | 1 x Risk Management Committee meeting facilitated | Achieved | 1 x Risk Management meeting facilitated | None | None | Quarterly Risk Management reports | 0
LEGAL SERVICES
To attend to the letigations by June 2019 | Human and financial resources | attended cases | skilled and capable workforce support inclusive growth | Litigations | 8 Litigations cases attended | Number of litigations attended | All litigations attended | All litigations attended | All litigations attended | All litigations attended | Achieved | All litigations attended | None | None | Summons and Court Judgments | 3000000
To draft requested Contracts by June 2019 | Human and financial resources | contracts | skilled and capable workforce. | Contracts | 50 Contracts and Services level Agreement drafted | Number of contracts requested and drafted | All contracts requested and drafted | All contracts requested and drafted | All contracts requested and drafted | All contracts requested and drafted | Achieved | All contracts requested and drafted | None | None | Contract Register and drafted contratcs and service level agreements | 0
To draft requested legal opinions by June 2019 | Human and financial resources | legal opionions | skilled and capable workforces | Legal opinions | 10 legal Opinions drafted | Number of Requested Legal Opinions drafted | All requested Legal Opinions drafted | All requested Legal Opinions drafted | All requested Legal Opinions drafted | All requested Legal Opinions drafted | Achieved | All requested Legal Opinions drafted | None | None | Drafted legal opinions register | 0
To capture claims by and against the municipality by June 2019 |  |  |  | Compilation of litigation Register | 2017/18 Litigation register | Number of cases by and against the municipality captured | All cases by and against the municipality captured | All cases by and against the municipality captured | All cases by and against the municipality captured | All cases by and against the municipality captured | Achieved | All cases by and against the municipality captured | None | None | Litigation register, copies of court judgments and Settlements agrements | 0
To record Contracts by June 2019 | human and financial resources | contracts register | skilled and capable workforces | Compilation of contract register | 300 contracts recorded | Number of contracts recorded | All contracts recorded | All contracts recorded | All contracts recorded | All contracts recorded | Achieved | All contracts recorded | None | None | Contracts Register
PERFORMANCE MANAGEMENT SYSTEM (PMS)
To facilitate performance Makgotla by June 2019 | Human and financial Resouces | Lekgotla | Improved performance | Facilitation of Makgotla | 4 Performance Makgotla Sessions held | Number of Performance Lekgotla Sessions facilitated | 4 Performance makgotla Sessions facilitated | 1 Performance Lekgotla Session facilitated | 1 Performance Lekgotla Session facilitated | 1 Performance Lekgotla Session facilitated | Achieved | 1 Performance Lekgotla facilitated on the 21 February 2019 at Jane Furse Statssa Office. | None | None | *Performance Lekgotla Sessions resolutions *attendence registers | R100 000. 00
To develop 2019/2020 Institutional SDBIP | Human and financial Resouces | SDBIP | Improved management of service delivery | Development of 2018/19 Institutional SDBIP | 2017/2018 Institutional SDBIP in place | Number of 2018/2019 Institutional SDBIP developed | 01 2019/2020 Institutional SDBIP developed | N/A | N/A | Draft 2019/2020 Institutional SDBIP developed | Achieved | Draft 2019/2020 Institutional SDBIP developed | None | None | Signed 2018/2019 Institutional SDBIP by Executive Mayor | 0
To compile 2017/2018 Institutional Annual Report by 31 January 2019 | Human Resources | Annual Report | Improved accountability | Compilation of 2017/2018 Annual report | 2017/2018 Annual Report in place | Number of 2017/2018 Annual Report developed | 01 2017/2018 Annual Report developed | No activity | No activity | *Draft 2017/2018 Annual Report in place *Public Participation *Final 2017/2018 Annual Report | Achieved | 2017/2018 Draft Annual Report developed and public participation cunducted from 6 February to 5 March 2019 | None | None | *2016/2017 Annual Report *Attendance Registers | 0
To develop 2018/2019 Performance Agreements for senior managers, managers and Performance commitment for level 4 & 5 officials | Human Resources | Signed performance agreements | Improved commitments | Development of 2018/2019 Performance Agreements for Senior Managers, Managers and Performance commitments for level 4 & 5 officials | 2017/2018 Performance agreements and Performance commitments in place | Number of 2018/2019 Performance Agreements for Senior Managers, managers and Performance Commitments for level 4 & 5’s developed | 07 2018/2019 performance agreements for Senior Managers, 32 managers and 80 performance commitments for level 4 & 5’s developed | 07 2018/2019 performance agreements for Senior Managers, 32 managers and 80 performance commitments for level 4 & 5’s developed | No activity | No activity | N/A | N/A | N/A | N/A | Signed Performance Agreements and Performance commiitments | 0
To facilitate the performance assessment for senior managers and managers by June 2019 | Human Resources | Persformance Assessments | Improved accountability | Facilitation of performance Assessments | 2017/2018 performance assessment for senior managers conducted | Number of performance assessment for senior managers conducted | 2 performance assessment (2017/18 Annual and 2018/19 Mid year) for senior managers conducted | No activity | 1 performance assessment (2017/18 Annual) for senior managers conducted | 2 performance assessment (2017/18 Annual and 2018/19 Mid year) for senior managers conducted | Achieved | 2 performance assessment (2017/18 Annual and 2018/19 Mid year) for senior managers conducted | None | None | Performance assessments reports | 0
To review PMS policy by June 2019. | Human Resources | Reviewed Policy and framework | Improved governance | PMS Policy and Framework Review | 2017/2018 PMS Policy and Framework in place | Percentage Review of PMS Policy and Framework | 100% Review of PMS Policy and Framework | No activity | 50% Submision of policy to stake holders for inputs. | 40% Circulation of policy to management and council structures | Achieved | 40% circulation of the policy done to Local Labour Forum | None | None | Council resolution | 0
To coordinate quarterly Back to Basics reports by June 2019 | Human Resources | Back to basics reports | Improved service delivery | Coordination of B2B reports | 2017/2018 B2B reports in place | Number of quarterly B2B reports coordinated | 4 quarterly B2B reports coordinated | 1 quarterly back to basics reports coordinated | 1 quarterly back to basics reports coordinated | 1 quarterly back to basics reports coordinated | Achieved | 1 quarterly back to basics report corodinated and district engagement session held on the 15 February 2019 | None | None | Quarterly Reports | 0
MUNICIPAL MANAGER | [9 empty] | DATE
MASEKO N.T.