## Sheet1
LOCAL ECONOMIC DEVELOPMENT (LED)
2017/18 SERVICE DELIVERY AND BUDGET IMPLEMENTATION PLAN: PLANNING AND ECONOMIC DEVELOPMENT
MEASURABLE OBJECTIVE | PROJECT | BASELINE 2016/2017 | INDICATORS | ANNUAL TARGET 2017/2018 | Q2 | AUGUST MONTHLY ACTIVITIES | ACHIEVED/NOT ACHIEVED | ACTUAL PROGRESS | CHALLENGES | REMEDIAL ACTION | Q2 | Q3 | Q4 | EVIDENCE (POE) | BUDGET | IMPACT
SPATIAL RATIONALE
To ensure the functionality of the District Municipal Planning Tribunal by June 2018 | Facilitation of District Municipal Planning Tribunal | District Municipal Planning Tribunal in place | Number of District Municipal Planning Tribunal sittings | 3 District Municipal Planning Tribunal sittings | 1 District Municipal Planning Tribunal sittings |  | N0t achieved | Coucil resolution, draft modalities and operation procedures in place for the restablishment of JDMPT | Local munipality council resoluions and By-laws are not finalised | Communicate with LM's to submit the council resolution on modalities. |  |  |  | *Reports *Attendance Registers | R700 000 | Improved business Information
To Support Local Municipalities on Spatial and Land Use Developments by June 2018 | Support to local municipalities on SDF, LUMS, Land Use By-laws and GIS | All LMs have SDFs, LUMS and Draft Land Use By-Laws and GIS | Number of engagements held | 4 engagements held | 2 engagements held |  | Achieved | 2 engagements held, Supported the LMs on SDF reviews and Demarcation of sites for Tribal Authorities. | None | None |  |  |  | *Reports *Attendance Registers | 0 | poverty alleviation
To facilitate land for District Municipal offices in Jane Furse by June 2018 | Facilitation of land for District Municipal Offices in Jane Furse | 10 ha and 50 ha of land available for development in Jane Furse area respectively | 10 ha if land in Jane Furse for Municipal Offices facilitated | 10ha of land in Jane Furse for Municipal Offices facilitated | No Activity |  | N/A. | Engagements with land claimants are still continuing. | N/A | N/A |  |  |  | Signed agreement | 0 | poverty alleviation
To review the Spatial Development Framework by June 2018 | Review of Spatial Development Framework (SDF) | 2012/2013 SDF in place | Number of SDFs reviewed | 1 SDFs reviewed | No Activity |  | N/A | Inception/status qou meeting held on the 30 November 2017 | N/A | N/A |  |  |  | Reviewed SDF | R700 000 | Enterprise development
To develop the Operational Procedure Manual for District Municipal Planning Tribunal | Development of Operational Procedure Manual for District Municipal Planning Tribunal | SPLUMA Regulations in place | Number of Operational Procedure Manual for District Municipal Planning Tribunal developed | 1 Operational Procedure Manual for District Municipal Planning Tribunal developed | No Activity |  | Achieved | Operational Procedure Manual for District Municipal Planning Tribunal developed | N/A | N/A |  |  |  | Reviewed SDF | R 0 | Improved economic development
LOCAL ECONOMIC DEVELOPMENT (LED) | [15 empty] | Improved productive
To facilitate business seminars by June 2018 | Facilitate the Business Seminars | 2016/2017 financial year 2 Business seminars facilitated (Tourism and Business Compliance) | Number of Business Seminars Facilitated | 2 Business Seminars Facilitated | 1 business seminar facilitated | Engage partners for joint collaboration | Achieved | 1 business seminar facilitated | None | None |  |  |  | Seminar Report Attendance Registers | 100000 | Improved business Information
To generate reports on municipal job creation by June 2018 | Municipal Job creation | 4 Reports generated for 2016/2017 | Number of reports generated on Municipal job creation | 4 reports generated on Municipal job creation | 2 report generated on Municipal job creation | Information gathering | Achieved | 2 reports generated on Municipal job creation | None | None |  |  |  | Quarterly reports | 0
To generate reports on EPWP implementation by June 2018 | Implementation of EPWP | 4 Quarterly reports generated | Number of reports on EPWP implementation | 4 reports on EPWP implementation generated | 2 reports on EPWP implementation generated | Induction workshop of beneficiaries | Achieved | 2 reports on EPWP implementation generated | None | None |  |  |  | Quarterly reports | 0
To conduct feasibility study for De Hoop dam and Flag Boshielo dam on fish farming by June 2018 | Feasibility study on Fish farming | None | Feasibility study conducted | Feasibility study conducted | Conducting feasibility study | Finalisation of Terms of Reference | Not achieved | Process for advertisement was finalised in December 2017 | None | None |  |  |  | *Copy of Terms of Reference | 300000
To facilitate Trainings for SMME’s and Cooperatives by June 2018 | Trainings for SMMEs and cooperatives. | 2 Trainings provided during 2016/2017 financial year | Number of Trainings provided to SMME’s and Cooperatives | 4 Trainings provided to SMME’s and Cooperatives | 1 Trainings provided to SMME’s and Cooperatives | No activity | Achieved | Training conducted to Makhuduthamaga and Fetakgomo Tubatse Cooperatives in partnership with DSD on the 20th and 21st of December respectfully | None | None |  |  |  | *Reports *Attendance registers | 0
To monitor the implementation of Social Labour Plans by June 2018 | Monitoring of Social Labour Plans | SLPs for 22 mines in LIM-476 in place | Number of quarterly reports on SLPs implementation | 4 quarterly reports on SLPs implementation | 2 quartely reports on SLPs implementation | Monthly engagement with DMR and Mining houses | Achieved | 2 reports on the mines' SLP's implementation have been generated | DMR not willing to co-operate in the process | To continue engaging DMR for co-operation |  |  |  | Reports | 0
GOOD GOVERNANCE AND PUBLIC PARTICIPATION
To review the IDP Framework/ Process Plan for 2018/19 by August 2017 | Review of 2018/19 IDP/Budget Framework/Process Plan | 2017/18 IDP/Budget Framework Process Plan in place | Number of IDP Frameworks/ Process Plans developed | 1 IDP Frameworks/ Process Plans developed | *Review of IDP Framework/Process Plan *Adoption by Council | Submission of 2018/19 IDP/Budget Framework/Process Plan to Council for adoption | Achieved | Framework/Process Plan was adopted by Council | None | None | N/A | N/A | N/A | *IDP Framework/Process Plan | 0
To review the IDP/Budget by May 2018 | Review of 2018/2019 IDP/Budget | 2017/18 IDP/Budget in place | Number of IDP/Budget reviewed | 1 IDP/Budget reviewed | Draft status quo report in place | No activity | Achieved | Status Quo report in place | None | None | Draft status quo report in place | Draft IDP/Budget | Approval of final IDP/Budget by Council | Status Quo report | 500000