## Sheet1
MEASURABLE OBJECTIVE | STRATEGY | INPUT | OUTPUT | OUTCOME | PROJECT | BASELINE 2017/2018 | INDICATORS | ANNUAL TARGET 2018/2019 | Q1 | Q2 | Q3 | Q4 | ACHIEVED/NOT ACHIEVED | ACTUAL PROGRESS | CHALLENGES | REMEDIAL ACTION | BUDGET 2018-2019 | EVIDENCE
To secure a stable and sustainable financial base for the future of the agency. Develop/facilitate business that creates sustainable jobs. Source funds for economic concepts/projects by June 2019. | Facilitate private investor | Human resources | Investor/operationla factory | job creation * revenue generation | Factory for dry sanitation technologies | MOU | #of factories facilitated | 1 factory constructed | Signed MOU | Construction | Monitoring of implementation | Monitoring of implementation | Achieved | MoU signed | The non implementation of the factory concept due to investor raising issues of value for money | Meeting held and agreed that a comprehensive feability study be conducted so that the fcatory does not depent only on SDM sanitation budget but explore other items that can be manufactured. | 0 | Signed MOU
| Facilitate appointment of consultants | Human resources | TOR's | feasibility study | Fresh Produce Market | TOR’s | #Business plans developed | 1 business plan developed | Issue of advert | appoint consultants | conducting feasibility study | conducting feaisbility study | No achieved | MOU signed with a private investor as we opted for an option of a private investor doing the work than the SDA | Lack of funds | Engagements held with private investor, DTI and FTLM | 0 | Approved copy of feasilibity study. Approved TOR's
| Facilitate private investor | Human resources | Appointed panel of consultants | Revenue generation | Investment promotion for Flag-Boshielo Dam/Recreational | Business plan | #investors attracted | 1 investor | SCM Process. Evaluation and appointment | Signing of MOA | Monitoring of implementation | Monitoring of implementation | Achieved | 3x Service providers appointed and handed business plans to review. | None | None | 0 | Appoitnment letter
| Facilitate operationalisation | Human resources | Enagemnets meetings | Job creation . Imporved | Agri-park | Approved plan | #Investors secured | 1 investor (DRDMR) | 1 enagement held with DRDLR | 1 enagements held with DRLDR | 1 Enaggement held with DRLDR | 1 enagagement with DRDLR | Not Achieved | No progress under the quarter | Agripark programme Is run by DRDLR, The Minister has currently suspended all the Technical comittees engagements | The only engagement being held are MINTECH and MINMEC | 0 | Minutes/attedence register
| Appoint consultant for accreditation | Financial resources | Accrediation certificate | skills development | Accreditation with SETA | Application | Number of MOU Finalised of Agri SETA and LGSETA accreditation | 2 MOU of Agri SETA and LGSETA accreditation finalised | *Assesment of training facilities Agri-Seta *application for LG SITA | *Assesment for LG SITA | *Signing of MOU for Agr-Seta and LG SETA | Training facilitation | Not Achieved | All necessary documents submitted to SP to finalise the matter | Delays/non perfromance by the SP to obtain accreditation from SETA | SP to be given until end of october 2018 to produce positive feedback or explore termination | 0 | certificates/appliction forms
| Facilitate registration process | Human & resources | registration certificates | trading rights | SDA Mining and Construction company | Board resolution | Number of companies registered with Registration of the company | 2 companies registered with Registration of the company | *Finalise regstration with statutory bodies | profile the companies | identify and forge partnerships | identify & forger partnerships | No achieved | Application for reservation of name done with CIPC awaiting a feedback | Finance paid for regisitration however the money was misallocated resulting in delays | SDA account cleared however we are awaiting for the board to finalise registration status of SDA as PTY vs Municipal Entity | 0 | certificates
| Monitoring and Evaluation of SLP and SPP | Human resources | Minutes/reports | compliance to mining charter | SLP and SPP | Board resolution | Improved implementation of SLP and SPP | 100% implementation of SLP and SPP | 1 enagement held with DMR&Mining houses | 1 engagement with DMR&Mining houses | 1 enagement with DMR & Mining houses | 1 enagenment with DMR &Mining houses | No achieved | None | No meeting took place under the quarter | Re-engage DMR to reeive commitees and esnure coordination of activities | 0 | Minutes/attedence register
| Implementation of MOU with MINTEK | Human&financial resources | Report | Enhanced knowledge/information | MINTEK | MOU | Implementation of the MOU | Research Report / Feasibility Study | TOR's and project plan | Draft report | Final draft | submission of report to SDA board and shareholder | Achieved | MOU signed and Draft Action plan in place | Lack of funding to finance R1,3 million for the study | Engage potential funders to assist in securing the required funds | 0 | Research report
| Facilitate local participation | Human reources | Investors | job creation/enahnces local manufacturing | Mining Input Supplier Park | Glencow MISP | % facilitation of local participation | 100% operation of the Mining Input Supply Park | 1 engagement with LEDA/DTI and Glencore | 1 enagement with LEDA/DTI&Glencore | 1 enagagement with LEDA/DTI/Glencore | 1 engagement with LEDA/DTI/Glencore | No achieved | LEDA is ceased with the matter at the provincial level. | Role of SDA in the SEZ project not yet clarified | New chaiperson of SDA will have one on one discusion with LEDA chaiperson to locate the role of SDA in particular as it relate to the MISP. | 0 | Minutes/attedence register
| Facilitate appointment of private investor | Human reources | developer | Revenue generation | Erf 488 portion 1 of 5 land development | Evaluation report | #private investor appointed | 1 investor appointed | Land transfer | Appoitnment of developer/investor | impementation | Implementation | Not achieved | SP appointed through SDM SCM proceses. Progress made is 90% | Delays by the SP to finalise the process within the 3 months anticipated | Official letter written to SP to fastrack the process | 0 | Appointment letter
| Facilitate stakeholder engagements | Human& financial resources | Implementation of commuications strategy | improved stakeholder engagement | Stakeholder management | *By-law , *shareholder compact | # of engagements held with the public | 1 engagement (AGM) | *website revamping *newsletter | *community/stakoeldher meetings *newsletter | *newsletter | *Annual General meeting | Not Achieved | Memo was sent to SCM to appoint a service provider for website revamping | service provider appointed by SCM could not continue to work on website due to company documents not in order | memo to SCM to appoint a new service provider | 100000 | Minutes/attedence register
| Facilitate the study/ research of Regional economic Plan | Human resources | Rsearch report | improved knowledge | Regional Economic Development Master Plan | None | Number of master plan developed | 1 Master Plan developed | TOR's and project plan | Stakeholder enagements | Draft master plan in place. | Final report | Not achieved | TOR's developed and steerring committee launched | lack of funding and internal capacity | Engage LEDA to augmnet the SDM LED budget to include regional master plan | 0 | Draft Master Plan